## Work List
Exported on: 2026-10-24 12:36:51
Filters applied:
Data source: VBGRAMG
District: SHAJAPUR
Block: All
Panchayat: KHADI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SHUJALPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1719007002/AV/22012034644044 — शमशान घाट शेड़ निर्माण खडी में । | Ongoing | 330972.38 | 0 | 2023-10-07
SHUJALPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Agro Forestry Block Plantation for Community | Plantation | 1719007002/DP/22012034590750 — वसुधा बंधन मेरी माटी मेरा देश ग्राम पंचायत खड़ी | Ongoing | 55847.4 | 0 | 2023-09-07
SHUJALPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1719007002/DP/22012034608520 — सार्वजनिक वृक्षारोपण विघुत ग्रीढ के पास ग्राम पंचायत खडी में | Ongoing | 427106.07 | 0 | 2023-10-01
SHUJALPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1719007002/IC/22012034886183 — सार्वजनिक कूप निर्माण कार्य पीर महाराज के पास ग्राम खड़ी | New | 0 | 0 | 2024-04-04
SHUJALPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1719007002/IC/22012034886184 — सार्वजनिक कूप निर्माण कार्य बलडे वाले महाराज के पास ग्राम खड़ी | New | 0 | 0 | 2024-04-04
SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Well for Individual | Construction of Well | 1719007002/IF/22012034382466 — Kpildhara kamal singh | Ongoing | 210000 | 0 | 2018-04-13
SHUJALPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1719007002/IF/22012034588005 — Individuals Agriculture Land Plantation Project Dinesh-Shankarlal | Ongoing | 114410 | 0 | 2020-08-12
SHUJALPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719007002/IF/IAY/4752402 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117035619 | Completed | 27000 | 0 | 2024-12-02 | 2026-09-16
SHUJALPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719007002/IF/IAY/4785664 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129836342 | Ongoing | 27000 | 0 | 2025-02-02
SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719007002/IF/IAY/5475326 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117682906 | Physically Completed | 23490 | 1800 | 2025-04-22 | 2026-07-19
SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719007002/IF/IAY/5476900 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122409210 | Ongoing | 27000 | 0 | 2025-06-19
SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719007002/IF/IAY/5478058 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129837892 | Physically Completed | 23490 | 1566 | 2025-04-22 | 2026-08-02
SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719007002/IF/IAY/5478603 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118015500 | Ongoing | 27000 | 13566 | 2025-04-22
SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719007002/IF/IAY/5478742 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143055620 | Ongoing | 27000 | 3300 | 2025-04-22
SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719007002/IF/IAY/5480910 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116397110 | Ongoing | 27000 | 0 | 2025-04-22
SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719007002/IF/IAY/5524503 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118015323 | Completed | 23490 | 0 | 2025-05-03 | 2026-08-24
SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719007002/IF/IAY/5525717 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129837328 | Ongoing | 27000 | 9966 | 2025-05-03
SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719007002/IF/IAY/5632775 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117683530 | Ongoing | 27000 | 0 | 2025-08-02
SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719007002/IF/IAY/5712166 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129836523 | Physically Completed | 23490 | 1566 | 2025-08-02 | 2026-08-02
SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719007002/IF/IAY/5725534 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117663844 | Ongoing | 27000 | 0 | 2025-09-04
SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719007002/IF/IAY/5730590 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125707628 | Ongoing | 27000 | 0 | 2025-09-04
SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719007002/IF/IAY/5861562 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126576102 | Ongoing | 27000 | 0 | 2026-01-10
SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719007002/IF/IAY/5861584 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129837366 | Ongoing | 27000 | 0 | 2026-01-10
SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719007002/IF/IAY/6260536 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122410630 | Approved | 27000 | 0 | 2025-04-25
SHUJALPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719007002/IF/IAY/6299837 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117683296 | Approved | 27000 | 0 | 2024-10-22
SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1719007002/IF/YD/22012035570756 — santosh so puna kapildhar akoop | Approved | 0 | 0 | 2025-04-14
SHUJALPUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Construction of Drainage Works in Waterlogged Land for Community | Land Development | 1719007002/LD/22012034528494 — Charagah Vikas Nirman Work Gram Tand khurd | Ongoing | 792213.45 | 0 | 2020-11-30
SHUJALPUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1719007002/LD/22012034537623 — चारागाह स्‍थल समतलीकरण कार्य | Ongoing | 601641.79 | 0 | 2021-03-23
SHUJALPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1719007002/RC/22012034658256 — सीसी रोड निर्माण कार्य मेंन रोड से पीरूलाल के मकान तक ग्राम खड़ी | Ongoing | 84500 | 0 | 2023-12-22
SHUJALPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1719007002/RC/22012034678123 — c.c.road nirman ram mandir ke pss khadi me | New | 0 | 0 | 2024-04-03
SHUJALPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1719007002/RC/22012034831396 — सीसी रोड एवं नाली निर्माण कार्य सोनू मालवीय से जितेंद्र राजाराम से व राम मंदिर से जोरावर तक जोरावर म | Approved | 51650 | 0 | 2024-04-04
SHUJALPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1719007002/RS/22012035130279 — आर सीसी नाली निर्माण कार्य निर्मल सिंह मालवीय से सुभाष पाटीदार और कमल सेन तक ग्राम खड़ी | Approved | 100000 | 0 | 2024-04-04
SHUJALPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1719007002/WC/22012035228896 — सार्वजनिक तालाब निर्माण कार्य भैरू महाराज वाली बल्डी पर ग्राम खड़ी | Approved | 0 | 0 | 2024-04-04
SHUJALPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1719007002/WC/22012035231755 — Water harvesting Pond Bheru Maharaj Wali Badli GP Khadi | Approved | 1499469.52 | 0 | 2024-10-02
SHUJALPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Contour Trench for Community | Construction of Trench | 1719007002/WC/22012035254157 — Contour Trench Bheru Maharaj ki Badli Par GP Khadi | Approved | 18733.55 | 0 | 2025-01-26
SHUJALPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1719007002/WC/22012035265561 — Amrit Sarovar Nirman Karya Khoyra Me GP khadi | Ongoing | 1490765.75 | 0 | 2025-05-15
SHUJALPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1719007/WC/22012035231616 — WATER HARVESTING POND GP KHADI | Approved | 0 | 0 | 2024-10-02