## Work List
Exported on: 2026-09-03 15:03:40
Filters applied:
Data source: MGNREGA + VBGRAMG
District: SHAJAPUR
Block: All
Panchayat: MANGROLAMAYAPUR
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SHUJALPUR | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1719007035/AV/22012034392251 — SHANTiDHAM NIRMAN WORK Manrola | Completed | 180000 | 173838.37 | 2019-02-28 | 2020-01-07
SHUJALPUR | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Food grain storage / Construction of Food grain Storage Building for Community | Constr of Food Grain storage | 1719007035/AV/22012034544106 — खादय भण्‍डार हेतु पक्‍का चबुतरा निर्मा्रण मगराेला मायापुर | Completed | 307550.88 | 263312.35 | 2020-12-05 | 2022-08-01
SHUJALPUR | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1719007035/AV/22012034580293 — DYNING HALL ARRANGEMENT AT P.S. SCHOOL G.P. MAGROLA | Closed | 0 | 0 | 2021-04-14
SHUJALPUR | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1719007035/AV/22012034580295 — DYNING HALL ARRANGEMENT AT MIDDLE SCHOOL G.P. MAGROLA | Closed | 0 | 0 | 2021-04-14
SHUJALPUR | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1719007035/AV/22012034580296 — DYNING HALL ARRANGEMENT AT KANYA SHALA SCHOOL G.P. MAGROLA | Closed | 0 | 0 | 2021-04-14
SHUJALPUR | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1719007035/AV/22012034583484 — DYNING HALL ARRNAMENT MIDDLE SCHOOL GP MANGROLAMAYAPUR | Completed | 21925.39 | 22598.05 | 2021-10-20 | 2022-08-15
SHUJALPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Bharat Nirman Seva Kendra / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1719007035/AV/22012034637192 — पंचायत भवन निर्माण कार्य ग्राम मगरोला मायापुर | Closed | 1000000 | 0 | 2023-05-04
SHUJALPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1719007035/DP/22012034487048 — सार्वजनिक कूप निर्माण मायापुर पप्‍प के खेत के पास | Completed | 559462.87 | 411269.56 | 2020-05-28 | 2021-12-02
SHUJALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Lining of minor Canal for Community / Lining of minor Canal for Community | Lining of Canal | 1719007035/DP/22012034541807 — Maa Ki Bagiya Balak Prathmik School Gp Magrola | Deleted | 9619.45 | 193 | 2022-01-29
SHUJALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1719007035/DP/22012034541928 — MAA KI BAGIYA KANYA PRATHMIK SCHOOL GP MANGROLA | Deleted | 9619.45 | 193 | 2022-01-29
SHUJALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1719007035/DP/22012034541929 — MAA KI BAGIYA PRATHMIK SCHOOL GP MANGROLAMAYAPUR | Deleted | 9619.45 | 193 | 2022-01-29
SHUJALPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1719007035/DP/22012034603212 — वसुधा वंदन मेरी माटी मेरा देश ग्राम पंचायत मगरोला | Closed | 0 | 0 | 2023-08-01
SHUJALPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1719007035/DP/22012034615197 — CNG(Community Nutrition Garden) Gram Panchayat Magrola | Closed | 927057.56 | 0 | 2024-01-26
SHUJALPUR | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1719007035/DP/51/?????? — 1719007035/DP/51/ | Completed | 0 | 16632 | 2012-05-29 | 2013-05-16
SHUJALPUR | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1719007035/DP/51/मुक्ति — मुक्ति धाम शांतीधाम निर्माण कार्य सर्वे न0 510 मंगरोला मायापुर | Completed | 415000 | 94619 | 2012-05-29 | 2012-05-14
SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007035/IF/22012034323915 — Hiteshi Kapildhara Saha Khet talab Makansing Shivnarayan | Completed | 234600 | 229648 | 2017-04-01 | 2018-09-26
SHUJALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007035/IF/22012034328521 — hiteshi kapildarakup and khet talab nirman sunil -baldev singh | Completed | 233450 | 236828 | 2017-03-24 | 2017-09-06
SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719007035/IF/22012034352809 — PLANTATION GP MAYAPUR MAGROLA | Completed | 335000 | 44828 | 2017-07-12 | 2021-12-06
SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719007035/IF/22012034353339 — PLANTATION AT GP MANG.MAYAPUR BHAGWAN | Deleted | 335000 | 0 | 2017-04-14
SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719007035/IF/22012034353341 — PLANTATION AT GP MAGROLA MAYAPUR LAKHAN | Deleted | 335000 | 0 | 2017-04-14
SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007035/IF/22012034384265 — KAPILDHARA KUP NIRMAN HUKAM SINGH S/O SUNAR SINGH | Completed | 210000 | 224484 | 2018-04-17 | 2019-09-02
SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007035/IF/22012034403616 — KAPILDHARA KUP NIRMAN CHAND SINGH S/O PRABHULAL | Completed | 210000 | 216132 | 2018-04-17 | 2019-05-21
SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007035/IF/22012034404828 — KAPILDHARA KUP NIRMAN TEJ SINGH s/o CHHATAR SINGH MAGROLA | Completed | 210000 | 206432 | 2018-06-05 | 2020-06-03
SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719007035/IF/22012034471104 — Khet Talab Nirman work Leelachar /hari singh | Deleted | 295000 | 1044 | 2019-03-10
SHUJALPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007035/IF/22012034588029 — kapil dhara kup Nirman Work Sumer singh- kamal singh | Completed | 246126.86 | 176337.94 | 2021-02-10 | 2025-01-30
SHUJALPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007035/IF/22012034634053 — KapilDhar Kup Nirman Work Dharmendra-Ramprasad | Completed | 246126.86 | 237628 | 2020-12-10 | 2022-06-25
SHUJALPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007035/IF/22012034654053 — Kapil dhara Kup Nirman work Uady Singh-Komal Singh | Deleted | 0 | 0 | 2020-10-02
SHUJALPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007035/IF/22012034656229 — Kapil dhara Kup Nirman work Kala Bai-Hari singh | Completed | 246126.86 | 242000.4 | 2021-02-10 | 2022-06-25
SHUJALPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007035/IF/22012034672914 — Kapil dhara Kup Nirman work manmohan Singh-Shivnarayan | Completed | 247839.67 | 240656 | 2021-06-16 | 2022-07-06
SHUJALPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007035/IF/22012034672915 — Kapil dhara Kup Nirman work Uaday Singh - Komal Singh | Deleted | 0 | 0 | 2021-01-25
SHUJALPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007035/IF/22012034672937 — Kapil dhara Kup Nirman work Bhagwat Singh- Sunar singh | Completed | 247839.67 | 242096 | 2021-04-30 | 2022-11-12
SHUJALPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007035/IF/22012034695573 — Kapil dhara Kup Nirman work Sukhram- Bhanwar ji | Completed | 247839.67 | 241003 | 2021-04-30 | 2022-06-25
SHUJALPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007035/IF/22012034723891 — Kapil dhara Kup Nirman work Jagdish- Shivnarayan | Completed | 247839.67 | 242219 | 2021-05-07 | 2022-08-01
SHUJALPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007035/IF/22012034731849 — Kapil dhara Kup Nirman work Devendra-Badrilal | Closed | 247839.67 | 0 | 2021-04-14
SHUJALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1719007035/IF/22012034731857 — Niji Kup Recharge pits Jeevan- Ramesh | Closed | 0 | 0 | 2021-04-14
SHUJALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1719007035/IF/22012034731861 — Niji Kup Recharge pits Makhan sing- Shivnarayan | Closed | 0 | 0 | 2021-04-14
SHUJALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1719007035/IF/22012034731867 — Niji Kup Recharge pits Nannuram- Bhanwar ji | Closed | 0 | 0 | 2021-04-14
SHUJALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1719007035/IF/22012034731881 — Niji Kup Recharge pits Hari singh | Closed | 0 | 0 | 2021-04-14
SHUJALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-borewellrecharge for Indiv / Construction of Sand filter for Borewell recharge for Individual | Well Recharge | 1719007035/IF/22012034731985 — Niji Borewell Rechwellreage Ram singh- Bhavani | Closed | 0 | 0 | 2021-04-14
SHUJALPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719007035/IF/22012034751439 — Khet Talab Nirman Work Prem singh- Ghisu singh | Closed | 337715.44 | 0 | 2021-04-14
SHUJALPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007035/IF/22012034756560 — Kapil dhara Kup Nirman work Uady singh- Komal Singh | Completed | 247839.67 | 241675 | 2021-05-22 | 2022-09-01
SHUJALPUR | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1719007035/IF/22012034846294 — Leach Pit Nirman Work Bhuri bai- Gopal | Closed | 0 | 0 | 2021-04-14
SHUJALPUR | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1719007035/IF/22012034846298 — Leach Pit Nirman Work Kmpu bai- Prahlad singh | Closed | 0 | 0 | 2021-04-14
SHUJALPUR | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1719007035/IF/22012034846302 — Leach Pit Nirman Work babita Bai- Dinesh | Closed | 0 | 0 | 2021-04-14
SHUJALPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719007035/IF/22012034978401 — khet talab ray singh prbhulal | Closed | 0 | 0 | 2022-04-26
SHUJALPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1719007035/IF/22012035467810 — JGSA 2025 Recharge Structure Rajendra Singh Kalusingh Magrola | Physically Completed | 23893.97 | 17056.62 | 2025-05-18 | 2026-04-19
SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1719007035/IF/22012035633533 — Ek Bagiya Maa Ke Naam RAJ KUNVAR MP19007035001 459 | Approved | 0 | 0 | 2025-08-01
SHUJALPUR | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007035/IF/2नविन कुप — नविन कुप निर्माण हरिनारायण शंकरलाल मंगरोला | Deleted | 149000 | 0 | 2009-03-01
SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/1004208 — Construction of IAY House -IAY REG. NO. MP1256013 | Completed | 15480 | 15480 | 2017-10-10 | 2018-03-03
SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/1004686 — Construction of IAY House -IAY REG. NO. MP1294665 | Completed | 15480 | 15480 | 2017-10-10 | 2018-03-08
SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/1007148 — Construction of IAY House -IAY REG. NO. MP1423427 | Completed | 15480 | 15480 | 2017-06-13 | 2018-02-06
SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/1014662 — Construction of IAY House -IAY REG. NO. MP1731723 | Completed | 15480 | 15136 | 2017-09-12 | 2018-03-03
SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/1021183 — Construction of IAY House -IAY REG. NO. MP1991425 | Completed | 15480 | 16512 | 2017-09-12 | 2017-10-30
SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/1032779 — Construction of IAY House -IAY REG. NO. MP2476039 | Completed | 15480 | 15652 | 2017-10-10 | 2018-03-13
SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/1049929 — Construction of IAY House -IAY REG. NO. MP3750313 | Completed | 15480 | 15480 | 2017-10-10 | 2018-03-13
SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/1056854 — Construction of IAY House -IAY REG. NO. MP1433692 | Completed | 15480 | 15308 | 2017-09-12 | 2018-03-13
SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/1403358 — Construction of IAY House -IAY REG. NO. MP2437426 | Completed | 15480 | 15660 | 2018-06-18 | 2018-09-16
SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/1404148 — Construction of IAY House -IAY REG. NO. MP2466217 | Completed | 15480 | 14616 | 2018-05-28 | 2019-11-14
SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/1923405 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4457105 | Completed | 15660 | 15294 | 2018-09-18 | 2020-02-18
SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/1924070 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4777105 | Completed | 15660 | 15246 | 2018-09-18 | 2020-02-27
SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/1924075 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4782212 | Completed | 15660 | 15684 | 2018-09-18 | 2020-01-17
SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/1924598 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5021981 | Completed | 15660 | 15696 | 2018-09-18 | 2020-02-27
SHUJALPUR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/2130200 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4767742 | Completed | 15840 | 15136 | 2019-08-08 | 2020-02-18
SHUJALPUR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/2168646 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5744610 | Completed | 15840 | 15840 | 2019-09-04 | 2020-02-27
SHUJALPUR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/2168680 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5745675 | Completed | 15840 | 15840 | 2019-07-10 | 2020-02-27
SHUJALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/320453 — Construction of IAY House -IAY REG. NO. MP1070325 | Completed | 15030 | 15647 | 2017-01-25 | 2018-04-07
SHUJALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/331050 — Construction of IAY House -IAY REG. NO. MP1093507 | Completed | 15030 | 14345 | 2017-01-31 | 2018-01-22
SHUJALPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/3702567 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115942223 | Completed | 18360 | 17952 | 2022-05-28 | 2022-11-15
SHUJALPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/3708928 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114782159 | Completed | 18360 | 17952 | 2022-05-28 | 2022-09-01
SHUJALPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/3708929 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114782321 | Completed | 18360 | 18360 | 2022-07-02 | 2022-11-11
SHUJALPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/3717303 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120907676 | Completed | 18360 | 17952 | 2022-07-26 | 2023-01-10
SHUJALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/372761 — Construction of IAY House -IAY REG. NO. MP1294628 | Completed | 15030 | 14345 | 2017-01-31 | 2018-01-22
SHUJALPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/3740976 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124490282 | Completed | 18360 | 17952 | 2022-05-28 | 2022-11-15
SHUJALPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/3754262 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121645363 | Completed | 18360 | 18360 | 2022-07-18 | 2022-08-30
SHUJALPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/3781712 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120787075 | Completed | 18360 | 17340 | 2022-05-28 | 2022-11-15
SHUJALPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/3781713 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120787117 | Completed | 18360 | 18156 | 2022-06-04 | 2022-08-28
SHUJALPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/3781715 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120787279 | Completed | 18360 | 17952 | 2022-05-28 | 2022-11-15
SHUJALPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/3781716 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120787322 | Completed | 18360 | 17544 | 2022-05-28 | 2022-12-03
SHUJALPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/3781718 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120787410 | Completed | 18360 | 17952 | 2022-05-28 | 2022-11-15
SHUJALPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/3787353 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124131928 | Completed | 18360 | 18156 | 2022-05-28 | 2022-11-15
SHUJALPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/3840520 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116913731 | Completed | 18360 | 17748 | 2022-05-28 | 2022-11-15
SHUJALPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/4038197 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114724116 | Completed | 18360 | 17952 | 2022-07-02 | 2022-12-22
SHUJALPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/4167893 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114782944 | Completed | 18360 | 18360 | 2022-07-18 | 2022-11-11
SHUJALPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/4168070 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115355292 | Completed | 18360 | 18156 | 2022-07-02 | 2022-12-04
SHUJALPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/4168285 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120907613 | Completed | 18360 | 18360 | 2022-07-02 | 2022-09-06
SHUJALPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/4208871 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113858619 | Completed | 18360 | 18360 | 2022-07-02 | 2022-09-01
SHUJALPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/4208893 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113876237 | Completed | 18360 | 18360 | 2022-07-02 | 2022-09-01
SHUJALPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/4211615 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119614007 | Completed | 18360 | 17952 | 2022-07-18 | 2022-11-15
SHUJALPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/4213066 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117259469 | Completed | 18360 | 18360 | 2022-07-02 | 2022-11-11
SHUJALPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/4214819 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124131124 | Completed | 18360 | 11832 | 2022-07-26 | 2022-09-01
SHUJALPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/4228048 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120787034 | Completed | 18360 | 18360 | 2022-07-02 | 2022-11-11
SHUJALPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/4230493 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124132331 | Completed | 18360 | 18360 | 2022-07-18 | 2022-11-11
SHUJALPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/4237878 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145848007 | Completed | 18360 | 16116 | 2022-07-26 | 2025-06-07
SHUJALPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/4257647 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145848269 | Completed | 18360 | 17952 | 2022-07-26 | 2022-12-22
SHUJALPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/4276148 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114720882 | Completed | 18360 | 18156 | 2022-07-26 | 2022-12-27
SHUJALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/431929 — Construction of IAY House -IAY REG. NO. MP1408212 | Completed | 15030 | 15450 | 2017-03-25 | 2018-03-03
SHUJALPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/4564681 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115942156 | Ongoing | 27000 | 20394 | 2025-01-07
SHUJALPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/4590007 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121646276 | Physically Completed | 23490 | 21870 | 2025-01-09 | 2026-05-03
SHUJALPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/4590017 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121646800 | Physically Completed | 23490 | 21384 | 2025-01-09 | 2026-03-15
SHUJALPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/4742253 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113671476 | Ongoing | 27000 | 21627 | 2024-12-12
SHUJALPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/4743344 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113888831 | Ongoing | 27000 | 21870 | 2025-01-05
SHUJALPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/4749015 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116099407 | Ongoing | 27000 | 21861 | 2025-01-10
SHUJALPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/4760723 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120787363 | Ongoing | 27000 | 20412 | 2024-12-12
SHUJALPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/4765090 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122416072 | Ongoing | 27000 | 21699 | 2025-01-07
SHUJALPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/4794566 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145822794 | Approved | 27000 | 0 | 2024-09-15
SHUJALPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/4866244 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124133574 | Ongoing | 27000 | 21294 | 2025-03-25
SHUJALPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/4893041 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124133972 | Ongoing | 27000 | 21816 | 2025-03-25
SHUJALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/54623 — Construction of IAY House -IAY REG. NO. MP-19-007-035-001/60 | Completed | 14310 | 13694 | 2016-07-05 | 2017-07-28
SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/5517387 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123792061 | Completed | 23490 | 23490 | 2025-11-12 | 2026-02-25
SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/5525749 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113650977 | Ongoing | 27000 | 14094 | 2025-05-21
SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/5525875 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121651110 | Completed | 23490 | 22446 | 2025-06-08 | 2026-01-05
SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/5526017 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124133194 | Physically Completed | 23490 | 19836 | 2025-05-28 | 2026-03-15
SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/5531430 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106419689 | Ongoing | 27000 | 261 | 2025-06-08
SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/5601206 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119291899 | Physically Completed | 23490 | 12789 | 2025-06-08 | 2026-08-16
SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/5659267 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119613062 | Physically Completed | 23490 | 14878 | 2025-06-08 | 2026-05-03
SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/5712274 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122415858 | Physically Completed | 23490 | 20358 | 2025-08-26 | 2026-03-15
SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/5734962 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121642750 | Physically Completed | 23490 | 22968 | 2025-10-28 | 2026-07-26
SHUJALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/57570 — Construction of IAY House -IAY REG. NO. MP-19-007-035-001/85 | Completed | 14310 | 14088 | 2017-01-10 | 2017-12-07
SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/5811710 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120908444 | Completed | 23490 | 22968 | 2025-09-29 | 2026-01-05
SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/5811816 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122416216 | Completed | 23490 | 22968 | 2025-09-20 | 2026-01-05
SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/5812175 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115942669 | Completed | 23490 | 23490 | 2025-09-29 | 2025-11-12
SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/5812401 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120787197 | Completed | 23490 | 23229 | 2025-09-29 | 2026-01-05
SHUJALPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/5998921 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145844777 | Physically Completed | 23490 | 9918 | 2026-04-16 | 2026-08-23
SHUJALPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/5999547 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121998812 | Physically Completed | 23490 | 18009 | 2026-04-04 | 2026-08-23
SHUJALPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/6000130 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114779068 | Ongoing | 27000 | 16704 | 2026-04-16
SHUJALPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/6000466 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120862770 | Ongoing | 27000 | 14616 | 2026-05-18
SHUJALPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/6000603 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119613403 | Ongoing | 27000 | 4176 | 2026-05-14
SHUJALPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/6000831 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117259589 | Ongoing | 27000 | 7308 | 2026-05-08
SHUJALPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/6001437 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119292679 | Physically Completed | 23490 | 14406 | 2026-04-04 | 2026-08-23
SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/6003641 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121643234 | Ongoing | 27000 | 10179 | 2026-03-23
SHUJALPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/6004119 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113706504 | Ongoing | 27000 | 7308 | 2026-05-18
SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/6004309 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120787160 | Approved | 27000 | 0 | 2026-02-23
SHUJALPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/6064827 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114990234 | Ongoing | 27000 | 6003 | 2026-04-08
SHUJALPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/6075155 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116913695 | Physically Completed | 23490 | 13284 | 2026-04-16 | 2026-08-23
SHUJALPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/6227696 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115942421 | Ongoing | 27000 | 0 | 2025-04-28
SHUJALPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/6227712 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114987914 | Approved | 27000 | 0 | 2025-03-26
SHUJALPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/6227723 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116473970 | Ongoing | 27000 | 0 | 2025-03-26
SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/6227726 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114989595 | Approved | 27000 | 0 | 2025-04-24
SHUJALPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/6227742 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116473575 | Ongoing | 27000 | 0 | 2025-04-28
SHUJALPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/6227869 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116473454 | Ongoing | 27000 | 0 | 2025-03-26
SHUJALPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/6227876 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115942452 | Ongoing | 27000 | 0 | 2025-03-26
SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/809800 — Construction of IAY House -IAY REG. NO. MP1387497 | Completed | 15480 | 15308 | 2017-06-13 | 2018-03-03
SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/809847 — Construction of IAY House -IAY REG. NO. MP1392562 | Completed | 15480 | 15480 | 2017-09-12 | 2018-03-08
SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/810349 — Construction of IAY House -IAY REG. NO. MP1433655 | Completed | 15480 | 14104 | 2017-06-13 | 2018-05-17
SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/813246 — Construction of IAY House -IAY REG. NO. MP1646086 | Completed | 15480 | 15480 | 2017-06-13 | 2018-03-13
SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/814397 — Construction of IAY House -IAY REG. NO. MP1738972 | Completed | 15480 | 15480 | 2017-12-12 | 2018-03-07
SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/817808 — Construction of IAY House -IAY REG. NO. MP2024981 | Completed | 15480 | 15480 | 2017-06-13 | 2018-02-06
SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/817919 — Construction of IAY House -IAY REG. NO. MP2032822 | Completed | 15480 | 15480 | 2017-12-12 | 2018-03-13
SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/820071 — Construction of IAY House -IAY REG. NO. MP2228962 | Completed | 15480 | 14448 | 2017-12-12 | 2018-03-08
SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/821071 — Construction of IAY House -IAY REG. NO. MP2325391 | Completed | 15480 | 15308 | 2017-06-13 | 2018-03-13
SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/821661 — Construction of IAY House -IAY REG. NO. MP2387789 | Completed | 15480 | 15308 | 2017-06-01 | 2018-02-13
SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/822128 — Construction of IAY House -IAY REG. NO. MP2438659 | Completed | 15480 | 15884 | 2017-06-01 | 2018-05-02
SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/822192 — Construction of IAY House -IAY REG. NO. MP2442661 | Completed | 15480 | 15308 | 2017-06-13 | 2018-03-13
SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/822593 — Construction of IAY House -IAY REG. NO. MP2503865 | Completed | 15480 | 15136 | 2017-09-12 | 2018-03-08
SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/822826 — Construction of IAY House -IAY REG. NO. MP2543896 | Completed | 15480 | 15480 | 2017-06-13 | 2018-02-06
SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/823096 — Construction of IAY House -IAY REG. NO. MP2588754 | Completed | 15480 | 15480 | 2017-10-10 | 2018-03-08
SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/823459 — Construction of IAY House -IAY REG. NO. MP2641927 | Completed | 15480 | 17640 | 2017-10-10 | 2019-03-13
SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/825429 — Construction of IAY House -IAY REG. NO. MP2995677 | Completed | 15480 | 14276 | 2017-05-29 | 2018-03-08
SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/827860 — Construction of IAY House -IAY REG. NO. MP3477269 | Completed | 15480 | 15480 | 2017-06-01 | 2018-02-06
SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007035/IF/IAY/828841 — Construction of IAY House -IAY REG. NO. MP3726616 | Completed | 15480 | 15480 | 2017-10-10 | 2018-03-13
SHUJALPUR | 2009-2010 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007035/IF/नवीनकूप निर्माण हरिनारायण शंकरलाल मा — नवीनकूप निर्माण हरिनारायण शंकरलाल मायापुर मगरोला | Completed | 59600 | 40190 | 2009-05-27 | 2010-03-23
SHUJALPUR | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Land Leveling / Levelling/shaping of Wasteland Land for Community | Land Development | 1719007035/LD/22012034303234 — MAGROLA ME KHAIL MAIDAN NIRMAN HIGH SCHOOL | Closed | 335000 | 0 | 2017-02-25
SHUJALPUR | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1719007035/LD/22012034303492 — MAGROLA KE MAYAPUR ME SHANTIDHAM SHED NIRMAN | Completed | 180000 | 177250.8 | 2017-03-03 | 2017-12-07
SHUJALPUR | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1719007035/LD/3799382469 — shantidham mayapur | Deleted | 0 | 0 | 2012-11-19
SHUJALPUR | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1719007035/LD/ग्रामीण क् — ग्रामीण क्रीडागंन स्‍कूल परिसर मायापुर | Completed | 0 | 152536 | 2012-05-08 | 2013-03-23
SHUJALPUR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1719007035/RC/14 — पंच परमेश्‍वर व मनरेगा से सीसी रोड एवं नाली निमार्ण शिवनारायण के घर से रामचन्‍्द्र बागरी के घर तक | Completed | 0 | 221889 | 2012-05-29 | 2013-03-30
SHUJALPUR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1719007035/RC/15 — पंच परमेश्‍वर व मनरेगा से सीसी रोड एवं नाली निमार्ण माखनसिंह के घर से रामकशिन के घर तक | Completed | 0 | 244507 | 2012-05-29 | 2013-03-25
SHUJALPUR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007035/RC/22012034155893 — panch parmeshwar+manrega se CC road and nali nirma | Completed | 123000 | 123559 | 2013-06-20 | 2014-07-15
SHUJALPUR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007035/RC/22012034155894 — panch parmeshwar+manrega se CC road and nali nirman theke ke pas wale raste se laxminarayan ke makan | Deleted | 0 | 0 | 2012-11-19
SHUJALPUR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007035/RC/22012034155895 — panch parmeshwar+manrega se CC road and nali nirman rammandir chok | Deleted | 0 | 0 | 2012-11-19
SHUJALPUR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007035/RC/22012034160996 — पंच परमेश्‍वर एवं मनरेगा से सीसी रोड एवं नाली निर् | Completed | 82000 | 83156.51 | 2012-05-29 | 2013-03-30
SHUJALPUR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007035/RC/22012034179051 — PANCH PARMESHWAR+MANREGA SE CC ROAD AND NALI NIRMAN SHARAB KE THEKE SE RAMMANDIR CHOK BAZAR TAK MAGR | Completed | 225000 | 222728 | 2013-08-30 | 2014-02-13
SHUJALPUR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007035/RC/22012034179358 — PANCH PARMESHWAR+MANREGA SE CC ROAD AND NALI NIRMAN ROOP SINGH KE GHAR SE GIRWAR SINGH KE GHAR TAK M | Completed | 225000 | 224786 | 2013-08-30 | 2014-03-29
SHUJALPUR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007035/RC/22012034199531 — MAGROLA KE GRAM MAYAPUR ME PP+MANREGA SE CC ROAD A | Completed | 62000 | 60022 | 2014-01-18 | 2014-02-02
SHUJALPUR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007035/RC/22012034204505 — MAGROLA MAYAPUR ME PP+MANREGA SE CC ROAD AND NALI | Completed | 112000 | 111768 | 2014-02-15 | 2014-03-15
SHUJALPUR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1719007035/RC/22012034204506 — MAGROLA MAYAPUR ME KHET SADAK NIRMAN MAIN ROAD SE | Completed | 1440000 | 417191.7 | 2014-02-15 | 2016-08-24
SHUJALPUR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Bitumen Top / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1719007035/RC/22012034221723 — magrola mayapur me Pp+manrega se cc road and nali | Completed | 213600 | 213950 | 2014-07-19 | 2014-12-14
SHUJALPUR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007035/RC/22012034221724 — pp+manrega se cc road and nali nirman mayapur magr | Deleted | 0 | 0 | 2014-01-26
SHUJALPUR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007035/RC/22012034221725 — pp+manrega se cc road and nali nirman mayapur magrola | Deleted | 0 | 0 | 2014-01-26
SHUJALPUR | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007035/RC/22012034282550 — cc road and nali nirman girvar ke mukya marg tak magrola | Completed | 158000 | 157998 | 2015-08-19 | 2016-06-06
SHUJALPUR | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007035/RC/22012034299183 — cc road and nali nirman Magrola | Closed | 0 | 0 | 2016-01-26
SHUJALPUR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007035/RC/22012034315640 — Cc road nali nirman mata mandir se jatav mohale tak magrola | Completed | 112000 | 109166.5 | 2016-10-26 | 2017-07-28
SHUJALPUR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007035/RC/22012034320843 — cc road and nali nirman | Closed | 0 | 0 | 2016-08-15
SHUJALPUR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007035/RC/22012034395824 — CC ROD VIDHALAY PARISHAR SE MEN ROD | Completed | 22500 | 23054 | 2019-03-04 | 2019-11-05
SHUJALPUR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007035/RC/22012034440074 — सी सी रोड एवं नाली निर्माण कार्य | Closed | 0 | 0 | 2019-01-26
SHUJALPUR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007035/RC/22012034446482 — सी सी रोड एवं नाली निर्माण राजेन्‍द्र के मकान से कालूसिंह के मकान तक | Completed | 104058 | 101900 | 2019-03-04 | 2020-02-27
SHUJALPUR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007035/RC/22012034446486 — सी सी रोड एवं नाली निर्माण हनुमान मंदिर से स्‍कुल से मेनरोड तक | Completed | 199720 | 195708 | 2019-03-04 | 2020-02-27
SHUJALPUR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007035/RC/22012034481862 — C C Road Nirman P.S School Se E. Kksha And Main Get Tak | Completed | 60000 | 57904 | 2019-11-08 | 2020-06-03
SHUJALPUR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007035/RC/22012034513258 — cc rod and nali nirman | Closed | 0 | 0 | 2019-11-29
SHUJALPUR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007035/RC/22012034528880 — C C Road And Nali Nirman work Lad singh ke Makan Se Santosh ke Makan Tak | Completed | 135000 | 135105 | 2020-07-13 | 2022-06-15
SHUJALPUR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007035/RC/22012034556359 — C C Road Nirman Work Main Road Se high school Ki Aur | Completed | 91800 | 91780 | 2021-02-02 | 2022-01-22
SHUJALPUR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007035/RC/22012034578075 — C C Road And Nali Nirman Work Shivpal Ke Makan Se Pintu Ke Makan Ki Aur | Completed | 90000 | 90131 | 2021-10-28 | 2022-04-14
SHUJALPUR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007035/RC/22012034602081 — C C Road Nirman Work Shantidham Parisar Me Magrola | Closed | 34650 | 0 | 2021-08-18
SHUJALPUR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007035/RC/22012034609293 — सीसी रोड निर्माण कार्य शांति धाम परिशर मगरोला | Completed | 34650 | 34873 | 2022-04-12 | 2022-07-05
SHUJALPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007035/RC/22012034639138 — सीसी नाली निर्माण कार्य माता मंदिर से में रोड तक ग्राम मगरोला | Completed | 149400 | 148431 | 2023-09-27 | 2024-07-31
SHUJALPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007035/RC/22012034664353 — सी सी रोड निर्माण कार्य कलाबाई के घर से ओम प्रकाश के मकान तक ग्राम मगरोला | Closed | 48900 | 0 | 2023-08-15
SHUJALPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007035/RC/22012034666370 — सी सी रोड निर्माण कार्य मुख्य रोड से शमशान तक डॉक्टर कलौनी ग्राम मगरोला | Closed | 60100 | 0 | 2023-08-15
SHUJALPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007035/RC/22012034668120 — सी सी रोड निर्माण कार्य हरिनारायण के घर से मेन रोड तक ग्राम मगरोला | Completed | 66700 | 66509 | 2023-10-16 | 2024-06-28
SHUJALPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007035/RC/22012034668140 — सी सी रोड निर्माण कार्य में रोड से शास. कूप व धनराज से माखन के घर तक ग्राम मगरोला | Completed | 213400 | 213354 | 2024-05-25 | 2025-10-30
SHUJALPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007035/RC/22012034668154 — सी सी रोड निर्माण कार्य नंदकिशोर के घर के सामने मुख्य सड़क तक ग्राम मगरौला | Closed | 35600 | 0 | 2023-08-15
SHUJALPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007035/RC/22012034678185 — CC ROAD AND NALI NIRMAN KARYA Gopal ke ghar se Main road tak | New | 0 | 0 | 2024-04-14
SHUJALPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007035/RC/22012034678186 — CC ROAD AND NALI NIRMAN KARYA Gopal ke ghar se Main road tak | New | 0 | 0 | 2024-04-14
SHUJALPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007035/RC/22012034678187 — CC ROAD AND NALI NIRMAN KARYA rakesh ke ghar se babulal ke ghar tak | New | 0 | 0 | 2024-04-14
SHUJALPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007035/RC/22012034678188 — CC ROAD AND NALI NIRMAN KARYA rakesh ke ghar se babulal ke ghar tak | New | 0 | 0 | 2024-04-14
SHUJALPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007035/RC/22012034684361 — सीसी रोड नाली निर्माण राकेश राठौड़ से बाबूलाल कुशवाह के मकान तक मगरोला | Closed | 48100 | 0 | 2024-01-26
SHUJALPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007035/RC/22012034828763 — सीसी रोड एवं नाली निर्माण कार्य मेंन रोड से लखन सिंह के मकान तक | Completed | 47000 | 46606.96 | 2024-12-27 | 2025-10-08
SHUJALPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007035/RC/22012034828765 — सीसी रोड एवं नाली निर्माण कार्य बाबू जाटव के घर से चांद सिंह के घर के सामने तक | Completed | 47000 | 45928 | 2024-11-20 | 2025-10-08
SHUJALPUR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Bitumen Top Roads for Community / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1719007035/RC/22012034842617 — सीसी रोड निर्माण कार्य मेन रोड से गोपाल सिंह के मकान तक ग्राम मगरोला | Completed | 35110 | 32259.6 | 2025-06-04 | 2025-11-05
SHUJALPUR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007035/RC/22012034842619 — सीसी रोड निर्माण कार्य सोसायटी की बाउंड्री से जमना प्रसाद के घर तक ग्राम मगरोला | Completed | 87650 | 87343.5 | 2025-05-20 | 2025-10-08
SHUJALPUR | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1719007035/RC/आंतरिक मार — आंतरिक मार्ग स्‍कूल से प्रहलाद सिंह तक बार्ड 16 से 18 सर्वे नं 844 मंगरोला | Completed | 344000 | 323091 | 2011-12-20 | 2012-03-31
SHUJALPUR | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1719007035/RC/ग्रेवल सडक — ग्रेवल सडक निर्माण मगरोला से श्‍मशान तक मगरोला | Completed | 233000 | 189327 | 2012-01-03 | 2012-03-31
SHUJALPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719007035/RS/22012034350334 — sayukt sochalay nirman 15 hitgrahi | Completed | 180000 | 179816 | 2017-06-19 | 2018-01-03
SHUJALPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1719007035/RS/22012035117967 — नाली निर्माण कार्य हरिनारायण के घर से में गली तक ग्राम मगरोला | Closed | 66700 | 0 | 2023-08-15
SHUJALPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1719007035/RS/22012035117976 — नाली निर्माण कार्य नंदकिशोर के घर सामने से से मुख्य सड़क तक ग्राम मगरोला | Closed | 35600 | 0 | 2023-08-15
SHUJALPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1719007035/RS/22012035117981 — नाली निर्माण कार्य मुख्य सड़क से शशकिया कूप व धनराज से माखन के घर तक | Closed | 213400 | 0 | 2023-10-06
SHUJALPUR | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1719007035/WC/008 — सार्वजनिक कूप निर्माण तलेनवाला गोहा मगरोला | Completed | 126000 | 408940 | 2008-04-02 | 2012-08-16
SHUJALPUR | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Mini Percolation tank / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1719007035/WC/22012034327392 — MAGROLA MAYAPUR ME TALAB JIRNODHAR | Closed | 115000 | 0 | 2017-05-29
SHUJALPUR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1719007035/WC/22012034426816 — Nala Trench nirman work 01 | Ongoing | 238455 | 65054 | 2019-02-28
SHUJALPUR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1719007035/WC/22012034426817 — Nala Trench nirman work 02 | Ongoing | 238455 | 47471 | 2019-02-28
SHUJALPUR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719007035/WC/22012034480802 — Soka pit Gagdde work Sarvajik Parisar me | Closed | 0 | 0 | 2019-07-25
SHUJALPUR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719007035/WC/22012034480983 — Soka Pit Gadde work Nirman Savjanik Parisar me | Closed | 0 | 0 | 2019-07-25
SHUJALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719007035/WC/22012034684414 — Hendapampa Recharge pits School Parisar me Magrola | Closed | 0 | 0 | 2021-04-14
SHUJALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719007035/WC/22012034684428 — Hendapampa Recharge pits School Parisar me Hendpampa02 | Closed | 0 | 0 | 2021-04-14
SHUJALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719007035/WC/22012034684437 — Hendapampa Recharge pits School Parisar me pit Mayapur | Closed | 0 | 0 | 2021-04-14
SHUJALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719007035/WC/22012034684463 — Sarvjanik Kup Recharge pits Magrola me | Closed | 0 | 0 | 2021-04-14
SHUJALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719007035/WC/22012034684466 — Sarvjanik Kup Recharge pits Mayapurme | Closed | 0 | 0 | 2021-04-14
SHUJALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1719007035/WC/22012034712298 — Navin Shaskiay Talab Nirman Work Gaushala Ke pas Gram Mayapur me | Deleted | 591892.41 | 1914 | 2021-05-27
SHUJALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1719007035/WC/22012034749252 — Roop Water Harveting Balak P.S. School Magrola | Completed | 12134 | 8878 | 2021-06-10 | 2021-12-06
SHUJALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1719007035/WC/22012034749266 — Roop Water Harveting High School Mayapur | Completed | 12134 | 10036 | 2021-06-10 | 2021-12-06
SHUJALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1719007035/WC/22012034749280 — Roop Water Harveting E-Kaksha Magrola | Completed | 12134 | 15054 | 2021-06-10 | 2021-12-06
SHUJALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1719007035/WC/22012034749292 — Roop Water Harveting Middle School magrola | Completed | 12134 | 12738 | 2021-06-10 | 2021-12-06
SHUJALPUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719007035/WC/22012034940621 — Handpump recharge pit gram magrolamayapur | Closed | 0 | 0 | 2022-04-01
SHUJALPUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719007035/WC/22012034940625 — Handpump recharge pit gram mayapur | Closed | 0 | 0 | 2022-04-01
SHUJALPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1719007035/WC/22012035171418 — construction of gabion structure GP Magrola | Closed | 52541.48 | 0 | 2024-01-26
SHUJALPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1719007035/WC/22012035296562 — JGSA 2025 Recharge Structure Sarvjanik Kup Girodiya Khal me Magrola | Physically Completed | 23893.97 | 7921.93 | 2025-05-13 | 2026-04-27
SHUJALPUR | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1719007035/WC/नवीनकूप निर्माण गीताबाई देवीसिंह माय — नवीनकूप निर्माण गीताबाई देवीसिंह मायापुर मगरोला | Completed | 44000 | 79016 | 2008-05-10 | 2010-02-26
SHUJALPUR | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1719007035/WH/19956233 — Talab Marammat ( Gehrikaran) Gram mayapur | Deleted | 100000 | 0 | 2016-05-26
SHUJALPUR | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1719007035/WH/19957121 — Talab marammat (gehrikaran) Madhyemik vidhyalay ke pass wali talai gram mangrola mayapur | Deleted | 100000 | 0 | 2016-06-04
SHUJALPUR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1719007035/WH/22012034332912 — Talab Renovation mangrolamayapur | Completed | 151000 | 101510 | 2018-06-12 | 2019-07-25
SHUJALPUR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1719007035/WH/22012034333220 — Talab Renovation Gram mayapur | Deleted | 0 | 0 | 2018-04-01
SHUJALPUR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007055/RC/22012034188168 — magrola mayapur me panch parmeshwar+manrega se cc | Completed | 126000 | 122688 | 2013-12-18 | 2014-01-29