## Work List
Exported on: 2026-09-13 21:21:13
Filters applied:
Data source: MGNREGA
District: SHAJAPUR
Block: All
Panchayat: UNDAI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SHUJALPUR | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1719007036/AV/22012034373588 — Shantidham Shed Nirman Bamora Marga par | Completed | 180000 | 179562.32 | 2018-06-05 | 2019-08-28
SHUJALPUR | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Repair & Maint of Anganwadi Building / Repair and Maintenance of Anganwadi Building for Community | Repair & Maint of Community infrastructure | 1719007036/AV/22012034588568 — Dinning hall arrangement ms undai | Deleted | 0 | 0 | 2021-04-14
SHUJALPUR | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Repair & Maint of Anganwadi Building / Repair and Maintenance of Anganwadi Building for Community | Repair & Maint of Community infrastructure | 1719007036/AV/22012034588570 — Dinning hall arrangement ms undai | Completed | 21925.39 | 21135.92 | 2021-09-22 | 2022-08-09
SHUJALPUR | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1719007036/AV/22012034664320 — shantidaham nirman kary undai | Ongoing | 235393.34 | 114006.59 | 2025-06-14
SHUJALPUR | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1719007036/AV/3768 — Aanganbadi/Other Rural Infrastructure,SHUJALPUR | Completed | 180000 | 97251 | 2015-09-28 | 2017-10-17
SHUJALPUR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1719007036/DP/22012034440932 — सार्वजनिक कुप निर्माण मा,वि,के पास | Closed | 0 | 0 | 2019-01-26
SHUJALPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1719007036/DP/22012034600606 — plantation work meri Mati Mera Desh | Deleted | 55847.4 | 1216.05 | 2023-09-25
SHUJALPUR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Drinking Water | Soak Pits / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1719007036/DW/144 — sarwajanik kup nirman titwas marg par | Deleted | 0 | 0 | 2012-11-20
SHUJALPUR | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Vermi Composting / Construction of Vermi Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1719007036/IF/22012034298435 — varim compost madanlal | Deleted | 0 | 0 | 2016-09-06
SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1719007036/IF/22012034313768 — pm awash | Deleted | 0 | 0 | 2017-04-01
SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007036/IF/22012034334831 — hiteshi kapildhara sah khettalab (Ram lal-pannalal) | Deleted | 232000 | 0 | 2017-04-25
SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007036/IF/22012034338510 — hiteshi kapil dhara kup nirman koshaiya bai-shrikishan phathak | Completed | 234600 | 229552 | 2017-05-13 | 2017-12-30
SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719007036/IF/22012034350123 — PLANTAITION GP UNDAI | Deleted | 335000 | 0 | 2017-05-19
SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719007036/IF/22012034353938 — PLANTATION GPUNDAI | Completed | 335000 | 110934 | 2017-06-26 | 2021-12-20
SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719007036/IF/22012034438371 — het Talab Niram work sajan singh/suraj singh | Completed | 295000 | 279096 | 2018-10-05 | 2019-02-22
SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719007036/IF/22012034438372 — het Talab Niram work rambabu/deep singh | Completed | 295000 | 283002 | 2018-10-05 | 2019-06-25
SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1719007036/IF/22012034457520 — रविन्द्र उत्तम सिंह खेत तालाब निर्माण | Deleted | 0 | 0 | 2019-01-26
SHUJALPUR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation - Shelter Belt for Individuals / Block Plantation of Shelter Belt Trees for Individuals | Plantation | 1719007036/IF/22012034457527 — कपिल धारा कुप निर्माण रामलाल पन्नलाल बागरी | Deleted | 0 | 0 | 2019-01-26
SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719007036/IF/22012034471068 — Khet Talab nirman work Jeevan /badriprasad | Completed | 295000 | 280884 | 2019-03-08 | 2019-05-31
SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719007036/IF/22012034471513 — Khet Talab Nirman work Ravindra/ Uattam singh | Completed | 295000 | 284052 | 2019-03-08 | 2019-06-05
SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007036/IF/22012034472127 — HITESHI KAPILDHARA KUP NIRMAN Ramlal/Pannalal | Completed | 214200 | 208140 | 2019-03-09 | 2019-09-15
SHUJALPUR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1719007036/IF/22012034525477 — kapil dhara kup nirman dhapu bai | Deleted | 0 | 0 | 2019-11-29
SHUJALPUR | 2019-2020 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Infra for Lqud Biomanure for Indviduals / Construction of Infrastructure for Liquid Biomanure for Individuals | Bio-Fertilizer | 1719007036/IF/22012034525479 — kapil dhara kup nirman jagdhish | Deleted | 0 | 0 | 2019-11-29
SHUJALPUR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1719007036/IF/22012034525480 — pashu shed nirman balvir singh | Deleted | 0 | 0 | 2019-11-29
SHUJALPUR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719007036/IF/22012034525481 — khet talab nirman antar singh | Deleted | 0 | 0 | 2019-11-29
SHUJALPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007036/IF/22012034534105 — Kapildhara kup nirman work bhanwar ji jagdhis | Completed | 234458.57 | 232000 | 2020-04-28 | 2020-11-27
SHUJALPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719007036/IF/22012034537060 — खेत तालाब निर्माण आन्‍नदसिह मांगीलाल | Completed | 310386.65 | 276760.62 | 2020-04-30 | 2020-11-27
SHUJALPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007036/IF/22012034544467 — हितेषी कपिलधारा कूप निर्माण जितेन्‍द्रसिंह पिता कैलाश | Completed | 234458.57 | 232000 | 2020-05-07 | 2020-11-27
SHUJALPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719007036/IF/22012034550319 — Khet Talab Nirman Work kaulash-Shankarlal | Completed | 332572.21 | 300205.06 | 2020-05-19 | 2020-09-15
SHUJALPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1719007036/IF/22012034579333 — Khet Samtlikaran Work Rajendra singh-indar singh | Completed | 107260.51 | 105787.2 | 2020-07-02 | 2020-12-31
SHUJALPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1719007036/IF/22012034579334 — Khet Samtlikaran Work Jitendra singh -Manohar singh | Completed | 220413.94 | 217121.91 | 2020-07-02 | 2020-12-31
SHUJALPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1719007036/IF/22012034580925 — Khet Samtlikaran Work Balvir -Ajab singh | Deleted | 0 | 0 | 2020-05-01
SHUJALPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1719007036/IF/22012034582332 — Land Levelling And Shaping Work Baldev-Ajab | Deleted | 0 | 0 | 2020-06-01
SHUJALPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1719007036/IF/22012034583019 — Land Levelling And Shaping Work Balvir-Ajab singh | Completed | 65228.53 | 60769.2 | 2020-07-15 | 2020-12-31
SHUJALPUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1719007036/IF/22012034584061 — Individuals Agriculture Land Plantation Project Chetan-Parvta singh | Completed | 144900 | 107792 | 2020-07-21 | 2023-07-11
SHUJALPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719007036/IF/22012034590854 — Individuals Agriculture Land Plantation Project Satish-Devi singh | Completed | 114410 | 88067 | 2020-08-12 | 2024-04-19
SHUJALPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007036/IF/22012034624954 — Kapildhara kup nirman work Ashok pathak- Gulab pathak | Ongoing | 246126.86 | 1719 | 2021-03-11
SHUJALPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1719007036/IF/22012034631438 — Land Levelling and shaping of Fallow Prahlad_Ramlal | Completed | 154121.16 | 153123.96 | 2020-11-23 | 2021-01-20
SHUJALPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007036/IF/22012034672854 — Kapil dhara Kup Nirman work Soram Bai- Jasmat Singh | Completed | 246126.86 | 246076 | 2021-04-21 | 2021-09-09
SHUJALPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719007036/IF/22012034672855 — Khet Talab Nirman Work Nem Singh- Kamal Singh | Completed | 332962.02 | 303177 | 2021-05-03 | 2021-09-13
SHUJALPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719007036/IF/22012034688895 — Khet Talab Nirman Work Pritam Singh-Shivnarayan | Completed | 337715.44 | 306651 | 2021-05-03 | 2021-09-13
SHUJALPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719007036/IF/22012034693329 — Khet Talab Nirman Work Mahipal -Manohar | Completed | 337715.44 | 309160 | 2021-04-26 | 2021-10-13
SHUJALPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007036/IF/22012034693339 — Kapil dhara Kup Nirman work Shivpal- badri singh | Deleted | 0 | 0 | 2021-04-01
SHUJALPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007036/IF/22012034694913 — Kapil dhara Kup Nirman work Arvind- Devi Singh | Deleted | 0 | 0 | 2021-04-01
SHUJALPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007036/IF/22012034751689 — Kapil dhara Kup Nirman work Lakhan singh- Bane singh | Completed | 289959.62 | 289772 | 2021-05-24 | 2023-03-03
SHUJALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1719007036/IF/22012034891093 — Leach Pit Nirman Work Vibhas Rai | Completed | 8771.46 | 7271.58 | 2021-11-10 | 2022-09-09
SHUJALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1719007036/IF/22012034891094 — Leach Pit Nirman Work Hemlta Bai | Completed | 8771.46 | 7269.66 | 2022-01-02 | 2022-09-09
SHUJALPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719007036/IF/22012034964351 — Khret talab virendra singh deep singh | Completed | 356340.1 | 279072 | 2022-05-04 | 2023-05-15
SHUJALPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007036/IF/22012035204766 — KAPILDHARA KUP LADKUVAR BAI GP UNDAI | Completed | 330281.59 | 313966.62 | 2024-03-16 | 2025-07-10
SHUJALPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007036/IF/22012035205384 — KAPILDHARA KUP MUKESH GP UNDAI | Deleted | 0 | 0 | 2024-01-26
SHUJALPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719007036/IF/22012035209992 — TALAB NIRMAN RADESHYAM SO BADRILAL | Closed | 348521.85 | 0 | 2024-01-26
SHUJALPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007036/IF/22012035213308 — KAPILDHARA KUP GORDHAN SINGH SO SOBHAN SINGH | Completed | 330281.59 | 322907 | 2024-03-12 | 2025-07-10
SHUJALPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007036/IF/22012035213422 — KAPILDHARA KUP GENDKUVAR BAI W/O TEJ SINGH GP UNDAI | Completed | 330281.59 | 309013 | 2024-03-12 | 2024-11-05
SHUJALPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007036/IF/22012035213424 — KAPILDHARA ARVIND, DEVISINGH GP UNDAI | Completed | 330281.59 | 303377 | 2024-03-12 | 2024-11-05
SHUJALPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007036/IF/22012035223509 — KAPILDHARA KUP NIRMALA W/O HUKUM SINGH GP UNDAI | Completed | 330281.59 | 326506 | 2024-03-16 | 2025-07-10
SHUJALPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1719007036/IF/22012035249081 — PLANTATION shivshing badri singh | Deleted | 0 | 0 | 2024-06-08
SHUJALPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Afforestation of wasteland Forestry trees for ind / Afforestation of wasteland Forestry trees for individual | Plantation | 1719007036/IF/22012035249089 — PLANTATION DEVISINGH PITA DILIP SINGH | Deleted | 0 | 0 | 2024-06-08
SHUJALPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Afforestation of wasteland Forestry trees for ind / Afforestation of wasteland Forestry trees for individual | Plantation | 1719007036/IF/22012035275852 — PLANTATION shivshing badri singh UNDAI | Deleted | 0 | 0 | 2024-07-08
SHUJALPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1719007036/IF/22012035277496 — PLANTATION SHVIPAL SINGH PITA BADRI SINGH UNDAI | Approved | 0 | 0 | 2024-07-05
SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719007036/IF/22012035277807 — निजी फलोद्यान कार्य शिवपाल पिता बद्री सिंह | Ongoing | 141756 | 46458 | 2025-08-24
SHUJALPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007036/IF/22012035309579 — KAPILDHARA KUP KALASH SINGH HARINARAYAN GP UNDAI | Approved | 310586.35 | 0 | 2025-01-26
SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007036/IF/22012035312168 — KAPILDHARA KUP RAMESHCHANDR GANPAT UNDAI | Ongoing | 310586.35 | 222734.48 | 2025-04-01
SHUJALPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719007036/IF/22012035314288 — TALAB NIRMAN ASHOK RAJPUT UNDAI | Deleted | 0 | 0 | 2025-03-08
SHUJALPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1719007036/IF/22012035338982 — JGSA2025RECHARGE PIT UNDAI | Deleted | 24000 | 0 | 2025-04-08
SHUJALPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1719007036/IF/22012035343816 — JGSA Recharge Structure Dugwell Satish Rajput Devi Singh | Completed | 23899.46 | 22536.32 | 2025-04-20 | 2025-12-15
SHUJALPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1719007036/IF/22012035343845 — JGSA Recharge Structure Dugwell Balveer Singh Ajab Singh Undai | Completed | 23899.46 | 22254.99 | 2025-04-20 | 2025-12-15
SHUJALPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1719007036/IF/22012035343871 — JGSA Recharge Structure Dugwell Sajan Singh Rajput Suraj Singh Undai | Completed | 23899.46 | 23037.99 | 2025-04-20 | 2025-12-16
SHUJALPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1719007036/IF/22012035343900 — JGSA Recharge Structure Anand Singh Mangilal Undai | Completed | 23899.46 | 21993.98 | 2025-04-20 | 2025-12-16
SHUJALPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1719007036/IF/22012035343918 — JGSA Recharge Structure Dugwell Jeevan Singh Badrilal undai | Physically Completed | 23899.46 | 20972.2 | 2025-07-03 | 2026-04-10
SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007036/IF/22012035375939 — KAPILDHARA KUP SHIVPALSHINGH BADRISINGH UNDAI | Ongoing | 310067.3 | 216873.74 | 2025-05-14
SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719007036/IF/22012035430967 — Construction Ponds ANTAR BAI W/O BALDEV SINGH UNDAI | Completed | 406897.87 | 346086 | 2025-05-02 | 2025-12-17
SHUJALPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1719007036/IF/22012035480621 — JGSA 2025 Recharge structure Dugwell krishnapal rajput pita hukum singh undai 5 | Completed | 23399.46 | 22420.72 | 2025-05-07 | 2025-12-16
SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719007036/IF/22012035497800 — Ponds Construction Ashok Rajput UNDAI | Completed | 279007.04 | 155181 | 2025-05-14 | 2025-12-17
SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719007036/IF/22012035503444 — Ponds Construction Mohansingh Pita Chandrsinh undai | Closed | 130262.62 | 261 | 2025-05-14
SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719007036/IF/22012035508815 — Ponds Construction Elamsingh Rajput Pita Amar Singh Undai | Closed | 273517.72 | 522 | 2025-05-14
SHUJALPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1719007036/IF/22012035521342 — JGSA 2025 Recharge structure Ladkuvar bai pati mohansingh undai | Completed | 23899.46 | 22819.78 | 2025-05-17 | 2025-12-16
SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719007036/IF/22012035592966 — Ek Bagiya Maa Ke Naam Bhuri Bai MP19007036001 123 | Ongoing | 271693.38 | 40983 | 2025-08-28
SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719007036/IF/22012035592980 — Ek Bagiya Maa Ke naam Radha Bai Meena MP19007036001 123 | Ongoing | 271693.38 | 42288 | 2025-08-24
SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719007036/IF/22012035596094 — Ek Bagiya Maa Ke Naam anju bai MP19007036001 199 | Approved | 0 | 0 | 2025-08-01
SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719007036/IF/22012035596100 — Ek Bagiya Maa Ke Naam Anju bai MP19007036001 199 | New | 0 | 0 | 2025-08-01
SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719007036/IF/22012035596620 — एक बगिया माँ के नाम श्रीकृष्ण समुह से राधा बाई उं | New | 0 | 0 | 2025-08-15
SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719007036/IF/22012035637122 — Ek Bagiya Maa Ke Naam MP19007036001 221 | Approved | 263511.37 | 0 | 2025-08-01
SHUJALPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Chatal/ Platform / Construction of Fish Drying Yards for Individual | Other Works | 1719007036/IF/9993675375 — indra awas | Completed | 14000 | 8190 | 2015-09-18 | 2018-05-04
SHUJALPUR | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Drainage in Water Logged Areas / Drainage of chaur or waterlogged areas Land for Individuals | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1719007036/IF/9993712155 — Med bandan | Deleted | 0 | 0 | 2016-04-01
SHUJALPUR | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Drainage in Water Logged Areas / Drainage of chaur or waterlogged areas Land for Individuals | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1719007036/IF/9993712157 — Medbandan | Deleted | 0 | 0 | 2016-04-01
SHUJALPUR | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Drainage in Water Logged Areas / Drainage of chaur or waterlogged areas Land for Individuals | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1719007036/IF/9993712164 — Med bandan | Deleted | 0 | 0 | 2016-04-01
SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/1232895 — Construction of IAY House -IAY REG. NO. MP1840056 | Completed | 15480 | 15708 | 2018-05-29 | 2019-09-16
SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/1232939 — Construction of IAY House -IAY REG. NO. MP1867627 | Completed | 15480 | 15660 | 2018-05-05 | 2018-08-13
SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/1232954 — Construction of IAY House -IAY REG. NO. MP1875495 | Completed | 15480 | 15660 | 2018-05-05 | 2018-08-13
SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/1454911 — Construction of IAY House -IAY REG. NO. MP1875512 | Completed | 15480 | 15660 | 2018-05-29 | 2018-10-02
SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/1454969 — Construction of IAY House -IAY REG. NO. MP1877645 | Completed | 15480 | 15660 | 2018-05-29 | 2018-09-14
SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/1458083 — Construction of IAY House -IAY REG. NO. MP1956879 | Completed | 15480 | 15660 | 2018-05-05 | 2018-08-15
SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/1477879 — Construction of IAY House -IAY REG. NO. MP2758105 | Completed | 15480 | 15660 | 2018-05-29 | 2018-11-12
SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/1482294 — Construction of IAY House -IAY REG. NO. MP2850210 | Completed | 15480 | 15312 | 2018-05-29 | 2018-12-07
SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/1497836 — Construction of IAY House -IAY REG. NO. MP3490343 | Completed | 15480 | 15508 | 2018-05-29 | 2019-05-12
SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/1497842 — Construction of IAY House -IAY REG. NO. MP3490440 | Completed | 15480 | 15312 | 2018-05-29 | 2018-09-14
SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/1499841 — Construction of IAY House -IAY REG. NO. MP3532694 | Completed | 15480 | 15660 | 2018-05-05 | 2018-09-14
SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/1499878 — Construction of IAY House -IAY REG. NO. MP3533433 | Completed | 15480 | 15660 | 2018-05-05 | 2018-09-14
SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/1500493 — Construction of IAY House -IAY REG. NO. MP3547061 | Completed | 15480 | 15660 | 2018-05-05 | 2018-08-30
SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/1501394 — Construction of IAY House -IAY REG. NO. MP3562585 | Completed | 15480 | 15312 | 2018-05-29 | 2018-10-14
SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/1502969 — Construction of IAY House -IAY REG. NO. MP3588431 | Completed | 15480 | 15660 | 2018-05-05 | 2018-08-15
SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/1670358 — Construction of IAY House -IAY REG. NO. MP3588735 | Completed | 15660 | 16704 | 2018-05-29 | 2018-11-12
SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/1670369 — Construction of IAY House -IAY REG. NO. MP3592629 | Completed | 15660 | 15660 | 2018-05-29 | 2018-11-12
SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/1926932 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4583563 | Completed | 15660 | 15486 | 2018-09-05 | 2019-01-28
SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/1927143 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5477776 | Completed | 15660 | 15660 | 2018-09-05 | 2019-04-02
SHUJALPUR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/2159376 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5497223 | Completed | 15840 | 15840 | 2019-07-02 | 2019-11-05
SHUJALPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/3682627 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115781220 | Completed | 18360 | 18360 | 2022-05-27 | 2022-10-03
SHUJALPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/3682629 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115781322 | Completed | 18360 | 18360 | 2022-05-27 | 2022-11-30
SHUJALPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/3682631 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115781417 | Completed | 18360 | 18360 | 2022-05-27 | 2022-09-09
SHUJALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/372946 — Construction of IAY House -IAY REG. NO. MP1303507 | Completed | 15030 | 14964 | 2017-01-28 | 2018-03-07
SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/374039 — Construction of IAY House -IAY REG. NO. MP1355605 | Suspended | 15030 | 0 | 2018-06-25
SHUJALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/376018 — Construction of IAY House -IAY REG. NO. MP1464414 | Completed | 15030 | 15340 | 2017-02-04 | 2018-02-23
SHUJALPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/3765034 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119567371 | Completed | 18360 | 18360 | 2022-05-27 | 2022-09-09
SHUJALPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/4168137 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123462719 | Completed | 18360 | 18360 | 2022-07-01 | 2022-10-22
SHUJALPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/4168240 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115781059 | Completed | 18360 | 18360 | 2022-07-01 | 2022-09-20
SHUJALPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/4214448 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120253290 | Completed | 18360 | 18360 | 2022-07-27 | 2023-02-01
SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/440523 — Construction of IAY House -IAY REG. NO. MP1470713 | Completed | 15030 | 15480 | 2017-04-08 | 2018-03-01
SHUJALPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/4552276 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113963264 | Completed | 21870 | 21870 | 2024-09-25 | 2025-02-13
SHUJALPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/45523 — Construction of IAY House -IAY REG. NO. MP-19-007-036-001/032 | Deleted | 14310 | 0 | 2015-12-12
SHUJALPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/4562313 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115781171 | Completed | 23490 | 21870 | 2024-09-25 | 2025-05-01
SHUJALPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/4562314 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115781183 | Completed | 23490 | 21627 | 2024-12-12 | 2025-05-29
SHUJALPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/4562317 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115781294 | Completed | 21870 | 21627 | 2024-09-25 | 2025-02-13
SHUJALPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/4587720 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120252986 | Completed | 21870 | 21870 | 2024-09-25 | 2025-05-01
SHUJALPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/4699783 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115781135 | Ongoing | 23490 | 0 | 2024-12-12
SHUJALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/54624 — Construction of IAY House -IAY REG. NO. MP-19-007-036-001/43 | Completed | 14310 | 15330 | 2017-03-07 | 2018-03-01
SHUJALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/54625 — Construction of IAY House -IAY REG. NO. MP-19-007-036-001/98 | Completed | 14310 | 11392 | 2016-07-09 | 2018-04-10
SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/5517506 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123810648 | Completed | 23490 | 23481 | 2025-04-29 | 2026-04-09
SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/5519005 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120252339 | Completed | 23490 | 23410 | 2025-04-29 | 2026-02-06
SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/5522030 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115781356 | Completed | 23490 | 20254 | 2025-04-29 | 2026-01-20
SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/5522565 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131852708 | Completed | 23490 | 23488 | 2025-04-29 | 2025-12-17
SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/5523101 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115781088 | Completed | 23490 | 23488 | 2025-04-29 | 2025-11-25
SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/5523463 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116471246 | Completed | 23490 | 23228 | 2025-04-29 | 2026-03-19
SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/5524581 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123030163 | Completed | 23490 | 23227 | 2025-04-29 | 2026-04-09
SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/5527613 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113963135 | Completed | 23490 | 23488 | 2025-04-29 | 2025-12-17
SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/5528562 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126208768 | Completed | 23490 | 23488 | 2025-04-29 | 2025-11-25
SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/5529307 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122168849 | Completed | 23490 | 22966 | 2025-04-29 | 2025-12-17
SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/5529682 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120253628 | Completed | 23490 | 23490 | 2025-05-09 | 2026-04-09
SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/5532077 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126591603 | Completed | 23490 | 22966 | 2025-04-29 | 2026-02-06
SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/5620050 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113963297 | Completed | 23490 | 22184 | 2025-05-17 | 2025-12-27
SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/5620109 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120251652 | Completed | 23490 | 23489 | 2025-05-17 | 2025-11-12
SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/5646153 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115781478 | Completed | 23490 | 23489 | 2025-07-31 | 2026-05-07
SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/5813525 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131707749 | Completed | 23490 | 23490 | 2025-12-21 | 2026-05-07
SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/783093 — Construction of IAY House -IAY REG. NO. MP1355610 | Completed | 15480 | 15480 | 2017-06-04 | 2018-03-01
SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/785025 — Construction of IAY House -IAY REG. NO. MP1475555 | Completed | 15480 | 15504 | 2017-12-16 | 2018-04-21
SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/785548 — Construction of IAY House -IAY REG. NO. MP1510846 | Completed | 15480 | 15492 | 2017-11-25 | 2018-04-21
SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/785549 — Construction of IAY House -IAY REG. NO. MP1510880 | Completed | 15480 | 15136 | 2017-11-25 | 2018-02-25
SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/785695 — Construction of IAY House -IAY REG. NO. MP1518777 | Completed | 15480 | 15480 | 2017-11-25 | 2018-02-25
SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/785702 — Construction of IAY House -IAY REG. NO. MP1519192 | Completed | 15480 | 15480 | 2017-11-25 | 2018-03-07
SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/785720 — Construction of IAY House -IAY REG. NO. MP1520318 | Completed | 15480 | 15480 | 2017-06-04 | 2018-02-15
SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/785724 — Construction of IAY House -IAY REG. NO. MP1520651 | Completed | 15480 | 15136 | 2017-12-02 | 2018-03-15
SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/785754 — Construction of IAY House -IAY REG. NO. MP1522152 | Completed | 15480 | 15480 | 2017-11-25 | 2018-02-19
SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/786893 — Construction of IAY House -IAY REG. NO. MP1589941 | Completed | 15480 | 15480 | 2017-06-01 | 2018-03-07
SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/786957 — Construction of IAY House -IAY REG. NO. MP1594659 | Completed | 15480 | 15480 | 2017-05-27 | 2018-02-03
SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/790601 — Construction of IAY House -IAY REG. NO. MP1839684 | Completed | 15480 | 15480 | 2017-11-18 | 2018-01-30
SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/790604 — Construction of IAY House -IAY REG. NO. MP1839804 | Completed | 15480 | 15228 | 2017-12-16 | 2018-10-25
SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/800957 — Construction of IAY House -IAY REG. NO. MP2756545 | Completed | 15480 | 15480 | 2017-06-01 | 2018-01-30
SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/800958 — Construction of IAY House -IAY REG. NO. MP2756615 | Completed | 15480 | 15308 | 2017-06-06 | 2018-02-25
SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/801366 — Construction of IAY House -IAY REG. NO. MP2803603 | Completed | 15480 | 15480 | 2017-11-04 | 2018-02-25
SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/804824 — Construction of IAY House -IAY REG. NO. MP3334175 | Completed | 15480 | 14620 | 2017-05-27 | 2017-11-03
SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/807362 — Construction of IAY House -IAY REG. NO. MP3821328 | Completed | 15480 | 15480 | 2017-06-06 | 2018-02-19
SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/818649 — Construction of IAY House -IAY REG. NO. MP2104241 | Completed | 15480 | 14448 | 2017-11-25 | 2018-02-25
SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007036/IF/IAY/819687 — Construction of IAY House -IAY REG. NO. MP2193078 | Completed | 15480 | 15652 | 2017-06-06 | 2018-03-07
SHUJALPUR | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007036/IF/नवीनकूप निर्माण देवीसिंह अजब‍ंसिंह उ — नवीनकूप निर्माण देवीसिंह अजब‍ंसिंह उण्‍डई | Completed | 44000 | 47230 | 2008-09-23 | 2008-03-31
SHUJALPUR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1719007036/LD/01/नंदन फल — नंदन फलोद्यान मदनसिंह पन्‍नालाल उडई | Completed | 193000 | 3728 | 2010-12-04 | 2012-12-11
SHUJALPUR | 2015-2016 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1719007036/LD/22012034230713 — khel medan swaraj bhawan | Completed | 96000 | 90328.1 | 2015-09-28 | 2016-06-03
SHUJALPUR | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1719007036/LD/22012034300145 — UNDAI ME SHANTIDHAM NIRMAN KARYA | Completed | 180000 | 139084.56 | 2017-02-06 | 2017-12-18
SHUJALPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Fallow Land for Community / Development of Fallow Land for Community | Land Development | 1719007036/LD/22012034941836 — PLANTATION UNDAI MANDIR KE PAS | Approved | 0 | 0 | 2024-06-08
SHUJALPUR | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1719007036/LD/नंदनवन फलोधान भंवरजी कनीराम उण्‍डई — नंदनवन फलोधान भंवरजी कनीराम उण्‍डई | Completed | 73600 | 26809 | 2008-08-02 | 2013-01-17
SHUJALPUR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007036/RC/22012034155710 — panch parmeshwar+manrega se CC road and nali nirman mukhya marg | Deleted | 0 | 0 | 2012-11-20
SHUJALPUR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007036/RC/22012034155712 — panch parmeshwar+manrega se CC road and nali nirman kumhar mohalla | Deleted | 0 | 0 | 2012-11-20
SHUJALPUR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007036/RC/22012034161179 — सांसद निधि एवं मनरेगा से सीसी रोड एवं नाली निर्माण | Completed | 148000 | 147684 | 2012-05-29 | 2013-03-30
SHUJALPUR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007036/RC/22012034170233 — panch parmeshwar+manrega se CC road and nali nirma | Completed | 185000 | 155228 | 2013-06-10 | 2013-12-09
SHUJALPUR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007036/RC/22012034188478 — UNDAI ME PANCH PARMESHWAR+MANREGA SE CC ROAD AND N | Completed | 224000 | 221760 | 2014-02-24 | 2014-07-20
SHUJALPUR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Bitumen Top / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1719007036/RC/22012034207186 — UNDAI ME PP+MANREGA SE CC ROAD AND NALI NIRMAN KUM | Completed | 52500 | 50328 | 2014-02-24 | 2014-07-19
SHUJALPUR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1719007036/RC/22012034210006 — UNDAI ME KHET SADAK BRAJESH PATHAK SE SURESH PATHA | Completed | 1440000 | 492 | 2014-03-03 | 2016-06-07
SHUJALPUR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007036/RC/22012034221726 — undai me pp+manrega se cc road and nali nirman him | Completed | 211000 | 45216 | 2014-09-05 | 2015-02-02
SHUJALPUR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007036/RC/22012034221727 — pp+manrega se cc road and nali nirman bagri mohalle me | Deleted | 0 | 0 | 2014-01-26
SHUJALPUR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007036/RC/22012034221728 — pp+manrega se cc road and nali nirman undai | Deleted | 0 | 0 | 2014-01-26
SHUJALPUR | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007036/RC/22012034266393 — cc road nali nirman | Completed | 118918 | 118405 | 2015-06-19 | 2016-06-03
SHUJALPUR | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1719007036/RC/22012034297517 — antarik path hanuman madir se aganwadi tak | Completed | 460000 | 179879.7 | 2016-01-30 | 2018-04-10
SHUJALPUR | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007036/RC/22012034298983 — Nali nrman | Deleted | 0 | 0 | 2015-10-02
SHUJALPUR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007036/RC/22012034298991 — Nali nirman | Deleted | 0 | 0 | 2016-04-01
SHUJALPUR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007036/RC/22012034298992 — C.c rod nirman | Deleted | 0 | 0 | 2016-04-01
SHUJALPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007036/RC/22012034320563 — c.C.Rod and nali nirman | Deleted | 0 | 0 | 2017-04-01
SHUJALPUR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007036/RC/22012034320796 — New w. CC Road n.nirman and | Deleted | 0 | 0 | 2016-08-15
SHUJALPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007036/RC/22012034320929 — c.C.Rod and nali nirman | Deleted | 0 | 0 | 2017-04-01
SHUJALPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007036/RC/22012034320968 — c.C.Rod and nali nirman | Deleted | 0 | 0 | 2017-04-01
SHUJALPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007036/RC/22012034320970 — c.C.Rod and nali nirman | Deleted | 0 | 0 | 2017-04-01
SHUJALPUR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007036/RC/22012034323751 — UNDAI ME CC ROAD AND NALI NIRMAN SWASTHYA BHAWAN SE SHANKAR LAL KE MAKAN TAK | Completed | 204000 | 201611 | 2017-02-04 | 2017-04-24
SHUJALPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1719007036/RC/22012034338485 — UNDAI ME SUDUR GRAM SADAK SAMPARK MANOHAR SINGH KE GHAR SE JAGDISH KAKA KE GHAR TAK | Completed | 722000 | 600481.51 | 2017-05-26 | 2019-09-27
SHUJALPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1719007036/RC/22012034369255 — Khet shadak | Deleted | 0 | 0 | 2017-11-24
SHUJALPUR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007036/RC/22012034396988 — C C Road And Nali Nirman work Dyaram Ke Makan se Dip singh ke makan Tak | Completed | 38097 | 36540 | 2018-10-05 | 2019-03-20
SHUJALPUR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007036/RC/22012034397190 — C C Road And Nali Nirman work Radheshyam Bagri se Gangaram ke makan tak | Completed | 40851 | 38802 | 2018-10-04 | 2019-03-15
SHUJALPUR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Interlocking block/tiles Roads for Comm / Construction of Inter-locking cement block/tiles Roads for Community | Constr of Cement Concrete Roads | 1719007036/RC/22012034439833 — C.c rod and Mali nirman | Deleted | 0 | 0 | 2019-01-26
SHUJALPUR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair-maint Interlocking block/tiles roads-Comm / Repair and maintenance of Inter-locking cement block/tiles Roads for Community | Repair & maint of Road | 1719007036/RC/22012034439835 — C.c rod and Mali nirman unfai | Deleted | 0 | 0 | 2019-01-26
SHUJALPUR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007036/RC/22012034447852 — C C Road And Nali Nirman work Ram mandir Se Mata ji ke Otle ke pas Tak | Deleted | 0 | 0 | 2019-01-25
SHUJALPUR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007036/RC/22012034447930 — C C Road And Nali Nirman work Ram mandir se mataji ke Otle ke pas | Completed | 38000 | 37116 | 2019-03-04 | 2019-12-05
SHUJALPUR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007036/RC/22012034447931 — C C Road And Nali Nirman work Jalm singh se Kamal bai ke makan Tak | Completed | 62826 | 61557 | 2019-03-04 | 2019-10-11
SHUJALPUR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007036/RC/22012034475152 — C c road and nali nirman work main road se shatidham v punamchadra malviya ke makan tak | Completed | 94500 | 88176 | 2019-10-14 | 2019-12-14
SHUJALPUR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007036/RC/22012034482277 — C C Road And Nali Manohar singh Ke Makan Se Badrilal Ke Makan Tak | Completed | 102000 | 102080 | 2019-11-29 | 2020-01-25
SHUJALPUR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Cement Concrete Roads for Comm / Repair and maintenance of Cement Concrete Roads for Community | Repair & maint of Road | 1719007036/RC/22012034513162 — c.c rod and nali nirman | Deleted | 0 | 0 | 2019-11-29
SHUJALPUR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Cement Concrete Roads for Comm / Repair and maintenance of Cement Concrete Roads for Community | Repair & maint of Road | 1719007036/RC/22012034513163 — c.c rod and nali nirman | Deleted | 0 | 0 | 2019-11-29
SHUJALPUR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Cement Concrete Roads for Comm / Repair and maintenance of Cement Concrete Roads for Community | Repair & maint of Road | 1719007036/RC/22012034513174 — c.c rod and nali nirman | Closed | 0 | 0 | 2019-11-29
SHUJALPUR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Cement Concrete Roads for Comm / Repair and maintenance of Cement Concrete Roads for Community | Repair & maint of Road | 1719007036/RC/22012034513228 — c.c.rod nirman | Closed | 0 | 0 | 2019-11-29
SHUJALPUR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Rpair & maint of brick/stone Kharanja Roads - Comm / Repair and maintenance of Kharanja (brick/stone) Roads for Community | Repair & maint of Road | 1719007036/RC/22012034513704 — puliya nirman | Closed | 0 | 0 | 2019-11-29
SHUJALPUR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007036/RC/22012034553732 — C C Road Nirman Work Kala ji Mandir Ke Samne | Completed | 26137 | 25840 | 2021-01-04 | 2021-02-07
SHUJALPUR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007036/RC/22012034555279 — C C Road Nirman Work Jagnnath singh ke Makan Se chand singh ke makan Tak | Completed | 43350 | 43320 | 2021-01-04 | 2021-02-07
SHUJALPUR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007036/RC/22012034602018 — C C Road And nali Niraman Sajan singh Ke Makan Makan Se Jagdish ke makan Tak | Completed | 63054 | 61374 | 2022-02-19 | 2022-08-09
SHUJALPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007036/RC/22012034663787 — सीसी रोड मिर्माण कार्य पंचायत भवन के सामने रास्ते पर ग्राम उन्ड़ई | Completed | 63500 | 62796 | 2023-10-28 | 2024-03-19
SHUJALPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007036/RC/22012034673016 — सीसी रोड निर्माण कार्य कालाजी महाराज से टीटवास मार्ग तक ग्राम ऊन्ड़ई | Completed | 65300 | 64859 | 2024-02-09 | 2024-04-15
SHUJALPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007036/RC/22012034677890 — CC ROAD NALI NIRMA KUMHAR MOHALLA UNDAI | New | 0 | 0 | 2024-01-26
SHUJALPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007036/RC/22012034682036 — सीसी रोड नाली निर्माण गोवर्धन से धन सिंह के मकान तक | Completed | 41572 | 40872 | 2024-03-11 | 2024-07-07
SHUJALPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007036/RC/22012034825748 — CC ROAD NALI NIRMA Shri KHEDAPATI HANUMAN MANDIR SE TEEN SHED TAK UNDAI | Approved | 0 | 0 | 2024-07-12
SHUJALPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007036/RC/22012034826537 — सीसी रोड निर्माण कार्य श्री खेड़ापति हनुमान मंदिर से टीन सेड के सामने तक l | Completed | 69300 | 68836 | 2024-09-19 | 2025-05-29
SHUJALPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007036/RC/22012034832128 — सीसी रोड निर्माण कार्य श्री हनुमान मंदिर के पास ग्राम undai | Completed | 69400 | 68000.16 | 2025-03-03 | 2025-05-29
SHUJALPUR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007036/RC/22012034842621 — सीसी रोड निर्माण कार्य शिशुपाल सेन से पप्पू के घर तक ग्राम मगरोला | Completed | 27590 | 25212 | 2025-09-15 | 2026-02-06
SHUJALPUR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007036/RC/22012034849140 — सीसी रोड निर्माण कार्य श्री खेड़ापति हनुमान मंदिर परिसर में | Ongoing | 63064 | 55593 | 2026-01-16
SHUJALPUR | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1719007036/RC/2/ग्रेवल स — ग्रेवल सडक निर्माण उण्‍डई से टिटवास तक उण्‍डई | Completed | 500000 | 493666 | 2011-06-03 | 2012-10-11
SHUJALPUR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1719007036/RC/33 — पंच परमेश्‍वर व मनरेगा से सीसी रोड पुनमचन्‍द्र के घर से इमरत लोहार के घर तक बागरी मोहल्‍ला उंडई | Completed | 131000 | 134408 | 2012-05-29 | 2013-03-22
SHUJALPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719007036/RS/22012034348504 — INDIVIDUAL HH LATRINE (05) UNDAI | Completed | 60000 | 59480 | 2017-06-04 | 2017-09-01
SHUJALPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1719007036/RS/22012034698683 — नाली निर्माण कार्य शिवनारायण के घर से पिपील तक ग्राम उन्ड़ाई | Completed | 37600 | 37430 | 2023-11-05 | 2024-06-28
SHUJALPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1719007036/RS/22012035121935 — नाली निर्माण कार्य हरिजन मोहल्ले में ग्राम उन्ड़ई | Completed | 41700 | 41490 | 2024-02-09 | 2024-06-28
SHUJALPUR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1719007036/WC/22012034424314 — नाला टेन्‍च निर्माण कार्य शमशान के पास | Deleted | 159000 | 3160 | 2018-10-01
SHUJALPUR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1719007036/WC/22012034424317 — नाला टेन्‍च निर्माण कार्य सजनसिह नेताजी के कुए के पास | Deleted | 159000 | 174 | 2018-10-01
SHUJALPUR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719007036/WC/22012034480810 — Soka pit Gagdde work Sarvajik Parisar me | Completed | 13427.24 | 13268.82 | 2020-02-03 | 2020-11-28
SHUJALPUR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719007036/WC/22012034480811 — Soka pit Gagdde work Sarvajik Parisar me | Completed | 13427.24 | 13268.82 | 2020-01-25 | 2020-11-28
SHUJALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1719007036/WC/22012034642647 — Check Dam Nirman Work Gajraj singh ke Khet Ke pas | Completed | 236536 | 235267 | 2021-05-18 | 2021-09-09
SHUJALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1719007036/WC/22012034721711 — Roop Water Harvesting Nirman Work Aaganwadi Bhavan par | Completed | 12300 | 11580 | 2021-09-14 | 2021-10-27
SHUJALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1719007036/WC/22012034721723 — Roop Water Harvesting Nirman Work Middle School Bhavan par | Completed | 12300 | 11580 | 2021-09-14 | 2021-10-27
SHUJALPUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719007036/WC/22012034940633 — Handpump recharge pit gram Undai | Closed | 0 | 0 | 2022-04-01
SHUJALPUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & Maint of Earthen Check Dam for Community / Repair and Maintenance of Earthen Check Dam for Community | Repair & Maint of Check Dam/Stop Dam | 1719007036/WC/22012034948995 — chack dem Nirman Kary shivnarayan ke khet ke pass undai | Completed | 145000 | 143412 | 2022-04-15 | 2022-08-09
SHUJALPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1719007036/WC/22012035187530 — स्टॉपडेम विस्तारीकरण एवं की निर्माण कार्य | Completed | 41000 | 38578.04 | 2024-03-11 | 2025-05-29
SHUJALPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand filter for borewell recharge for Community | Well Recharge | 1719007036/WC/22012035269033 — JGSA 2025 Recharge structure borewell hanuman mandir parisar undai | New | 0 | 0 | 2025-04-14
SHUJALPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand filter for borewell recharge for Community | Well Recharge | 1719007036/WC/22012035269034 — JGSA 2025 Recharge structure borewell hanuman mandir parisar undai | Approved | 0 | 0 | 2025-04-14
SHUJALPUR | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007036/WC/नवीनकूप निर्माण देवीसिंह अजबसिंह उण् — नवीनकूप निर्माण देवीसिंह अजब‍ंसिंह उण्‍डई | Completed | 44000 | 78503 | 2008-09-23 | 2010-03-10
SHUJALPUR | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1719007036/WC/नवीन कूप निर्माण राधाकशिन बद्रीप्रसा — नवीन कूप निर्माण राधाकशिन बद्रीप्रसाद उण्‍डई | Completed | 44000 | 110732.6 | 2008-05-08 | 2010-02-26
SHUJALPUR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1719007036/WH/22012034332883 — Talab Renovation Middle School ke pas | Completed | 49000 | 26100 | 2018-06-18 | 2018-07-10