## Work List
Exported on: 2026-09-03 02:51:08
Filters applied:
Data source: VBGRAMG
District: SHAJAPUR
Block: All
Panchayat: MAGRANIYA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SHUJALPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1719007050/IF/22012035205889 — कपिलधारा कूप निर्माण जुझारसिंह मेवाडा | New | 0 | 0 | 2024-01-27
SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007050/IF/22012035530852 — कपिलधारा कूप निर्माण कार्य लक्ष्मीनारायण पिता मनुदास ग्राम मगरानिया | Ongoing | 289832.38 | 0 | 2025-05-30
SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/5715590 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119880353 | Ongoing | 27000 | 11400 | 2025-10-08
SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/5861463 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115111123 | Ongoing | 27000 | 11400 | 2026-01-06
SHUJALPUR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1719007050/RC/22012034554234 — Aproch Road Nirman Work Radheshyam Ke Makan Se Shamshan Tak | Ongoing | 1495314.87 | 0 | 2021-02-02
SHUJALPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1719007050/RS/22012035124778 — नाली निर्माण कार्य रमेश के घर से सियाराम के घर तक एवं कैलाश के घर से पुलिया तक ग्राम मगरानीय | Ongoing | 103500 | 0 | 2024-03-07