## Work List
Exported on: 2026-09-06 03:04:02
Filters applied:
Data source: MGNREGA + VBGRAMG
District: SHAJAPUR
Block: All
Panchayat: PARDAKHEDI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
KALAPIPAL | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Bharat Nirman Seva Kendra / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1719008006/AV/22012034368796 — शांतिधाम शेड निर्माण घाट खेडी | Completed | 180000 | 178978.6 | 2017-10-09 | 2019-03-13
KALAPIPAL | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1719008006/AV/22012034515649 — बाउण्‍डी वॉल माध्‍यमिक विधालय परिसर पारदाखेडी | Completed | 644218.07 | 636822.53 | 2020-08-20 | 2021-12-07
KALAPIPAL | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1719008006/DP/22012034441014 — सार्वजनिक कूप निर्माण | Closed | 0 | 0 | 2019-01-26
KALAPIPAL | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1719008006/DP/22012034441015 — सार्वजनिक कूप निर्माण | Closed | 0 | 0 | 2019-01-26
KALAPIPAL | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1719008006/DP/22012034541894 — MAA KI BAGIYA MIDDLE SCHOOL GP PARDAKHEDI | Completed | 10000.06 | 7274 | 2022-04-28 | 2024-04-19
KALAPIPAL | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Canal Line Plantation-Horticulture - Community / Canal Line Plantation of Horticulture Trees for Community | Plantation | 1719008006/DP/22012034597202 — Vasudha Vandan Amrit Vatika (75) School And Panchyat Bhawan Parisar Gp Pardakhedi | Closed | 55847.4 | 0 | 2023-08-01
KALAPIPAL | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1719008006/DP/22012034615599 — सार्वजनिक कूप कार्य नरसिंहपुर कछार शासकीय स्कूल के पास | Closed | 0 | 0 | 2024-02-10
KALAPIPAL | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719008006/IF/1000002569 — कपिलधारा कुप निर्माण प्रेमनारायण उमरावसिंह | Deleted | 0 | 0 | 2013-03-20
KALAPIPAL | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719008006/IF/1000002572 — कपिलधारा कुप निर्माण मोतीलाल मिठुलाल | Deleted | 0 | 0 | 2013-03-20
KALAPIPAL | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719008006/IF/202रामबाबु — कपिल धारा रामबाबु जमनाप्रसाद | Completed | 235000 | 181025.66 | 2011-11-15 | 2013-03-21
KALAPIPAL | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719008006/IF/22012034350229 — सार्वजनिक व़क्षारोपण शांतिधाम मे पारदाखेडी | Completed | 335000 | 23880 | 2017-06-17 | 2024-09-15
KALAPIPAL | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719008006/IF/22012034350230 — सार्वजनिक व़क्षारोपण शांतिधाम मे घाटखेडी | Completed | 335000 | 23880 | 2017-06-17 | 2024-09-15
KALAPIPAL | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719008006/IF/22012034382838 — कपिलधारा कूप मथारापर्साद/राधेकीसन | Closed | 0 | 0 | 2017-11-21
KALAPIPAL | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719008006/IF/22012034382845 — कपिलधारा कूप बाबूलाल/पर्भूलाला | Deleted | 0 | 0 | 2017-11-21
KALAPIPAL | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719008006/IF/22012034382846 — कपिलधारा कूप शिवपरसदा/राधेकिसन | Closed | 0 | 0 | 2017-11-21
KALAPIPAL | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719008006/IF/22012034439166 — खेत तालाब निर्माण भंवरलाल रूपसिंह राजपूत | Completed | 287844 | 78129 | 2018-10-07 | 2022-08-27
KALAPIPAL | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719008006/IF/22012034472337 — kapil dhara kup nirman ramful kamal singh | Completed | 210000 | 194412 | 2019-03-09 | 2020-06-03
KALAPIPAL | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1719008006/IF/22012034492931 — SOKHTA GADDA JASMAT S/O SHYAMLAL | Closed | 0 | 0 | 2019-06-28
KALAPIPAL | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1719008006/IF/22012034492932 — SOKHTA GADDA GOVIND S/O BHURIYA | Closed | 0 | 0 | 2019-06-28
KALAPIPAL | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1719008006/IF/22012034492934 — SOKHTA GADDA JITENDRA S/O BHAGWAN SINGH | Closed | 0 | 0 | 2019-06-28
KALAPIPAL | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719008006/IF/22012034513882 — KAPIL DHARA KUP NIRMAN NARMADA PRASAD S/O PANNALAL | Completed | 234458.62 | 211584 | 2020-01-30 | 2022-01-04
KALAPIPAL | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719008006/IF/22012034516595 — KAPIL DHARA KUP NIRMAN RADHESHYAM S/O KISHANLAL | Completed | 234458.57 | 212724 | 2020-02-03 | 2022-01-04
KALAPIPAL | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719008006/IF/22012034519784 — कपिलधारा कूप रिचार्ज पिट बाबूलाल ि‍पिता प्रभुलाल | Deleted | 0 | 0 | 2019-11-19
KALAPIPAL | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719008006/IF/22012034520604 — KAPIL DHARA KUP NIRMAN BABULAL S/O PRABHULAL | Closed | 0 | 0 | 2019-08-15
KALAPIPAL | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1719008006/IF/22012034582234 — नंदनफल उदयान प्रेमनारायण पिता रामलाल | Closed | 144899 | 0 | 2020-04-05
KALAPIPAL | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1719008006/IF/22012034582272 — नन्‍दनफलोउदयान सुरजसिहं पिता गणेशराम मीना | Completed | 144899 | 104294.6 | 2020-08-25 | 2024-07-22
KALAPIPAL | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1719008006/IF/22012034582276 — नन्‍दनफलोउदयान रामचरण पिता रामलाल मीना | Closed | 144899 | 0 | 2020-04-05
KALAPIPAL | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1719008006/IF/22012034582279 — नन्‍दनफलोउदयान गजराज सिहं पिता रामचरण मीना | Completed | 144899 | 103064.6 | 2020-08-25 | 2024-09-04
KALAPIPAL | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1719008006/IF/22012034582286 — नन्‍दनफलोउदयान धारासिहं पिता गणेशराम मीना | Completed | 144899 | 107648 | 2020-08-29 | 2024-04-09
KALAPIPAL | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Forestry Trees-Fields-Individuals / Block Plantation of Forestry Trees in Fields for Individuals | Plantation | 1719008006/IF/22012034600764 — नन्‍दन फलोउदयान मनोज पिता गणेशराम | Completed | 115200 | 102268 | 2020-08-25 | 2024-04-09
KALAPIPAL | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719008006/IF/22012034643148 — KAPIL DHARA KUP NIRMAN RAMBIHARI S/O MULCHAND GP PARDAKHEDI | Completed | 246126.86 | 228942.6 | 2020-12-27 | 2021-12-07
KALAPIPAL | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719008006/IF/22012034647108 — KHET TALAB NIRMAN SURAJ SINGH S/O HARDEV SINGH GP PARDAKHEDI | Completed | 332962.02 | 249938 | 2021-01-02 | 2021-12-07
KALAPIPAL | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719008006/IF/22012034647109 — KHET TALAB NIRMAN RAY SINGH S/O RUGNATH SINGH GP PARDAKHEDI | Completed | 332962.02 | 251130 | 2021-01-02 | 2021-12-07
KALAPIPAL | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719008006/IF/22012034647685 — KAPIL DHARA KUP NIRMAN MADHO SINGH S/O BAPULAL GP PARDAKHEDI | Completed | 246126.86 | 237031.6 | 2021-01-04 | 2021-12-07
KALAPIPAL | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719008006/IF/22012034647686 — KAPIL DHARA KUP NIRMAN RAMCHARAN S/O RAMLAL | Completed | 246126.86 | 233611.6 | 2021-01-04 | 2021-12-07
KALAPIPAL | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719008006/IF/22012034659613 — KAPIL DHARA KUP NIRMAN MOHAN SINGH S/O KAMAL SINGH GP PARDAKHEDI | Completed | 246126.86 | 220825 | 2021-03-20 | 2024-06-10
KALAPIPAL | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719008006/IF/22012034670272 — KAPIL DHARA KUP NIRMAN PREMNARAYAN S/O RAMLAL GP PARDAKHEDI | Closed | 0 | 0 | 2021-01-26
KALAPIPAL | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719008006/IF/22012034709366 — खेत तलब निरामन (हुकम सिंह -भगिराथ मेना) | Closed | 0 | 0 | 2021-04-14
KALAPIPAL | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1719008006/IF/22012034851940 — NANDAN FALODYAN VINOD S/O GANESHRAM GP PARDAKHEDI | Completed | 115000 | 95300 | 2021-09-23 | 2024-07-22
KALAPIPAL | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1719008006/IF/22012034854298 — कम्‍पोज्‍ड पीट हितग्राही रायसिहं पिता रघुनाथ सिहं के घर केपास पारदाखेडी | Completed | 12630.91 | 12134 | 2021-11-23 | 2022-09-12
KALAPIPAL | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1719008006/IF/22012034854300 — कम्‍पोज्‍ड पीट हितग्राही सुरजसिहं पिता गणेशराम ग्राम पारदाखेडी | Closed | 0 | 0 | 2021-08-15
KALAPIPAL | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1719008006/IF/22012034854305 — कम्‍पोज्‍ड पीट हितग्राही शिवप्रसाद पिता राधाकिशन ग्राम घाटखेडी | Completed | 12630.91 | 10976 | 2021-12-08 | 2022-09-12
KALAPIPAL | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719008006/IF/22012034942977 — Khet Talab Nirman Work | Closed | 0 | 0 | 2022-01-24
KALAPIPAL | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719008006/IF/22012035000930 — कपिलधारा कुप निर्माण गुरुबगस पिता दुर्गाप्रसाद | Ongoing | 257014.43 | 56786 | 2022-05-28
KALAPIPAL | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719008006/IF/22012035008954 — नन्द्न फलोउघान निर्माण कार्य मुकेश मीना /ठाकुरप्रसाद | Completed | 123998.2 | 102092.1 | 2022-09-18 | 2025-10-29
KALAPIPAL | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719008006/IF/22012035009261 — नन्द्न फलोउघान निर्माण कार्य कान्ताबप्रसाद/ जयनारायण | Completed | 123997.2 | 91592.1 | 2022-09-18 | 2025-10-29
KALAPIPAL | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719008006/IF/22012035009262 — नन्द्न फलोउघान निर्माण कार्य राममोहन/रामगोपाल | Completed | 123997.2 | 101561.1 | 2022-09-18 | 2026-02-05
KALAPIPAL | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719008006/IF/22012035009263 — नन्द्न फलोउघान निर्माण कार्य रायसिह /रूगनाथ सिंह | Completed | 123997.2 | 108356.1 | 2022-09-18 | 2025-10-29
KALAPIPAL | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719008006/IF/22012035009264 — नन्द्न फलोउघान निर्माण कार्य फूलवतीबाई /जगदीश | Closed | 123997.2 | 0 | 2022-04-14
KALAPIPAL | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719008006/IF/22012035009265 — नन्द्न फलोउघान निर्माण कार्य लखनलाल/ गोवर्धहनसिंह | Closed | 123997.2 | 0 | 2022-04-14
KALAPIPAL | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719008006/IF/22012035090956 — KAPILDHARA KUP NIRMAN Work jamnaprasad - jagram Meena | Completed | 273118.74 | 252458.22 | 2023-05-25 | 2025-05-17
KALAPIPAL | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719008006/IF/22012035107366 — KAPILDHARA KUP NIRMAN Work Kunjilal- Kewalram Meena | Ongoing | 273062.65 | 218404.77 | 2023-06-23
KALAPIPAL | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719008006/IF/22012035132770 — नन्दवन फलोउघान उपयोजना कार्य राकेश मीना-ठाकुरप्रसाद मीना | Physically Completed | 120821.76 | 106529.05 | 2023-08-18 | 2026-06-16
KALAPIPAL | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719008006/IF/22012035203960 — कपिलधारा कुप निर्माण ब्रजकिशोर पिता कमलसिहं | Completed | 282417.57 | 254577.97 | 2024-03-13 | 2025-10-29
KALAPIPAL | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719008006/IF/22012035218923 — KapilDhara Kup Nirman Work Vishnuprasad- Nannulal Meena | Ongoing | 282417.57 | 248535.97 | 2024-03-15
KALAPIPAL | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Mini Percolation Tank for Individuals / Construction of Mini Percolation Tank for Individuals | Construction of Percolation Tank | 1719008006/IF/22012035218930 — KapilDhara Kup Nirman Work Bhagirath-Kishanlal Meena | Completed | 282417.57 | 226173.97 | 2024-03-15 | 2025-10-29
KALAPIPAL | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719008006/IF/22012035218950 — Khet Talab Niraman Work Nilesh-Bhagvan Singh jat | Completed | 297250.11 | 211838 | 2024-03-15 | 2025-10-29
KALAPIPAL | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1719008006/IF/22012035260241 — नन्दन फलोउघान निर्माण कार्य हुकमसिंह भागीरथ मीना | Ongoing | 147792 | 114009 | 2024-10-25
KALAPIPAL | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1719008006/IF/22012035260369 — नन्दन फलोउघान निर्माण कार्य अनारसिंह भागीरथ मीना | Ongoing | 147792 | 115230 | 2024-10-18
KALAPIPAL | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719008006/IF/22012035454174 — Khet Talab Nirman Work Omprakash shrikishan | Deleted | 0 | 0 | 2025-04-01
KALAPIPAL | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1719008006/IF/22012035458757 — JGSA 2025 RECHARGE STRUCTURE kapildhara kup Nirman Radheshyam Kishnlal Gp pardakhedi | Deleted | 0 | 0 | 2025-04-01
KALAPIPAL | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1719008006/IF/22012035459105 — JGSA 2025 RECHARGE STRUCTURE kapildhara kup Nirman Radheshyam Kishanlal | Physically Completed | 25899.46 | 17447.26 | 2025-05-05 | 2026-04-10
KALAPIPAL | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719008006/IF/22012035460091 — Khet Talab Nirman Work Omprakash Shrikishan | Completed | 322971.89 | 179568 | 2025-05-12 | 2026-04-16
KALAPIPAL | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1719008006/IF/22012035477124 — JGSA 2025 RECHARGE STRUCTURE Kapildhara kup Mohan pardhakhedi | Physically Completed | 23399.46 | 17447.26 | 2025-05-08 | 2026-04-10
KALAPIPAL | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1719008006/IF/22012035477131 — JGSA 2025 RECHARGE STRUCTURE Kapildhara kup Ramfool pardhakhedi | Physically Completed | 23399.46 | 17447.26 | 2025-05-08 | 2026-04-10
KALAPIPAL | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719008006/IF/22012035523699 — Khet Talab Nirman Work Mansingh Meena Shrikisan Gp pardakhedi | Closed | 147621.16 | 261 | 2025-05-17
KALAPIPAL | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719008006/IF/22012035563430 — Khet Talab Nirman Work Man Singh Shrikishan | Completed | 388929.8 | 250560 | 2025-06-10 | 2026-04-21
KALAPIPAL | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1719008006/IF/22012035586414 — EK BAGIYA MAA KE NAME SILOCHNA MEENA Ray Singh 118747637 | New | 0 | 0 | 2025-08-01
KALAPIPAL | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719008006/IF/2कपिलधारा — कपिलधारा कुप रामसिंह जगन्‍नाथ पारदाखेडी | Completed | 59600 | 71136 | 2009-02-23 | 2011-03-30
KALAPIPAL | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719008006/IF/9993647751 — कपिल धारा मोती पिटटुलाल | Deleted | 0 | 0 | 2014-01-26
KALAPIPAL | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719008006/IF/9993647752 — कपिल धारा कुप प्रेमनारायण उमरावसिह | Deleted | 0 | 0 | 2014-06-26
KALAPIPAL | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719008006/IF/9993658215 — माेतीसिह मिठठुलाल कपिलधारा कूप निर्माण | Deleted | 0 | 0 | 2015-01-26
KALAPIPAL | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1719008006/IF/9993658216 — राय‍सिंह रघुनाथसिंह पशु शेड निर्माण | Deleted | 0 | 0 | 2015-01-26
KALAPIPAL | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1719008006/IF/9993658219 — सिध्‍दनाथ सिंह रामलाल पशु शेडनिर्माण | Deleted | 0 | 0 | 2015-01-26
KALAPIPAL | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719008006/IF/9993667870 — नन्‍दनफलोघान प्रेमनारायण रामलाल | Deleted | 134819 | 0 | 2015-06-28
KALAPIPAL | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719008006/IF/9993667938 — नन्‍दन फलोउघान जयनारायण दरियावसिह | Deleted | 0 | 0 | 2015-06-15
KALAPIPAL | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719008006/IF/9993667939 — नन्‍दन फलोउघान धापुबाई माधोसिंह | Deleted | 134819 | 0 | 2015-06-30
KALAPIPAL | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719008006/IF/9993668046 — नन्‍दन फलोउघान फूलवतीबाई जगदीश | Deleted | 134819 | 0 | 2015-06-28
KALAPIPAL | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719008006/IF/9993668050 — नन्‍दन फलोउघान फूलसिंह गोपीलाल | Deleted | 134819 | 0 | 2015-06-28
KALAPIPAL | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719008006/IF/9993668052 — नन्‍दन फलोउघान मथराप्रसाद रामलाल | Deleted | 134819 | 0 | 2015-06-28
KALAPIPAL | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719008006/IF/9993668071 — नन्‍दन फलोउघान रामसिंह रघ्‍ाुनाथ | Deleted | 134819 | 0 | 2015-06-28
KALAPIPAL | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719008006/IF/9993668072 — नन्‍दन फलोउघान भंवरलाल रूपसिह | Deleted | 134819 | 0 | 2015-06-28
KALAPIPAL | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719008006/IF/9993668075 — नन्‍दन फलोउघान आनन्‍दसिंह फतेसिंह | Deleted | 134819 | 0 | 2015-06-28
KALAPIPAL | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719008006/IF/9993668080 — नन्‍दन फलोउघान रामसिह रूपसिंह | Deleted | 134819 | 0 | 2015-06-28
KALAPIPAL | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719008006/IF/9993668261 — नन्‍दन फलोउघान मोहनलाल रामलाल | Deleted | 134819 | 0 | 2015-06-30
KALAPIPAL | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719008006/IF/9993670362 — नंदनफलौघान धीरजसिह शम्‍भुसिह | Completed | 91000 | 29226 | 2015-07-20 | 2017-12-12
KALAPIPAL | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719008006/IF/9993670363 — नंदनफलौघान पर्वतसिह हरदेवसिह | Completed | 91000 | 26526 | 2015-07-27 | 2017-12-12
KALAPIPAL | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719008006/IF/9993670364 — नंदनफलौघान मनोहरसिह गणेशराम | Completed | 91000 | 16974 | 2015-08-13 | 2017-12-12
KALAPIPAL | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719008006/IF/9993671481 — नंदनफलौघान रायसिह रूघनाथसिह | Completed | 91000 | 23028 | 2015-08-14 | 2017-12-12
KALAPIPAL | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719008006/IF/9993671482 — नंदनफलौघान रामगोपाल हीरालाल | Completed | 91000 | 22233 | 2015-08-14 | 2017-12-12
KALAPIPAL | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719008006/IF/9993682144 — नन्‍दनवन फलोउघान माधोसिंह बाफूलाल | Completed | 46000 | 15423 | 2015-10-20 | 2017-12-12
KALAPIPAL | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Development of Waste Land / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1719008006/IF/9993744618 — पर्वतसिंह हरदेवसिंह मेढबंधान निर्माण | Deleted | 17500 | 0 | 2016-06-03
KALAPIPAL | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Development of Waste Land / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1719008006/IF/9993744815 — रायसिंह पिता रूगनाथ मेढबंधान निर्माण कार्य | Deleted | 21000 | 0 | 2016-06-04
KALAPIPAL | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Reclamation of Land / Drainage of chaur or waterlogged areas Land for Individuals | Land Development | 1719008006/IF/9993744818 — रामगोपल पिता हीरालाल मेढबंधान निर्माण कार्य | Deleted | 17500 | 0 | 2016-06-04
KALAPIPAL | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008006/IF/IAY/118293 — Construction of IAY House -IAY REG. NO. MP-19-008-006-002/72 | Completed | 14310 | 16984 | 2017-01-29 | 2024-04-20
KALAPIPAL | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008006/IF/IAY/1797776 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2968704 | Completed | 15660 | 15660 | 2018-06-08 | 2018-08-27
KALAPIPAL | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008006/IF/IAY/1800939 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2978541 | Completed | 15660 | 15660 | 2018-06-08 | 2018-09-28
KALAPIPAL | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008006/IF/IAY/1802185 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3812571 | Completed | 15660 | 14616 | 2018-07-03 | 2019-03-22
KALAPIPAL | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008006/IF/IAY/1802473 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3968785 | Completed | 15660 | 15660 | 2018-07-03 | 2018-12-01
KALAPIPAL | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008006/IF/IAY/1922555 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4116842 | Completed | 15660 | 15660 | 2018-09-21 | 2019-02-02
KALAPIPAL | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008006/IF/IAY/1923224 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4365548 | Completed | 15660 | 14616 | 2018-09-17 | 2019-03-22
KALAPIPAL | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008006/IF/IAY/1923251 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4380286 | Completed | 15660 | 15660 | 2018-09-17 | 2019-02-02
KALAPIPAL | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008006/IF/IAY/1923721 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4605432 | Completed | 15660 | 15660 | 2018-09-21 | 2018-12-24
KALAPIPAL | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008006/IF/IAY/1923728 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4608324 | Completed | 15660 | 14616 | 2018-09-21 | 2019-03-22
KALAPIPAL | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008006/IF/IAY/1924064 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4774373 | Completed | 15660 | 14616 | 2018-09-21 | 2019-03-22
KALAPIPAL | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008006/IF/IAY/1937725 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2217398 | Completed | 15660 | 14616 | 2018-09-21 | 2019-03-22
KALAPIPAL | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008006/IF/IAY/1937849 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1458078 | Completed | 15660 | 15660 | 2018-09-17 | 2018-12-01
KALAPIPAL | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008006/IF/IAY/2112256 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4387290 | Completed | 15840 | 15840 | 2019-10-07 | 2020-01-23
KALAPIPAL | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008006/IF/IAY/2112260 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4387344 | Completed | 15840 | 15840 | 2019-09-23 | 2019-12-18
KALAPIPAL | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008006/IF/IAY/2114779 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4420309 | Completed | 15840 | 15840 | 2019-10-07 | 2020-01-23
KALAPIPAL | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008006/IF/IAY/2124551 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4627282 | Completed | 15840 | 15840 | 2019-10-07 | 2020-03-31
KALAPIPAL | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008006/IF/IAY/2124943 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4640323 | Completed | 15840 | 15840 | 2019-09-03 | 2020-01-14
KALAPIPAL | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008006/IF/IAY/2127214 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4702696 | Completed | 15840 | 15840 | 2019-10-07 | 2020-01-23
KALAPIPAL | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008006/IF/IAY/2144495 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5123215 | Completed | 15840 | 15840 | 2019-10-07 | 2020-03-31
KALAPIPAL | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008006/IF/IAY/2164398 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5630180 | Completed | 15840 | 15840 | 2019-10-07 | 2020-01-23
KALAPIPAL | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008006/IF/IAY/2166233 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5678098 | Completed | 15840 | 15840 | 2019-09-03 | 2020-02-22
KALAPIPAL | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008006/IF/IAY/2169719 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2984681 | Completed | 15840 | 15840 | 2019-11-01 | 2020-02-10
KALAPIPAL | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008006/IF/IAY/2169788 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2323271 | Completed | 15840 | 15840 | 2019-11-01 | 2020-02-10
KALAPIPAL | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008006/IF/IAY/2227996 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4695222 | Completed | 15840 | 15840 | 2019-10-07 | 2020-02-05
KALAPIPAL | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008006/IF/IAY/2228335 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5141732 | Completed | 15840 | 15840 | 2019-09-23 | 2020-03-31
KALAPIPAL | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008006/IF/IAY/237372 — Construction of IAY House -IAY REG. NO. MP1453877 | Completed | 15030 | 15090 | 2017-01-29 | 2017-11-15
KALAPIPAL | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008006/IF/IAY/259199 — Construction of IAY House -IAY REG. NO. MP2288825 | Completed | 15030 | 15758 | 2017-01-29 | 2017-11-15
KALAPIPAL | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008006/IF/IAY/264680 — Construction of IAY House -IAY REG. NO. MP3828698 | Completed | 15030 | 14756 | 2017-01-29 | 2017-12-14
KALAPIPAL | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008006/IF/IAY/272411 — Construction of IAY House -IAY REG. NO. MP2912194 | Completed | 15030 | 15985 | 2017-01-29 | 2018-01-08
KALAPIPAL | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008006/IF/IAY/277126 — Construction of IAY House -IAY REG. NO. MP3561739 | Completed | 15030 | 10688 | 2017-01-29 | 2018-08-28
KALAPIPAL | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008006/IF/IAY/4328049 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116027619 | Completed | 18360 | 18343 | 2022-09-13 | 2023-10-08
KALAPIPAL | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008006/IF/IAY/4361920 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141418442 | Completed | 18360 | 18309 | 2022-11-10 | 2023-10-08
KALAPIPAL | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008006/IF/IAY/4383221 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116887077 | Completed | 18360 | 18306 | 2022-12-03 | 2023-10-16
KALAPIPAL | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008006/IF/IAY/4408452 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141418713 | Completed | 19890 | 19890 | 2023-07-14 | 2024-01-22
KALAPIPAL | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008006/IF/IAY/4561846 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115900815 | Completed | 21870 | 21870 | 2024-11-06 | 2025-04-02
KALAPIPAL | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008006/IF/IAY/649825 — Construction of IAY House -IAY REG. NO. MP2961005 | Completed | 15030 | 15030 | 2017-03-05 | 2017-11-15
KALAPIPAL | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008006/IF/IAY/701803 — Construction of IAY House -IAY REG. NO. MP1454252 | Completed | 15030 | 15480 | 2017-09-19 | 2017-12-14
KALAPIPAL | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008006/IF/IAY/702057 — Construction of IAY House -IAY REG. NO. MP1458078 | Deleted | 15030 | 0 | 2018-02-01
KALAPIPAL | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008006/IF/IAY/739509 — Construction of IAY House -IAY REG. NO. MP2217398 | Deleted | 15030 | 0 | 2018-02-01
KALAPIPAL | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008006/IF/IAY/739911 — Construction of IAY House -IAY REG. NO. MP2228524 | Completed | 15030 | 15136 | 2017-10-18 | 2017-12-27
KALAPIPAL | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008006/IF/IAY/740109 — Construction of IAY House -IAY REG. NO. MP2232854 | Completed | 15030 | 14448 | 2017-10-18 | 2018-05-01
KALAPIPAL | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008006/IF/IAY/759616 — Construction of IAY House -IAY REG. NO. MP2939238 | Completed | 15030 | 15480 | 2017-09-19 | 2017-12-28
KALAPIPAL | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008006/IF/IAY/760203 — Construction of IAY House -IAY REG. NO. MP2966375 | Completed | 15030 | 16512 | 2017-10-18 | 2018-01-19
KALAPIPAL | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008006/IF/IAY/761263 — Construction of IAY House -IAY REG. NO. MP3017662 | Completed | 15030 | 16512 | 2017-10-24 | 2018-01-19
KALAPIPAL | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008006/IF/IAY/825254 — Construction of IAY House -IAY REG. NO. MP2960915 | Completed | 15480 | 15136 | 2017-10-18 | 2017-12-29
KALAPIPAL | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008006/IF/IAY/985417 — Construction of IAY House -IAY REG. NO. MP2946850 | Completed | 15480 | 14448 | 2017-10-24 | 2018-05-01
KALAPIPAL | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719008006/IF/कपिलधारा क — कपिलधारा कूप भरतसिंह हजारीलाल पारदाखेडी | Completed | 59600 | 88424 | 2009-02-23 | 2009-09-03
KALAPIPAL | 2015-2016 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1719008006/LD/22012034231651 — शांतिधाम निर्माण श्‍मशान में पारदाखेडी | Deleted | 0 | 0 | 2015-08-09
KALAPIPAL | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1719008006/LD/22012034232198 — शांतिधाम निर्माण पारदाखेडी | Completed | 674000 | 433313.97 | 2015-10-13 | 2018-06-15
KALAPIPAL | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1719008006/LD/22012034254951 — शांतिधाम निर्माण घाटखेडी में | Deleted | 1200000 | 0 | 2017-03-13
KALAPIPAL | 2017-2018 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1719008006/LD/22012034314909 — खैलमैदान निर्माण ग्राम घाटखेडी | Completed | 180000 | 42444 | 2017-06-01 | 2021-11-10
KALAPIPAL | 2014-2015 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1719008006/LD/9926713317 — डो्गंरी वाले जंगल मे व़क्षारोपण | Deleted | 0 | 0 | 2014-06-26
KALAPIPAL | 2016-2017 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1719008006/PG/9425895302 — खैलमैदान निर्माण पारदाखेडी में | Completed | 186000 | 9018 | 2017-03-19 | 2018-10-29
KALAPIPAL | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1719008006/RC/1ग्रेवल सड — ग्रेवल सडक भगवानसिह के मकान के पास से खल्‍या घाट तक घाटखेडी पारदाखेडी | Deleted | 0 | 0 | 2008-11-20
KALAPIPAL | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719008006/RC/22012034156195 — पंचपरमेश्‍वर मनरेगा सी.सी.रोड निर्माण रामफुल के मक | Completed | 132000 | 102107.08 | 2013-09-23 | 2016-08-27
KALAPIPAL | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719008006/RC/22012034156198 — सी सी रोड निर्माण जमनाप्रसाद से रामनारायण के मकान तक | Deleted | 0 | 0 | 2013-03-20
KALAPIPAL | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719008006/RC/22012034156205 — सी सी रोड निर्माण कालुकुमार के मकान से देवीिसंह के | Completed | 119000 | 102596.83 | 2013-09-20 | 2016-08-27
KALAPIPAL | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719008006/RC/22012034156206 — सी.सी.रोड निर्माण घाटखेडी से भगवानसिंह के मकान तक | Deleted | 0 | 0 | 2013-03-20
KALAPIPAL | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719008006/RC/22012034165969 — पंच परमेश्‍वर + मनरेगा सी सी रौड ठाकुरप्रसाद के मक | Deleted | 0 | 0 | 2013-01-30
KALAPIPAL | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719008006/RC/22012034166569 — सी सी रौड पंचपरमेश्‍वर रामसिह के मकान से देवनारायण | Completed | 145000 | 173058.94 | 2012-05-03 | 2016-08-27
KALAPIPAL | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719008006/RC/22012034166814 — सी सी रौड ठाकुर प्रसाद के मकान से हनुमान मंदिर तक | Completed | 128400 | 155958.05 | 2012-05-03 | 2016-08-27
KALAPIPAL | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719008006/RC/22012034166816 — सी सी रौड श्री राम मंदिर से देव महाराज के ओटला तक | Completed | 128000 | 140790.1 | 2012-05-03 | 2016-08-27
KALAPIPAL | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719008006/RC/22012034221628 — सी.सी.रोड निर्माण विष्‍णु के मकान से पंचायत भवन त | Deleted | 0 | 0 | 2014-01-26
KALAPIPAL | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1719008006/RC/22012034221629 — खेत सडक योजना मुख्‍य मार्ग से कि शनलाल छितरमल के खेत तक | Deleted | 0 | 0 | 2014-01-26
KALAPIPAL | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1719008006/RC/22012034221630 — खेंत सडक योजना मुख्‍य मार्ग से घाटखेडी तक | Deleted | 0 | 0 | 2014-01-26
KALAPIPAL | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719008006/RC/22012034224643 — c.c.rod jamna ke makan se ramcharan ka makan takar | Deleted | 0 | 0 | 2014-01-26
KALAPIPAL | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719008006/RC/22012034225110 — मनोहरसिहके मकानसे देवीसिह के मकान तक | Deleted | 0 | 0 | 2014-06-26
KALAPIPAL | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719008006/RC/22012034225116 — मनोहरसिहके मकानसे देवीसिह के मकान तक | Deleted | 249000 | 0 | 2014-06-26
KALAPIPAL | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719008006/RC/22012034225178 — सी सी रोड विष्‍णु के मकान से पंचायत भवन तक | Deleted | 0 | 0 | 2014-01-26
KALAPIPAL | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719008006/RC/22012034225179 — सी सी रोड जमना के मकान से रामचरण के मकान तक | Deleted | 0 | 0 | 2014-01-26
KALAPIPAL | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719008006/RC/22012034225182 — श्री राम मंदिर से काला जी के ओटला तक | Deleted | 0 | 0 | 2014-01-26
KALAPIPAL | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1719008006/RC/22012034225220 — ग्रेवल रोड कालाजी के ओटले से भगवान सिह के मकान तक | Deleted | 0 | 0 | 2014-01-26
KALAPIPAL | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1719008006/RC/22012034225376 — मुख्‍य मार्ग से जीतमल के खेत तक | Deleted | 0 | 0 | 2014-01-26
KALAPIPAL | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1719008006/RC/22012034225543 — मुख्‍य मार्ग से रामसिह के खेत से घाटखेडी तक | Deleted | 0 | 0 | 2014-06-26
KALAPIPAL | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719008006/RC/22012034262514 — सी.सी.रोड निर्माण विष्‍णु के मकान से पंचायत भवन तक | Deleted | 0 | 0 | 2015-01-26
KALAPIPAL | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719008006/RC/22012034262515 — सी.सी.रोड निर्माण जमना के मकान से रामचरण के मकान तक | Deleted | 0 | 0 | 2015-01-26
KALAPIPAL | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719008006/RC/22012034262524 — सी.सी.राेड निर्माण राममंदिर से कालाजी के ओटाला तक | Deleted | 0 | 0 | 2015-01-26
KALAPIPAL | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719008006/RC/22012034267700 — सी सी रौड पंचपरमेश्‍वर मनरेगा निर्माण मनोहरसिह के मकान से देवीसिह के मकान तक | Completed | 99000 | 78685.68 | 2015-10-13 | 2018-04-19
KALAPIPAL | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719008006/RC/22012034286370 — सी सी रौड निर्माण जमनाप्रसाद के मकान से रामचरण मीना के मकान तक | Completed | 149000 | 131191.77 | 2015-12-12 | 2016-08-27
KALAPIPAL | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1719008006/RC/22012034293481 — सुदूर ग्राम संपर्क खेत सडक योजना ग्राम पारदाखेडी से ठाकुरप्रसाद के खेत की ओर | Completed | 1465000 | 1284112.41 | 2015-12-21 | 2019-12-18
KALAPIPAL | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719008006/RC/22012034303914 — सी सी रोड निर्माण लखनलाल के मकान जयनारायण के मकान की ओर | Completed | 161000 | 111179.79 | 2016-12-18 | 2018-04-19
KALAPIPAL | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719008006/RC/22012034317730 — सी सी रोड एवं नाली निर्माण प्रा विधालय भवन से गुलाबसिंह के मकान की ओर | Completed | 178000 | 100649.89 | 2016-12-18 | 2019-03-13
KALAPIPAL | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719008006/RC/22012034320797 — Cc road | Closed | 0 | 0 | 2016-10-02
KALAPIPAL | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719008006/RC/22012034320813 — सी सी रोड एवं नाली निर्माण कार्य | Closed | 60000 | 0 | 2016-10-02
KALAPIPAL | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719008006/RC/22012034330032 — सी सी रोड एवं नाली निर्माण रतनलाल जाट के मकान से प्रा वि शाला भवन तक | Completed | 166000 | 58154 | 2017-03-19 | 2019-03-13
KALAPIPAL | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719008006/RC/22012034449005 — सीसी रोड एवं नाली निर्माण प्रावि से मांगीलाल जाट के मकान तक | Completed | 184000 | 98896 | 2019-03-06 | 2020-11-28
KALAPIPAL | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719008006/RC/22012034513029 — CC ROAD AND NALI NIRMAN SHIV MANDIR SE MAIN ROAD TAK PARDAKHEDI | Closed | 23000 | 0 | 2019-08-15
KALAPIPAL | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719008006/RC/22012034513030 — CC ROAD AND NALI NIRMAN INDAR SINGH KE MAKAN SE HARIJAN MOHALLA TAK GHATKHEDI | Closed | 33000 | 0 | 2019-08-15
KALAPIPAL | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719008006/RC/22012034513031 — CC ROAD AND NALI NIRMAN LILA BAI KE MAKAN SE MOHANLAL MEENA KE MAKAN TAK PARDAKHEDI | Completed | 27075 | 25428 | 2020-02-06 | 2020-11-28
KALAPIPAL | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719008006/RC/22012034513032 — CC ROAD AND NALI NIRMAN PURANA PANCHAYAT BHAWAN SE MAIN ROAD TAK PARDAKHEDI | Completed | 63563 | 51922 | 2020-02-06 | 2020-11-28
KALAPIPAL | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1719008006/RC/22012034524885 — सुदुर ग्राम सम्‍पर्क सडक | Closed | 0 | 0 | 2020-04-05
KALAPIPAL | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1719008006/RC/22012034525411 — सुदुर ग्राम सडक कालाजी के चबुतरे से शांतिधाम तक घाटखेडी | Completed | 577150.08 | 224570 | 2020-06-24 | 2024-09-20
KALAPIPAL | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719008006/RC/22012034554567 — CC NIRMAN KARYA HANUMAN MANDIR SE JIND MAHARAJ KE OTLE KI AUR GP PARDAKHEDI | Completed | 44396 | 44650 | 2020-12-31 | 2021-09-16
KALAPIPAL | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1719008006/RC/22012034569435 — GRAM PARDAKHEDI ME THAKUR PRASAD KE KHET SE CHAND SINGH KE KHET TAK KHET SADAK | Completed | 1331728.96 | 1101114.4 | 2021-05-22 | 2026-02-24
KALAPIPAL | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719008006/RC/22012034590996 — CC ROAD NIRMAN INDAR SINGH KE MAKAN SE PANNALAL KE MAKAN KI AUR GP KHAJURI ALAHDAD | Completed | 44000 | 43618 | 2022-01-19 | 2023-01-04
KALAPIPAL | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719008006/RC/22012034622862 — सी सी रोड निर्माण शिवमंदिर के सामने | Closed | 0 | 0 | 2022-10-02
KALAPIPAL | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719008006/RC/22012034625432 — C C Road Nirman Work Main Road Se ShivMandir Tak | Completed | 26439 | 25500 | 2023-09-25 | 2024-09-04
KALAPIPAL | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719008006/RC/22012034677884 — C C Road Nirman Work gram me | New | 0 | 0 | 2024-01-27
KALAPIPAL | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719008006/RC/22012034832395 — C C Road nirman Work prathmik School Se Ram mandir Ki Aur | Completed | 59386 | 50165.7 | 2025-03-07 | 2026-02-05
KALAPIPAL | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1719008006/RC/2ग्रेवल सड — ग्रेवल सडक भगवानसिह के मकान के पास से खल्‍या घाट तक घाटखेडी पारदाखेडी | Deleted | 211000 | 155077 | 2009-01-21
KALAPIPAL | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1719008006/RC/4अर्थवर्क — अर्थवर्क ग्राम घाटखेडी से भगवान सिह के मकान तक | Deleted | 366000 | 143972 | 2009-05-21
KALAPIPAL | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Drainage Channel / Construction of Flood/ Diversion Channel for Community | Solid and Liquid Waste Management | 1719008006/RS/22012034254412 — शौचालय विजेन्‍द्र सिह दरियावसिह निर्मलवाटिका | Deleted | 0 | 0 | 2014-07-15
KALAPIPAL | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Drainage Channel / Construction of Flood/ Diversion Channel for Community | Solid and Liquid Waste Management | 1719008006/RS/22012034254416 — शौचालय राधेलाल निर्मलवाटिका | Deleted | 0 | 0 | 2014-06-26
KALAPIPAL | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Drainage Channel / Construction of Flood/ Diversion Channel for Community | Solid and Liquid Waste Management | 1719008006/RS/22012034254417 — शौचालय सिद़नाथ रामलाल निर्मलवाटिका | Deleted | 0 | 0 | 2014-06-26
KALAPIPAL | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Drainage Channel / Construction of Flood/ Diversion Channel for Community | Solid and Liquid Waste Management | 1719008006/RS/22012034254421 — शैचालय देवीसिह श्रीकिशन निर्मलवाटिका | Deleted | 0 | 0 | 2014-06-26
KALAPIPAL | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Drainage Channel / Construction of Flood/ Diversion Channel for Community | Solid and Liquid Waste Management | 1719008006/RS/22012034254423 — शौचालय रामनाथसिह शेरसिह निर्मलवाटिका | Deleted | 0 | 0 | 2014-06-26
KALAPIPAL | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Drainage Channel / Construction of Flood/ Diversion Channel for Community | Solid and Liquid Waste Management | 1719008006/RS/22012034254426 — शौचालय टीकाराम भाग‍चन्‍द्र निर्मलवाटिका | Deleted | 0 | 0 | 2014-06-26
KALAPIPAL | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719008006/RS/22012034377392 — व्यक्तिगत शौचालय निर्माण श्रीकिशन एवं अन्य 9 हितग्राही पारदाखेडी | Completed | 115000 | 114080 | 2017-10-24 | 2018-09-05
KALAPIPAL | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1719008006/RS/22012034558152 — सामुदायिक कम्‍पोज्‍ड पीट प्राथ्‍ामिक भवन के पीछे ग्राम पंचायत पारदाखेडी ग्रामपारदाखेडी | Completed | 12630.91 | 10762.88 | 2021-11-23 | 2023-07-06
KALAPIPAL | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1719008006/RS/22012034558161 — सामुदायिक कम्‍पोज्‍ड पीट मोहल्‍ले के पास ग्राम पंचायत पारदाखेडी ग्रामपारदाखेडी | Completed | 12630.91 | 9757.68 | 2021-11-23 | 2023-07-06
KALAPIPAL | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1719008006/RS/22012034558165 — सामुदायिक कम्‍पोज्‍ड पीट पुराने पंचायत भवन के पास ग्राम पंचायत पारदाखेडी ग्रामपारदाखेडी | Closed | 12630.91 | 0 | 2021-08-15
KALAPIPAL | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1719008006/RS/22012034558170 — सामुदायिक कम्‍पोज्‍ड पीट बाखल मोहल्‍ला के पास ग्राम पंचायत पारदाखेडी ग्रामपारदाखेडी | Closed | 0 | 0 | 2021-08-15
KALAPIPAL | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1719008006/RS/22012034558175 — सामुदायिक कम्‍पोज्‍ड पीट प्रेमनारायण के घर के पास ग्राम पंचायत पारदाखेडी ग्रामपारदाखेडी | Closed | 0 | 0 | 2021-08-15
KALAPIPAL | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1719008006/RS/22012034558179 — सामुदायिक कम्‍पोज्‍ड पीट हरिजन मोहल्‍ला के पास ग्राम पंचायत पारदाखेडी ग्राम घाटखेडी | Closed | 12630.91 | 0 | 2021-08-15
KALAPIPAL | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1719008006/RS/22012034558183 — सामुदायिक कम्‍पोज्‍ड पीट मोहनलाल के घर के पास ग्राम पंचायत पारदाखेडी ग्राम घाटखेडी | Completed | 12630.91 | 11555 | 2021-12-08 | 2022-09-12
KALAPIPAL | 2016-2017 | D--RURAL INFRASTUCTURE / Bharat Nirman Sewa Kendra | Upgradation/extension of Panchayat Bhawan / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Repair & Maint of Community infrastructure | 1719008006/SK/9993648841 — Bharat Nirman Rajeev Gandhi Sewa Kendra,PARDAKHEDI | Completed | 1285000 | 425543.52 | 2017-01-08 | 2020-11-28
KALAPIPAL | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Boulder Check / Construction of Boulder Check Dam for Community | Boulder Check/Gully Plug | 1719008006/WC/22012034354108 — बोरी बंधान कार्य घाट खेडी | Completed | 6000 | 5848 | 2017-09-21 | 2017-11-10
KALAPIPAL | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Boulder Check / Construction of Boulder Check Dam for Community | Boulder Check/Gully Plug | 1719008006/WC/22012034354109 — बोरी बंधान कार्य पारदाखेडी | Completed | 6000 | 5160 | 2017-09-21 | 2017-11-13
KALAPIPAL | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1719008006/WC/22012034379791 — चेकडेम | Closed | 0 | 0 | 2017-11-21
KALAPIPAL | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1719008006/WC/22012034380011 — चेकडेम | Closed | 0 | 0 | 2017-11-21
KALAPIPAL | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1719008006/WC/22012034425329 — नाला गहरीकरण खेडी का घाटखेडी | Completed | 99603 | 88392 | 2018-10-07 | 2019-05-28
KALAPIPAL | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1719008006/WC/22012034425335 — खेडी के नाले पर चेक डेम निर्माण घाटखेडी | Closed | 404000 | 0 | 2018-08-15
KALAPIPAL | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719008006/WC/22012034477185 — SOKHTA GADDA SARWAJANIK KUP KE PASS PARDAKHEDI | Closed | 0 | 0 | 2019-06-28
KALAPIPAL | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719008006/WC/22012034477186 — SOKHTA GADDA MADHYAMIK VIDHYALAYA KE PASS HAND PUMP PARDAKHEDI | Closed | 0 | 0 | 2019-06-28
KALAPIPAL | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719008006/WC/22012034477187 — SOKHTA GADDA SARWAJANIK HANDPUMP RAISINGH KE GHAR KE PASS PARDAKHEDI | Closed | 0 | 0 | 2019-06-28
KALAPIPAL | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719008006/WC/22012034477188 — SOKHTA GADDA GAJRAJ S/O RAMCHARAN KE GHAR KE PASS SARWAJANIK HAND PUMP PARDAKHEDI | Closed | 0 | 0 | 2019-06-28
KALAPIPAL | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719008006/WC/22012034477189 — SOKHTA GADDA PRATHMIK VIDHYALAY KE PASS HAND PUMP GHATKHEDI | Closed | 0 | 0 | 2019-06-28
KALAPIPAL | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719008006/WC/22012034477190 — SOKHTA GADDA KALAJI KE OTLE KE PASS HANDPUMP GHATKHEDI | Closed | 0 | 0 | 2019-06-28
KALAPIPAL | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719008006/WC/22012034477191 — SOKHTA GADDA HARIJAN MOHALLE KE HANDPUMP ME GHATKHEDI | Closed | 0 | 0 | 2019-06-28
KALAPIPAL | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719008006/WC/22012034477192 — SOKHTA GADDA RAMNARAYAN SINGH KE GHAR KE PASS HANDPUMP GHATKHEDI | Closed | 0 | 0 | 2019-06-28
KALAPIPAL | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719008006/WC/22012034477193 — SOKHTA GADDA RAMMANDIR KE PASS HAND PUMP GHATKHEDI | Closed | 0 | 0 | 2019-06-28
KALAPIPAL | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1719008006/WC/22012034479584 — WATER ROOF HARVESTING PANCHAYAT BHAWAN | Completed | 9780 | 9116 | 2019-08-11 | 2021-12-07
KALAPIPAL | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719008006/WC/22012034625088 — सोकता गढढा रिचार्ज पीट | Completed | 14467.3 | 14496.79 | 2021-05-17 | 2021-09-13
KALAPIPAL | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719008006/WC/22012034625091 — सोकता गढढा रिचार्ज पिट | Completed | 14467.3 | 14303.79 | 2021-05-17 | 2022-09-12
KALAPIPAL | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719008006/WC/22012034759551 — sokta gadda midiil school ke paas hendpum pardhakhedi | Completed | 14467.3 | 13054.18 | 2021-06-24 | 2023-07-06
KALAPIPAL | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719008006/WC/22012034759552 — sokta gadda midiil school ke paas hendpum pardhakhedi | Closed | 0 | 0 | 2021-04-14
KALAPIPAL | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719008006/WC/22012034759568 — sokta gadda hanuman mandir ke paas hendpum pardhakhedi | Completed | 14467.3 | 9580.41 | 2021-06-24 | 2023-07-06
KALAPIPAL | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719008006/WC/22012034759583 — sokta gadda gajraj meena ke ghar ke paas hendpum pardhakhedi | Completed | 14467.3 | 13054.41 | 2021-06-24 | 2023-07-06
KALAPIPAL | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719008006/WC/22012034759603 — recharg pit premnarayan ke khet par teubell ke paas pardhakhedi | Completed | 14467.3 | 13054.41 | 2021-06-24 | 2023-07-06
KALAPIPAL | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719008006/WC/22012034759620 — sokta gadda lal ji ram ke ghar ke paas hendpum ghatkhedi | Closed | 0 | 0 | 2021-04-14
KALAPIPAL | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719008006/WC/22012034940318 — सोख्‍ता गडडा निर्माण कार्य ग्राम में | Closed | 15140.3 | 0 | 2022-04-01
KALAPIPAL | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Stone graded Bund for Community / Construction of Stone graded Bund for Community | Construction of Bund | 1719008006/WC/22012035172083 — Boulder Nala Bund Nirman Work 1 | Completed | 15460.54 | 7732 | 2024-03-02 | 2025-05-17
KALAPIPAL | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1719008006/WC/22012035233409 — Dugout pond nirman Dhomri Ke pas Gram Paradkhedi | Completed | 676490.56 | 282462 | 2025-03-17 | 2026-04-16
KALAPIPAL | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1719008006/WC/22012035294748 — JGSA 2025 RECHARGE STRUCTURE Middile School Ke Pass Gp pardakhedi | Physically Completed | 25899.46 | 15620.26 | 2025-05-11 | 2026-04-10
KALAPIPAL | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Artificial Recharge of Well Through Sand Filter / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1719008006/WC/मीडिल स्‍क — सार्वजनिक कूप निर्माण मीडिल स्‍कुल के पास | Completed | 384000 | 338010 | 2011-11-15 | 2016-08-27
KALAPIPAL | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1719008006/WH/19962207 — तालाब जीर्णोद्वार शासकीय तालाब बडली ग्राम घाटखेंडी ग्राम पंचायत पारदाखेडी खसरा नम्बर 44 | Closed | 147000 | 0 | 2017-04-14
KALAPIPAL | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1719008006/WH/19963207 — तालाब ज़िर्णॉदोर् पारदाखेडी | Completed | 267000 | 516 | 2017-06-06 | 2018-09-06
KALAPIPAL | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1719008006/WH/22012034453265 — TALAB JIRNODHHAR / MARAMMAT KARYA GP Pardakhedi | Closed | 0 | 0 | 2021-10-02
KALAPIPAL | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1719008006/WH/22012034919945 — तालाब जीर्णोद्वार कार्य शासकीय तालाब बडली ग्राम घाटखेडी खसरा नम्बर 44 | Completed | 147000 | 146814 | 2022-03-18 | 2022-12-07