## Work List
Exported on: 2026-10-23 20:00:31
Filters applied:
Data source: VBGRAMG
District: SHAJAPUR
Block: All
Panchayat: BAGODA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
KALAPIPAL | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play Ground for Government School for Community | Construction of Play field | 1719008015/AV/22012034664093 — खैलमैदान निर्माण कार्य मांगलिक भवन के सामने ग्राम पंचायत बागोदा | New | 0 | 0 | 2024-10-02
KALAPIPAL | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1719008015/IC/22012034886331 — सार्वजनिक कूप निर्माण पुलिया के पास ग्राम पंचायत बागोदा | New | 0 | 0 | 2024-10-02
KALAPIPAL | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1719008015/IF/22012035282371 — Kapildhara Kup Nirman Work Rupesh Singh Chawda Shiv Singh Chawda | Ongoing | 285144.63 | 0 | 2025-01-06
KALAPIPAL | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1719008015/IF/22012035284894 — Kapildhara Kup Nirman Work Mohan Singh Chawda Vikram Singh Chawda | Ongoing | 299173.39 | 0 | 2025-03-02
KALAPIPAL | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1719008015/IF/22012035298446 — Kapildhara Kup Nirman Work Mohan Singh Rajput Bhagwat Singh | Ongoing | 292960.1 | 300 | 2025-03-02
KALAPIPAL | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1719008015/IF/22012035333066 — Kapildhara Kup Nirman Work Jasamat Singh Setan Singh Rajput | Ongoing | 300526.73 | 50 | 2025-04-25
KALAPIPAL | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1719008015/IF/22012035493486 — Kapildhara Kup Nirman Work Lokendra Rajput Govrdhan Singh | Ongoing | 304664.03 | 1800 | 2025-05-20
KALAPIPAL | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719008015/IF/IAY/5888117 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120683243 | Completed | 23490 | 0 | 2026-04-09 | 2026-07-22
KALAPIPAL | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719008015/IF/IAY/5888118 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120686168 | Completed | 27000 | 3915 | 2026-05-08 | 2026-09-22
KALAPIPAL | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719008015/IF/IAY/5888120 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120712041 | Completed | 23490 | 0 | 2026-04-25 | 2026-07-22
KALAPIPAL | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719008015/IF/IAY/5888239 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120694392 | Completed | 23490 | 522 | 2026-04-18 | 2026-07-22
KALAPIPAL | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719008015/IF/IAY/5888240 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120700521 | Completed | 27000 | 10500 | 2026-04-24 | 2026-09-12
KALAPIPAL | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719008015/IF/IAY/5888307 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127965024 | Completed | 27000 | 4950 | 2026-04-18 | 2026-09-22
KALAPIPAL | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719008015/IF/IAY/5888335 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120714541 | Completed | 23490 | 5220 | 2026-04-24 | 2026-08-31
KALAPIPAL | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719008015/IF/IAY/5888336 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120715289 | Completed | 23490 | 0 | 2026-04-24 | 2026-07-22
KALAPIPAL | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719008015/IF/IAY/5888338 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120699073 | Completed | 23490 | 5220 | 2026-04-09 | 2026-09-12
KALAPIPAL | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719008015/IF/IAY/5888379 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120708450 | Completed | 23490 | 3380 | 2026-04-24 | 2026-09-12
KALAPIPAL | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719008015/IF/IAY/6080622 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120836312 | Completed | 27000 | 8800 | 2026-04-24 | 2026-08-31
KALAPIPAL | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1719008015/WC/22012035203298 — डग आउट पोंड निर्माण कार्य कुंडाल में ग्राम पंचायत बागोदा | Approved | 0 | 0 | 2024-06-06
KALAPIPAL | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1719008015/WC/22012035230115 — तालाब निर्माण (डग आउट पोंड ) कुडांल में ग्राम पंचायत बागोदा | Approved | 1264332.28 | 0 | 2024-10-02
KALAPIPAL | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Borewell for Community | Well Recharge | 1719008015/WC/22012035298397 — JGSA 2025 RECHARGE STRUCTURE -सार्वजनिक कूप nale k pas बागोदा GP Bagoda | Approved | 25899.46 | 0 | 2025-04-01
KALAPIPAL | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1719008015/WC/22012035298399 — JGSA 2025 RECHARGE STRUCTURE -सार्वजनिक कूप खेड़ी पर बागोड़ा GP Bagoda | Approved | 25899.46 | 0 | 2025-04-01
KALAPIPAL | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1719008015/WC/VB/22012035332089 — Dugwell Recharge Structure Sarvjanik Kup Babulal Ke Ghar ke pas GP BAGODA | Approved | 0 | 0 | 2026-06-29