## Work List
Exported on: 2026-09-02 20:51:53
Filters applied:
Data source: VBGRAMG
District: SHAJAPUR
Block: All
Panchayat: LASUDALYAMALAK
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
KALAPIPAL | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1719008037/DP/22012034444930 — सार्वजनिक कूप निर्माण खडलावाला माल के पास | Ongoing | 535000 | 0 | 2019-03-09
KALAPIPAL | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719008037/IF/22012035219819 — KapilDhara Kup Nirman Work Sukhram- Phundilal | Ongoing | 282417.57 | 600 | 2024-03-14
KALAPIPAL | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719008037/IF/22012035350660 — Kapildhara Kup Nirman Work Parasmani Devi Rakesh | Ongoing | 307953.3 | 0 | 2025-05-07
KALAPIPAL | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719008037/IF/22012035350685 — Kapildhara Kup Nirman Work Ramraj Parmar Prahalad parmar | Ongoing | 307953.3 | 0 | 2025-05-03
KALAPIPAL | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719008037/IF/22012035350700 — Kapildhara Kup Nirman Work Rajesh Parmar Makhan Singh | Ongoing | 307953.3 | 20100 | 2025-05-15
KALAPIPAL | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008037/IF/IAY/4141084 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114833636 | Approved | 27000 | 0 | 2022-05-24
KALAPIPAL | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008037/IF/IAY/4955114 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120553657 | Completed | 23490 | 0 | 2025-04-16 | 2026-07-23
KALAPIPAL | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008037/IF/IAY/5004593 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119410828 | Ongoing | 27000 | 0 | 2025-04-16
KALAPIPAL | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008037/IF/IAY/5877970 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115063493 | Ongoing | 27000 | 0 | 2026-04-08
KALAPIPAL | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719008037/RC/22012034535059 — CC SHANTIDHAM PARISAR ME AVM GATE NIRMAN GP LASUDIYA MALAK | Ongoing | 109000 | 0 | 2020-11-25
KALAPIPAL | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1719008037/RC/22012034574604 — खेत सड़क निर्माण कार्य लसु.मलक पानी की टंकी से धुबोटि के कांकड़ तक ग्राम पंचायत लसूड़लिया मलक | Ongoing | 1993532.22 | 0 | 2021-11-10
KALAPIPAL | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719008037/RC/22012034673939 — C C Road Nirman Work Gram me | New | 0 | 0 | 2024-01-27
KALAPIPAL | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719008037/RC/22012034839486 — C C Road NIrman Work Hadlyakhura Road Se Mukesh Ke Makan Ki Aur | Approved | 90461 | 0 | 2024-12-16