## Work List
Exported on: 2026-10-26 17:16:55
Filters applied:
Data source: MGNREGA + VBGRAMG
District: DEWAS
Block: All
Panchayat: GHATIYAKALAN
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SONKATCH | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1720002004/AV/22012034374667 — Shantidham nirman ghattiyakal | Completed | 180000 | 175273.96 | 2019-03-02 | 2020-06-19
SONKATCH | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Kitchen Shed / Construction of Kitchen shed Building for Community | Constr of Kitchen Shed | 1720002004/AV/22012034589225 — डाइनिंग हाल बैठक व्यवस्था कार्य घटियाकला | Closed | 0 | 0 | 2021-08-15
SONKATCH | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Kitchen Shed / Construction of Kitchen shed Building for Community | Constr of Kitchen Shed | 1720002004/AV/22012034589458 — डाइनिंग हाल बैठक व्यवस्था कार्य मिडिल स्कूल | Closed | 23925.39 | 0 | 2021-08-15
SONKATCH | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Kitchen Shed / Construction of Kitchen shed Building for Community | Constr of Kitchen Shed | 1720002004/AV/22012034594748 — डाइनिंग हाल बैठक व्यवस्था कार्य मिडिल स्कूल मिडिल स्कूल | Closed | 0 | 0 | 2021-08-15
SONKATCH | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1720002004/DP/22012034486284 — निर्मलनीर ( नदी के रास्तें) | Closed | 0 | 0 | 2020-01-26
SONKATCH | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1720002004/DP/22012034520288 — निर्मल नीर इश्वर मोहल्ले के पास | Closed | 566510.07 | 0 | 2020-06-05
SONKATCH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Raising of Nursery for Community / Raising of Nursery for Community | Nursery Development | 1720002004/DP/22012034542923 — मिडिल स्कूल घतियाकला | Ongoing | 14475.4 | 386 | 2022-02-04
SONKATCH | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Sericulture- in Fields-Community / Block Plantation of Sericulture Trees in Fields for Community | Plantation | 1720002004/DP/22012034607040 — वसुधा वंदन अमृत वाटिका ग्राम घटिया कला | Closed | 55847.4 | 0 | 2023-04-04
SONKATCH | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Drinking Water | Soak Pits / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1720002004/DW/9993657076 — निर्मलनिर,शान्तिधाम के पास | Completed | 435000 | 400842.35 | 2016-01-08 | 2019-06-07
SONKATCH | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Drinking Water | Soak Pits / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1720002004/DW/9993657567 — निर्मालनिर,गोया के पास घ्‍टया कला | Completed | 425000 | 363131.36 | 2016-02-17 | 2021-08-10
SONKATCH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Well for Individual | Construction of Well | 1720002004/IF/22012034342019 — khet talab sah kup nirman,bondersingh ramchandra | Ongoing | 230000 | 227704 | 2017-05-22
SONKATCH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1720002004/IF/22012034342853 — plantetion nipaniya ke raaste se ghatyakalan tak | Completed | 335000 | 40588 | 2017-05-29 | 2024-09-27
SONKATCH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1720002004/IF/22012034342863 — plantetion shantidham va kridangan ke pas | Completed | 335000 | 38740 | 2017-05-29 | 2024-07-13
SONKATCH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002004/IF/22012034391796 — khet talab with kup nirman gorav krishnapal | Completed | 230000 | 229564 | 2018-01-13 | 2019-12-12
SONKATCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002004/IF/22012034441174 — Kapildhara Kup makhan dolaji | Closed | 210000 | 0 | 2018-08-20
SONKATCH | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002004/IF/22012034458863 — Kapildharakup nirman | Deleted | 0 | 0 | 2019-05-20
SONKATCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002004/IF/22012034467559 — Kapildhara kup nirman madansingh mangilal | Completed | 210000 | 207728 | 2019-03-02 | 2024-01-31
SONKATCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1720002004/IF/22012034468004 — Khet talab niraman shantabai raysingh | Ongoing | 288000 | 5964 | 2019-03-07
SONKATCH | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002004/IF/22012034491723 — Khet talab nirman | Deleted | 0 | 0 | 2019-04-25
SONKATCH | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002004/IF/22012034526909 — NRLM Work nirman khet talab nirman maya kelash | Closed | 0 | 0 | 2019-10-02
SONKATCH | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002004/IF/22012034526910 — NRLM Work nirman Khet talab nirman | Closed | 0 | 0 | 2019-10-02
SONKATCH | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002004/IF/22012034526911 — NRLM Work nirman kup nirman niaram guddi subhash | Closed | 0 | 0 | 2019-10-02
SONKATCH | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1720002004/IF/22012034526936 — NRLM Work Pashushed Rukhamadi | Closed | 0 | 0 | 2019-10-02
SONKATCH | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002004/IF/22012034541056 — खेत तालाब मानसिंह बापूसिंह | Completed | 310386.65 | 261820 | 2020-05-14 | 2021-01-22
SONKATCH | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002004/IF/22012034541057 — खेत तालाब (मोती सिंह बापूसिंह ) | Completed | 310386.65 | 225910 | 2020-05-09 | 2021-09-12
SONKATCH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002004/IF/22012034542448 — खेत तालाब (गेंदीबाई अम्बाराम ) | Completed | 310386.65 | 224459 | 2021-04-01 | 2021-09-09
SONKATCH | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002004/IF/22012034544710 — खेत तालाब धापूबाई माधोसिंह | Completed | 310386.65 | 266760 | 2020-05-17 | 2021-01-22
SONKATCH | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002004/IF/22012034551886 — Kapildhara kup niraman mansingh bapusingh samuh | Closed | 242453.87 | 0 | 2020-04-26
SONKATCH | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002004/IF/22012034552796 — samhuhik kapil dhara shyamlal dhakad | Completed | 242453.87 | 215457.04 | 2020-05-12 | 2022-11-16
SONKATCH | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002004/IF/22012034562328 — khet talab (madhusudan babulal) | Completed | 332572.21 | 262200 | 2020-06-03 | 2021-01-22
SONKATCH | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002004/IF/22012034618691 — खेत तालाब (चंदर पिता देवा ) | Completed | 332962.02 | 288420 | 2020-10-02 | 2021-09-09
SONKATCH | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002004/IF/22012034647747 — khet talab (lakhan s/o narayan) | Completed | 332962.02 | 259194 | 2021-01-01 | 2021-09-09
SONKATCH | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002004/IF/22012034650415 — Khet talab Krishna baai | Completed | 332962.02 | 256154 | 2021-01-14 | 2023-02-01
SONKATCH | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002004/IF/22012034664924 — खेत तालाब (घासीराम पिता खुमान ) | Completed | 332962.02 | 246636 | 2021-03-15 | 2024-10-28
SONKATCH | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002004/IF/22012034670227 — खेत तालाब राजेश बाबूलाल | Completed | 332962.02 | 297570 | 2021-03-15 | 2021-09-09
SONKATCH | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1720002004/IF/22012034670228 — खेत तालाब मुकेश बाबूलाल | Ongoing | 332962.02 | 172411.49 | 2021-03-15
SONKATCH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002004/IF/22012034828122 — khet talab kamal umravsingh | Completed | 338902.57 | 125161 | 2021-08-07 | 2024-05-20
SONKATCH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002004/IF/22012034831263 — खेत तालाब (प्रेमसिंह पन्नालाल) | Completed | 338902.57 | 222704 | 2021-08-06 | 2023-02-01
SONKATCH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002004/IF/22012034939660 — khet talab madan singh raam singh | Completed | 338902.57 | 202027.74 | 2022-03-11 | 2026-02-26
SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002004/IF/22012034957652 — khet talab gulabsingh s/o dariyavsingh | Completed | 338902.57 | 160038 | 2022-04-08 | 2024-02-02
SONKATCH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002004/IF/22012034957655 — khet talab radheshyam s/o sidhusingh | Closed | 338902.57 | 0 | 2022-01-26
SONKATCH | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1720002004/IF/22012034992381 — व्यक्तिगत मेजिक पिट /10 घटियाकला | Closed | 77722.26 | 0 | 2022-04-15
SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002004/IF/22012035003208 — खेत तालाब निर्माण - पंकज पिता रामचन्द्र | Deleted | 0 | 0 | 2022-05-20
SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002004/IF/22012035003416 — खेत तालाब निर्माण - दीपक पिता राजेश | Deleted | 0 | 0 | 2022-04-26
SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002004/IF/22012035003420 — खेत तालाब निर्माण - दीपक पिता राजेश | Deleted | 0 | 0 | 2022-04-26
SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002004/IF/22012035003422 — खेत तालाब निर्माण - दीपक पिता राजेश | Deleted | 0 | 0 | 2022-04-26
SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002004/IF/22012035003426 — खेत तालाब निर्माण - दीपक पिता राजेश | Deleted | 0 | 0 | 2022-04-26
SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002004/IF/22012035035664 — खेत तालाब निर्माण - दीपक पिता राजेश | Completed | 326610.42 | 230112 | 2022-11-26 | 2024-02-02
SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002004/IF/22012035035668 — खेत तालाब निर्माण - पंकज पिता रामचरण | Completed | 326610.42 | 202164 | 2022-11-25 | 2025-06-24
SONKATCH | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Agro Forestry Block Plantation for Individual | Plantation | 1720002004/IF/22012035121922 — निजी खेत में फलोद्यान - गोरव पिता कृष्णपाल | Ongoing | 160000 | 102539.16 | 2023-07-21
SONKATCH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1720002004/IF/22012035390508 — JGSA 2025 Recharge Structure Kapil Dhara Kup Sugan Bai Rajaram Malviya | Physically Completed | 25899.46 | 24126.6 | 2025-04-28 | 2026-03-31
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1720002004/IF/22012035402788 — Khet Talab Nirman Babulal Rajaram | New | 0 | 0 | 2025-04-15
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002004/IF/22012035402868 — Khet Talab Nirman Babulal Rajaram | Physically Completed | 407856.23 | 232702.2 | 2025-04-30 | 2026-04-27
SONKATCH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1720002004/IF/22012035402933 — JGSA 2025 Recharge Structure Kapil Dhara Kup Ghasiram Malviya | Physically Completed | 25899.46 | 25669.82 | 2025-04-28 | 2026-03-31
SONKATCH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1720002004/IF/22012035456136 — GJSA Recharge pit Dariyav Ganna ji 2025 | Physically Completed | 25899.46 | 13182.25 | 2025-05-07 | 2026-04-17
SONKATCH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1720002004/IF/22012035456278 — JGSA 2025 Recharge Structure Madanlal mangilal 2025 | Physically Completed | 25899.46 | 25662.49 | 2025-05-07 | 2026-03-31
SONKATCH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1720002004/IF/22012035456302 — JGSA 2025 Recharge Structure Gourav nagar | Physically Completed | 25899.46 | 25690.49 | 2025-05-07 | 2026-03-31
SONKATCH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1720002004/IF/22012035456338 — JGSA 2025 Recharge Structure Kailaschandra 2025 | Physically Completed | 25899.46 | 25649.71 | 2025-05-07 | 2026-03-31
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002004/IF/22012035460399 — JGSA 2025 khet talab mangilal laluji ghatiyakalan | Physically Completed | 392636.77 | 200344.2 | 2025-05-19 | 2026-06-10
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002004/IF/22012035557508 — JGSA 2025 khet talab mohan pita badrilal ghatiyakalan | Physically Completed | 302213.52 | 149284.88 | 2025-06-09 | 2026-05-27
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1720002004/IF/22012035589365 — Ek bagiya maa ke naam Anita malwiya MP2000200400156 Ghatiyakalan | Ongoing | 271689.33 | 64247.94 | 2025-08-27
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1720002004/IF/22012035589366 — Ek bagiya maa ke naam Santosh bai MP20002004001204 Ghatiyakalan | Ongoing | 271689.33 | 59416.2 | 2025-08-27
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1720002004/IF/22012035592692 — Ek bagiya maa ke naam Anita Malviya MP20002004001/56 | Deleted | 0 | 0 | 2025-08-01
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1720002004/IF/22012035597081 — Ek Bagiya Maa Ke Naam Anita bai MP20002004001 56 | Deleted | 0 | 0 | 2025-08-01
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1720002004/IF/22012035600012 — Ek Bagiya Maa Ke Naam shanta bai MP-20-002-004-001/76 | Closed | 0 | 0 | 2025-08-01
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1720002004/IF/22012035600015 — Ek Bagiya Maa Ke Naam kala MP-20-002-004-001/138 | New | 0 | 0 | 2025-08-01
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1720002004/IF/22012035600016 — Ek Bagiya Maa Ke Naam kala MP-20-002-004-001/138 | Ongoing | 272600.27 | 70485.9 | 2025-09-10
SONKATCH | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002004/IF/2224 — कपिलधारा कूप निर्माण धमैन्‍द्र बाबुलाल | Completed | 255000 | 223438 | 2012-05-03 | 2013-07-25
SONKATCH | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002004/IF/2225 — कपिलधारा कूप निर्माण हुकम बाबूलाल | Completed | 255000 | 179731 | 2012-06-07 | 2013-07-07
SONKATCH | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1720002004/IF/2226 — कपिलधारा कूप निर्माण मदनलाल बद्रीलाल | Completed | 255000 | 205595.8 | 2012-05-03 | 2014-06-26
SONKATCH | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002004/IF/2227 — कपिलधारा कूप निर्माण मधुसुमन बाबुलाल | Completed | 255000 | 206868 | 2012-05-03 | 2013-07-07
SONKATCH | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002004/IF/2228 — कपिलधारा कूप निर्माण भागवन्‍ता बाई उमराव भारति | Completed | 266000 | 243843.7 | 2012-05-31 | 2013-03-25
SONKATCH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002004/IF/9993722917 — कपिलधारा-राजेशसालगराम | Closed | 0 | 0 | 2016-01-26
SONKATCH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002004/IF/9993722922 — कपिलधारा-कैलाश-दौलाजी | Closed | 0 | 0 | 2016-01-26
SONKATCH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002004/IF/9993722926 — कपिलधारा-प्रेमसिंहपन्नालाल | Closed | 0 | 0 | 2016-01-26
SONKATCH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1720002004/IF/9993722982 — मेडबंधान-सिद्धु रुग्गा | Closed | 0 | 0 | 2016-01-26
SONKATCH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1720002004/IF/9993722986 — मेडबंधान-बद्रिलालउमराव | Closed | 0 | 0 | 2016-01-26
SONKATCH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1720002004/IF/9993722989 — मेडबंधान-राजेशसालगराम | Closed | 0 | 0 | 2016-01-26
SONKATCH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1720002004/IF/9993722991 — मेडबंधान-मोती-केशा | Closed | 0 | 0 | 2016-01-26
SONKATCH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1720002004/IF/9993722993 — मेडबंधान-उमरवलालु | Closed | 0 | 0 | 2016-01-26
SONKATCH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1720002004/IF/9993722995 — मेडबंधान-सुभास चंदू | Closed | 0 | 0 | 2016-01-26
SONKATCH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1720002004/IF/9993723003 — भुमिसमतलीकरण-मोहन मिस्रीलाल | Closed | 0 | 0 | 2016-01-26
SONKATCH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1720002004/IF/9993723006 — भुमिसमतलीकरण-माखन दौलाजी | Closed | 0 | 0 | 2016-01-26
SONKATCH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1720002004/IF/9993723018 — भुमिसमतलीकरण-चदरदेवा | Closed | 0 | 0 | 2016-01-26
SONKATCH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1720002004/IF/9993725273 — भुमिसमतलीकरण-जगदिश-उमराव | Closed | 0 | 0 | 2016-01-26
SONKATCH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1720002004/IF/9993726098 — भुमिसमतलीकरण-रामबाबु-रायसिंह | Closed | 0 | 0 | 2016-01-26
SONKATCH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1720002004/IF/9993726101 — भुमिसमतलीकरण-बहादुरसिंह अम्बाराम | Closed | 0 | 0 | 2016-01-26
SONKATCH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1720002004/IF/9993726103 — भुमिसमतलीकरण-बलवान-सालगराम | Closed | 0 | 0 | 2016-01-26
SONKATCH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Piggery shed / Construction of Piggery Shelter for Individuals | Piggery Shelter | 1720002004/IF/9993726106 — पशुशैड-माखन दौलाजि | Closed | 0 | 0 | 2016-01-26
SONKATCH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002004/IF/IAY/1056194 — Construction of IAY House -IAY REG. NO. MP1405699 | Closed | 17100 | 0 | 2017-05-11
SONKATCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002004/IF/IAY/1072343 — Construction of IAY House -IAY REG. NO. MP2048693 | Completed | 15480 | 14792 | 2018-04-20 | 2019-08-08
SONKATCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002004/IF/IAY/1295614 — Construction of IAY House -IAY REG. NO. MP2703922 | Completed | 15480 | 15660 | 2018-04-29 | 2018-11-03
SONKATCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002004/IF/IAY/1889256 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5213432 | Completed | 15660 | 15138 | 2018-07-24 | 2019-03-21
SONKATCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002004/IF/IAY/1892977 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4455501 | Completed | 15660 | 15660 | 2018-07-24 | 2019-01-25
SONKATCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002004/IF/IAY/1894031 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4997537 | Completed | 15660 | 15486 | 2018-07-24 | 2018-12-21
SONKATCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002004/IF/IAY/1894297 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5182494 | Completed | 15660 | 15176 | 2018-07-24 | 2019-09-12
SONKATCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002004/IF/IAY/1894320 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5199064 | Completed | 15660 | 14862 | 2018-07-24 | 2019-08-15
SONKATCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002004/IF/IAY/1894367 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5218075 | Completed | 15660 | 15152 | 2018-07-24 | 2019-08-15
SONKATCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002004/IF/IAY/1894401 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5246459 | Completed | 15660 | 15624 | 2018-09-12 | 2019-09-30
SONKATCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002004/IF/IAY/1894812 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5540801 | Completed | 15660 | 15084 | 2018-08-28 | 2019-12-12
SONKATCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002004/IF/IAY/1901868 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4402881 | Completed | 15660 | 14964 | 2018-07-24 | 2019-08-15
SONKATCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002004/IF/IAY/1901987 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4695823 | Completed | 15660 | 15138 | 2018-08-28 | 2018-12-21
SONKATCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002004/IF/IAY/1902075 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4749093 | Completed | 15660 | 15486 | 2018-07-24 | 2019-03-21
SONKATCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002004/IF/IAY/1902084 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4752752 | Completed | 15660 | 14790 | 2018-07-25 | 2019-09-12
SONKATCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002004/IF/IAY/1902957 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5628525 | Completed | 15660 | 15660 | 2018-07-24 | 2018-11-23
SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002004/IF/IAY/3788693 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100711205 | Completed | 18360 | 18326 | 2022-07-19 | 2023-11-15
SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002004/IF/IAY/3798010 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100636110 | Completed | 18360 | 17544 | 2022-07-12 | 2023-07-21
SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002004/IF/IAY/3798011 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100636134 | Completed | 18360 | 18224 | 2022-07-12 | 2023-07-31
SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002004/IF/IAY/3798012 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100636206 | Completed | 18360 | 17442 | 2022-07-12 | 2023-11-05
SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720002004/IF/IAY/3810262 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118515842 | Approved | 27000 | 0 | 2022-05-02
SONKATCH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002004/IF/IAY/3826527 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117644045 | Completed | 18360 | 15691 | 2023-07-25 | 2024-09-19
SONKATCH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002004/IF/IAY/39222 — Construction of IAY House -IAY REG. NO. MP-20-002-004-001/13 | Completed | 14310 | 159 | 2016-03-29 | 2019-08-15
SONKATCH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002004/IF/IAY/39223 — Construction of IAY House -IAY REG. NO. MP-20-002-004-001/69 | Completed | 14310 | 13485 | 2016-03-30 | 2018-06-07
SONKATCH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002004/IF/IAY/39224 — Construction of IAY House -IAY REG. NO. MP-20-002-004-001/93 | Completed | 14310 | 13515 | 2016-03-29 | 2018-06-07
SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002004/IF/IAY/4241873 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106403308 | Completed | 18360 | 18360 | 2022-09-01 | 2022-11-16
SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002004/IF/IAY/4242989 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113833905 | Completed | 18360 | 18360 | 2022-09-01 | 2022-12-30
SONKATCH | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002004/IF/IAY/428510 — Construction of IAY House -IAY REG. NO. MP1384265 | Completed | 15030 | 14702 | 2017-03-08 | 2018-04-20
SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002004/IF/IAY/4299694 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115403576 | Completed | 18360 | 3876 | 2022-11-22 | 2024-07-13
SONKATCH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002004/IF/IAY/4531688 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100636220 | Physically Completed | 21870 | 21870 | 2024-10-09 | 2026-05-18
SONKATCH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002004/IF/IAY/4531830 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100771759 | Physically Completed | 23490 | 21375 | 2024-10-31 | 2026-06-11
SONKATCH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720002004/IF/IAY/4548886 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106403480 | Ongoing | 27000 | 19197 | 2024-10-31
SONKATCH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002004/IF/IAY/4551144 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113833919 | Physically Completed | 21870 | 21870 | 2024-10-09 | 2026-05-18
SONKATCH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002004/IF/IAY/4551146 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113834244 | Physically Completed | 23490 | 21870 | 2024-10-09 | 2026-06-11
SONKATCH | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002004/IF/IAY/478493 — Construction of IAY House -IAY REG. NO. MP1961043 | Completed | 15030 | 14727 | 2017-02-04 | 2018-05-29
SONKATCH | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002004/IF/IAY/478494 — Construction of IAY House -IAY REG. NO. MP1961053 | Completed | 15030 | 15061 | 2017-02-04 | 2018-04-05
SONKATCH | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002004/IF/IAY/484005 — Construction of IAY House -IAY REG. NO. MP2044011 | Completed | 15030 | 14727 | 2017-02-04 | 2018-04-20
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002004/IF/IAY/5147222 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113834076 | Physically Completed | 23490 | 23490 | 2025-07-04 | 2026-05-18
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002004/IF/IAY/5151395 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113834123 | Physically Completed | 23490 | 23229 | 2025-04-05 | 2026-05-20
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002004/IF/IAY/5163632 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100636078 | Physically Completed | 23490 | 23490 | 2025-05-14 | 2026-01-23
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002004/IF/IAY/5182767 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106403361 | Physically Completed | 23490 | 22707 | 2025-05-14 | 2026-06-11
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002004/IF/IAY/5190622 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113834003 | Physically Completed | 23490 | 23490 | 2025-06-06 | 2026-05-18
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002004/IF/IAY/5200589 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114061875 | Physically Completed | 23490 | 23490 | 2025-05-14 | 2026-05-18
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002004/IF/IAY/5221735 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106403393 | Physically Completed | 23490 | 22446 | 2025-05-19 | 2026-06-11
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002004/IF/IAY/5225633 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114164399 | Completed | 23490 | 23490 | 2025-04-05 | 2025-10-03
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002004/IF/IAY/5661594 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113834333 | Physically Completed | 23490 | 22707 | 2025-07-27 | 2026-06-11
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002004/IF/IAY/5662806 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118516451 | Physically Completed | 23490 | 21924 | 2025-07-27 | 2026-06-11
SONKATCH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002004/IF/IAY/732727 — Construction of IAY House -IAY REG. NO. MP2044156 | Completed | 15030 | 15480 | 2017-05-07 | 2018-04-05
SONKATCH | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1720002004/IF/IAY/733473 — Construction of IAY House -IAY REG. NO. MP2063323 | Approved | 27000 | 0 | 2017-03-21
SONKATCH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002004/IF/IAY/734057 — Construction of IAY House -IAY REG. NO. MP2079377 | Completed | 15030 | 14508 | 2017-05-14 | 2018-05-29
SONKATCH | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1720002004/IF/IAY/734532 — Construction of IAY House -IAY REG. NO. MP2093455 | Approved | 27000 | 0 | 2017-03-21
SONKATCH | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1720002004/IF/IAY/751721 — Construction of IAY House -IAY REG. NO. MP2603099 | Approved | 27000 | 0 | 2017-03-21
SONKATCH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002004/IF/IAY/752086 — Construction of IAY House -IAY REG. NO. MP2615151 | Completed | 15030 | 15480 | 2017-05-07 | 2018-04-05
SONKATCH | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1720002004/IF/IAY/753235 — Construction of IAY House -IAY REG. NO. MP2658591 | Approved | 27000 | 0 | 2017-03-21
SONKATCH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002004/IF/IAY/753240 — Construction of IAY House -IAY REG. NO. MP2658648 | Completed | 15030 | 15480 | 2017-05-14 | 2018-04-05
SONKATCH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002004/IF/IAY/754058 — Construction of IAY House -IAY REG. NO. MP2692761 | Completed | 15030 | 15342 | 2017-06-22 | 2018-05-29
SONKATCH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002004/IF/IAY/818065 — Construction of IAY House -IAY REG. NO. MP2044181 | Completed | 15480 | 15480 | 2017-05-22 | 2018-04-05
SONKATCH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002004/IF/IAY/818117 — Construction of IAY House -IAY REG. NO. MP2048903 | Completed | 15480 | 15318 | 2017-05-29 | 2018-05-29
SONKATCH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002004/IF/IAY/818269 — Construction of IAY House -IAY REG. NO. MP2064866 | Completed | 15480 | 15354 | 2017-05-29 | 2018-05-29
SONKATCH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002004/IF/IAY/823824 — Construction of IAY House -IAY REG. NO. MP2692738 | Completed | 15480 | 15480 | 2017-05-29 | 2018-04-05
SONKATCH | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002004/IF/कूप निर्माण, अंबाराम राजाराम — घटियाकला, कपिलधारा कूप निर्माण, अंबाराम राजाराम | Completed | 201000 | 91557 | 2010-06-10 | 2012-04-14
SONKATCH | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002004/IF/कूप निर्माण, पप्‍पू बद्री — घटियाकला, कपिलधारा कूप निर्माण, पप्‍पू बद्री | Completed | 201000 | 22200 | 2009-03-01 | 2012-04-14
SONKATCH | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720002004/LD/2066 — खेल किर्डागना,प्रा.वि.के पास | Completed | 69000 | 20862 | 2012-02-02 | 2012-04-10
SONKATCH | 2015-2016 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1720002004/LD/22012034249011 — किडान्‍गन,प्रधानमंत्री सडक के पास | Completed | 448000 | 397621.47 | 2016-01-08 | 2017-10-25
SONKATCH | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720002004/LD/3799394055 — मेढ बंधान घासीराम खुमानसिंह | Completed | 33000 | 29784 | 2013-06-08 | 2014-01-12
SONKATCH | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720002004/LD/3799394057 — मेढ बंधान माखनसिंह दोलाजी | Completed | 33000 | 18396 | 2013-06-08 | 2013-12-25
SONKATCH | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720002004/LD/3799394059 — मेढ बंधान श्‍यामलाल गंगाराम | Completed | 33000 | 5256 | 2013-06-08 | 2014-11-11
SONKATCH | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720002004/LD/3799394060 — मेढ बंधान, दौला भवाना | Completed | 33000 | 26280 | 2013-06-08 | 2013-12-25
SONKATCH | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720002004/LD/3799394064 — मेढ बंधान, धरमैन्‍द्र बाबुलाल | Completed | 33000 | 14016 | 2013-06-08 | 2014-11-11
SONKATCH | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720002004/LD/3799394066 — मेढ बंधान भागवन्‍ताबाई उमराव | Completed | 33000 | 7884 | 2013-06-08 | 2014-11-11
SONKATCH | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720002004/LD/3799401970 — क्रिडान्‍गन,माध्‍यमिक शाला भवन परिसर | Completed | 184000 | 132372 | 2013-08-15 | 2013-12-10
SONKATCH | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720002004/LD/3799401982 — Kidangan-Egs sala se parisar | Completed | 27000 | 26564 | 2013-08-15 | 2013-10-15
SONKATCH | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720002004/LD/3799405082 — मेढ बंधान,गंगाराम मुन्‍नालाल | Completed | 33000 | 23652 | 2013-09-21 | 2014-11-11
SONKATCH | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720002004/LD/3799414202 — मेढ बंधान,भेरूसिंह धुलसिंह | Completed | 33000 | 10512 | 2013-12-12 | 2014-11-11
SONKATCH | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720002004/LD/3799414210 — मेढ बंधान,सरदारसिंह धुलसिंह | Completed | 33000 | 9636 | 2013-12-12 | 2014-11-11
SONKATCH | 2013-2014 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1720002004/LD/3799418896 — शान्तिधाम निर्माण,घटियाकला | Completed | 376000 | 138669.64 | 2014-01-07 | 2017-10-25
SONKATCH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002004/RC/22012034176158 — पंच परमेश्‍वर,बाबुनेता के घर से केशरसिंह के घर तक | Completed | 155000 | 136848 | 2013-07-24 | 2015-02-26
SONKATCH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1720002004/RC/22012034191481 — आंतरिक मार्ग इंदिरा कालोनी से बाबूलाल के मकान तक, | Completed | 491000 | 384634 | 2014-01-27 | 2017-10-25
SONKATCH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1720002004/RC/22012034194017 — पंच परमेश्‍वर,केशरसिंह के घर से देविसिंह के घर तक | Completed | 76000 | 59825 | 2013-12-12 | 2015-02-26
SONKATCH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002004/RC/22012034197854 — पंच परमेश्‍वर,निर्भयसिंह के घर से करणसिंह के घर | Completed | 38000 | 37031 | 2014-01-07 | 2015-07-15
SONKATCH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1720002004/RC/22012034201557 — खेत सडक,घटियाकला,तकतसिंह के खेत से सजनसिंह के खेत | Deleted | 0 | 0 | 2013-12-25
SONKATCH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1720002004/RC/22012034201559 — खेत सडक,घटियाकला,तकतसिंह के खेत से सजनसिंह के खेत | Completed | 1487000 | 171634.3 | 2014-01-31 | 2014-11-02
SONKATCH | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002004/RC/22012034228939 — सान्‍सदनिधी,देवकरण मालविय के घर से प्रधानमन्‍त्री | Completed | 87000 | 32499 | 2014-09-27 | 2017-11-25
SONKATCH | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002004/RC/22012034310843 — पंच परमेश्‍वर सी सी रोड हिरालाल के मकान से बाबूलाल के बाडे तक | Deleted | 44000 | 0 | 2016-01-26
SONKATCH | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002004/RC/22012034326680 — CC ROAD mangilal ke GHAR rakash ke GHAR TAK | Completed | 30700 | 26754 | 2017-02-28 | 2020-06-19
SONKATCH | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002004/RC/22012034326762 — CC Road gangaram ke GHAR se Mohandas mishreelal ke GHAR tak | Completed | 13200 | 19902 | 2017-02-28 | 2019-12-18
SONKATCH | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002004/RC/22012034330126 — cc road sidhu dhakad ke makan se harijan kundi tak | Deleted | 79000 | 0 | 2017-03-08
SONKATCH | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002004/RC/22012034330128 — cc road Anokhilal ke ghar se sidhhu ke ghar tak | Completed | 13200 | 6708 | 2017-09-03 | 2018-06-16
SONKATCH | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1720002004/RC/22012034337264 — sudur gram sampar sadak nirman gattiyakala | Completed | 1410000 | 1035921.26 | 2017-05-18 | 2022-04-12
SONKATCH | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1720002004/RC/22012034341417 — sudur gram sampakr sadak keilash ke ghar se peerpadlya ki our | Closed | 375000 | 0 | 2017-05-01
SONKATCH | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002004/RC/22012034348778 — cc road babulal jamadar ke ghar se rambabu ke ghar ratk | Deleted | 7800 | 0 | 2016-10-02
SONKATCH | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002004/RC/22012034349208 — cc road pappu ke makan se antarsingh ke makan tak | Completed | 146000 | 72240 | 2017-08-13 | 2018-09-20
SONKATCH | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002004/RC/22012034349231 — cc road gulabsingh ke makan se bherumaharaj tak | Deleted | 51000 | 0 | 2016-10-02
SONKATCH | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002004/RC/22012034450205 — cc road babulal jamadar ke ghar se rambabu ke ghar tak | Closed | 3500 | 0 | 2019-01-26
SONKATCH | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002004/RC/22012034450208 — cc road Gulabsinghke makan se mukesh ke makan tak | Closed | 11500 | 0 | 2019-01-26
SONKATCH | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002004/RC/22012034450211 — cc rod nirman nihalsingh ke ghar se dharmendra ke ghar tak | Closed | 3900 | 0 | 2019-01-26
SONKATCH | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002004/RC/22012034480674 — cc road (shashkiy kup se jgdish ke makan tak) | Closed | 49000 | 0 | 2019-08-15
SONKATCH | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002004/RC/22012034555471 — c c road babulal ke makan se makhan ke makan tak) | Completed | 36000 | 36660 | 2021-01-07 | 2022-01-06
SONKATCH | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002004/RC/280 — सी.सी. रोड,भवरसिह के मकान से श्रीराम मन्दिर | Completed | 75000 | 40384 | 2012-03-15 | 2012-04-01
SONKATCH | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002004/RC/281 — सी.सी.रोड,प्रा.वि. से भवरसिह के मकान तक | Completed | 150000 | 39809 | 2012-03-07 | 2015-02-26
SONKATCH | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002004/RC/283 — पंचप्रमेश्वेर,सी.सी. रोड प्रधानमंत्री रोड से श्रीर | Completed | 86000 | 81264 | 2012-03-01 | 2012-12-10
SONKATCH | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1720002004/RC/293 — आंतरिक मुर्मिकरन,अम्बाराम मलवीय के मकान तक | Completed | 155000 | 116523 | 2012-03-01 | 2013-04-25
SONKATCH | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002004/RC/494 — पंच परमेश्‍वर,प्रहलदसिंह के घर से नाथुसिंह केमकान | Completed | 138000 | 172800 | 2012-11-22 | 2014-02-25
SONKATCH | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002004/RC/548 — पंचप्रमेश्वेर,सी.सी. रोड हरिजन कुन्‍डी सें सितला म | Completed | 36000 | 41430 | 2013-03-09 | 2013-05-25
SONKATCH | 2007-2008 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1720002004/RC/गेवल पहुच मार्ग घटटीया कला सामस — गेवल पहुच मार्ग घटटीया कला सामस खेडी | Completed | 415000 | 141600 | 2008-02-21 | 2012-04-10
SONKATCH | 2007-2008 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1720002004/RC/गेवलसडक घटटकला से टाडा उमरोद मार्ग घ — गेवलसडक घटटकला से टाडा उमरोद मार्ग घटटकला | Completed | 1280000 | 954778 | 2008-03-13 | 2012-12-25
SONKATCH | 2007-2008 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1720002004/RC/गेवल सडक घटटीया भाना से समास खेडी मा — गेवल सडक घटटीया कला से समास खेडी मार्ग तक पहुच मार्ग | Completed | 415000 | 187344 | 2008-02-03 | 2012-04-10
SONKATCH | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002004/RC/ग्राम पंचायत घटिटयाकला सी;सी;रोड., ह — ग्राम पंचायत घटिटयाकला सीसीरोड., हनुमान मंदिर से अजा मोहल्‍ला | Completed | 138700 | 76105 | 2008-08-21 | 2012-04-14
SONKATCH | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002004/RC/सी;सी;रोड., ह — ग्राम पंचायत घटिटयाकला सीसीरोड., हनुमान मंदिर से सज्‍जनसिंह के मकान तक | Completed | 92500 | 93861 | 2008-05-08 | 2012-04-10
SONKATCH | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720002004/RS/22012034256012 — शौचालय निर्माण,हरिसिंह उमरावसिंह | Completed | 5400 | 5400 | 2014-08-02 | 2015-02-02
SONKATCH | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720002004/RS/22012034256014 — शौचालय निर्माण औमप्रकाश बाबुलाल | Deleted | 0 | 0 | 2014-04-14
SONKATCH | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720002004/RS/22012034256287 — सोचालयनिर्माण ओमप्रकाश बाबूलाल | Completed | 5400 | 5400 | 2014-08-02 | 2015-02-02
SONKATCH | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720002004/RS/22012034256302 — सोचालयनिर्माणहिदॆस श्यामलाल | Completed | 5400 | 5400 | 2014-08-02 | 2015-02-02
SONKATCH | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720002004/RS/22012034256473 — शौचालय निर्माण,जगदीशसिह उमरावसिह | Completed | 5400 | 5400 | 2014-08-02 | 2015-02-02
SONKATCH | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720002004/RS/22012034256475 — शौचलय निर्माण,बद्रिलाल उमराव | Completed | 5400 | 5400 | 2014-08-02 | 2015-02-02
SONKATCH | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720002004/RS/22012034256477 — शौचलय निर्माण,बहादुरसिंह अम्‍बाराम | Completed | 5400 | 5400 | 2014-08-02 | 2015-02-02
SONKATCH | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720002004/RS/22012034256481 — शौचालय निर्माण,धरमेन्‍द्र बाबुलाल | Completed | 5400 | 5400 | 2014-08-02 | 2015-02-02
SONKATCH | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720002004/RS/22012034256483 — शौचलय निर्माण,शुभाष अम्‍बाराम | Completed | 5400 | 5400 | 2014-08-02 | 2015-02-02
SONKATCH | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720002004/RS/22012034260623 — शौचालय निर्माण देवेन्‍द्र कैलाश | Completed | 5400 | 5400 | 2014-08-06 | 2015-02-02
SONKATCH | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720002004/RS/22012034260630 — शौचालय निर्माण,माखनसिंह दौलाजी | Completed | 5400 | 5400 | 2014-08-05 | 2015-02-02
SONKATCH | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720002004/RS/22012034260636 — शौचालय निर्माण,कैलाशचन्‍द्र दौनाजी | Completed | 5400 | 5400 | 2014-08-05 | 2015-02-02
SONKATCH | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720002004/RS/22012034260638 — शौचालय निर्माण,राजेश घासीराम | Completed | 5400 | 5400 | 2014-08-15 | 2015-02-02
SONKATCH | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720002004/RS/22012034260750 — शौचालय निर्माण,अन्‍तरसिंह निर्भयसिंह | Deleted | 5400 | 0 | 2014-04-25
SONKATCH | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720002004/RS/22012034260751 — शौचालय निर्माण भवर घीसाजी | Completed | 5400 | 5400 | 2014-08-16 | 2015-02-02
SONKATCH | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720002004/RS/22012034260753 — शौचालय निर्माण,शुभाष चन्‍दुभारती | Completed | 5400 | 5400 | 2014-08-16 | 2015-02-02
SONKATCH | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720002004/RS/22012034260754 — शौचालय निर्माण,बाबुलाल मानसिंह | Completed | 5400 | 5400 | 2014-08-16 | 2015-02-02
SONKATCH | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720002004/RS/22012034260755 — शौचालय निर्माण,कैशरसिंह नग्‍जीराम | Completed | 5400 | 5400 | 2014-08-16 | 2016-09-25
SONKATCH | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720002004/RS/22012034283964 — शौचालय निर्माण धीरज -गोरधन | Completed | 3180 | 3180 | 2015-09-20 | 2016-09-25
SONKATCH | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720002004/RS/22012034283971 — शौचालय निर्माण हीरालाल घासीराम | Completed | 3180 | 3180 | 2015-09-20 | 2016-05-15
SONKATCH | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720002004/RS/22012034283979 — शौचालय निर्माण मदनलाल मांगीलाल | Completed | 3180 | 3339 | 2015-09-20 | 2016-05-15
SONKATCH | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720002004/RS/22012034283983 — शौचालय निर्माण हिम्मतसिंघ नारायणसिंघ | Completed | 3180 | 3180 | 2015-09-20 | 2016-05-15
SONKATCH | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720002004/RS/22012034283989 — शौचालय निर्माण बाबूलाल नारायणसिंघ | Completed | 3180 | 3180 | 2015-09-20 | 2017-10-25
SONKATCH | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720002004/RS/22012034283994 — शौचालय निर्माण आत्माराम नारायणसिंघ | Completed | 3180 | 3180 | 2015-09-20 | 2017-10-25
SONKATCH | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720002004/RS/22012034283999 — शौचालय निर्माण प्रेमनारायण देवकरण | Completed | 3180 | 3180 | 2015-09-20 | 2017-10-25
SONKATCH | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720002004/RS/22012034284006 — शौचालय निर्माण भवरसिंघ करणसिंघ | Completed | 3180 | 3180 | 2015-09-20 | 2016-05-15
SONKATCH | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720002004/RS/22012034284010 — शौचालय निर्माण अशोक देवकरण | Completed | 3180 | 3180 | 2015-09-20 | 2017-10-25
SONKATCH | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720002004/RS/22012034284014 — शौचालय निर्माण अमरसिंघ नारायणसिंघ | Completed | 3180 | 3021 | 2015-09-20 | 2017-10-25
SONKATCH | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720002004/RS/22012034289515 — शौचालय निर्माण,जशोदाबाई नारायणसिंह | Completed | 3180 | 3180 | 2015-10-20 | 2017-10-25
SONKATCH | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720002004/RS/22012034289519 — शोचलायनिर्माण,फतेसिंह घासीराम | Completed | 3180 | 3180 | 2015-10-20 | 2017-10-25
SONKATCH | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720002004/RS/22012034289520 — शौचालय निर्माण,गणपतसिंह भागिरथ | Completed | 3180 | 3180 | 2015-10-20 | 2016-05-15
SONKATCH | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1720002004/RS/22012034609782 — SBM- सामुदायिक स्वच्छता परिसर ग्राम घटियाकला | Completed | 44000 | 42784 | 2022-01-07 | 2026-02-25
SONKATCH | 2013-2014 | D--RURAL INFRASTUCTURE / Bharat Nirman Sewa Kendra | New Construction / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1720002004/SK/1022 — Bharat Nirman Rajeev Gandhi Sewa Kendra,GHATIYAKALAN | Completed | 1285000 | 906116.99 | 2013-09-28 | 2021-08-10
SONKATCH | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1720002004/WC/22012034328811 — नविन तालाब-नाइ वाले भेरु महाराज वाला नाला | Completed | 205000 | 185214.02 | 2017-06-08 | 2020-06-19
SONKATCH | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1720002004/WC/22012034442765 — Checkdam keilash ke khet ke pass | Completed | 433000 | 407432 | 2019-03-08 | 2021-01-22
SONKATCH | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1720002004/WC/22012034442770 — chekdam sidhuusingh ke khet ke pass nale me | Closed | 0 | 0 | 2019-02-26
SONKATCH | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1720002004/WC/22012034475038 — Rain Watar Harwestingh School ke pass | Deleted | 0 | 0 | 2019-05-25
SONKATCH | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1720002004/WC/22012034477206 — recharge pit (aa ja basti main) | Completed | 13427.22 | 9680 | 2019-08-28 | 2020-09-07
SONKATCH | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand filter for borewell recharge for Community | Well Recharge | 1720002004/WC/22012034483798 — sokhata gadda egs School ke pass | Completed | 13427.22 | 8624 | 2019-08-28 | 2024-01-31
SONKATCH | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand filter for borewell recharge for Community | Well Recharge | 1720002004/WC/22012034483799 — Sokhata gadda | Completed | 13427.22 | 9680 | 2019-08-28 | 2020-09-11
SONKATCH | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1720002004/WC/22012034507796 — Percolation tank(babulal ke khet ke paas) | Completed | 310385.56 | 244108 | 2019-12-18 | 2020-06-19
SONKATCH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1720002004/WC/22012034736839 — CTR - रूफ वाटर हार्वेस्टिंग पंचायत भवन के पास | Closed | 26207.76 | 0 | 2021-04-26
SONKATCH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dykes for Community | Underground Dyke for Ground Water Recharge | 1720002004/WC/22012034932042 — डाइक निर्माण माखन सिंह के खेत के पास | Closed | 47931.83 | 0 | 2022-01-26
SONKATCH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dykes for Community | Underground Dyke for Ground Water Recharge | 1720002004/WC/22012034932043 — डाइक निर्माण माखन सिंह के खेत के पास | Closed | 47931.83 | 0 | 2022-01-26
SONKATCH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dykes for Community | Underground Dyke for Ground Water Recharge | 1720002004/WC/22012034932046 — डाइक निर्माण घासीराम के खेत के पास | Closed | 47931.83 | 0 | 2022-01-26
SONKATCH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dykes for Community | Underground Dyke for Ground Water Recharge | 1720002004/WC/22012034932051 — डाइक निर्माण मुकेश के खेत के पास | Closed | 45524.07 | 0 | 2022-01-26
SONKATCH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dykes for Community | Underground Dyke for Ground Water Recharge | 1720002004/WC/22012034932055 — डाइक निर्माण श्याम लाल के खेत के पास | Closed | 0 | 0 | 2022-01-26
SONKATCH | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Repair & Maint of gabion Spur for Comm / Repair & Maintenance of Gabion Spur for Community | Repair & maint of Water Harvesting Structures | 1720002004/WC/22012035135305 — gabian ghasiram malviya ke khet ke pass | Ongoing | 248441.84 | 221 | 2024-01-24
SONKATCH | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1720002004/WC/22012035135320 — nirmal neer checkdamke pass | Ongoing | 537251.35 | 144914.91 | 2023-11-27
SONKATCH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1720002004/WC/22012035279659 — JGSA 2025 Recharge Structure Sarvajanic Kup Indira Calony | Physically Completed | 25899.46 | 13964.26 | 2025-05-07 | 2026-04-20
SONKATCH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1720002004/WC/22012035294270 — JGSA 2025 Recharge Structure Nirmal neer goya ke pas 2025 | Physically Completed | 25899.46 | 16314.25 | 2025-05-07 | 2026-04-16
SONKATCH | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1720002004/WC/30 — घटिटयाकला, स्‍टाप डेम | Physically Completed | 5397000 | 3887794 | 2009-11-04 | 2020-12-18
SONKATCH | 2007-2008 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002004/WC/कपि‍ल धारा सर्वजनि‍क नि‍मान घटटीयाकल — कपि‍ल धारा सर्वजनि‍क नि‍मान घटटीयाकला | Completed | 358000 | 218374.5 | 2008-03-05 | 2017-10-25
SONKATCH | 2007-2008 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002004/WC/करण बापु घटीया कला कुप ि‍मान — कुप ि‍मान करण बापु घटीयाकला | Completed | 67400 | 52277 | 2007-12-13 | 2012-04-05
SONKATCH | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1720002004/WC/कूप निर्माण, इंदिरा कॉलोनी — घटियाकला, सार्वजनिक कूप निर्माण, इंदिरा कॉलोनी | Completed | 358000 | 314212 | 2009-03-01 | 2013-08-20
SONKATCH | 2007-2008 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002004/WC/दरीयाव नारबत सीह गन्‍न्ना जी घटीया क — कुपनि‍मान दरीयाव नारबत सीह गन्‍न्ना जी घटीया कला | Deleted | 67400 | 10975 | 2008-01-31
SONKATCH | 2007-2008 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002004/WC/दोला भवाना कुप ि‍मानघ् घटीटया कला — कुपनि‍मान दोला भवाना घटीटया कला | Completed | 67400 | 93369 | 2007-12-06 | 2012-04-15
SONKATCH | 2007-2008 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002004/WH/कपि‍लधारा कुप (दरीयाव नरवत सीह ) — कपि‍लधारा कुप (दरीयाव नरवत सीह ) | Completed | 67400 | 58360 | 2007-12-13 | 2012-04-14
SONKATCH | 2007-2008 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002004/WH/कपि‍लधारा कुप (दोला जी Ghatiyakala — कपि‍लधारा कुप (लक्ष्‍मण दोला जी Ghatiyakala ) | Completed | 67400 | 92615 | 2008-01-24 | 2012-04-14
SONKATCH | 2007-2008 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002004/WH/कपि‍ल धारा रुपसीह देवीसीह घटटीयाकल — कपि‍ल धारा रुपसीह देवीसीह घटटीयाकला | Deleted | 0 | 0 | 2007-12-13
SONKATCH | 2007-2008 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002004/WH/कपि‍ल धारा रुपसीह रामेश्‍वर घटटीकला — कपि‍ल धारा रुपसीह रामेश्‍वर घटटीकला | Completed | 133000 | 34678 | 2008-01-28 | 2012-04-14
SONKATCH | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1720002004/WH/कपि‍ल धारा सर्वजनि‍क पि‍ली खदन के पा — कपि‍ल धारा सर्वजनि‍क पि‍ली खदन के पास नि‍मान घटटीयाकला | Completed | 0 | 379081 | 2008-03-04 | 2013-04-25
SONKATCH | 2007-2008 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002004/WH/कुप नि‍मान घसीराम खुमान घटीयाकना — कुप नि‍मान घसीराम खुमान घटीयाकना | Completed | 67400 | 175548 | 2008-01-30 | 2012-04-05
SONKATCH | 2007-2008 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002004/WH/कुप नि‍मान तकतसीह बन्‍सीलाल घटीयाक — कुप नि‍मान तकतसीह बन्‍सीलाल घटीयाकना | Completed | 67400 | 137759 | 2008-02-21 | 2012-04-05
SONKATCH | 2007-2008 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002004/WH/कुप नि‍मान लीला सुगन अमबाराम राजाराम — कुप नि‍मान लीला सुगन अमबाराम राजाराम घटीयाकना | Completed | 67400 | 130055 | 2008-02-23 | 2012-04-05