## Work List
Exported on: 2026-10-27 17:49:15
Filters applied:
Data source: VBGRAMG
District: DEWAS
Block: All
Panchayat: DHANDEDA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SONKATCH | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Agro Forestry Block Plantation for Community | Plantation | 1720002006/DP/22012034604273 — वसुधा वंदन वाटिका मांगलिक भवन के पास पाडल्या मोहब्बा | Ongoing | 55847.4 | 0 | 2023-08-29
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1720002006/IF/22012035588155 — Ek Bagiya Maa ke Naam Mankunwar bai MP20002006001170 | Ongoing | 271689.33 | 20100 | 2025-09-04
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1720002006/IF/22012035588170 — Ek Bagiya Maa ke Naam Sugan Bai Parmar MP2000200600114A Dhandeda | Ongoing | 271689.33 | 9000 | 2025-08-30
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1720002006/IF/22012035588179 — Ek Bagiya Maa ke Naam Gokal Bai MP20002006001208A | Ongoing | 271678.55 | 10800 | 2025-10-14
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1720002006/IF/22012035589359 — Ek bagiya maa ke naam shyamu bai MP2000200600173 dhandeda | Ongoing | 271689.33 | 0 | 2025-08-30
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1720002006/IF/22012035589360 — Ek bagiya maa ke naam Elu bai tatiyaa MP20002006001167 Dhandeda | Ongoing | 271689.33 | 16200 | 2025-08-29
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1720002006/IF/22012035589361 — Ek bagiya maa ke naam Ailu bai chouhan MP20002006001172 Dhandeda | Ongoing | 271689.33 | 16200 | 2025-08-29
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1720002006/IF/22012035589363 — Ek bagiya maa ke naam Siddhi bai MP200020060023A | Ongoing | 271689.33 | 12600 | 2025-08-30
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1720002006/IF/22012035589364 — Ek bagiya maa ke naam MP2000200600257 Dhandeda | Ongoing | 271689.33 | 21600 | 2025-09-22
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1720002006/IF/22012035597824 — EK BAGIYA MAA KE NAAM RESHAM BAI TATIYA MP20002006001/181A | Ongoing | 272600.27 | 10800 | 2025-09-10
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1720002006/IF/22012035600706 — Ek bagiya maa ke naam Sugan bai MP20002006002/19 | Ongoing | 272600.27 | 21600 | 2025-08-30
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1720002006/IF/22012035600737 — Ek bagiya maa ke naam Sheela bai malviya MP20002006002/5 | Ongoing | 272600.27 | 18000 | 2025-08-30
SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720002006/IF/IAY/3703355 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103411738 | Approved | 27000 | 0 | 2022-05-01
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720002006/IF/IAY/3894315 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147831461 | Ongoing | 27000 | 0 | 2025-06-10
SONKATCH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1720002006/IF/IAY/39230 — Construction of IAY House -IAY REG. NO. MP-20-002-006-001/81 | Approved | 27000 | 0 | 2015-11-23
SONKATCH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720002006/IF/IAY/4555043 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113670345 | Physically Completed | 27000 | 0 | 2024-10-10 | 2026-10-01
SONKATCH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720002006/IF/IAY/4556298 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113916010 | Physically Completed | 27000 | 0 | 2024-10-10 | 2026-10-01
SONKATCH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720002006/IF/IAY/4566576 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116467852 | Physically Completed | 27000 | 0 | 2024-11-05 | 2026-10-01
SONKATCH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720002006/IF/IAY/4585388 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120657375 | Physically Completed | 23490 | 0 | 2024-10-22 | 2026-08-19
SONKATCH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720002006/IF/IAY/4601272 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123884281 | Approved | 27000 | 0 | 2024-09-15
SONKATCH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720002006/IF/IAY/4673219 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115791090 | Physically Completed | 23490 | 0 | 2024-12-21 | 2026-07-30
SONKATCH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720002006/IF/IAY/4737138 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106093787 | Physically Completed | 27000 | 0 | 2024-11-18 | 2026-10-01
SONKATCH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720002006/IF/IAY/4758172 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118587472 | Physically Completed | 27000 | 0 | 2024-12-21 | 2026-10-01
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720002006/IF/IAY/5162753 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113872237 | Physically Completed | 23490 | 0 | 2025-04-08 | 2026-07-27
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720002006/IF/IAY/5180196 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114132638 | Physically Completed | 23490 | 900 | 2025-04-05 | 2026-07-30
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720002006/IF/IAY/5199957 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120659435 | Ongoing | 27000 | 0 | 2025-05-19
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720002006/IF/IAY/5217307 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102203840 | Physically Completed | 27000 | 0 | 2025-04-05 | 2026-10-14
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720002006/IF/IAY/5222625 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115912380 | Physically Completed | 23490 | 0 | 2025-05-07 | 2026-07-27
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720002006/IF/IAY/5222674 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114901730 | Ongoing | 27000 | 1800 | 2025-05-19
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720002006/IF/IAY/5228236 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118601957 | Physically Completed | 23490 | 0 | 2025-05-26 | 2026-07-30
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720002006/IF/IAY/5229422 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105377456 | Ongoing | 27000 | 0 | 2025-04-08
SONKATCH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720002006/IF/IAY/5405079 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113640801 | Approved | 27000 | 0 | 2025-03-07
SONKATCH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720002006/IF/IAY/5542829 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116003288 | Ongoing | 27000 | 16500 | 2026-05-16
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720002006/IF/IAY/5615310 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114128207 | Ongoing | 27000 | 0 | 2025-06-04
SONKATCH | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1720002006/IF/IAY/805775 — Construction of IAY House -IAY REG. NO. MP3496507 | Approved | 27000 | 0 | 2017-03-31
SONKATCH | 2026-2027 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost Pit for Community | Construction of NADEP/Vermi Compost Pit | 1720002006/RS/VB/YD/22012035140207 — Constr of NADEP Compost structure for 1 | Approved | 33321.4 | 0 | 2026-09-22
SONKATCH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1720002006/WC/22012035215236 — parcolation tank padlya mohaba ke raste par | Ongoing | 199729.24 | 0 | 2024-12-07
SONKATCH | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1720002006/WC/VB/YD/22012035337532 — Construction of Recharge Pits for 1 | Approved | 28570.85 | 0 | 2026-08-15
SONKATCH | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1720002006/WC/VB/YD/22012035337533 — Constr of Boulder Anicut Check Dam for 1 | Approved | 70698.95 | 0 | 2026-08-15
SONKATCH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1720002/IF/22012035389245 — JGSA 2025 recharge structure kapildhara kailash chandra | New | 0 | 0 | 2025-04-20