## Work List
Exported on: 2026-10-23 05:57:04
Filters applied:
Data source: MGNREGA + VBGRAMG
District: DEWAS
Block: All
Panchayat: KUMARIYABANBIR
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SONKATCH | 2013-2014 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1720002011/AV/131 — Aanganbadi Bhavan Nirman Sewa Kendra,SONKATCH | Completed | 709000 | 170688.5 | 2013-08-27 | 2017-07-10
SONKATCH | 2014-2015 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1720002011/AV/2031 — Aanganbadi Bhavan Nirman Sewa Kendra,SONKATCH | Completed | 180000 | 173278 | 2014-08-25 | 2017-10-25
SONKATCH | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Construction of Cattle Shelter for Community / Construction of Cattle Shelter for Community | Cattle Shed | 1720002011/AV/22012034470528 — Goshala nirman kumariya banveer pahadi par | Physically Completed | 2771628.29 | 2523141.84 | 2019-11-16 | 2026-03-30
SONKATCH | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1720002011/DP/20234 — व्रक्षा रोपण,शमशान घाट पर कुमारिया बनवीर | Completed | 323000 | 65890 | 2010-09-14 | 2012-04-12
SONKATCH | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1720002011/DP/22012034445186 — Nirmal nir nirman kanjar dera kumariya banveer | Completed | 535000 | 311162 | 2019-03-10 | 2020-01-29
SONKATCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1720002011/DP/22012034445188 — Nirmanl nir nirman shantidham ke pass | Completed | 535000 | 177384 | 2019-03-10 | 2023-07-17
SONKATCH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Raising of Nursery for Community / Raising of Nursery for Community | Nursery Development | 1720002011/DP/22012034542943 — मां की बगिया मा वि परिसर कुमारिया बनवीर | Completed | 14675.4 | 2316 | 2022-02-13 | 2023-05-30
SONKATCH | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Shelter Belt Trees (Comm) / Boundary Line Plantation of Shelter Belt Trees for Community | Plantation | 1720002011/DP/22012034564262 — वृक्षा रोपण कार्य - अमृत सरोवर के पास कुमारिय बनवीर | Closed | 0 | 0 | 2022-08-02
SONKATCH | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Shelter Belt Trees (Comm) / Boundary Line Plantation of Shelter Belt Trees for Community | Plantation | 1720002011/DP/22012034564265 — वृक्षा रोपण कार्य - अमृत सरोवर के पास कुमारिय बनवीर | Closed | 0 | 0 | 2022-08-02
SONKATCH | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Shelter Belt Trees (Comm) / Boundary Line Plantation of Shelter Belt Trees for Community | Plantation | 1720002011/DP/22012034564732 — वृक्षा रोपण कार्य - अमृत सरोवर के पास कुमारिया बनवीर | Physically Completed | 412718.19 | 108450.6 | 2023-09-02 | 2026-06-16
SONKATCH | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1720002011/DP/22012034604279 — वसुधा वंदन वाटिका अमृत सरोवर के पास कुमारिया बनवीर | Physically Completed | 55847.4 | 29574.4 | 2023-08-26 | 2026-05-13
SONKATCH | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002011/IF/2145 — कुप निर्माण,पुरण मुन्नाजी | Completed | 254000 | 237034 | 2012-02-23 | 2012-07-05
SONKATCH | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002011/IF/2146 — कुप निर्माण,रुपसिह करणसिह | Completed | 254000 | 176067 | 2012-02-23 | 2013-01-31
SONKATCH | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002011/IF/22012034327726 — खेत तालाब सह कूप निर्माण (गंगाबाई विधवा पूरण ) | Completed | 230000 | 229719 | 2017-03-20 | 2018-08-20
SONKATCH | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002011/IF/22012034327734 — खेत तालाब सह कूप निर्माण (राजलबाई विधवा नरबत ) | Completed | 230000 | 229483 | 2017-03-20 | 2019-02-14
SONKATCH | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002011/IF/22012034327807 — खेत तालाब सह कुप निर्माण (पीरूलाल पिता अमरा जी) | Completed | 230000 | 236943 | 2017-03-20 | 2018-08-20
SONKATCH | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002011/IF/22012034327808 — खेत तालाब सह कुप निर्माण (नटवर पिता फेरनिया ) | Completed | 230000 | 233163 | 2017-03-20 | 2018-08-20
SONKATCH | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002011/IF/22012034327969 — खेत तालाब सह कुप निर्माण ( राजल बाई विधवा भागीरथ) | Closed | 230000 | 0 | 2017-03-20
SONKATCH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1720002011/IF/22012034341679 — vrakchha Ropan (shantidham ke pass narsari /anganwadi, school parisar) kumariya banvir | Completed | 335000 | 178867 | 2017-06-01 | 2022-10-28
SONKATCH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1720002011/IF/22012034365727 — vrakcha ropan (khel medan dehriya baldi) | Completed | 335000 | 59404 | 2017-07-20 | 2024-06-04
SONKATCH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002011/IF/22012034385279 — Khet talab with kup nirman | Deleted | 0 | 0 | 2017-10-26
SONKATCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002011/IF/22012034411092 — कपिलधारा कुप निर्माण कमलसिंह /अमर सिंह | Completed | 210000 | 206662 | 2018-05-15 | 2019-02-15
SONKATCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002011/IF/22012034411108 — KAPILDHARA KUP NIRMAN SAVITRABAI/DEVKARAN | Completed | 210000 | 204400 | 2018-05-22 | 2019-06-27
SONKATCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002011/IF/22012034411117 — कपिलधारा कुप निर्माण धर्मेंद्र/सोबालसिंह | Completed | 210000 | 206488 | 2018-05-15 | 2019-02-15
SONKATCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002011/IF/22012034411127 — कपिलधारा कुप निर्माण मायाबाई/विजेंद्रसिंह | Completed | 210000 | 197440 | 2018-05-15 | 2019-02-15
SONKATCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002011/IF/22012034415816 — कपिलधारा कुप निर्माण लीलाबाई/मेहरवानसिंह | Completed | 210000 | 204400 | 2018-06-02 | 2019-06-27
SONKATCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002011/IF/22012034418264 — कपिलधारा कुप निर्माण प्रेमकला/राजेश | Completed | 210000 | 220408 | 2018-06-10 | 2019-06-27
SONKATCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002011/IF/22012034472113 — कपिलधारा कूप निर्माण-जितेंद्र/दलेपसिंह | Completed | 210000 | 210880 | 2019-03-10 | 2019-08-16
SONKATCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002011/IF/22012034472121 — कपिलधारा कूप निर्माण-सुरेन्द्र/हरीसिंह | Completed | 210000 | 202254 | 2019-03-10 | 2019-09-15
SONKATCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002011/IF/22012034472124 — कपिलधारा कूप निर्माण-फुलसिंह/शेरसिंह | Completed | 210000 | 202078 | 2019-03-10 | 2020-05-14
SONKATCH | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002011/IF/22012034472198 — कपिलधारा कूप निर्माण-कल्याण/इंदरसिंह | Completed | 210000 | 205208 | 2019-04-14 | 2021-01-06
SONKATCH | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002011/IF/22012034550872 — Khet talab nirman surendra singh jeevan singh | Closed | 321415.72 | 0 | 2020-04-06
SONKATCH | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002011/IF/22012034550874 — खेत तालाब निर्माण विजेंद्र सिंह जीवन सिंह | Completed | 321415.72 | 247570 | 2020-05-06 | 2021-09-09
SONKATCH | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002011/IF/22012034559443 — खेत तालाब निर्माण - जसपालसिंह कमलसिंह | Completed | 324950.18 | 243580 | 2020-05-30 | 2022-09-09
SONKATCH | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002011/IF/22012034578554 — खेत तालाब निर्माण - लाखनसिंह पिता हरिसिंह | Completed | 338353.75 | 281770 | 2020-07-02 | 2022-09-09
SONKATCH | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002011/IF/22012034626566 — खेत तालाब निर्माण धीरजसिंह चेनसिंह | Completed | 314402.63 | 271130 | 2020-11-18 | 2021-09-09
SONKATCH | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002011/IF/22012034635648 — खेत तालाब निर्माण - जसमत सिंह सोबाल सिंह | Completed | 322032.19 | 277114 | 2020-12-31 | 2021-09-09
SONKATCH | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002011/IF/22012034665249 — समूह कपिलधारा कूप निर्माण - जोगेंद्र सिंह ,कमल ,दिगपाल पिता आत्माराम | Completed | 246126.86 | 245732 | 2021-03-03 | 2021-09-01
SONKATCH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002011/IF/22012034665255 — खेत तालाब सोबालसिह पिता गंगा राम | Completed | 314018.23 | 204156 | 2021-04-08 | 2022-03-16
SONKATCH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002011/IF/22012034665256 — खेत तालाब हिम्मतसिह करणसिंह | Completed | 314018.23 | 244861 | 2021-04-01 | 2022-11-02
SONKATCH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002011/IF/22012034672027 — खेत तालाब निर्माण ग्यानसिह जाब कार्ड नंबर 457 | Completed | 314018.23 | 186245 | 2021-04-01 | 2022-03-16
SONKATCH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1720002011/IF/22012034672028 — खेत तालाब निर्माण -रामचन्द्र | Ongoing | 314018.23 | 32038 | 2021-04-08
SONKATCH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002011/IF/22012034677009 — खेत तालाब निर्माण - करणसिंह पूरनसिंह | Completed | 314018.23 | 242778 | 2021-04-24 | 2022-11-02
SONKATCH | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002011/IF/22012034677026 — खेत तालाब निर्माण - मनोहरसिंह केशर सिंह | Deleted | 0 | 0 | 2021-01-26
SONKATCH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002011/IF/22012034681300 — खेत तालाब निर्माण- मनोहर सिंह सूरज सिंह | Completed | 314018.23 | 255532 | 2021-04-01 | 2022-03-16
SONKATCH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002011/IF/22012034750277 — CTR- खेत तालाब निर्माण -पप्पू पिता फूल सिंह | Completed | 327512.03 | 268356 | 2021-05-24 | 2023-08-19
SONKATCH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002011/IF/22012034940702 — खेत तालाब निर्माण धनीबाई पति फतेहसिंह देहरिया पेठ | Completed | 338902.57 | 102672 | 2022-02-24 | 2024-09-18
SONKATCH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002011/IF/22012034942358 — खेत तालाब निर्माण धनीबाई पति फतेहसिंह देहरिया पेठ | Closed | 0 | 0 | 2021-10-02
SONKATCH | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1720002011/IF/22012034992645 — व्यक्तिगत मेजिक पिट /5/कुमारिया ब्ननवीर | Closed | 35738.44 | 0 | 2022-04-15
SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002011/IF/22012035054325 — समूह कपिलधारा कूप निर्माण - 1विजेंद्र पिता बावल 2 हरि पिता किशन सिंह 3 नगजी राम पिता किशन सिंह | Deleted | 0 | 0 | 2023-01-02
SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002011/IF/22012035059923 — समूह कपिलधारा कूप निर्माण - 1विजेंद्र पिता बावल 2 हरि पिता किशन सिंह 3 नगजी राम पिता किशन सिंह | Completed | 322223.97 | 266322.28 | 2023-02-27 | 2024-03-01
SONKATCH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002011/IF/22012035110627 — कपिलधारा कूप - सज्जनसिंह पिता भेरू सिंह ,कृपालसिंह पिता हिम्मतसिंह , भवर पिता बाबू | Completed | 385027.83 | 312188 | 2023-06-17 | 2024-03-01
SONKATCH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002011/IF/22012035226425 — खेत तालाब निर्माण चेतनसिंह पिता अकेसिंह | Completed | 305357.23 | 258417 | 2024-11-25 | 2025-04-29
SONKATCH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002011/IF/22012035287892 — खेत तालाब निर्माण सजन बाई पति आत्माराम कुमारिया बनवीर | Closed | 0 | 0 | 2024-10-02
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002011/IF/22012035313128 — Khet talab nirman Harisingh Amarsingh | Completed | 365365.98 | 286147 | 2025-04-12 | 2026-02-16
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002011/IF/22012035351533 — khet talab nirman tejubai devkaran | Completed | 454210.33 | 335646 | 2025-04-22 | 2026-03-25
SONKATCH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1720002011/IF/22012035391148 — well lichpit Vijendra s/o baval | Completed | 25899.46 | 25449.09 | 2025-04-27 | 2026-02-25
SONKATCH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1720002011/IF/22012035391269 — well lichpit Lila bai W/o meharvan singh | Ongoing | 25899.46 | 10049.73 | 2025-04-27
SONKATCH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1720002011/IF/22012035391344 — well lichpit surendra s/o Harisingh | Completed | 25899.46 | 24144.15 | 2025-05-02 | 2026-02-16
SONKATCH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1720002011/IF/22012035391406 — well lichpit Kamal singh s/o amarsingh | Closed | 25899.46 | 261 | 2025-04-27
SONKATCH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1720002011/IF/22012035391443 — well lichpit Kamal s/o atmaram | Closed | 25899.46 | 261 | 2025-05-02
SONKATCH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1720002011/IF/22012035391497 — well lichpit Premkala w/o Rajensh | New | 0 | 0 | 2025-04-14
SONKATCH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1720002011/IF/22012035391499 — well lichpit Premkala w/o Rajensh | Completed | 25899.46 | 25449.27 | 2025-04-27 | 2026-02-16
SONKATCH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1720002011/IF/22012035391546 — well lichpit Dharmendra s/o sobalsingh | Closed | 0 | 0 | 2025-04-14
SONKATCH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1720002011/IF/22012035391592 — well lichpit sajan singh s/o Bherusingh | Ongoing | 25899.46 | 10050.81 | 2025-05-02
SONKATCH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1720002011/IF/22012035391625 — well lichpit Jitendra s/o Dalepsingh | Ongoing | 25899.46 | 10050.81 | 2025-04-27
SONKATCH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1720002011/IF/22012035449371 — dug well shanta bai s/o bhagirth | Completed | 25899.46 | 25448.28 | 2025-05-07 | 2026-02-16
SONKATCH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1720002011/IF/22012035449405 — dug well fool singh s/o shersingh | Completed | 25899.46 | 25449.81 | 2025-05-07 | 2026-02-16
SONKATCH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1720002011/IF/22012035449500 — dug well gangabai w/o puran | Completed | 25899.46 | 25449.43 | 2025-05-07 | 2026-02-16
SONKATCH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1720002011/IF/22012035449522 — dug well Dharmendra s/o sobalsingh | New | 0 | 0 | 2025-04-14
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002011/IF/22012035482098 — kapil dhara kup nirman sima w/o narendra singh | Closed | 0 | 0 | 2025-04-14
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002011/IF/22012035483950 — खेत तालाब निर्माण कविता बाई लाखनसिंह | Completed | 453226.33 | 247689 | 2025-05-12 | 2026-05-03
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002011/IF/22012035526376 — JGM KHET TALAB NIRMAN FATESINGH BHERUSINGH | Completed | 391040.64 | 240642 | 2025-05-21 | 2026-05-13
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1720002011/IF/22012035589977 — Ek Bagiya Maa Ke Naam Gora bai MP20002011001 8-A | Ongoing | 272600.27 | 119573.1 | 2025-09-19
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1720002011/IF/22012035590018 — Ek Bagiya Maa Ke Naam Amila bai MP20002011001 217-C | Ongoing | 272600.27 | 134609.48 | 2025-09-19
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1720002011/IF/22012035593913 — Ek Bagiya Maa Ke Naam Gora babi | New | 0 | 0 | 2025-08-01
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1720002011/IF/22012035599579 — Ek Bagiya Maa Ke Naam Prachi MP-20-002-011-001/101-A | Ongoing | 272600.27 | 112010 | 2025-08-28
SONKATCH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002011/IF/9993682195 — इंदरा अवास,अमरदास प्रेमदास पि वर्ग कुमारीया बन | Completed | 7155 | 1113 | 2015-11-01 | 2017-10-25
SONKATCH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002011/IF/9993682198 — इंदरा आवास,छितु घिसाजी अजा कुमारीया बन | Completed | 7155 | 1113 | 2015-11-01 | 2017-10-25
SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002011/IF/IAY/3934269 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104906015 | Completed | 18360 | 17646 | 2022-11-05 | 2023-07-18
SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002011/IF/IAY/3963194 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105707436 | Completed | 18360 | 18360 | 2022-07-07 | 2023-01-01
SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002011/IF/IAY/3965809 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106755679 | Completed | 18360 | 17952 | 2022-09-23 | 2023-07-18
SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002011/IF/IAY/3965815 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106756775 | Completed | 18360 | 18360 | 2022-09-30 | 2023-01-20
SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002011/IF/IAY/3965820 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106757834 | Completed | 18360 | 17646 | 2022-11-30 | 2023-09-01
SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002011/IF/IAY/3966532 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105367229 | Completed | 18360 | 18360 | 2022-09-30 | 2023-06-28
SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720002011/IF/IAY/3970260 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104908012 | Approved | 27000 | 0 | 2022-05-06
SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002011/IF/IAY/3971459 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102996348 | Completed | 18360 | 18360 | 2022-07-16 | 2023-01-01
SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720002011/IF/IAY/3974442 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115160686 | Approved | 27000 | 0 | 2022-05-07
SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002011/IF/IAY/3974449 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115163357 | Completed | 18360 | 17765 | 2022-09-30 | 2023-08-09
SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002011/IF/IAY/4056950 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102950066 | Completed | 18360 | 18156 | 2022-10-01 | 2023-07-18
SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002011/IF/IAY/4058043 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105378594 | Completed | 18360 | 18360 | 2022-09-23 | 2023-01-20
SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002011/IF/IAY/4058908 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104903960 | Completed | 18360 | 18156 | 2023-01-02 | 2023-09-17
SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002011/IF/IAY/4059745 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106877625 | Completed | 18360 | 18241 | 2022-07-20 | 2023-07-31
SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002011/IF/IAY/4060896 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105424123 | Completed | 18360 | 18360 | 2022-09-23 | 2023-06-28
SONKATCH | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002011/IF/IAY/40986 — Construction of IAY House -IAY REG. NO. MP-20-002-011-001/12 | Completed | 14310 | 13891 | 2017-02-03 | 2018-03-31
SONKATCH | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002011/IF/IAY/40987 — Construction of IAY House -IAY REG. NO. MP-20-002-011-001/23 | Completed | 14310 | 13557 | 2017-02-03 | 2018-03-31
SONKATCH | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002011/IF/IAY/40988 — Construction of IAY House -IAY REG. NO. MP-20-002-011-002/37 | Completed | 14310 | 8577 | 2017-02-03 | 2018-03-31
SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002011/IF/IAY/4129838 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104902420 | Completed | 18360 | 15912 | 2022-11-29 | 2023-12-10
SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002011/IF/IAY/4129843 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104906336 | Completed | 18360 | 18360 | 2022-07-16 | 2023-01-20
SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002011/IF/IAY/4130159 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102911026 | Completed | 18360 | 18360 | 2022-07-16 | 2023-01-01
SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002011/IF/IAY/4130957 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100620902 | Completed | 18360 | 18360 | 2022-07-20 | 2023-01-01
SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002011/IF/IAY/4131110 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106753010 | Completed | 18360 | 17969 | 2022-09-23 | 2023-11-01
SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002011/IF/IAY/4241381 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113451823 | Completed | 18360 | 17459 | 2022-08-17 | 2023-10-29
SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002011/IF/IAY/4242053 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102995265 | Completed | 18360 | 18156 | 2022-07-07 | 2023-07-18
SONKATCH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002011/IF/IAY/4242412 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113969144 | Completed | 18360 | 18564 | 2023-07-27 | 2023-12-26
SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002011/IF/IAY/4242436 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113989011 | Completed | 18360 | 15929 | 2023-02-02 | 2024-09-19
SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002011/IF/IAY/4243922 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116293450 | Completed | 18360 | 18224 | 2022-11-11 | 2023-08-27
SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002011/IF/IAY/4277626 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105449951 | Completed | 18360 | 18224 | 2022-11-30 | 2023-09-01
SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002011/IF/IAY/4363149 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106883956 | Completed | 18360 | 18088 | 2022-09-30 | 2023-08-17
SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002011/IF/IAY/4363432 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114860208 | Completed | 18360 | 17646 | 2022-11-05 | 2023-08-02
SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002011/IF/IAY/4363437 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114872252 | Completed | 18360 | 18360 | 2022-11-21 | 2023-06-28
SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002011/IF/IAY/4363835 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100623043 | Completed | 18360 | 18088 | 2022-12-10 | 2023-08-17
SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002011/IF/IAY/4365352 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105420478 | Completed | 18360 | 18275 | 2022-09-23 | 2023-09-17
SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002011/IF/IAY/4383723 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102942544 | Completed | 18360 | 18360 | 2022-11-30 | 2023-06-28
SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002011/IF/IAY/4384049 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114857471 | Completed | 18360 | 18156 | 2022-12-10 | 2023-07-18
SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002011/IF/IAY/4390160 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105710930 | Completed | 18360 | 17756 | 2023-02-02 | 2023-11-01
SONKATCH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002011/IF/IAY/4536041 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102926994 | Completed | 23490 | 20484 | 2024-10-15 | 2025-11-04
SONKATCH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002011/IF/IAY/4734795 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102915698 | Completed | 23490 | 21618 | 2024-12-23 | 2025-11-04
SONKATCH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002011/IF/IAY/4734823 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102927810 | Completed | 23490 | 20223 | 2024-11-12 | 2025-11-04
SONKATCH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002011/IF/IAY/4742094 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107079494 | Completed | 23490 | 19683 | 2024-11-25 | 2025-11-04
SONKATCH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002011/IF/IAY/4744541 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113995951 | Completed | 23490 | 16524 | 2024-11-26 | 2025-11-04
SONKATCH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002011/IF/IAY/4862217 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102918946 | Completed | 23490 | 21870 | 2024-12-23 | 2025-05-02
SONKATCH | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002011/IF/IAY/508495 — Construction of IAY House -IAY REG. NO. MP2362497 | Completed | 15030 | 13919 | 2017-02-03 | 2018-03-31
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002011/IF/IAY/5155091 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100624908 | Completed | 23490 | 23490 | 2025-05-24 | 2025-10-03
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002011/IF/IAY/5188465 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114869257 | Completed | 23490 | 18792 | 2025-04-12 | 2026-01-09
SONKATCH | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002011/IF/IAY/519018 — Construction of IAY House -IAY REG. NO. MP2530390 | Completed | 15030 | 14615 | 2017-02-03 | 2018-03-31
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002011/IF/IAY/5255041 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106744666 | Completed | 23490 | 23490 | 2025-05-04 | 2026-05-09
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002011/IF/IAY/5271246 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100671153 | Completed | 23490 | 23490 | 2025-04-21 | 2026-02-22
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002011/IF/IAY/5278219 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113449044 | Completed | 23490 | 23490 | 2025-04-12 | 2026-01-09
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002011/IF/IAY/5291097 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105427643 | Completed | 23490 | 22968 | 2025-05-11 | 2026-01-09
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002011/IF/IAY/5318739 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105380950 | Physically Completed | 23490 | 23490 | 2025-05-24 | 2026-05-18
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002011/IF/IAY/5324188 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105446445 | Physically Completed | 23490 | 22968 | 2025-04-21 | 2026-06-15
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002011/IF/IAY/5330646 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106750954 | Completed | 23490 | 22446 | 2025-04-12 | 2026-02-22
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002011/IF/IAY/5433121 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105461682 | Completed | 23490 | 22968 | 2025-04-21 | 2026-01-09
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002011/IF/IAY/5458050 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104023393 | Completed | 23490 | 23476 | 2025-04-30 | 2026-05-09
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002011/IF/IAY/5505519 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115132535 | Completed | 23490 | 23490 | 2025-05-21 | 2026-03-20
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002011/IF/IAY/5511897 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113456650 | Completed | 23490 | 22968 | 2025-05-24 | 2026-01-09
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002011/IF/IAY/5511898 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113456809 | Completed | 23490 | 22185 | 2025-06-20 | 2026-02-22
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002011/IF/IAY/5512855 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106739367 | Completed | 23490 | 23490 | 2025-05-24 | 2026-01-09
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720002011/IF/IAY/5641960 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105466229 | Physically Completed | 23490 | 20358 | 2025-07-25 | 2026-07-20
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002011/IF/IAY/5701873 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114156087 | Physically Completed | 23490 | 18531 | 2026-02-23 | 2026-06-28
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002011/IF/IAY/5769539 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113451368 | Physically Completed | 23490 | 23229 | 2025-10-23 | 2026-05-20
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720002011/IF/IAY/6374067 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106897162 | Approved | 27000 | 0 | 2025-04-11
SONKATCH | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720002011/LD/22012034235761 — मेड बंधान,पप्‍पु फुलसिंह | Completed | 35000 | 30846 | 2015-11-01 | 2015-12-10
SONKATCH | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Land Leveling / Levelling/shaping of Wasteland Land for Community | Land Development | 1720002011/LD/22012034235762 — मेड बंधान,मोडसिंह रतनसिंह | Completed | 35000 | 2385 | 2015-11-01 | 2016-01-28
SONKATCH | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720002011/LD/22012034235763 — मेड बंधान,मेहरवानसिंह करणसिंह | Completed | 35000 | 318 | 2015-12-25 | 2017-10-25
SONKATCH | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1720002011/LD/22012034254114 — शान्तिधाम निर्माण देहरीया पेठ | Completed | 527000 | 388389 | 2016-03-18 | 2020-05-14
SONKATCH | 2015-2016 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1720002011/LD/22012034254115 — किडान्‍गन निर्माण,ई.जी,एस स्‍कुल के सामने देहरीया पेठ | Completed | 360000 | 222686.27 | 2016-03-18 | 2019-02-15
SONKATCH | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Dev of Silvipasture Grassslands for Community / Development of Silvipasture Grassslands for Community | Grass Land Development | 1720002011/LD/22012034474336 — Sokhata gadda niramn kumariya banbeer | Closed | 0 | 0 | 2019-10-02
SONKATCH | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Dev of Silvipasture Grassslands for Community / Raising of Fodder Cultivation for Community | Grass Land Development | 1720002011/LD/22012034474406 — Charagah nirman kumariya banveer | Ongoing | 1498767.46 | 131670 | 2020-07-30
SONKATCH | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720002011/LD/3799402375 — किडान्‍गन,मा वि.प्रा विध्‍यालय | Completed | 50000 | 49908 | 2013-08-27 | 2014-02-25
SONKATCH | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720002011/LD/3799419961 — शान्तिधाम निर्माण,कुमारीया बनविर | Completed | 376000 | 298539 | 2014-01-13 | 2015-03-11
SONKATCH | 2014-2015 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720002011/LD/9926708962 — भुमि समतलीकरण रणजीत उमराव | Completed | 170000 | 105661 | 2014-06-16 | 2015-03-11
SONKATCH | 2014-2015 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720002011/LD/9926709110 — भुमि समतलीकरण सुगनबाई रणजीत | Completed | 156000 | 82896 | 2014-06-16 | 2016-07-18
SONKATCH | 2014-2015 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720002011/LD/9926709467 — भुमि समतलीकरण लखनसिंह चन्‍दरसिंह | Completed | 156000 | 100951 | 2014-06-16 | 2015-03-11
SONKATCH | 2015-2016 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1720002011/PG/9425888080 — क्रिडांगन कुमारिया बनवीर | Deleted | 0 | 0 | 2016-01-26
SONKATCH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1720002011/RC/22012034164833 — सी सी रोड केशरसिंह के मकान सें शाला भवन तक | Completed | 104000 | 57816 | 2013-05-07 | 2014-02-15
SONKATCH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002011/RC/22012034173363 — पंच परमेश्‍वर, पि‍प्‍लरावा रोड से अनोखी के मकान तक | Completed | 127000 | 108264 | 2013-07-01 | 2014-02-15
SONKATCH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1720002011/RC/22012034173365 — पंच परमेश्‍वर,करणसिंह के मकान से हेण्‍पंम्‍प तक | Completed | 58000 | 13140 | 2013-12-30 | 2014-01-15
SONKATCH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002011/RC/22012034198789 — पंच परमेश्‍वर,कलाबाई के घर से नाले तक | Completed | 183000 | 181224 | 2014-01-13 | 2014-03-25
SONKATCH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002011/RC/22012034227915 — सान्‍सद निधी,कन्‍जर मोहल्‍ला कुमारीया बनविर | Deleted | 87000 | 0 | 2013-08-25
SONKATCH | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002011/RC/22012034297361 — पंच परमेश्‍वर,धनसिंह के घर से ई जी एस स्‍कुल तक | Completed | 57000 | 69329 | 2016-01-31 | 2017-10-25
SONKATCH | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002011/RC/22012034300398 — सी,सी,रोड अम्‍बाराम के घर से पिपलरावा रोड | Completed | 38000 | 32565 | 2016-04-14 | 2017-10-25
SONKATCH | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002011/RC/22012034325137 — सी,सी,रोड,चौकीदार के घर से कल्‍याणसिंह के घर तक | Completed | 110000 | 89178 | 2017-02-04 | 2019-02-15
SONKATCH | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002011/RC/22012034325144 — सी,सी,रोड निर्माण धनसिंह के घर से सुरजसिंह के घर तक | Completed | 137000 | 40860 | 2017-02-12 | 2019-02-15
SONKATCH | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Gravel Road Roads for Comm / Repair and maintenance of Gravel Road Roads for Community | Repair & maint of Road | 1720002011/RC/22012034332049 — सुदुर ग्राम सम्पर्क (प्रधानमंत्री सड़क देहरिया पेठ से सोबाल के मकान तक | Completed | 444000 | 458626 | 2017-03-20 | 2019-07-15
SONKATCH | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002011/RC/22012034344963 — सी,सी,रोड निर्माण बाबूराव के घर से ज्ञानदास के घर तक | Deleted | 28116000000 | 0 | 2017-09-16
SONKATCH | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel / Mitti Murram Road for Community | Construction of Road and Culvert | 1720002011/RC/22012034523076 — अप्रोच रोड - देहरिया पेट से शमशान घाट तक | Physically Completed | 643727.37 | 239810 | 2020-12-25 | 2026-08-21
SONKATCH | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002011/RC/22012034573610 — सी सी रोड निर्माण - प्रधान मंत्री रोड से बाबु सिंह के प्लाट तक | Closed | 22000 | 0 | 2021-06-07
SONKATCH | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002011/RC/22012034622380 — सी सी रोड निर्माण - दरियाव सिंह के मकान से धर्मेन्द्र के मकान की और हरिजन कालोनी | Completed | 51700 | 51374 | 2022-12-10 | 2023-11-23
SONKATCH | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002011/RC/22012034640637 — सी सी रोड निर्माण - फुलसिंह के घर से सुभाष राठोर की दुकान तक | Completed | 22000 | 18564 | 2023-08-31 | 2023-12-14
SONKATCH | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002011/RC/22012034640638 — सी सी रोड - अजाब सिंह के मकान से फुलसिंह के घर तक | Completed | 22000 | 6188 | 2023-07-10 | 2023-12-14
SONKATCH | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002011/RC/22012034644863 — सी सी रोड निर्माण - वीरेंदर सिंह के घर से कल्याणसिंह के घर | Closed | 24300 | 0 | 2023-04-25
SONKATCH | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1720002011/RC/229 — ग्रेवल सडक निर्माण,सोभालसिह के खेत से नाले वाले तक | Completed | 496000 | 451328 | 2011-09-01 | 2013-01-21
SONKATCH | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002011/RC/269 — पंच प्रमेश्वर,सी.सी रोड देवकरण के मकान से शाला भवन तक | Completed | 73000 | 67260 | 2012-03-15 | 2013-01-21
SONKATCH | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1720002011/RC/477 — पंच परमेश्‍वर,जसमतसिंह के मकान से अम्‍बाराम के मकान तक | Completed | 193000 | 77768 | 2012-09-26 | 2013-01-12
SONKATCH | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002011/RC/518 — पंच परमेश्‍वर करणसिंह के मकन से कुण्‍डी तक | Completed | 26000 | 9544 | 2013-01-03 | 2014-02-15
SONKATCH | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002011/RC/519 — पंच परमेश्‍वर, सोबालसिंह के मकान से हमीरसिंह के मकान तक | Completed | 163000 | 72280 | 2013-03-04 | 2013-03-21
SONKATCH | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1720002011/RC/55 — ग्रेवल सड्क, रोजबल्‍डी से कुमारियाबनवीर | Completed | 497000 | 281833 | 2010-06-10 | 2012-04-19
SONKATCH | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1720002011/RC/56 — ग्रेवल सड्क, बाबूलाल के बाडे से फुलसिंह के कुए तक | Completed | 497000 | 113150 | 2010-06-03 | 2012-04-19
SONKATCH | 2007-2008 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1720002011/RC/आबादी से प्रधानमंृी सड्क टुंगनी मार् — ग्राम पंचायत कुमारियाबनवीर,ग्रेवल सड्क, आबादी से प्रधानमंृी सड्क टुंगनी मार्ग तक | Completed | 1194000 | 846751 | 2008-03-29 | 2012-04-19
SONKATCH | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002011/RC/बनवीर सीसी;रेाड्, श्‍मशानघाट से मेन — ग्राम पंचायत कुमारिया बनवीर सीसीरेाड्, श्‍मशानघाट से मेन रोड् तक | Completed | 185000 | 61716 | 2008-08-03 | 2009-02-20
SONKATCH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720002011/RS/22012034204426 — शौचालय निर्माण,नारायण गणपत | Completed | 5400 | 4400 | 2014-02-16 | 2015-02-16
SONKATCH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720002011/RS/22012034204429 — शौचालय निर्माण,गणपत बापु | Completed | 5400 | 4400 | 2014-02-16 | 2015-02-21
SONKATCH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720002011/RS/22012034204434 — शौचालय निर्माण,मेरवान नारायण | Deleted | 5400 | 0 | 2013-12-25
SONKATCH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720002011/RS/22012034204437 — शौचालय निर्माण,कुमेर हिम्‍मत | Deleted | 5400 | 0 | 2014-02-16
SONKATCH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720002011/RS/22012034204455 — शौचालय निर्माण,क्रपालसिंह हिम्‍मतसिंह | Completed | 5400 | 4400 | 2014-02-16 | 2014-11-20
SONKATCH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720002011/RS/22012034204471 — शौचालय निर्माण,विक्षाम हिम्‍मतसिंह | Completed | 5400 | 4400 | 2014-02-16 | 2014-11-21
SONKATCH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720002011/RS/22012034204483 — शौचलय निर्माण,सावित्राबाई बाबुलाल | Completed | 5400 | 4400 | 2014-02-16 | 2014-11-21
SONKATCH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720002011/RS/22012034204485 — शौचालय निर्माण,फुलसिंह शेरसिंह | Deleted | 5400 | 0 | 2013-12-25
SONKATCH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720002011/RS/22012034204506 — शौचालय निर्माण,केलासचन्‍द्र शिवनारायण | Deleted | 5400 | 0 | 2013-12-25
SONKATCH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720002011/RS/22012034204511 — शौचालय निर्माण,शिवनारायण राधाकिशन | Deleted | 4400 | 0 | 2013-12-25
SONKATCH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720002011/RS/22012034204515 — शौचालय निर्माण,सोदराबाई कमलसिंह | Completed | 4400 | 4108 | 2014-02-16 | 2014-11-21
SONKATCH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720002011/RS/22012034206244 — शौचालय निर्माण,भादर रणजित | Completed | 5400 | 4108 | 2014-02-16 | 2014-11-21
SONKATCH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720002011/RS/22012034206246 — शौचालय निर्माण,धनसिंह शैरसिंह | Completed | 5400 | 4400 | 2014-02-16 | 2014-11-21
SONKATCH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720002011/RS/22012034209108 — शौचालय निर्माण रूपसिंह करण | Completed | 5400 | 4400 | 2014-02-23 | 2014-11-20
SONKATCH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720002011/RS/22012034209109 — शैचालय निर्माण भेरूसिंह शेरसिंह | Deleted | 5400 | 0 | 2014-02-23
SONKATCH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720002011/RS/22012034209110 — शौचालय निर्माण बजेसिंह रामसिंह | Completed | 5400 | 4400 | 2014-02-23 | 2015-02-16
SONKATCH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720002011/RS/22012034209112 — शौचालय निर्माण अजापसिंह सेवाराम | Completed | 5400 | 4400 | 2014-02-23 | 2015-02-21
SONKATCH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720002011/RS/22012034209114 — शौचालय निर्माण सोबालसिंह मोतिसिंह | Completed | 5400 | 4400 | 2014-02-23 | 2015-02-21
SONKATCH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720002011/RS/22012034209115 — शौचालय निर्माण मागिलाल छोगालाल | Completed | 5400 | 4400 | 2014-02-23 | 2014-11-21
SONKATCH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720002011/RS/22012034209117 — शौचालय निर्माण,देवकरण चेनसिंह | Completed | 5400 | 4400 | 2014-02-23 | 2014-11-21
SONKATCH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720002011/RS/22012034209119 — शौचालय निर्माण रामसिंह रायसिंह | Completed | 5400 | 4108 | 2014-02-23 | 2014-11-21
SONKATCH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720002011/RS/22012034209123 — शौचालय निर्माण अन्‍तरबाई सजनसिंह | Completed | 5400 | 4400 | 2014-02-23 | 2015-02-16
SONKATCH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720002011/RS/22012034209125 — शौचालय निर्माण मानसिंह जगन्‍नाथसिंह | Completed | 5400 | 4108 | 2014-02-23 | 2015-02-21
SONKATCH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720002011/RS/22012034209127 — शौचालय निर्माण जयसिंह जगन्‍नाथ | Completed | 5400 | 4400 | 2014-02-23 | 2015-02-16
SONKATCH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720002011/RS/22012034209129 — शौचालय निर्माण बद्रीलाल मागिलाल | Completed | 5400 | 2920 | 2014-02-23 | 2015-07-15
SONKATCH | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1720002011/RS/22012034497479 — SBM- सामुदायिक स्वच्छता परिसर ग्राम कुमारिय बनवीर | Completed | 44000 | 41990 | 2020-09-29 | 2021-04-05
SONKATCH | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1720002011/WC/2018 — सार्वजनिक कुप निर्मान,पटाडिया रास्ते के नाले पर(देहरियापेड) | Completed | 358000 | 203404 | 2010-12-09 | 2013-02-21
SONKATCH | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1720002011/WC/2019 — सार्वजनिक कुप निर्मान,शमशानघाट्(कुमारियाबनवीर) | Completed | 358000 | 248201 | 2010-12-09 | 2012-04-16
SONKATCH | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Continuous Contour Trench / Construction of Continuous Contour Trench for Community | Construction of Trench | 1720002011/WC/22012034330143 — Kantur trench dehariya baldi(kumariya banavir) | Completed | 361000 | 52632 | 2017-06-21 | 2019-02-15
SONKATCH | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Loose Boulder Structure / Construction of Stone boulder Gully Plugs for Community | Boulder Check/Gully Plug | 1720002011/WC/22012034382216 — loose boulder | Closed | 0 | 0 | 2017-10-26
SONKATCH | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Gabions / Construction of Gabion Check Dam for Individuals | Constr of Gabion | 1720002011/WC/22012034382217 — gabian | Closed | 0 | 0 | 2017-10-26
SONKATCH | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1720002011/WC/22012034382218 — check dam | Closed | 0 | 0 | 2017-10-26
SONKATCH | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1720002011/WC/22012034382219 — check dam | Closed | 0 | 0 | 2017-10-26
SONKATCH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1720002011/WC/22012034382220 — farm pond | Closed | 0 | 0 | 2017-10-26
SONKATCH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1720002011/WC/22012034382221 — farm pond | Closed | 0 | 0 | 2017-10-26
SONKATCH | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1720002011/WC/22012034385994 — check dam(mankuwar baai ke khet ke paas) | Closed | 0 | 0 | 2017-10-02
SONKATCH | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1720002011/WC/22012034437958 — chekdam niraman | Closed | 0 | 0 | 2019-05-24
SONKATCH | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & maint of Mini Percolation Tank for Comm / Repair and maintenance of Mini Percolation Tank for Community | Repair & maint of Percolation Tank | 1720002011/WC/22012034448177 — parcoletion tank roj baldi ke pass | Closed | 0 | 0 | 2019-01-26
SONKATCH | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1720002011/WC/22012034477328 — recharge pit (manglik bhawan) | Closed | 0 | 0 | 2019-04-24
SONKATCH | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1720002011/WC/22012034477329 — recharge pit (kanjar dayra) | Closed | 0 | 0 | 2019-04-24
SONKATCH | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand filter for borewell recharge for Community | Well Recharge | 1720002011/WC/22012034484318 — Sokhata gadda nirman primary school parisar kumariya banveer | Completed | 13427.22 | 8960 | 2019-08-27 | 2021-04-05
SONKATCH | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand filter for borewell recharge for Community | Well Recharge | 1720002011/WC/22012034484319 — Sokhata gadda nirman p.s school parisar | Completed | 13427.22 | 8960 | 2019-08-27 | 2021-05-04
SONKATCH | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand filter for borewell recharge for Community | Well Recharge | 1720002011/WC/22012034484320 — Sokhata gadda nirman Akesingh ke ghar ke pass hemdpump | Completed | 13427.22 | 8960 | 2019-08-27 | 2021-04-05
SONKATCH | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1720002011/WC/22012034592016 — तलाई निर्माण - गो शाळा के पास | Closed | 0 | 0 | 2020-10-28
SONKATCH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1720002011/WC/22012034770339 — रूफ वाटर हार्वेस्टिंग आंगनबाड़ी भवन देहरिया बल्डीरूफ वाटर हार्वेस्टिंग आंगनबाड़ी भवन देहरिया बल्डी | Closed | 23418.16 | 0 | 2021-04-26
SONKATCH | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dykes for Community | Underground Dyke for Ground Water Recharge | 1720002011/WC/22012034934890 — डायिक निर्माण - गंगाबाई के खेत के पास | Closed | 58964.66 | 0 | 2022-04-01
SONKATCH | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dykes for Community | Underground Dyke for Ground Water Recharge | 1720002011/WC/22012034935336 — डायिक निर्माण - कल्याणसिंह के खेत के पास | Closed | 57643.4 | 0 | 2022-04-06
SONKATCH | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dykes for Community | Underground Dyke for Ground Water Recharge | 1720002011/WC/22012034935349 — डायिक निर्माण - इंदरसिंह के खेत के पास | Closed | 73436.43 | 0 | 2022-04-01
SONKATCH | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dykes for Community | Underground Dyke for Ground Water Recharge | 1720002011/WC/22012034935358 — डायिक निर्माण - देवकरण के खेत के पास | Closed | 68172.08 | 0 | 2022-04-01
SONKATCH | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dykes for Community | Underground Dyke for Ground Water Recharge | 1720002011/WC/22012034935381 — डायिक निर्माण - नरेन्द्र जोशी के खेत के पास | Closed | 0 | 0 | 2022-04-01
SONKATCH | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1720002011/WC/22012034940949 — नवीन तालाब शांति धाम के पास | Completed | 1470828.2 | 1293262.1 | 2022-04-20 | 2023-11-23
SONKATCH | 2022-2023 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1720002011/WC/22012034968608 — नाला डायवर्सन परकोलेशन टैंक से नवीन तालाब तक | Completed | 89654.04 | 56304 | 2022-05-25 | 2023-08-19
SONKATCH | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1720002011/WC/22012035114266 — पर्कॉयलेशन टैंक गौशाला के पास कुमारिया बनवीर | Physically Completed | 622177.54 | 400573 | 2023-10-03 | 2026-03-30
SONKATCH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1720002011/WC/22012035241389 — पर्कोंलेशन टैंक पहाड़ी पर कुमारिया बनवीर | Completed | 198727.19 | 162756 | 2025-01-21 | 2025-05-27
SONKATCH | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1720002011/WC/82 — तलाई निर्माण , श्‍मशानघाट के पास | Completed | 500000 | 352304 | 2010-06-03 | 2013-02-21
SONKATCH | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1720002011/WC/9993637080 — सी,पी,टी नाला खुदाई वक्ष्रा रोपण नर्सरी | Completed | 404000 | 113880 | 2013-09-30 | 2014-01-15
SONKATCH | 2007-2008 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002011/WC/कपलिधारा कुमारीया देवामाती लालसीह — कपलिधारा कुमारीया देवामाती लालसीह | Completed | 67400 | 135191.5 | 2007-12-21 | 2012-04-18
SONKATCH | 2007-2008 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002011/WC/कपलिधारा कुमारीया बनवीर छोगु भेरासीह — कपलिधारा कुमारीया बनवीर छोगु भेरासीह | Completed | 67400 | 112349 | 2007-12-04 | 2012-04-18
SONKATCH | 2007-2008 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002011/WC/कपलिधारा कुमारीया बनवीर धासीराम — कपलिधारा कुमारीया बनवीर धासीराम | Completed | 67400 | 41381 | 2007-12-03 | 2009-03-08
SONKATCH | 2007-2008 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002011/WC/कपलिधारा कुमारीया बनवीर बदीलाल व परी — कपलिधारा कुमारीया बनवीर बदीलाल व परीवार | Completed | 67400 | 134000 | 2007-12-20 | 2009-11-24
SONKATCH | 2007-2008 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002011/WC/कपलिधारा कुमारीया बनवीर राजलबाइ — कपलिधारा कुमारीया बनवीर राजलबाइ | Completed | 67400 | 53094 | 2007-12-02 | 2009-12-27
SONKATCH | 2007-2008 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002011/WC/कपलिधारा कुमारीया बनवीर लालसीह — कपलिधारा कुमारीया बनवीर लालसीह | Completed | 67400 | 66495 | 2007-12-20 | 2012-04-18
SONKATCH | 2007-2008 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002011/WC/कपलिधारा कुमारीया बनवीर ि‍जतेन्‍द — कपलिधारा कुमारीया बनवीर ि‍जतेन्‍द | Completed | 67400 | 43376 | 2008-01-01 | 2012-04-18
SONKATCH | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Sub Surface Dam / Construction of Underground Dykes for Community | Underground Dyke for Ground Water Recharge | 1720002011/WC/कुमारिया बनवीर, नवीन तालाब निर्माण, — ग्राम पंचायत कुमारिया बनवीर, नवीन तालाब निर्माण, बीसूखेड्ी मार्ग | Completed | 419000 | 828 | 2008-03-29 | 2008-03-04
SONKATCH | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1720002011/WC/तलाइ नि‍मान टुगनी माग पर अनोप सीह के — तलाइ नि‍मान टुगनी माग पर अनोप सीह के खेत के पास कुमा(रीया बानवीर | Completed | 220500 | 4586 | 2008-01-21 | 2012-04-16
SONKATCH | 2007-2008 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002011/WC/मेहरबान कलेजा कुमा(रीया बानवीर कुप — कुप नि‍मान मेहरबान कलेजा कुमारीया बानवीर | Completed | 67400 | 100557 | 2008-01-28 | 2012-04-18
SONKATCH | 2007-2008 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002011/WC/सीलो बाइ जासमत कुमा(रीया बानवीर कुप — कुपनि‍मान सीलो बाइ जासमत कुमारीया बानवीर | Completed | 67400 | 122142 | 2008-01-17 | 2009-12-08
SONKATCH | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1720002011/WH/19960619 — तालाब जीर्णोद्धार निर्माण कुमारिया बनवीर | Completed | 164000 | 133464 | 2017-05-21 | 2019-06-27
SONKATCH | 2007-2008 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002011/WH/कुप नि‍मान लाला धन्‍ना कुमारीयाबनवी — कुप नि‍मान लाला धन्‍ना कुमारीयाबनवीर | Completed | 0 | 29251 | 2008-01-03 | 2009-02-27