## Work List
Exported on: 2026-09-02 00:24:37
Filters applied:
Data source: MGNREGA + VBGRAMG
District: DEWAS
Block: All
Panchayat: BERAKHEDI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SONKATCH | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Food grain storage / Construction of Food grain Storage Building for Community | Constr of Food Grain storage | 1720002027/AV/22012034545760 — खाद्यान्न भण्डार चबूतरा निर्माण बेरखेडी | Completed | 802553.42 | 614192 | 2021-02-20 | 2024-07-31
SONKATCH | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Land Development / Levelling/shaping of Wasteland Land for Community | Land Development | 1720002027/DP/20242 — क्रीडांगना बेराखेडी | Completed | 236000 | 100896 | 2013-02-09 | 2015-03-11
SONKATCH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Raising of Nursery for Groups / Raising of Nursery for Groups | Nursery Development | 1720002027/DP/22012034544727 — मा की बगिया मा वी | Closed | 14675.4 | 0 | 2021-08-15
SONKATCH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Raising of Nursery for Community / Raising of Nursery for Community | Nursery Development | 1720002027/DP/22012034544728 — मा की बगिया ई जी इस नई आबादी | Closed | 14675.4 | 0 | 2021-08-15
SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1720002027/DP/22012034574081 — निर्मल नीर चोधरी मोहल्ला ( मोहन सिंह के बाडे के पास ) | Closed | 624557.07 | 0 | 2022-08-15
SONKATCH | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1720002027/DP/22012034600281 — वसुंधा वंदन अमृत वाटिका देव महाराज के पास ग्राम पंचायत बेराखेदी | Closed | 55847.4 | 0 | 2023-06-02
SONKATCH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Rural Drinking Water | DUGWELLS / Construction of Irrigation Open Well for Community | Construction of Well | 1720002027/DW/22012034355216 — neermal neer | Deleted | 0 | 0 | 2017-10-26
SONKATCH | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Drinking Water | Soak Pits / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1720002027/DW/9993659325 — सार्वजनिक कूप पंचायत भवन के पास | Completed | 435000 | 379666.1 | 2016-04-12 | 2020-12-21
SONKATCH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Rural Drinking Water | DUGWELLS / Construction of Irrigation Open Well for Community | Construction of Well | 1720002027/DW/9993659952 — निर्मल नीर पंचायत भवन के पास | Deleted | 0 | 0 | 2016-01-26
SONKATCH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Rural Drinking Water | DUGWELLS / Construction of Irrigation Open Well for Community | Construction of Well | 1720002027/DW/9993659957 — निर्मल नीर शमशानघाट के पास | Deleted | 0 | 0 | 2016-01-26
SONKATCH | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1720002027/FP/22012034625877 — नाला डायवर्सन - बलरामसिंह के खेत के पास | Completed | 29660.19 | 22388 | 2021-07-09 | 2023-04-12
SONKATCH | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002027/IF/22012034305623 — IAY lilabai narayan | Completed | 42155 | 7014 | 2016-12-03 | 2018-05-29
SONKATCH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1720002027/IF/22012034342127 — वर्क्षारोपण - देव महाराज के सामने बेराखेड़ी | Ongoing | 535000 | 44740 | 2017-05-24
SONKATCH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002027/IF/22012034385177 — khet talab with kup nirman | Closed | 0 | 0 | 2017-10-26
SONKATCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002027/IF/22012034412719 — kapildharakup recharjpit Ramnathsingh sodansingh | Completed | 210000 | 208750 | 2018-05-24 | 2020-05-23
SONKATCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002027/IF/22012034447248 — KAPILDHARA KUP SUNITA BAI | Completed | 210000 | 204028 | 2018-12-24 | 2020-06-05
SONKATCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002027/IF/22012034449089 — KAPILDHARA KUP RAJENDRA SINGH | Completed | 210000 | 208452 | 2019-01-03 | 2020-06-05
SONKATCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002027/IF/22012034450141 — kapildhara kup lal singh chouhan | Closed | 0 | 0 | 2018-10-02
SONKATCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002027/IF/22012034450146 — lalsingh kapildhara kup | Completed | 210000 | 206152 | 2019-01-10 | 2020-06-05
SONKATCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002027/IF/22012034450319 — rajendra singh | Completed | 210000 | 207020 | 2019-01-10 | 2020-11-12
SONKATCH | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002027/IF/22012034455070 — Kapildhara kup nirman | Deleted | 0 | 0 | 2019-04-20
SONKATCH | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002027/IF/22012034471009 — kapildhara radheshyam devijiprasad | Completed | 210000 | 206604 | 2019-06-03 | 2020-11-06
SONKATCH | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002027/IF/22012034471052 — kapildhara kup prahaladsingh s/o raaisingh | Completed | 210000 | 207480 | 2019-06-03 | 2020-11-06
SONKATCH | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002027/IF/22012034471179 — kapildhara kup jojansingh s/o sodansinggh | Deleted | 210000 | 0 | 2019-06-25
SONKATCH | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002027/IF/22012034471183 — kapildhara kup maheshchandra s/o mangilal sharma | Completed | 210000 | 207400 | 2019-06-03 | 2020-11-06
SONKATCH | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002027/IF/22012034544648 — Khet TALAB NIRMAN - ARJUNSINGH ANTARSINGH | Completed | 303308.59 | 273600 | 2020-04-26 | 2020-07-10
SONKATCH | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002027/IF/22012034576534 — Khet Talab Nirman sorambai endarsingh | Closed | 0 | 0 | 2020-04-26
SONKATCH | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002027/IF/22012034665966 — खेत तालाब निर्माण - अनारसिंह पिता निर्भयसिंह | Completed | 314018.23 | 232722 | 2021-03-05 | 2021-09-09
SONKATCH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002027/IF/22012034669016 — खेत तालाब निर्माण - सोरम बाई पति इन्दर सिंह | Completed | 314018.23 | 261078 | 2021-04-06 | 2022-03-23
SONKATCH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002027/IF/22012034812951 — Khet Talab nirman - jagganath punaji | Completed | 327784.58 | 158646 | 2021-07-09 | 2023-09-08
SONKATCH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1720002027/IF/22012034812955 — med bandhan - anarsingh nirbhayasingh | Closed | 0 | 0 | 2021-06-17
SONKATCH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1720002027/IF/22012034813031 — निजी खेत में फलौउद्यान- भारत सिंह तकत सिंह | Ongoing | 154000 | 32261 | 2021-07-09
SONKATCH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1720002027/IF/22012034813035 — फलौउद्यान - नारायण सिंह राजाराम | Completed | 154000 | 49290 | 2021-07-09 | 2026-04-02
SONKATCH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1720002027/IF/22012034813048 — मेड बंधान निर्माण - सोरम बाई इंदरसिंह | Closed | 0 | 0 | 2021-04-26
SONKATCH | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1720002027/IF/22012035000614 — नाडेप लोकेंद्र सिंह संग्राम सिंह | Closed | 0 | 0 | 2022-05-15
SONKATCH | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1720002027/IF/22012035000620 — नाडेप तेज सिंह मोहन सिंह | Closed | 0 | 0 | 2022-05-15
SONKATCH | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1720002027/IF/22012035000645 — मेजिक पिट निर्माण हितग्राही केलाश प्रथविराज योगेश संजू मोहन प्रेमसिंह | Closed | 0 | 0 | 2022-05-15
SONKATCH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002027/IF/22012035172646 — khet talab nirman - Devilal pita Bheru lal | Closed | 445662.11 | 0 | 2023-09-26
SONKATCH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1720002027/IF/22012035394651 — JGSA2025 Recharge pit kapildhara kup prahalad singh s/o raaisingh | Physically Completed | 25899.46 | 17879.73 | 2025-04-28 | 2026-03-26
SONKATCH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1720002027/IF/22012035395189 — JGSA2025Recharge structure lal singh chouhan | Closed | 25899.46 | 14094 | 2025-04-28
SONKATCH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1720002027/IF/22012035395260 — JGSA2025 recharge structure chhatar singh s/o dulesingh | Physically Completed | 25899.46 | 22557.99 | 2025-04-28 | 2026-03-31
SONKATCH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1720002027/IF/22012035395290 — JGSA2025 Recharge structure kapildhara kup Sunita Bai | Physically Completed | 25899.46 | 18402.15 | 2025-04-28 | 2026-04-27
SONKATCH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1720002027/IF/22012035395349 — JGSA2025 Recharge structure kapildhara kup radheshyam s/o devijiprasad | Physically Completed | 25899.46 | 25448.67 | 2025-04-28 | 2026-03-24
SONKATCH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1720002027/IF/22012035395411 — JGSA2025 Recharge structure kapildhara kup Rajendra singh | Ongoing | 25899.46 | 12528 | 2025-04-28
SONKATCH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1720002027/IF/22012035395462 — JGSA2025 Recharge structure kapil dhara kup Maan kunwar bai w/o roopsingh | Physically Completed | 25899.46 | 25188.57 | 2025-04-28 | 2026-03-24
SONKATCH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1720002027/IF/22012035395510 — JGSA2025 Recharge structure kapil dhara kup vikaram s/o tulsiram | Physically Completed | 25899.46 | 25449.51 | 2025-04-28 | 2026-03-14
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002027/IF/22012035544975 — JGSA 2025 Khet talab nirman Rajkuwar Bai Endar singh | Completed | 322361.97 | 252126 | 2025-05-27 | 2026-01-22
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1720002027/IF/22012035587852 — Ek Bagiya Maa Ke Naam Mohan kuwar MP20002027001 118-B | Ongoing | 271689.33 | 261 | 2025-08-27
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1720002027/IF/22012035587860 — Ek Bagiya Maa Ke Naam Rajkuwar bai MP20002027001 434 | Ongoing | 277431.33 | 33001 | 2025-08-27
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1720002027/IF/22012035593899 — Ek Bagiya Maa Ke Naam pavitra bai | Ongoing | 272600.27 | 55617 | 2025-09-02
SONKATCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002027/IF/IAY/1887655 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4162615 | Completed | 15660 | 15660 | 2018-09-27 | 2018-11-23
SONKATCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002027/IF/IAY/1888875 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4803576 | Completed | 15660 | 15660 | 2018-08-02 | 2018-11-23
SONKATCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002027/IF/IAY/1889714 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4848383 | Completed | 15660 | 15590 | 2018-10-13 | 2019-08-15
SONKATCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002027/IF/IAY/1889926 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5511510 | Completed | 15660 | 14964 | 2018-08-13 | 2019-07-24
SONKATCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002027/IF/IAY/1889938 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5538335 | Completed | 15660 | 15668 | 2018-09-27 | 2019-07-05
SONKATCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002027/IF/IAY/1890141 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5568443 | Completed | 15660 | 15360 | 2018-08-13 | 2019-05-29
SONKATCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002027/IF/IAY/1892285 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4142637 | Completed | 15660 | 15660 | 2018-08-13 | 2019-01-28
SONKATCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002027/IF/IAY/1892299 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4151139 | Completed | 15660 | 15486 | 2018-08-02 | 2019-01-25
SONKATCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002027/IF/IAY/1892300 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4151844 | Completed | 15660 | 15668 | 2018-08-29 | 2019-07-05
SONKATCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002027/IF/IAY/1892311 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4156204 | Completed | 15660 | 15312 | 2018-08-13 | 2019-01-28
SONKATCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002027/IF/IAY/1892326 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4162592 | Completed | 15660 | 15720 | 2018-08-13 | 2019-07-05
SONKATCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002027/IF/IAY/1893678 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4812850 | Completed | 15660 | 15138 | 2018-08-29 | 2019-01-25
SONKATCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002027/IF/IAY/1894028 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4996232 | Completed | 15660 | 15332 | 2018-08-02 | 2019-05-29
SONKATCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002027/IF/IAY/1896388 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4143999 | Completed | 15660 | 15404 | 2018-08-02 | 2019-08-15
SONKATCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002027/IF/IAY/1896412 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4164200 | Completed | 15660 | 15324 | 2018-08-02 | 2019-05-25
SONKATCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002027/IF/IAY/1897629 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5523514 | Completed | 15660 | 14616 | 2018-10-21 | 2019-01-25
SONKATCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002027/IF/IAY/1897634 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5533632 | Completed | 15660 | 15336 | 2018-08-02 | 2019-05-29
SONKATCH | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002027/IF/IAY/2243240 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5194392 | Completed | 15840 | 15488 | 2019-09-03 | 2020-05-04
SONKATCH | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002027/IF/IAY/274815 — Construction of IAY House -IAY REG. NO. MP3227406 | Completed | 15030 | 17200 | 2017-01-25 | 2018-05-29
SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002027/IF/IAY/3690907 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100669150 | Completed | 18360 | 17238 | 2022-07-23 | 2023-08-03
SONKATCH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002027/IF/IAY/39242 — Construction of IAY House -IAY REG. NO. MP-20-002-027-001/74 | Approved | 27000 | 0 | 2015-11-23
SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002027/IF/IAY/4037669 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100692451 | Completed | 18360 | 18360 | 2022-07-20 | 2022-12-26
SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002027/IF/IAY/4040665 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115348034 | Completed | 18360 | 18241 | 2022-07-23 | 2023-09-23
SONKATCH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002027/IF/IAY/4391990 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124464001 | Completed | 18360 | 18785 | 2023-06-06 | 2023-09-23
SONKATCH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002027/IF/IAY/4532215 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100690594 | Ongoing | 27000 | 18954 | 2024-10-08
SONKATCH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002027/IF/IAY/4532231 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100692487 | Physically Completed | 23490 | 20754 | 2025-03-09 | 2026-08-19
SONKATCH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002027/IF/IAY/4555830 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114769221 | Ongoing | 27000 | 18801 | 2024-10-08
SONKATCH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002027/IF/IAY/4583878 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119088891 | Physically Completed | 23490 | 21780 | 2024-10-08 | 2026-07-29
SONKATCH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002027/IF/IAY/4745661 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114077673 | Physically Completed | 23490 | 20412 | 2024-11-08 | 2026-08-19
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002027/IF/IAY/5150532 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124467258 | Ongoing | 27000 | 16965 | 2025-04-03
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002027/IF/IAY/5154087 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100502289 | Physically Completed | 23490 | 22968 | 2025-04-02 | 2026-06-15
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002027/IF/IAY/5156351 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113871139 | Physically Completed | 23490 | 23229 | 2025-04-02 | 2026-05-20
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002027/IF/IAY/5164681 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115351519 | Physically Completed | 23490 | 22968 | 2025-06-08 | 2026-06-15
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002027/IF/IAY/5191284 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100690567 | Physically Completed | 23490 | 22968 | 2025-04-03 | 2026-06-15
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002027/IF/IAY/5210502 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120237427 | Ongoing | 27000 | 13833 | 2025-04-03
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002027/IF/IAY/5841574 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100690778 | Physically Completed | 23490 | 20097 | 2025-10-17 | 2025-12-11
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002027/IF/IAY/5841648 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113896078 | Physically Completed | 23490 | 21402 | 2025-10-17 | 2026-08-19
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002027/IF/IAY/5841713 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120262747 | Approved | 27000 | 0 | 2025-04-11
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002027/IF/IAY/5841761 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113851820 | Physically Completed | 23490 | 18270 | 2025-10-25 | 2026-04-12
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002027/IF/IAY/5842118 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113888123 | Physically Completed | 23490 | 22968 | 2025-10-17 | 2026-06-15
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002027/IF/IAY/5842158 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113881040 | Physically Completed | 23490 | 21402 | 2025-10-24 | 2026-04-12
SONKATCH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002027/IF/IAY/68200 — Construction of IAY House -IAY REG. NO. MP-20-002-027-001/37 | Approved | 27000 | 0 | 2016-01-01
SONKATCH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002027/IF/IAY/68201 — Construction of IAY House -IAY REG. NO. MP-20-002-027-001/68 | Approved | 27000 | 0 | 2016-01-01
SONKATCH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002027/IF/IAY/718162 — Construction of IAY House -IAY REG. NO. MP1666053 | Completed | 15030 | 16512 | 2017-05-11 | 2018-05-25
SONKATCH | 2009-2010 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002027/IF/कूप निर्माण, अजयसिंह छतरसिंह — कपिलधारा कूप निर्माण, अजयसिंह छतरसिंह | Completed | 189000 | 161155 | 2009-05-01 | 2012-04-02
SONKATCH | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1720002027/IF/कूप निर्माण, छतरसिंह दुलेसिंह — कपिलधारा कूप निर्माण, छतरसिंह दुलेसिंह | Deleted | 0 | 0 | 2012-04-02
SONKATCH | 2009-2010 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002027/IF/कूप निर्माण, मोडसिंह गुला‍बसिंह — कपिलधारा कूप निर्माण, मोडसिंह गुला‍बसिंह | Completed | 153000 | 182929 | 2009-04-15 | 2012-04-02
SONKATCH | 2009-2010 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002027/IF/निर्माण, छतरसिंह दुलेसिंह — कपिलधारा कूप निर्माण, छतरसिंह दुलेसिंह | Completed | 209000 | 194775 | 2009-05-01 | 2015-03-11
SONKATCH | 2007-2008 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002027/IF/बैराखेड्ी, कपिल धारा, तुलसीराम गोपाल — ग्राम पंचायत बैराखेड्ी, कपिल धारा, तुलसीराम गोपाल | Completed | 160000 | 71149 | 2008-03-13 | 2009-07-02
SONKATCH | 2007-2008 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002027/IF/बैराखेड्ी, कपिल धारा, नरायण भवाना — ग्राम पंचातय बैराखेड्ी, कपिल धारा, नरायण भवाना | Completed | 160000 | 178426 | 2008-03-13 | 2014-03-21
SONKATCH | 2007-2008 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002027/IF/बैराखेड्ी, कपिल धारा, मुकेश हरिसिंह — ग्राम पंचायत बैराखेड्ी, कपिल धारा, मुकेश हरिसिंह | Completed | 160000 | 134800 | 2008-03-13 | 2009-05-26
SONKATCH | 2007-2008 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002027/IF/बैराखेड्ी, कपिल धारा, रूपसिंह तकतसिं — ग्राम पंचायत बैराखेड्ी, कपिल धारा, रूपसिंह तकतसिंह | Completed | 160000 | 96508 | 2008-03-26 | 2012-04-02
SONKATCH | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720002027/LD/3799394443 — मेढ बंधान, रामा अमराजी बीसाखेडी | Deleted | 0 | 0 | 2013-04-15
SONKATCH | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720002027/LD/3799403984 — क्रिडान्‍गन,मा,शाला,भवन बेराखेडी | Completed | 236000 | 16790 | 2013-09-13 | 2015-03-11
SONKATCH | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1720002027/OP/21/06/2007 — ग्राम पंचायत बैराखेड्ी लाईन डिपार्टमेंट, सुरक्षा कार्य | Completed | 300000 | 540373 | 2008-07-01 | 2018-05-30
SONKATCH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002027/RC/22012034186532 — पंच परमेश्‍वर,रामदेवजी मन्दिर से छापरी तक | Completed | 35000 | 27986.8 | 2013-09-27 | 2014-02-15
SONKATCH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002027/RC/22012034197851 — पंच परमेश्‍वर,तेजाराम के घर से छतरसिंह के घर | Completed | 196000 | 148872 | 2014-01-07 | 2015-03-12
SONKATCH | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002027/RC/22012034290614 — पंच परमेश्‍वर,अनोखीलाल के घर से कोदरसिंह के मकान तक | Completed | 83000 | 72981 | 2015-11-30 | 2017-02-02
SONKATCH | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002027/RC/22012034309024 — सी सी रोड पुनमचन्‍द के मकान से चौबारा रोड तक | Deleted | 0 | 0 | 2016-01-26
SONKATCH | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002027/RC/22012034309027 — सी सी रोड सरदारसिंह के मकान से शासकिय रासते तक | Deleted | 0 | 0 | 2016-01-26
SONKATCH | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1720002027/RC/22012034338420 — सी सी रोड गोपालसिंह के मकान से अम्बे माता के चोक तक | Completed | 25000 | 27864 | 2017-05-19 | 2019-09-13
SONKATCH | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002027/RC/22012034338429 — सी सी रोड (हटेसिह के मकान से मोड़सिह के मकान तक ) | Completed | 152248 | 65016 | 2017-05-19 | 2019-12-20
SONKATCH | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1720002027/RC/22012034380964 — sudur gram sampark babai | Closed | 0 | 0 | 2017-10-02
SONKATCH | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002027/RC/22012034530281 — सीसी रोड निर्माण-दयाराम के मकान से EGS स्कूल तक | Completed | 48000 | 49590 | 2020-07-28 | 2023-01-11
SONKATCH | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1720002027/RC/22012034539776 — सुदूर खेत सड़क निर्माण - जगदीश मेमोरियल स्कूल से गजराजसिंह के खेत तक | Completed | 1493438.69 | 1449428.31 | 2020-09-24 | 2024-08-21
SONKATCH | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002027/RC/22012034552038 — सी सी रोड निर्माण - हरी सिंह के मकान से डीपी के पास | Completed | 32000 | 28500 | 2021-02-05 | 2023-04-12
SONKATCH | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002027/RC/22012034566384 — सी सी रोड निर्माण - डीपी से नाले की और | Closed | 17500 | 0 | 2021-03-20
SONKATCH | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002027/RC/22012034577952 — सीसी रोड निर्माण ईश्वर सिंह के घर से मोहन चौधरी के घर तक | Closed | 0 | 0 | 2021-04-24
SONKATCH | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002027/RC/22012034577953 — सीसी रोड निर्माण ईश्वर सिंह के घर से मोहन चौधरी के घर तक | Closed | 50000 | 0 | 2022-06-17
SONKATCH | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002027/RC/22012034654694 — cc road nirman Rakesh sharma ke makan se kundi tak | Closed | 46000 | 0 | 2023-05-26
SONKATCH | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002027/RC/22012034654698 — पुलिया निर्माण शमशान के रास्ते पर | Closed | 44000 | 0 | 2023-04-26
SONKATCH | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002027/RC/333 — पंच प्रमेश्वर,सी.सी रोड रामदेवजी मन्दिर से कुम्हार मोहल्ला | Completed | 87000 | 89828 | 2012-04-02 | 2012-04-14
SONKATCH | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002027/RC/492 — पंच प्रमेश्वर, नाथुसिंहके मकानसे कष्‍णमदिर स्‍वरसि | Completed | 135000 | 123117.41 | 2013-01-02 | 2014-01-22
SONKATCH | 2007-2008 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1720002027/RC/गेवल सडक बेराखेडी अवगमन सुलभना पहुच — गेवल सडक बेराखेडी घाट वाले महाराज से नई अबाादी रोड् तक | Completed | 400000 | 553525 | 2007-11-30 | 2012-04-02
SONKATCH | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1720002027/RC/ग्रेवल सड्क, अर्जुनसिंह के खेत से पि — ग्राम पंचायत बैराखेड्ी ग्रेवल सड्क, अर्जुनसिंह के | Completed | 431000 | 348602.87 | 2008-11-02 | 2016-09-23
SONKATCH | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1720002027/RC/तालाब से अजुनसिंह के टद्ययूबवेल तक — ग्राम पंचायत बैराखेड्ी ग्रेवल सड्क, तालाब से अजुनसिंह के टद्ययूबवेल तक | Completed | 431000 | 312810 | 2008-11-09 | 2009-06-10
SONKATCH | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1720002027/RC/सड्क, संग्रामसिंह के मकान से ताल — ग्राम पंचायत बैराखेड्ी, ग्रेवल सड्क, संग्रामसिंह के मकान से तालाब तक | Completed | 431000 | 560467 | 2008-10-05 | 2009-05-27
SONKATCH | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720002027/RS/22012034284040 — शौचालय निर्माण दिलिपसिंह कोदरसिंह | Completed | 3180 | 318 | 2015-09-20 | 2016-08-24
SONKATCH | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720002027/RS/22012034284042 — शौचालय निर्माण दर्याव रामाजी | Completed | 3180 | 318 | 2015-09-20 | 2016-08-24
SONKATCH | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720002027/RS/22012034389681 — SBM sardar bhawana | Completed | 12000 | 860 | 2018-01-15 | 2023-11-08
SONKATCH | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720002027/RS/22012034389683 — SBM vikram sevaji | Completed | 12000 | 10896 | 2018-01-15 | 2021-01-13
SONKATCH | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720002027/RS/22012034394109 — sbm umrao chena ji | Completed | 12000 | 9176 | 2018-04-23 | 2021-01-13
SONKATCH | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720002027/RS/22012034394113 — sbm kelash chena ji | Deleted | 12000 | 4350 | 2018-04-23
SONKATCH | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720002027/RS/22012034396163 — sbm ambaram kanaji | Closed | 12000 | 0 | 2018-02-05
SONKATCH | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1720002027/RS/22012034598625 — SBM- सामुदायिक स्वच्छता परिसर ग्राम बेराखेड़ी | Deleted | 0 | 0 | 2021-10-23
SONKATCH | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1720002027/RS/22012034609791 — SBM- सामुदायिक स्वच्छता परिसर ग्राम बैराखेडी | Completed | 44000 | 33582 | 2022-02-04 | 2024-12-21
SONKATCH | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1720002027/RS/22012034613202 — नाली निर्माण - रणवीर सिंह के मकान से पंचायत के पीछे | Closed | 16300 | 0 | 2021-10-02
SONKATCH | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1720002027/RS/22012034613212 — नाली निर्माण - प्रेमसिंह के मकान से नाले की और | Completed | 19500 | 18528 | 2022-01-21 | 2023-08-19
SONKATCH | 2013-2014 | D--RURAL INFRASTUCTURE / Bharat Nirman Sewa Kendra | Upgradation/extension of panchayat Bhawan / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Repair & Maint of Community infrastructure | 1720002027/SK/2260 — Bharat Nirman Rajeev Gandhi Sewa Kendra,BERAKHEDI | Physically Completed | 1285000 | 715682.5 | 2014-02-21 | 2026-03-30
SONKATCH | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Staggered Trench / Construction of Staggered Trench for Community | Construction of Trench | 1720002027/WC/22012034329576 — नवीन तालाब निर्माण ग्राम बैराखेडी | Completed | 200000 | 52596 | 2017-06-22 | 2020-05-16
SONKATCH | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1720002027/WC/22012034382210 — check dam | Closed | 0 | 0 | 2017-10-26
SONKATCH | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Loose Boulder Structure / Construction of Stone boulder Gully Plugs for Community | Boulder Check/Gully Plug | 1720002027/WC/22012034382211 — loose boulder | Closed | 0 | 0 | 2017-10-26
SONKATCH | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1720002027/WC/22012034385271 — check dam( roji ghat) | Completed | 588000 | 563616 | 2018-03-09 | 2019-08-18
SONKATCH | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Coast Line Plntation-Coastal Shelter Belt-Comm / Along the coast Line Plantation of Coastal Shelter Belt Trees for Community | Plantation | 1720002027/WC/22012034474925 — Bori bandhan niraman | Deleted | 0 | 0 | 2019-05-25
SONKATCH | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1720002027/WC/22012034474976 — Sokhata Pit | Closed | 6125.07 | 0 | 2019-05-25
SONKATCH | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1720002027/WC/22012034474977 — Sokhata Pit | Closed | 0 | 0 | 2019-05-25
SONKATCH | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1720002027/WC/22012034474978 — Sokhata Pit | Closed | 0 | 0 | 2019-05-25
SONKATCH | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1720002027/WC/22012034475004 — Rain water harwesting systam | Deleted | 0 | 0 | 2019-05-25
SONKATCH | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1720002027/WC/22012034475005 — Rain water harwesting systam school bhawan | Deleted | 0 | 0 | 2019-05-26
SONKATCH | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1720002027/WC/22012034477324 — recharge pit (primary school) | Closed | 0 | 0 | 2019-04-24
SONKATCH | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1720002027/WC/22012034477325 — recharge pit (midile school) | Closed | 0 | 0 | 2019-04-24
SONKATCH | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand filter for borewell recharge for Community | Well Recharge | 1720002027/WC/22012034484321 — Sokhata gadda nirman Devilala ke ghar ke pass hendpump ke pass | Completed | 13427.22 | 6336 | 2019-08-30 | 2020-06-25
SONKATCH | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand filter for borewell recharge for Community | Well Recharge | 1720002027/WC/22012034484322 — Sokhata gadda nirman EGS school ke pass hendpump | Completed | 13427.22 | 12672 | 2019-08-30 | 2020-09-22
SONKATCH | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1720002027/WC/22012034485159 — recharge pit (middile school handpump) | Completed | 13427.22 | 12672 | 2019-09-12 | 2020-06-25
SONKATCH | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1720002027/WC/22012034502319 — Talai nirman Dabra dabari rakhaya ke pass berakhedi | Completed | 432525.56 | 358867.85 | 2019-12-05 | 2020-08-25
SONKATCH | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1720002027/WC/22012034527273 — Talab nirman Bawdi par | Completed | 435562.35 | 342592 | 2020-03-06 | 2021-03-25
SONKATCH | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1720002027/WC/22012034541931 — Talai nirman Balramsingh ke khet ke pass | Deleted | 386188.5 | 0 | 2020-01-26
SONKATCH | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1720002027/WC/22012034551386 — Talai nirman Balram ke khet ke pass | Completed | 374187.65 | 356798 | 2020-06-06 | 2022-03-23
SONKATCH | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1720002027/WC/22012034616269 — परकोलेशन टैंक- सोबल सिंग के खेत के पास | Completed | 492531.79 | 355944 | 2021-02-27 | 2022-12-01
SONKATCH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1720002027/WC/22012034767652 — रूफ वाटर हार्वेस्टिंग - प्राथमिक विद्यालय बेरखेडी | Closed | 24755.28 | 0 | 2021-04-12
SONKATCH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & maint of Mini Percolation Tank for Comm / Repair and maintenance of Mini Percolation Tank for Community | Repair & maint of Percolation Tank | 1720002027/WC/22012034868951 — percolation tank amar singh ke khet ke paas | Completed | 450794.83 | 170688 | 2022-02-04 | 2024-03-21
SONKATCH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1720002027/WC/22012034897280 — parcotaion Tank - Amarsingh ke khet ke pass | Closed | 0 | 0 | 2021-10-10
SONKATCH | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1720002027/WC/22012035000880 — parkolation Tank Et Bhatte ke pass | Physically Completed | 622665.98 | 325420.5 | 2022-10-02 | 2026-04-07
SONKATCH | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1720002027/WC/22012035011630 — पर्कोलेसन टैंक - रघुवीर सिंह के घर के पास | Physically Completed | 615507.23 | 464449 | 2022-11-18 | 2026-03-30
SONKATCH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1720002027/WC/22012035260079 — नवीन तालाब निर्माण कार्य ग्राम बेराखेडी | Ongoing | 2173000 | 117450 | 2025-04-23
SONKATCH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1720002027/WH/22012034454805 — Check dam repair | Completed | 523783.18 | 449172.18 | 2022-02-11 | 2023-07-06
SONKATCH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1720002027/WH/22012034454818 — तालाब जीर्णोद्धार बैराखेड़ी | Completed | 912048.93 | 789945.73 | 2022-02-04 | 2023-08-03