## Work List
Exported on: 2026-09-27 00:18:47
Filters applied:
Data source: VBGRAMG
District: DEWAS
Block: All
Panchayat: BABAI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002048/IF/22012035452863 — खेत तालाब निर्माण मेहरबान किसन बाबई | Physically Completed | 464129.11 | 0 | 2025-05-18 | 2026-07-10
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1720002048/IF/22012035597352 — Ek Bagiya Maa Ke Naam Krishna Bai MP-20-002-048-001/107 | New | 0 | 0 | 2025-08-01
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1720002048/IF/22012035608482 — EK BAGIYA MAA KE NAM Krishna Bai MP-20-002-048-001/107 | Ongoing | 272600.27 | 1800 | 2025-09-10
SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002048/IF/IAY/3703129 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106191692 | Approved | 27000 | 0 | 2022-04-29
SONKATCH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002048/IF/IAY/39251 — Construction of IAY House -IAY REG. NO. MP-20-002-048-001/13 | Ongoing | 27000 | 0 | 2016-03-31
SONKATCH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002048/IF/IAY/4547233 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106191881 | Physically Completed | 27000 | 0 | 2025-01-09 | 2026-09-21
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002048/IF/IAY/4856355 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150074071 | Ongoing | 27000 | 0 | 2025-04-03
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002048/IF/IAY/5147965 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106190281 | Physically Completed | 23490 | 5400 | 2025-07-09 | 2026-08-19
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002048/IF/IAY/5162437 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106198253 | Physically Completed | 23490 | 1800 | 2025-07-09 | 2026-08-19
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002048/IF/IAY/5162898 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106198155 | Physically Completed | 23490 | 4800 | 2025-07-09 | 2026-08-19
SONKATCH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002048/IF/IAY/5178328 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106190646 | Approved | 27000 | 0 | 2025-02-19
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002048/IF/IAY/5179714 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106196609 | Physically Completed | 23490 | 5400 | 2025-07-09 | 2026-08-19
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002048/IF/IAY/5183975 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115112900 | Physically Completed | 23490 | 0 | 2025-07-09 | 2026-08-23
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002048/IF/IAY/5189537 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106197933 | Physically Completed | 23490 | 5400 | 2025-07-09 | 2026-08-19
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002048/IF/IAY/5190189 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106191718 | Ongoing | 27000 | 0 | 2025-07-09
SONKATCH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002048/IF/IAY/5201098 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106198303 | Approved | 27000 | 0 | 2025-02-27
SONKATCH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002048/IF/IAY/5201428 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115113642 | Physically Completed | 23490 | 0 | 2025-02-19 | 2026-08-23
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002048/IF/IAY/5205753 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106197995 | Ongoing | 27000 | 0 | 2025-07-09
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002048/IF/IAY/5206818 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115113321 | Physically Completed | 23490 | 3600 | 2025-07-09 | 2026-08-19
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002048/IF/IAY/5206990 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106198040 | Ongoing | 27000 | 0 | 2025-07-09
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002048/IF/IAY/5221433 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106188777 | Ongoing | 27000 | 0 | 2025-07-09
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002048/IF/IAY/5265111 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106191741 | Physically Completed | 23490 | 0 | 2025-07-09 | 2026-08-19
SONKATCH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002048/IF/IAY/5273402 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115113513 | Approved | 27000 | 0 | 2025-03-04
SONKATCH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002048/IF/IAY/5306248 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150082625 | Approved | 27000 | 0 | 2025-03-04
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002048/IF/IAY/5463338 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106192071 | Ongoing | 27000 | 9300 | 2025-07-09
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002048/IF/IAY/5464308 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106198292 | Approved | 27000 | 0 | 2025-04-09
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002048/IF/IAY/5465309 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106196279 | Ongoing | 27000 | 0 | 2025-07-09
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002048/IF/IAY/5475902 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105036370 | Ongoing | 27000 | 3600 | 2025-07-09
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002048/IF/IAY/5479603 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150073936 | Ongoing | 27000 | 0 | 2025-07-09
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002048/IF/IAY/5570900 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106192178 | Ongoing | 27000 | 0 | 2025-07-09
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002048/IF/IAY/5571957 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106192020 | Ongoing | 27000 | 0 | 2025-07-09
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002048/IF/IAY/5571958 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106192101 | Ongoing | 27000 | 0 | 2025-07-09
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002048/IF/IAY/5661323 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106189104 | Ongoing | 27000 | 3600 | 2025-07-09
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002048/IF/IAY/5663443 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106198052 | Ongoing | 27000 | 0 | 2025-07-09
SONKATCH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002048/IF/IAY/5867677 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106191751 | Approved | 27000 | 0 | 2025-02-27
SONKATCH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002048/IF/IAY/5867678 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106192206 | Physically Completed | 27000 | 0 | 2025-02-27 | 2026-09-20
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002048/IF/IAY/5880328 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106198138 | Approved | 27000 | 0 | 2025-08-20
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002048/IF/IAY/5992020 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150073975 | Approved | 27000 | 0 | 2026-02-26
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002048/IF/IAY/5992459 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105464835 | Approved | 27000 | 0 | 2026-02-28
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002048/IF/IAY/5995855 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106192008 | Approved | 27000 | 0 | 2026-02-28
SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002048/IF/IAY/6139113 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106198021 | Approved | 27000 | 0 | 2026-02-28
SONKATCH | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1720002048/LD/22012034537175 — समीदायिक चारागाह ओढ़नी तालाब के पास | Ongoing | 1495256.26 | 0 | 2021-02-14
SONKATCH | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1720002048/RC/22012034560257 — सुदूर सड़क गोशाला एवम सामुदायिक चरागाह पहुच मार्ग | Ongoing | 811082.29 | 0 | 2021-03-02
SONKATCH | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1720002048/WH/22012034453609 — cheak dam reparing school ke paas | Ongoing | 271784.11 | 0 | 2022-04-27