## Work List
Exported on: 2026-09-04 16:28:02
Filters applied:
Data source: VBGRAMG
District: DEWAS
Block: All
Panchayat: KOTHDI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
KANNOD | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Shelter Belt Trees (Comm) / Boundary Line Plantation of Shelter Belt Trees for Community | Plantation | 1720004033/DP/22012034627472 — PLANTATION DILIP KE KHET SE DIPCHAND KE KHET TAK KOTHDI | Approved | 433563.17 | 0 | 2024-07-04
KANNOD | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Shelter Belt Trees (Comm) / Boundary Line Plantation of Shelter Belt Trees for Community | Plantation | 1720004033/DP/22012034627473 — PLANTATIONSUNIL KE KHET SE HABBU KE KHET TAK KOTHDI | Approved | 433563.17 | 0 | 2024-07-04
KANNOD | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720004033/IF/22012034319553 — कपिलधारा सुक्की बाई पति रामपप्रसाद | Ongoing | 200000 | 0 | 2017-02-09
KANNOD | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720004033/IF/22012034451597 — KAPILDHARA SOBHAGSHING JAGRAM KOTHADI | Ongoing | 200000 | 0 | 2019-04-04
KANNOD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720004033/IF/22012034470973 — KAPIL DHARA NIRMAN OMPRAKASH RANGLAL KOTHADI | Ongoing | 200000 | 0 | 2019-03-08
KANNOD | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Staggered Trench for individual / Construction of Staggered Trench for individual | Construction of Trench | 1720004033/IF/22012035173507 — CPT NIRMAN RAMADHAR BHAGIRATH BHILDI | Ongoing | 38778.49 | 0 | 2023-10-06
KANNOD | 2023-2024 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Infra for Lqud Biomanure for Indviduals / Construction of Infrastructure for Liquid Biomanure for Individuals | Bio-Fertilizer | 1720004033/IF/22012035211287 — kapil dhara nirman kedar badriprasad kothdi | Ongoing | 267031.31 | 0 | 2024-02-27
KANNOD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1720004033/IF/22012035419876 — DUGWELL RECHARGE PIT SUNDARLAL HARIRAM BHILDI KOTHDID | Approved | 25899.46 | 0 | 2025-04-01
KANNOD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1720004033/IF/22012035420005 — DUGWELL RECHARGE PIT PRAKASH AHAITAN KOTHDI | Approved | 25899.46 | 0 | 2025-04-01
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720004033/IF/22012035527858 — KAPIL DHARA MIRMAN SUDAMA HARNARAYAN BHIDI KOTHDI | Ongoing | 332649.15 | 0 | 2025-06-05
KANNOD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1720004033/IF/22012035571413 — dugweel richage pit rakesh kanahiyalal | Approved | 25899.46 | 0 | 2025-04-01
KANNOD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1720004033/IF/22012035571530 — dugweel richage pit dinesh kothadi | Approved | 25899.46 | 0 | 2025-04-01
KANNOD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004033/IF/IAY/4705462 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120591001 | Approved | 27000 | 0 | 2024-09-21
KANNOD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004033/IF/IAY/4739658 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105746541 | Approved | 27000 | 0 | 2024-10-04
KANNOD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004033/IF/IAY/4848485 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100790551 | Ongoing | 27000 | 0 | 2024-11-28
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004033/IF/IAY/5178804 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106479177 | Ongoing | 27000 | 0 | 2025-05-02
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004033/IF/IAY/5287333 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121380507 | Ongoing | 27000 | 3300 | 2025-10-14
KANNOD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004033/IF/IAY/5377718 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100790410 | Approved | 27000 | 0 | 2025-03-29
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004033/IF/IAY/5387304 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104908280 | Ongoing | 27000 | 0 | 2025-05-02
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004033/IF/IAY/5410386 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106204526 | Approved | 27000 | 0 | 2025-04-03
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004033/IF/IAY/5569738 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105760579 | Physically Completed | 23490 | 1566 | 2025-05-02 | 2026-08-09
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004033/IF/IAY/5683492 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106669578 | Physically Completed | 23490 | 0 | 2025-07-16 | 2026-08-16
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004033/IF/IAY/5753899 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121991135 | Ongoing | 27000 | 8400 | 2026-01-15
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004033/IF/IAY/5754073 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106098538 | Physically Completed | 23490 | 5200 | 2025-10-26 | 2026-08-09
KANNOD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004033/IF/IAY/5870799 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106257051 | Approved | 27000 | 0 | 2025-02-21
KANNOD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004033/IF/IAY/5870884 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125572074 | Approved | 27000 | 0 | 2025-03-25
KANNOD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004033/IF/IAY/6112086 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120552295 | Ongoing | 27000 | 0 | 2026-08-31
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004033/IF/IAY/6112132 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106203302 | Approved | 27000 | 0 | 2026-03-01
KANNOD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004033/IF/IAY/6112491 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100790896 | Ongoing | 27000 | 21000 | 2026-06-08
KANNOD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004033/IF/IAY/6112507 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121368813 | Ongoing | 27000 | 4200 | 2026-07-17
KANNOD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004033/IF/IAY/6112568 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106650429 | Physically Completed | 23490 | 800 | 2026-04-25 | 2026-07-26
KANNOD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004033/IF/IAY/6112806 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105757245 | Ongoing | 27000 | 0 | 2026-08-30
KANNOD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004033/IF/IAY/6112930 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106208458 | Ongoing | 27000 | 8400 | 2026-04-25
KANNOD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004033/IF/IAY/6114252 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106669606 | Physically Completed | 23490 | 4959 | 2026-05-24 | 2026-08-16
KANNOD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004033/IF/IAY/6114496 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121379980 | Ongoing | 27000 | 8400 | 2026-07-11