## Work List
Exported on: 2026-09-11 13:11:06
Filters applied:
Data source: VBGRAMG
District: DEWAS
Block: All
Panchayat: BAMNIKHURD
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
KANNOD | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Bharat Nirman Seva Kendra / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1720004047/AV/22012034463028 — पचायत भवन निमाण ग्राम बमनीखुर्द | Ongoing | 579200 | 41400 | 2019-03-10
KANNOD | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1720004047/AV/22012034662018 — PLAY GROUND NIRMAN | New | 0 | 0 | 2024-10-15
KANNOD | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1720004047/DP/22012034625569 — MIYAWAKI PLANTATION SAMUDAYIK BHAWAN PAS MAGRIYA BAMNIKHURD | Ongoing | 343764.98 | 0 | 2024-08-17
KANNOD | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Shelter Belt Trees (Comm) / Boundary Line Plantation of Shelter Belt Trees for Community | Plantation | 1720004047/DP/22012034627934 — PLANTATION NIMKHEDA SE SANTOSH KE KHET KI OR GADIYA BAMNIKHURD | Ongoing | 433563.17 | 900 | 2024-09-26
KANNOD | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Shelter Belt Trees (Comm) / Boundary Line Plantation of Shelter Belt Trees for Community | Plantation | 1720004047/DP/22012034627935 — PLANTATION GADIYA SE BHUJRAM KE KHET OR GADIYA BAMNIKHURD | Ongoing | 433563.17 | 0 | 2024-09-26
KANNOD | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Shelter Belt Trees (Comm) / Boundary Line Plantation of Shelter Belt Trees for Community | Plantation | 1720004047/DP/22012034627937 — PLANTATION HANUMAN MANDIR NAHAR KI OR GADIYA BAMNIKHURD | Ongoing | 433563.17 | 0 | 2024-09-28
KANNOD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720004047/IF/22012034473777 — कपिल धारा कुपनिमाण मेह्बुब पिता रसीद खा बामनीखुद् | Ongoing | 200000 | 0 | 2019-03-25
KANNOD | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720004047/IF/22012034618573 — कपिलधारा कुप निर्माण मुफीद्खा पिता बाबुखा ग्राम गादिया | Ongoing | 246126.86 | 0 | 2020-10-17
KANNOD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720004047/IF/22012035226406 — kapil dhara nirman kailash gabda bamnikhurd | Ongoing | 269031.31 | 0 | 2024-07-10
KANNOD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720004047/IF/22012035279763 — KHET TALAB NIRMAN AKRAM ISHAK BAMNIKHURD | Ongoing | 383892.97 | 0 | 2025-01-03
KANNOD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720004047/IF/22012035281879 — KAPIL DHARA NIRMAN MANOJ SURESH BAMNIKHURD | Ongoing | 298922.95 | 0 | 2024-12-28
KANNOD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1720004047/IF/22012035399572 — DUGWELL RECHARGE PIT Rahis pita Isabkha bamnikhurd | New | 0 | 0 | 2025-04-01
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1720004047/IF/22012035589435 — Ek Bagiya Maa Ke Naam Bharti Rajesh 456 | Ongoing | 283221.89 | 8700 | 2025-08-27
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1720004047/IF/22012035589439 — Ek Bagiya Maa Ke Naam Savitribai Ramprasad 57 | Ongoing | 266577.25 | 8700 | 2025-09-06
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1720004047/IF/22012035589443 — Ek Bagiya Maa Ke Naam Sapeena Bi Anwar 461 | Ongoing | 283221.89 | 8400 | 2025-08-27
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1720004047/IF/22012035592276 — EK BAGIYA MAA KE NAAM FARIDA HUSAIN 463 A BAMNIKHURD | Ongoing | 283221.89 | 5400 | 2025-09-01
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1720004047/IF/22012035592286 — EK BAGIYA MAA KE NAAM NAGINA BEE 464 BAMNIKHURD | Ongoing | 266577.25 | 6300 | 2025-09-06
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1720004047/IF/22012035602903 — Ek Bagiya Maa Ke Naam Sushma Bai Bilar Singh 104 B | Approved | 0 | 0 | 2025-08-01
KANNOD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004047/IF/IAY/4622817 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127155773 | Ongoing | 27000 | 300 | 2024-10-15
KANNOD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004047/IF/IAY/4768637 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124103096 | Ongoing | 27000 | 0 | 2024-12-17
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004047/IF/IAY/5112669 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124109772 | Ongoing | 27000 | 0 | 2025-08-11
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004047/IF/IAY/5131522 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124618292 | Ongoing | 27000 | 0 | 2025-05-05
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004047/IF/IAY/5133850 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147325170 | Ongoing | 27000 | 0 | 2025-04-30
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004047/IF/IAY/5337907 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127153291 | Ongoing | 27000 | 2100 | 2025-06-03
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004047/IF/IAY/5673052 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128494805 | Ongoing | 27000 | 0 | 2025-09-13
KANNOD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004047/IF/IAY/5870814 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124157532 | Approved | 27000 | 0 | 2025-02-25
KANNOD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004047/IF/IAY/6117154 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131420141 | Ongoing | 27000 | 2100 | 2026-05-15