## Work List
Exported on: 2026-09-05 05:46:31
Filters applied:
Data source: VBGRAMG
District: DEWAS
Block: All
Panchayat: NAMANPUR
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
KANNOD | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1720004074/DP/22012034601577 — VASHUDHA VANDAN -AMRIT VATIKA GP NAMANPUR | Physically Completed | 55847.4 | 0 | 2023-08-27 | 2026-08-04
KANNOD | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1720004074/DP/22012034626226 — PLANTATION SAHMSHAN PARISAR NAMANPUR | Approved | 475884.29 | 0 | 2024-07-04
KANNOD | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720004074/IF/22012035223040 — khet talab nirman ghasiram natthu namanpur | Ongoing | 385261.22 | 0 | 2024-03-16
KANNOD | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720004074/IF/22012035223046 — khet talab nirman babulal shivlal namanpur | Ongoing | 385261.22 | 0 | 2024-03-16
KANNOD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1720004074/IF/22012035457113 — dugwell recharge pit nirman bondar bhailal / premsingh | New | 0 | 0 | 2025-04-14
KANNOD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1720004074/IF/22012035463870 — dugwell recharge pit nirman bhailal / premsingh | New | 0 | 0 | 2025-04-14
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1720004074/IF/22012035593183 — Ek bagiya maa ke name Girja nandlal MP-20-004-074-003/390 | Ongoing | 266577.25 | 0 | 2025-09-07
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1720004074/IF/22012035593194 — Ek bagiya maa ke name Rukhmani bai iswar 208 | Ongoing | 266577.25 | 0 | 2025-09-03
KANNOD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004074/IF/IAY/3795221 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106192937 | Approved | 27000 | 0 | 2022-05-03
KANNOD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004074/IF/IAY/3799809 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102451340 | Ongoing | 27000 | 0 | 2022-06-03
KANNOD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004074/IF/IAY/4557210 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113811708 | Ongoing | 27000 | 0 | 2024-12-25
KANNOD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004074/IF/IAY/4735398 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100815544 | Ongoing | 27000 | 2100 | 2024-12-03
KANNOD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004074/IF/IAY/4737468 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105654042 | Approved | 27000 | 0 | 2024-10-02
KANNOD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004074/IF/IAY/4738696 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106192824 | Ongoing | 27000 | 0 | 2024-12-25
KANNOD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004074/IF/IAY/4738706 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106194591 | Completed | 23490 | 0 | 2024-12-25 | 2026-08-05
KANNOD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004074/IF/IAY/4739355 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105516540 | Ongoing | 27000 | 0 | 2024-12-03
KANNOD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004074/IF/IAY/4741589 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106645410 | Ongoing | 27000 | 8100 | 2024-12-03
KANNOD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004074/IF/IAY/4746183 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113810846 | Ongoing | 27000 | 0 | 2024-12-25
KANNOD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004074/IF/IAY/4862187 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102452796 | Ongoing | 27000 | 0 | 2024-12-10
KANNOD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004074/IF/IAY/4863587 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115039313 | Ongoing | 27000 | 0 | 2024-12-10
KANNOD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004074/IF/IAY/4882481 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106194550 | Ongoing | 27000 | 4200 | 2025-01-21
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004074/IF/IAY/5146499 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113811747 | Ongoing | 27000 | 0 | 2025-04-19
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004074/IF/IAY/5148394 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105487403 | Ongoing | 27000 | 0 | 2025-04-19
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004074/IF/IAY/5149736 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106192249 | Ongoing | 27000 | 6000 | 2025-04-19
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004074/IF/IAY/5155533 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105628841 | Ongoing | 27000 | 8400 | 2025-04-19
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004074/IF/IAY/5161966 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121822823 | Ongoing | 27000 | 0 | 2025-04-19
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004074/IF/IAY/5164720 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100789242 | Ongoing | 27000 | 0 | 2025-04-19
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004074/IF/IAY/5168080 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106192343 | Ongoing | 27000 | 0 | 2025-04-19
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004074/IF/IAY/5179232 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102450314 | Ongoing | 27000 | 0 | 2025-04-19
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004074/IF/IAY/5181792 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102450582 | Ongoing | 27000 | 0 | 2025-04-19
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004074/IF/IAY/5182387 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119783185 | Ongoing | 27000 | 2100 | 2025-04-19
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004074/IF/IAY/5182753 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105468945 | Ongoing | 27000 | 0 | 2025-04-19
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004074/IF/IAY/5186918 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114023061 | Ongoing | 27000 | 0 | 2025-04-19
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004074/IF/IAY/5198693 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121816367 | Ongoing | 27000 | 7800 | 2025-04-19
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004074/IF/IAY/5201280 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113810767 | Ongoing | 27000 | 0 | 2025-04-19
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004074/IF/IAY/5216415 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102452518 | Ongoing | 27000 | 8400 | 2025-07-08
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004074/IF/IAY/5217971 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113811199 | Ongoing | 27000 | 8400 | 2025-04-19
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004074/IF/IAY/5221526 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114819379 | Ongoing | 27000 | 0 | 2025-07-08
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004074/IF/IAY/5228566 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113762666 | Ongoing | 27000 | 0 | 2025-04-19
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004074/IF/IAY/5229032 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106174599 | Ongoing | 27000 | 4200 | 2025-06-29
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004074/IF/IAY/5232006 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105628963 | Ongoing | 27000 | 0 | 2025-04-19
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004074/IF/IAY/5235907 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105475069 | Ongoing | 27000 | 8400 | 2025-04-19
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004074/IF/IAY/5242923 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113811363 | Ongoing | 27000 | 4200 | 2025-04-19
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004074/IF/IAY/5384684 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100597971 | Ongoing | 27000 | 4200 | 2025-05-07
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004074/IF/IAY/5392597 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103436490 | Ongoing | 27000 | 0 | 2025-07-08
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004074/IF/IAY/5400767 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106195320 | Ongoing | 27000 | 4200 | 2025-06-29
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004074/IF/IAY/5495320 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100785876 | Ongoing | 27000 | 0 | 2025-05-23
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004074/IF/IAY/5495515 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102451212 | Ongoing | 27000 | 0 | 2025-07-08
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004074/IF/IAY/5496017 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120412624 | Ongoing | 27000 | 2100 | 2025-07-08
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004074/IF/IAY/5496933 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100596357 | Ongoing | 27000 | 8400 | 2025-05-23
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004074/IF/IAY/5496941 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102450747 | Ongoing | 27000 | 0 | 2025-06-29
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004074/IF/IAY/5568201 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100786012 | Ongoing | 27000 | 0 | 2025-05-23
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004074/IF/IAY/5569349 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100608935 | Ongoing | 27000 | 0 | 2025-05-23
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004074/IF/IAY/5569838 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113810876 | Ongoing | 27000 | 0 | 2025-05-23
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004074/IF/IAY/5622561 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114819895 | Ongoing | 27000 | 0 | 2025-07-08
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004074/IF/IAY/5639086 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102452913 | Ongoing | 27000 | 0 | 2025-07-08
KANNOD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004074/IF/IAY/5643580 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105487967 | Approved | 27000 | 0 | 2025-02-24
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004074/IF/IAY/5643597 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106645390 | Ongoing | 27000 | 4200 | 2025-07-08
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004074/IF/IAY/5683449 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100786147 | Ongoing | 27000 | 0 | 2025-07-23
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004074/IF/IAY/5690397 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102452373 | Approved | 27000 | 0 | 2025-04-29
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004074/IF/IAY/5775383 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105450681 | Ongoing | 27000 | 8400 | 2026-02-05
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004074/IF/IAY/5775397 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114022490 | Ongoing | 27000 | 4200 | 2025-12-17
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004074/IF/IAY/5775416 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115037130 | Completed | 23490 | 0 | 2026-02-26 | 2026-07-08
KANNOD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004074/IF/IAY/5775567 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100786561 | Ongoing | 27000 | 4200 | 2026-07-02
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004074/IF/IAY/5775645 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114819443 | Ongoing | 27000 | 0 | 2026-01-07
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004074/IF/IAY/5863063 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126625326 | Ongoing | 27000 | 0 | 2025-12-17
KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004074/IF/IAY/5936412 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100654027 | Approved | 27000 | 0 | 2026-02-17
KANNOD | 2022-2023 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1720004074/WC/22012034903692 — cpt nirman bondabai ke khet se rajesh ke khet tak namanpur | Ongoing | 755490.44 | 0 | 2022-05-27
KANNOD | 2022-2023 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1720004074/WC/22012034903697 — cpt nirman segrigation shed sed se puliya tak namanpur | Ongoing | 755490.44 | 0 | 2022-05-27