## Work List
Exported on: 2026-09-04 12:56:41
Filters applied:
Data source: VBGRAMG
District: DEWAS
Block: All
Panchayat: GHATIYAGAYASUR
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BAGLI | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1720005002/AV/22012034662470 — SHANTIDHAM SHED NIRMAN KARY GHATIYAGAYASUR GP GHATIYAGAYASUR | Physically Completed | 235393.34 | 0 | 2025-06-01 | 2026-08-25
BAGLI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720005002/IF/22012034471004 — Kapil Dhara Hiteshi Lokendrasingh Narayan Ghatiyagyasur | Ongoing | 200000 | 0 | 2019-03-08
BAGLI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720005002/IF/22012035275214 — HITESI KAPILDHARA NIRMAN KARY KAILASH FULSINGH GHATIYAGAYASUR GP GHATIYAGAYASUR | Physically Completed | 294981.17 | 0 | 2024-12-28 | 2026-07-27
BAGLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720005002/IF/22012035275221 — HITESI KAPILDHARA NIRMAN KARY BANESINGH GULABSINGH GHATIYAGAYASUR GP GHATIYAGAYASUR | Physically Completed | 294981.17 | 0 | 2025-04-24 | 2026-08-25
BAGLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Staggered Trench for individual / Construction of Staggered Trench for individual | Construction of Trench | 1720005002/IF/22012035357254 — RFR FARM FOND KHET TALAB NIRMAN Gajraj Singh Ambaram Garam Muradpur Garam panchayt Ghatiya gayasur | New | 0 | 0 | 2025-04-14
BAGLI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-borewellrecharge for Indiv / Construction of Sand filter for Borewell recharge for Individual | Well Recharge | 1720005002/IF/22012035370117 — JGSA 2025 Recharge Stucturre Kapildhra Kup Akhilesh Kalu Singh Gp Ghatiyagyasur | Ongoing | 25899.46 | 0 | 2025-04-28
BAGLI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1720005002/IF/22012035573282 — JGSA 2025Recharge Stucturre Kapildhra Kup Kailash Deva Ji GP Ghatiyagayasur | Approved | 0 | 0 | 2025-04-14
BAGLI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1720005002/IF/22012035573287 — JGSA 2025Recharge Stucturre Kapildhra Kup Ramesh Kanheyalal Gp Ghatiyagyasur | Approved | 0 | 0 | 2025-04-14
BAGLI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1720005002/IF/22012035573293 — JGSA 2025Recharge Stucturre Kapildhra Kup Bhart Singh Antarsingh Gp Ghatiyagayasur | Approved | 0 | 0 | 2025-04-14
BAGLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720005002/IF/IAY/5204344 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102340637 | Physically Completed | 23490 | 0 | 2026-04-24 | 2026-07-29
BAGLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720005002/IF/IAY/5227990 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106319487 | Physically Completed | 23490 | 0 | 2025-11-17 | 2026-07-29
BAGLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720005002/IF/IAY/5867698 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106630627 | Physically Completed | 23490 | 0 | 2026-04-24 | 2026-07-29
BAGLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720005002/IF/IAY/6228677 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106319347 | Ongoing | 27000 | 0 | 2026-06-07
BAGLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1720005002/IF/VB/22012035663232 — PASHU SHED NIRMAN REKHA BAI BHARAT GAHTIYAGAYASUR NRLM | Ongoing | 134193.36 | 0 | 2026-08-12
BAGLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1720005002/IF/VB/22012035664286 — PASU SHED NIRMAN KARY AKILABAI RAMCHARAN GHATIYAGAYASUR GP GHATIYAGAYASUR | Approved | 0 | 0 | 2026-08-06
BAGLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1720005002/IF/VB/22012035664287 — PASU SHED NIRMAN KARY KAVITA MANOHARSINGH GHATIYAGAYASUR GP GHATIYAGAYASUR | Approved | 0 | 0 | 2026-08-06
BAGLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1720005002/IF/VB/22012035664288 — PASU SHED NIRMAN KARY ANITABAI KARSANPAL MURADPUR GP GHATIYAGAYASUR | Approved | 0 | 0 | 2026-08-06
BAGLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1720005002/IF/VB/22012035664289 — PASU SHED NIRMAN KARY ALAKA AKHILESH MURADPUR GP GHATIYAGAYASUR | Approved | 0 | 0 | 2026-08-06
BAGLI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1720005002/WC/22012035231995 — TALAB NIRMAN KARY GUTHAN PAR TEJSINGH KE KHET KE PASS GHATIYAGAYASUR GP GHATIYAGAYASUR | Approved | 0 | 0 | 2024-04-01