## Work List
Exported on: 2026-10-24 13:50:24
Filters applied:
Data source: VBGRAMG
District: DEWAS
Block: All
Panchayat: TAPPASUKALYA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BAGLI | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Centre Building for Community | Constr of Aganwadi | 1720005015/AV/22012034661037 — ANGANWADI BHAVAN NIRMAN KARY NO 02 TAPPASUKALYA GP TAPPASUKALYA | Physically Completed | 180000 | 6300 | 2024-11-07 | 2026-08-01
BAGLI | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1720005015/AV/22012034666107 — शमशान शेड निर्माण कार्य बड़ीगड़ी बाग़ में ग्रा.पं.टप्पासुकल्या | New | 0 | 0 | 2025-05-22
BAGLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1720005015/IF/22012035322811 — HITESI KAPILDHARA KOOP NIRMAN KARY SAPNA VISVASHSINGH MAHUDIYA GP TAPPSUKALYA | Ongoing | 322434.5 | 7500 | 2025-05-13
BAGLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1720005015/IF/22012035322812 — HITESI KAPILDHARA KOOP NIRMAN KARY SURAJSINGH BHAGIRATH MAHUDIYA GP TAPPSUKALYA | Ongoing | 322434.5 | 0 | 2025-04-25
BAGLI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1720005015/IF/22012035334313 — JGSA DUGWELL RECHARGE PARMANAND ONKAR GRAM BHRAHMPURI GP TAPPASUKALYA | New | 0 | 0 | 2025-04-12
BAGLI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1720005015/IF/22012035334321 — JGSA DUGWELL RECHARGE INDAR SHANKARLAL GRAM BHRAHMPURI GP TAPPASUKALYA | New | 0 | 0 | 2025-04-12
BAGLI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1720005015/IF/22012035334327 — JGSA DUGWELL RECHARGE BHURIBAI MANSINGH GRAM BHRAHMPURI GP TAPPASUKALYA | New | 0 | 0 | 2025-04-12
BAGLI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1720005015/IF/22012035334332 — JGSA DUGWELL RECHARGE SITARAM BAPU JI GRAM BHRAHMPURI GP TAPPASUKALYA | New | 0 | 0 | 2025-04-12
BAGLI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1720005015/IF/22012035334335 — JGSA DUGWELL RECHARGE RAYSINGH SAJAN GRAM BHRAHMPURI GP TAPPASUKALYA | New | 0 | 0 | 2025-04-12
BAGLI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1720005015/IF/22012035425907 — JGSA DUGWELL RECHARGE SUNDARBAI TAKATSINGH GRAM TAPPASUKALYA GP TAPPASUKALYA | Ongoing | 25899.46 | 0 | 2025-05-04
BAGLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1720005015/IF/22012035447365 — JGSA KHET TALAB NIRMAN MUKESH DARIYAV GRAM TAPPASUKALYA GP TAPPASUKALYA | Ongoing | 199969.9 | 0 | 2025-05-04
BAGLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1720005015/IF/22012035483805 — JGSA KHET TALAB NIRMAN RADHESHYAM PATIDAR MOHANLAL TAPPASUKALYA GP TAPPASUKALYA | Ongoing | 450885.64 | 0 | 2025-05-21
BAGLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1720005015/IF/22012035593782 — Eb Bagiya Maa Ke Naam Urmilabai Kumersingh Gram Brahmpuri Gp Tappasuklya | Ongoing | 263510.03 | 57900 | 2025-09-07
BAGLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1720005015/IF/22012035618381 — Ek bagiya ma ke naam sonambai sunil gram bhrahmpuri Gp Tappasukalya | Ongoing | 263510.03 | 55800 | 2025-09-18
BAGLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1720005015/IF/22012035618403 — Ek bagiya ma ke naam baskanya bai dulichand gram bhrahmpuri Gp Tappasukalya | Ongoing | 263510.03 | 45000.06 | 2025-09-18
BAGLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1720005015/IF/22012035618419 — Ek bagiya ma ke naam Jasrathbai Parmanand gram bhrahmpuri Gp Tappasukalya | Ongoing | 263510.03 | 66600 | 2025-09-18
BAGLI | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1720005015/IF/IAY/128803 — Construction of IAY House -IAY REG. NO. MP-20-005-015-008/04 | Approved | 27000 | 0 | 2016-02-04
BAGLI | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1720005015/IF/IAY/128804 — Construction of IAY House -IAY REG. NO. MP-20-005-015-008/11 | Approved | 27000 | 0 | 2016-02-04
BAGLI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1720005015/IF/IAY/1583795 — Construction of IAY House -IAY REG. NO. MP2341649 | Approved | 27000 | 0 | 2018-03-29
BAGLI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720005015/IF/IAY/4535076 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102342846 | Physically Completed | 23490 | 0 | 2024-09-27 | 2026-07-29
BAGLI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720005015/IF/IAY/4542550 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105899493 | Physically Completed | 23490 | 0 | 2024-11-29 | 2026-07-29
BAGLI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720005015/IF/IAY/4545111 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105721577 | Physically Completed | 23490 | 0 | 2025-01-07 | 2026-07-29
BAGLI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720005015/IF/IAY/4545114 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105722785 | Physically Completed | 23490 | 0 | 2025-02-14 | 2026-07-29
BAGLI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720005015/IF/IAY/4545136 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105725358 | Physically Completed | 23490 | 0 | 2024-09-27 | 2026-07-29
BAGLI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720005015/IF/IAY/4546535 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106958454 | Physically Completed | 21870 | 0 | 2024-09-27 | 2026-07-29
BAGLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720005015/IF/IAY/5135120 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102343041 | Physically Completed | 23490 | 0 | 2025-05-23 | 2026-07-29
BAGLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720005015/IF/IAY/5135122 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102343379 | Physically Completed | 23490 | 0 | 2025-05-23 | 2026-07-29
BAGLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720005015/IF/IAY/5135124 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102347592 | Physically Completed | 23490 | 0 | 2025-04-03 | 2026-07-29
BAGLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720005015/IF/IAY/5135125 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102347658 | Physically Completed | 23490 | 0 | 2025-04-03 | 2026-07-23
BAGLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720005015/IF/IAY/5135314 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125321951 | Physically Completed | 23490 | 0 | 2025-05-23 | 2026-07-29
BAGLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720005015/IF/IAY/5135436 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105805508 | Physically Completed | 23490 | 0 | 2025-05-23 | 2026-07-29
BAGLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720005015/IF/IAY/5135636 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125336779 | Physically Completed | 23490 | 0 | 2025-07-24 | 2026-07-23
BAGLI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720005015/IF/IAY/5135739 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103961865 | Approved | 27000 | 0 | 2025-02-19
BAGLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720005015/IF/IAY/5135741 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104040596 | Physically Completed | 23490 | 0 | 2025-05-23 | 2026-07-29
BAGLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720005015/IF/IAY/5135742 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104046697 | Physically Completed | 23490 | 0 | 2025-05-23 | 2026-07-29
BAGLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720005015/IF/IAY/5136650 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105900420 | Physically Completed | 23490 | 0 | 2025-05-23 | 2026-07-29
BAGLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720005015/IF/IAY/5136816 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105571779 | Physically Completed | 23490 | 0 | 2025-05-23 | 2026-07-23
BAGLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720005015/IF/IAY/5137735 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104942354 | Physically Completed | 23490 | 0 | 2025-05-23 | 2026-07-29
BAGLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720005015/IF/IAY/5137848 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104032282 | Physically Completed | 23490 | 0 | 2025-04-03 | 2026-07-29
BAGLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720005015/IF/IAY/5138398 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104936907 | Physically Completed | 23490 | 0 | 2025-05-23 | 2026-07-29
BAGLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720005015/IF/IAY/5138643 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125325569 | Physically Completed | 23490 | 0 | 2025-04-03 | 2026-07-29
BAGLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720005015/IF/IAY/5138846 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103961271 | Physically Completed | 23490 | 0 | 2025-04-03 | 2026-07-23
BAGLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720005015/IF/IAY/5139111 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105569276 | Physically Completed | 23490 | 0 | 2025-05-23 | 2026-07-12
BAGLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720005015/IF/IAY/5139893 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106958971 | Ongoing | 27000 | 14400 | 2025-05-23
BAGLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720005015/IF/IAY/5139894 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106959355 | Physically Completed | 23490 | 0 | 2025-05-23 | 2026-07-29
BAGLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720005015/IF/IAY/5140939 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104933147 | Physically Completed | 23490 | 0 | 2025-07-24 | 2026-07-29
BAGLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720005015/IF/IAY/5140940 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104933382 | Physically Completed | 23490 | 0 | 2025-06-21 | 2026-07-29
BAGLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720005015/IF/IAY/5141480 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126203315 | Physically Completed | 23490 | 0 | 2025-05-23 | 2026-07-29
BAGLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720005015/IF/IAY/5141632 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105715913 | Physically Completed | 23490 | 0 | 2025-04-03 | 2026-07-23
BAGLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720005015/IF/IAY/5141900 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105729108 | Physically Completed | 23490 | 0 | 2025-04-03 | 2026-07-29
BAGLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720005015/IF/IAY/5142034 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125324983 | Physically Completed | 23490 | 0 | 2025-05-23 | 2026-07-29
BAGLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720005015/IF/IAY/5142112 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105793645 | Physically Completed | 23490 | 0 | 2025-05-23 | 2026-07-29
BAGLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720005015/IF/IAY/5142147 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105720650 | Physically Completed | 23490 | 0 | 2025-05-23 | 2026-07-23
BAGLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720005015/IF/IAY/5142148 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105726336 | Physically Completed | 23490 | 0 | 2025-05-23 | 2026-07-29
BAGLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720005015/IF/IAY/5143992 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102113450 | Physically Completed | 23490 | 0 | 2025-05-23 | 2026-07-29
BAGLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720005015/IF/IAY/5163103 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102343002 | Physically Completed | 23490 | 0 | 2025-05-23 | 2026-07-29
BAGLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720005015/IF/IAY/5213002 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102107874 | Physically Completed | 23490 | 0 | 2025-05-23 | 2026-07-29
BAGLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720005015/IF/IAY/5537957 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105569120 | Physically Completed | 23490 | 0 | 2025-07-28 | 2026-07-26
BAGLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720005015/IF/IAY/5671750 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102337489 | Physically Completed | 23490 | 0 | 2025-07-28 | 2026-07-29
BAGLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720005015/IF/IAY/5671757 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105800716 | Physically Completed | 23490 | 0 | 2025-07-28 | 2026-07-29
BAGLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720005015/IF/IAY/5700446 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105566319 | Physically Completed | 23490 | 0 | 2025-07-28 | 2026-07-29
BAGLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720005015/IF/IAY/5813424 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104942556 | Physically Completed | 23490 | 0 | 2025-09-30 | 2026-07-29
BAGLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720005015/IF/IAY/6117488 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105900030 | Approved | 27000 | 0 | 2026-02-17
BAGLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720005015/IF/IAY/6228656 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125337969 | Approved | 27000 | 0 | 2026-02-17
BAGLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720005015/IF/IAY/6383242 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105795101 | Approved | 27000 | 0 | 2026-08-14
BAGLI | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1720005015/IF/IAY/94394 — Construction of IAY House -IAY REG. NO. MP-20-005-015-008/16 | Approved | 27000 | 0 | 2015-11-07
BAGLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1720005015/IF/VB/22012035663460 — PASU SHED NIRMAN KARY KUSUMBAI RAMESH TAPPASUKALYA GP TAPPASUKALYASU | Approved | 134613.74 | 0 | 2026-07-01
BAGLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1720005015/IF/VB/22012035663462 — PASU SHED NIRMAN KARY PAYALBAI RAJENDRA HARJIPURA GP TAPPASUKALYA | Approved | 134613.74 | 0 | 2026-07-01
BAGLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1720005015/IF/VB/22012035663464 — PASU SHED NIRMAN KARY KAMALABAI LAXMANSINGH HARJIPURA GP TAPPASUKALYA | Approved | 134613.74 | 0 | 2026-07-01
BAGLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1720005015/IF/VB/22012035663747 — HITESI KAPIL DHARA KUP NIRMAN KARY MANGILAL MOTI HARJIPURA GP TAPPASUKLYA | Deleted | 0 | 0 | 2026-08-02
BAGLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1720005015/IF/VB/22012035664259 — PASU SHED NIRMAN KARY LALITABAI VIKARMSINGH MAHUDIYA GP TAPPASUKLYA | Deleted | 0 | 0 | 2026-08-06
BAGLI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Gabion Anicut for Individuals / Construction of Gabion Check Dam for Individual | Constr of Gabion | 1720005015/IF/VB/22012035664262 — GABION CHECK DAM ANITABAI KE KHET KE PASS HARJIPURA GP TAPPASUKLYA | Deleted | 0 | 0 | 2026-08-06
BAGLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1720005015/IF/VB/YD/22012035665147 — Construction of Irrigation Open Well Mangilal Moti Gram Harjipura Gp Tappasukalya | Approved | 0 | 0 | 2026-09-15
BAGLI | 2026-2027 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1720005015/RC/VB/YD/22012034854667 — Construction of Cement Concrete Road Bhagchand Ke Ghar Se Banesingh Ke Ghar Ki Or Gram Harjipura | Approved | 0 | 0 | 2026-09-15
BAGLI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1720005015/WC/22012035310358 — सीसीटी निर्माण कार्य ब्रह्मपुरी भेरूपुरा रोड पर ग्राम पंचायत टप्पासुकल्या | Ongoing | 220920.75 | 0 | 2025-07-01
BAGLI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1720005015/WC/VB/22012035330800 — GABION CHECK DAM NIRMAN KARY MAHU NADI KE NALE PAR TAPPSUKLYA GP TAPPSUKLYA | Ongoing | 104934.74 | 1800 | 2026-08-09
BAGLI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1720005015/WC/VB/22012035330996 — GABION CHECK DAM NIRMAN KARY BAHADURSINGH KE KHET KE PASS HARJIPURA GP TAPPSUKLYA | Ongoing | 113738.98 | 20100 | 2026-08-09
BAGLI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1720005015/WC/VB/22012035331238 — GABION CHECK DAM NIRMAN KARY MAHU NADI KE NALE PAR TAPPSUKLYA GP TAPPSUKLYA | Deleted | 0 | 0 | 2026-08-03
BAGLI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1720005015/WC/VB/22012035332526 — GABION CHECK DAM ANITABAI KE KHET KE PASS HARJIPURA GP TAPPASUKLYA | Approved | 118086.89 | 0 | 2026-08-06
BAGLI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1720005015/WC/VB/22012035332527 — GABION CHECK DAM BRAJLAL KE KHET KE PASS TAPPASUKLYA GP TAPPASUKLYA | Approved | 102065.15 | 0 | 2026-08-06
BAGLI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1720005015/WC/VB/22012035333414 — GABION CHECK DAM MEHARBAN NAGAR NALE PAR TAPPASUKLYA GP TAPPASUKLYA | Approved | 159481.47 | 0 | 2026-08-10
BAGLI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry Check Dam for Community | Construction of Check Dam/Stop Dam | 1720005015/WC/VB/YD/22012035335234 — Constr of Masonry/CC Anicut for Yogendra Singh ke khet ke pass Gp Tappasuklya | Approved | 0 | 0 | 2026-08-10
BAGLI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1720005015/WC/VB/YD/22012035335235 — Constr of Boulder Anicut Check Dam Mahu Nadi ke par Gp Tappasuklya | Deleted | 0 | 0 | 2026-08-10
BAGLI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1720005015/WC/VB/YD/22012035336942 — Construction of Mini Percolation Tank For Pintu Ke Khet Pass Gp Tappasukalya | Approved | 0 | 0 | 2026-10-14