## Work List
Exported on: 2026-09-13 11:50:17
Filters applied:
Data source: VBGRAMG
District: DEWAS
Block: All
Panchayat: AGURLI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BAGLI | 2021-2022 | C--COMMON INFRASTRUCTURE FOR NRLM COMPLIANT SELF HELP GROUPS / Anganwadi/Other Rural Infrastructure | Constr of agri produce storage building for groups / Construction of Agricultural produce storage Building for Groups | Constr of Food Grain storage | 1720005047/AV/22012034569648 — slwm segrigation shed agurli | Ongoing | 1216344.19 | 0 | 2021-11-15
BAGLI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720005047/IF/22012035284176 — कपिल धारा निर्माण लक्ष्मण सिंह मांगीलाल ग्राम पंचायत आगुरली | New | 0 | 0 | 2024-10-02
BAGLI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720005047/IF/22012035284340 — कपिल धारा निर्माण लक्ष्मण सिंह मांगीलाल अगरली | New | 0 | 0 | 2024-10-02
BAGLI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720005047/IF/22012035286556 — कपिल धारा निर्माण रतनसिंह राघौराम अगूरली | Ongoing | 312155.12 | 0 | 2025-01-10
BAGLI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720005047/IF/22012035294675 — कपिल धारा निर्माण संतोषकुमार अंबाराम आगुरली | New | 0 | 0 | 2024-10-02
BAGLI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1720005047/IF/22012035418394 — JGSA Richarge Pit nirman Santosh Das Ke char ke pass GP Agurli | Ongoing | 25899.46 | 0 | 2025-05-18
BAGLI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1720005047/IF/22012035423794 — JGSA Recharge Pit nirman Ravi Suresh Ke Ghar par GP Agurli | Ongoing | 25899.46 | 0 | 2025-05-01
BAGLI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1720005047/IF/22012035446794 — JGSA Richarge Pit nirman Miththubai Kamal ke kuwa ke pass GP Agurli | Ongoing | 25899.46 | 0 | 2025-05-21
BAGLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720005047/IF/22012035545557 — JGSA FORMPOND BALBAN SINGH KAMAL SINGH AGURLI | Approved | 0 | 0 | 2025-04-14
BAGLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720005047/IF/IAY/1946923 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4928104 | Ongoing | 27000 | 0 | 2025-09-11
BAGLI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720005047/IF/IAY/4984928 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105148334 | Ongoing | 27000 | 0 | 2025-03-22
BAGLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720005047/IF/IAY/6067096 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP101002613 | Completed | 23490 | 0 | 2026-05-28 | 2026-08-20
BAGLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720005047/IF/IAY/6067352 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102390759 | Approved | 27000 | 0 | 2026-02-24
BAGLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720005047/IF/IAY/6067906 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105148663 | Approved | 27000 | 0 | 2026-02-24
BAGLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720005047/IF/IAY/6067907 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105149335 | Approved | 27000 | 0 | 2026-02-24
BAGLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720005047/IF/IAY/6067921 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105151344 | Approved | 27000 | 0 | 2026-03-04
BAGLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720005047/IF/IAY/6068061 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105355072 | Approved | 27000 | 0 | 2026-02-24
BAGLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720005047/IF/IAY/6068452 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105917672 | Ongoing | 27000 | 0 | 2026-09-12
BAGLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720005047/IF/IAY/6068570 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106016564 | Ongoing | 27000 | 12600 | 2026-07-18
BAGLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720005047/IF/IAY/6069046 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106440890 | Ongoing | 27000 | 0 | 2026-06-09
BAGLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720005047/IF/IAY/6102165 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120835582 | Approved | 27000 | 0 | 2026-02-24
BAGLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720005047/IF/IAY/6103284 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104943971 | Physically Completed | 23490 | 3600 | 2026-05-28 | 2026-08-09
BAGLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720005047/IF/IAY/6103513 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105147703 | Approved | 27000 | 0 | 2026-02-25
BAGLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720005047/IF/IAY/6104363 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105148796 | Approved | 27000 | 0 | 2026-02-24
BAGLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720005047/IF/IAY/6106862 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106344186 | Completed | 23490 | 0 | 2026-05-08 | 2026-09-04
BAGLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720005047/IF/IAY/6108328 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105508384 | Ongoing | 27000 | 12600 | 2026-05-28
BAGLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720005047/IF/IAY/6109786 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102390806 | Ongoing | 27000 | 5400 | 2026-05-28
BAGLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720005047/IF/IAY/6110784 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105049041 | Ongoing | 27000 | 8400 | 2026-08-01
BAGLI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1720005047/WC/22012035240692 — NISTARI TALAB NIRMAN KARY RAKESH CHODHRI FARMS VILLAGE AGURLI GP AGURLI | Approved | 0 | 0 | 2024-04-01