## Work List
Exported on: 2026-09-09 03:18:45
Filters applied:
Data source: VBGRAMG
District: DEWAS
Block: All
Panchayat: MACHWAS
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
KHATEGAON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1720006003/DP/22012034604316 — वसुधा वंदन अमृत वाटिका माध्यमिकविधालय 75 पोधे ग्राम मचवास | Ongoing | 55847.4 | 0 | 2023-09-09
KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720006003/IF/22012034969926 — कपिलधारा कूप निर्माण नत्थू पिता गंगाप्रसाद ग्रामं मचवास | Ongoing | 257014.43 | 0 | 2024-06-12
KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720006003/IF/22012035279826 — कपिलधारा कूप निर्माण रूखान (रुसान) पिता ज्ञान सिंह ग्राम खातामऊ | Approved | 0 | 0 | 2024-08-18
KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720006003/IF/22012035282773 — कपिलधारा कूप निर्माण चिन्ताबाई पति संतोष ग्राम मचवास | Ongoing | 267533.14 | 0 | 2025-06-03
KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720006003/IF/22012035536906 — कपिलधारा कूप निर्माण गुलबिबाई बेवानसिंह ग्राम मचवास | Ongoing | 267533.14 | 0 | 2025-06-03
KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1720006003/IF/22012035598937 — Ek Bagiya Maa ke Naam Laxmi Bai Katare MP-20-006-003-002/68 47/3 35/3 | Ongoing | 263510.03 | 0 | 2025-09-01
KHATEGAON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006003/IF/IAY/2144102 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5113242 | Ongoing | 27000 | 0 | 2019-07-10
KHATEGAON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006003/IF/IAY/3973408 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114136248 | Ongoing | 27000 | 0 | 2022-08-17
KHATEGAON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006003/IF/IAY/4036697 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105890951 | Approved | 27000 | 0 | 2022-05-10
KHATEGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006003/IF/IAY/40444 — Construction of IAY House -IAY REG. NO. MP-20-006-003-001/12 | Approved | 27000 | 0 | 2015-11-24
KHATEGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006003/IF/IAY/40445 — Construction of IAY House -IAY REG. NO. MP-20-006-003-001/13 | Approved | 27000 | 0 | 2015-11-24
KHATEGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006003/IF/IAY/40446 — Construction of IAY House -IAY REG. NO. MP-20-006-003-003/09 | Approved | 27000 | 0 | 2015-11-24
KHATEGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006003/IF/IAY/40448 — Construction of IAY House -IAY REG. NO. MP-20-006-003-004/25 | Approved | 27000 | 0 | 2015-11-24
KHATEGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006003/IF/IAY/40449 — Construction of IAY House -IAY REG. NO. MP-20-006-003-002/010 | Approved | 27000 | 0 | 2015-11-24
KHATEGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006003/IF/IAY/40451 — Construction of IAY House -IAY REG. NO. MP-20-006-003-003/012 | Approved | 27000 | 0 | 2015-11-24
KHATEGAON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006003/IF/IAY/4064594 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113848217 | Approved | 27000 | 0 | 2022-05-13
KHATEGAON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006003/IF/IAY/4280859 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121687567 | Approved | 27000 | 0 | 2022-06-30
KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006003/IF/IAY/4537778 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103554257 | Completed | 23490 | 0 | 2024-11-05 | 2026-08-14
KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006003/IF/IAY/4542518 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105890563 | Completed | 23490 | 0 | 2024-11-11 | 2026-08-14
KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006003/IF/IAY/4669044 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103534342 | Completed | 23490 | 0 | 2024-10-15 | 2026-08-14
KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006003/IF/IAY/4669066 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103554891 | Completed | 23490 | 0 | 2024-11-11 | 2026-08-14
KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006003/IF/IAY/4670010 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105884118 | Completed | 23490 | 0 | 2024-10-16 | 2026-08-14
KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006003/IF/IAY/4670012 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105884426 | Completed | 23490 | 0 | 2024-10-10 | 2026-08-14
KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006003/IF/IAY/4670013 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105888497 | Ongoing | 27000 | 0 | 2025-03-06
KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006003/IF/IAY/4670822 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105922734 | Completed | 23490 | 0 | 2024-10-16 | 2026-08-14
KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006003/IF/IAY/4671065 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114134897 | Physically Completed | 23490 | 0 | 2024-12-30 | 2026-08-07
KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006003/IF/IAY/4671068 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114136143 | Physically Completed | 23490 | 0 | 2024-12-30 | 2026-08-07
KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006003/IF/IAY/4675470 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122256487 | Physically Completed | 23490 | 0 | 2024-12-30 | 2026-08-07
KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006003/IF/IAY/4675632 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122515201 | Ongoing | 27000 | 0 | 2024-10-16
KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006003/IF/IAY/4682432 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145678543 | Ongoing | 27000 | 0 | 2025-12-27
KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006003/IF/IAY/4847057 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113848123 | Ongoing | 27000 | 0 | 2025-01-16
KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006003/IF/IAY/4847059 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113848626 | Physically Completed | 23490 | 0 | 2024-12-30 | 2026-08-04
KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006003/IF/IAY/4848748 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103548683 | Ongoing | 27000 | 0 | 2025-04-04
KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006003/IF/IAY/4848749 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103550230 | Ongoing | 27000 | 0 | 2025-03-06
KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006003/IF/IAY/4850017 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123034153 | Physically Completed | 23490 | 0 | 2024-12-30 | 2026-08-04
KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006003/IF/IAY/5344038 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103553334 | Physically Completed | 23490 | 0 | 2025-05-16 | 2026-08-06
KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006003/IF/IAY/5344555 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114134937 | Physically Completed | 23490 | 0 | 2025-09-05 | 2026-08-23
KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006003/IF/IAY/5345885 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103547037 | Ongoing | 27000 | 0 | 2025-05-30
KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006003/IF/IAY/5346795 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123493652 | Ongoing | 27000 | 0 | 2025-08-04
KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006003/IF/IAY/5347019 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122152451 | Approved | 27000 | 0 | 2025-03-13
KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006003/IF/IAY/5348930 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114136046 | Ongoing | 27000 | 0 | 2025-08-26
KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006003/IF/IAY/5349111 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103553856 | Physically Completed | 23490 | 0 | 2025-05-30 | 2026-08-06
KHATEGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006003/IF/IAY/5349112 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103554046 | Ongoing | 27000 | 0 | 2026-07-08
KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006003/IF/IAY/5349189 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113848390 | Approved | 27000 | 0 | 2025-03-25
KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006003/IF/IAY/5349191 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113848748 | Ongoing | 27000 | 0 | 2026-01-08
KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006003/IF/IAY/5350240 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148820754 | Ongoing | 27000 | 0 | 2025-07-14
KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006003/IF/IAY/5351952 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127490259 | Ongoing | 27000 | 0 | 2025-09-04
KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006003/IF/IAY/5352045 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127511727 | Approved | 27000 | 0 | 2025-03-09
KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006003/IF/IAY/5470559 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113848553 | Ongoing | 27000 | 0 | 2025-08-26
KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006003/IF/IAY/5470675 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121684253 | Ongoing | 27000 | 0 | 2025-08-26
KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006003/IF/IAY/5553362 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103527038 | Ongoing | 27000 | 0 | 2025-09-03
KHATEGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006003/IF/IAY/5686162 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114134482 | Ongoing | 27000 | 4200 | 2026-04-03
KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006003/IF/IAY/5686389 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119516049 | Ongoing | 27000 | 0 | 2025-09-03
KHATEGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006003/IF/IAY/5921196 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103577062 | Ongoing | 27000 | 0 | 2026-07-01
KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006003/IF/IAY/5924106 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105922634 | Approved | 27000 | 0 | 2025-03-25
KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006003/IF/IAY/6067630 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103552451 | Approved | 27000 | 0 | 2026-02-17
KHATEGAON | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720006003/RC/22012034473877 — सी सी रोड पी एम मुख्य सड़क से गोलू के खा ले तक | Ongoing | 55800 | 0 | 2019-08-19
KHATEGAON | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dykes for Community | Underground Dyke for Ground Water Recharge | 1720006003/WC/22012035237925 — निर्माण शा.नाला स्टॉपडेम के पास ग्राम खातामऊ | Approved | 0 | 0 | 2024-08-18
KHATEGAON | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1720006003/WC/VB/22012035330335 — रूफ टॉप वाटर हार्वेस्टिंग निर्माण शा.मा.वि. माना मचवास | Approved | 0 | 0 | 2026-04-14
KHATEGAON | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1720006003/WC/VB/22012035330337 — रूफ टॉप वाटर हार्वेस्टिंग निर्माण शा.प्रा.वि. माना मचवास | Approved | 0 | 0 | 2026-04-14
KHATEGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1720/DP/22012034531345 — Bamboo Plantation Machwash 226 | Ongoing | 6531000 | 0 | 2021-08-14
KHATEGAON | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1720/DP/22012034625596 — Bamboo plantation lingapani 229 | Ongoing | 2417000 | 0 | 2024-08-19
KHATEGAON | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1720/DP/22012034629137 — Bamboo plantation lingapani 229 part-2 | Ongoing | 2474000 | 0 | 2025-06-13