## Work List
Exported on: 2026-10-02 05:27:22
Filters applied:
Data source: VBGRAMG
District: DEWAS
Block: All
Panchayat: LILI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
KHATEGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound Wall for Government School for Community | Constr of Compound wall | 1720006018/AV/22012034604879 — बॉउंड्रीवॉल निर्माण मा.वि. कुमानगॉव | Ongoing | 315000 | 0 | 2021-11-26
KHATEGAON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1720006018/DP/22012034543974 — माँ की बगिया मा.वि. ग्राम लीली | Ongoing | 13215.93 | 0 | 2022-05-27
KHATEGAON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1720006018/DP/22012034548764 — माँ की बगिया प्रा.वि. ग्राम मोला | Ongoing | 13215.93 | 0 | 2022-05-27
KHATEGAON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Agro Forestry Block Plantation for Community | Plantation | 1720006018/DP/22012034601502 — वसुधा वंदन (अमृत वाटिका) पंचायत भवन एवं मा.वि. परिसर 75 पोधे ग्राम लीली | Ongoing | 55847.4 | 0 | 2023-09-10
KHATEGAON | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1720006018/IF/22012035389572 — डगवेल रिचार्ज सुरेश पिता सीताराम ग्राम लीली | Ongoing | 25899.46 | 0 | 2025-05-03
KHATEGAON | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1720006018/IF/22012035389637 — डगवेल रिचार्ज संतोष पिता फूलचंद ग्राम कुमनगांव | Ongoing | 25899.46 | 0 | 2025-05-02
KHATEGAON | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1720006018/IF/22012035389704 — डगवेल रिचार्ज रमेश पिता हरलाल ग्राम मोला | Ongoing | 25899.46 | 0 | 2025-05-02
KHATEGAON | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1720006018/IF/22012035538481 — डग वेल रिचार्ज कोदर् पिता मांगीलाल ग्राम मौला | Ongoing | 25899.46 | 0 | 2025-05-22
KHATEGAON | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1720006018/IF/22012035538587 — डग वेल रिचार्ज सरस्वती बाई पति केलाश ग्राम मौला | Ongoing | 25899.46 | 0 | 2025-05-23
KHATEGAON | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1720006018/IF/22012035538624 — डग वेल रिचार्ज सुनीता बाई पिता अनिल ग्राम लीली | Approved | 25899.46 | 0 | 2025-04-14
KHATEGAON | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1720006018/IF/22012035540679 — डगवेल रिचार्ज रामनारायण पिता नत्थू ग्राम कुमनगाव | Ongoing | 25899.46 | 0 | 2025-05-22
KHATEGAON | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1720006018/IF/22012035540731 — डगवेल रिचार्ज रामु पिता नत्थू ग्राम कुमनगाव | Ongoing | 25899.46 | 0 | 2025-05-22
KHATEGAON | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1720006018/IF/22012035540755 — डगवेल रिचार्ज प्रदीप पिता पूनम ग्राम कुमनगाव | Ongoing | 25899.46 | 0 | 2025-05-22
KHATEGAON | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1720006018/IF/22012035540796 — डगवेल रिचार्ज घासीराम पिता नत्थू ग्राम कुमनगाव | Ongoing | 25899.46 | 0 | 2025-05-22
KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1720006018/IF/22012035595285 — Ek Bagiya Maa ke Naam Muli bai MP-20-006-018-003/55 163/6 | Ongoing | 263510.03 | 0 | 2025-09-04
KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1720006018/IF/22012035595289 — Ek Bagiya Maa ke Naam Rekha bai dhanware MP-20-006-018-003/51 127/3 | Ongoing | 269386.03 | 12600 | 2025-09-05
KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006018/IF/IAY/4533759 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102093856 | Completed | 23490 | 0 | 2025-02-05 | 2026-08-13
KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006018/IF/IAY/4542022 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105320609 | Completed | 23490 | 0 | 2024-12-06 | 2026-08-13
KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006018/IF/IAY/4542752 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106013714 | Completed | 23490 | 0 | 2024-10-17 | 2026-08-13
KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006018/IF/IAY/4556739 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114038155 | Completed | 23490 | 0 | 2024-11-14 | 2026-08-13
KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006018/IF/IAY/4556741 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114038184 | Completed | 23490 | 0 | 2024-10-17 | 2026-08-13
KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006018/IF/IAY/4744755 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114038208 | Completed | 23490 | 0 | 2024-12-06 | 2026-08-13
KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006018/IF/IAY/5155866 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114038192 | Ongoing | 27000 | 0 | 2025-12-14
KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006018/IF/IAY/5194231 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105324212 | Approved | 27000 | 0 | 2025-03-01
KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006018/IF/IAY/5202458 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120652524 | Completed | 23490 | 0 | 2025-04-28 | 2026-08-13
KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006018/IF/IAY/5222611 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118437879 | Completed | 23490 | 0 | 2025-04-29 | 2026-08-13
KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006018/IF/IAY/5226382 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121554272 | Completed | 23490 | 0 | 2025-04-29 | 2026-08-13
KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006018/IF/IAY/5269393 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122457948 | Completed | 23490 | 0 | 2025-04-28 | 2026-08-13
KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006018/IF/IAY/5290041 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144263847 | Ongoing | 27000 | 2100 | 2026-01-15
KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006018/IF/IAY/5322404 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114038195 | Approved | 27000 | 0 | 2025-03-29
KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006018/IF/IAY/5330764 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114038189 | Ongoing | 27000 | 0 | 2025-07-18
KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006018/IF/IAY/5338699 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118379349 | Approved | 27000 | 0 | 2025-03-24
KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006018/IF/IAY/5359062 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102125764 | Physically Completed | 27000 | 0 | 2025-06-24 | 2026-09-28
KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006018/IF/IAY/5368907 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118438885 | Completed | 23490 | 0 | 2025-04-29 | 2026-08-13
KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006018/IF/IAY/5467598 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121569648 | Physically Completed | 27000 | 0 | 2025-06-25 | 2026-09-29
KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006018/IF/IAY/5469592 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116316114 | Ongoing | 27000 | 4800 | 2026-01-10
KHATEGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006018/IF/IAY/5470447 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121570129 | Ongoing | 27000 | 300 | 2026-07-17
KHATEGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1720006018/IF/IAY/94375 — Construction of IAY House -IAY REG. NO. MP-20-006-018-001/34 | Approved | 27000 | 0 | 2015-10-29
KHATEGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1720006018/IF/IAY/94376 — Construction of IAY House -IAY REG. NO. MP-20-006-018-002/13 | Approved | 27000 | 0 | 2015-10-29
KHATEGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1720006018/IF/IAY/94377 — Construction of IAY House -IAY REG. NO. MP-20-006-018-003/13 | Approved | 27000 | 0 | 2015-10-29
KHATEGAON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in fields for Community | Plantation | 1720/DP/22012034552985 — Bamboo plantation mola 295 | Ongoing | 2896000 | 0 | 2022-05-03