## Work List
Exported on: 2026-10-26 21:05:48
Filters applied:
Data source: VBGRAMG
District: DEWAS
Block: All
Panchayat: BARBAI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1720006038/IF/22012035548377 — खेत तालाब निर्माण प्रह्लाद पिता पंचम ग्राम बरवई | Approved | 0 | 0 | 2025-04-14
KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1720006038/IF/22012035564233 — खेत तालाब निर्माण मुंशी पिता हीरालाल ग्राम बरवई | Approved | 0 | 0 | 2025-04-14
KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1720006038/IF/22012035591425 — Ek Bagiya Maa ke Naam Lalita Bai MP-20-006-038-001/251-b 404/1/1 | Ongoing | 266577.25 | 11400 | 2025-09-06
KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1720006038/IF/22012035591451 — Ek Bagiya Maa ke Naam Kala bai MP-20-006-038-001/251-D 404/1/5 | Ongoing | 269386.03 | 15600 | 2025-09-06
KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006038/IF/IAY/4577183 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118041434 | Physically Completed | 23490 | 0 | 2024-11-19 | 2026-08-06
KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006038/IF/IAY/4578037 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118094281 | Physically Completed | 23490 | 0 | 2024-11-18 | 2026-08-06
KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006038/IF/IAY/4582512 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118863080 | Physically Completed | 27000 | 0 | 2024-11-04 | 2026-10-15
KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006038/IF/IAY/4771074 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124804012 | Physically Completed | 27000 | 0 | 2024-12-02 | 2026-09-29
KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006038/IF/IAY/4771102 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124810441 | Physically Completed | 27000 | 0 | 2024-11-29 | 2026-08-30
KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006038/IF/IAY/4862386 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116258808 | Physically Completed | 23490 | 0 | 2025-04-07 | 2026-08-06
KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006038/IF/IAY/4865907 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127359504 | Physically Completed | 23490 | 0 | 2025-04-07 | 2026-08-06
KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006038/IF/IAY/5120898 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116416109 | Physically Completed | 23490 | 0 | 2025-05-15 | 2026-08-06
KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006038/IF/IAY/5203539 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119384400 | Physically Completed | 27000 | 0 | 2025-09-24 | 2026-10-15
KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006038/IF/IAY/5215393 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127363907 | Ongoing | 27000 | 0 | 2025-08-03
KHATEGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006038/IF/IAY/5692415 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119575054 | Ongoing | 27000 | 0 | 2026-05-02
KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006038/IF/IAY/5772469 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118818304 | Physically Completed | 23490 | 0 | 2025-09-02 | 2026-08-06
KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006038/IF/IAY/5773674 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123402143 | Ongoing | 27000 | 0 | 2025-09-02
KHATEGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006038/IF/IAY/5773872 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119690465 | Ongoing | 27000 | 11100 | 2026-04-28
KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006038/IF/IAY/5841886 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124803463 | Approved | 27000 | 0 | 2025-03-25
KHATEGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006038/IF/IAY/5874313 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122847516 | Physically Completed | 27000 | 21000 | 2026-05-02 | 2026-10-04
KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006038/IF/IAY/6158483 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118807369 | Approved | 27000 | 0 | 2026-02-17
KHATEGAON | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dyke for Community | Underground Dyke for Ground Water Recharge | 1720006038/WC/22012035243694 — डाइक निर्माण शा.नाला पर संतोष-नर्मदाप्रसाद के खेत के पास ग्राम बरवई | Approved | 0 | 0 | 2024-10-02
KHATEGAON | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dyke for Community | Underground Dyke for Ground Water Recharge | 1720006038/WC/22012035243697 — डाइक निर्माण शा.नाला पर महेश-जगन्नाथ के खेत के पास ग्राम बरवई | Approved | 0 | 0 | 2024-10-02
KHATEGAON | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dyke for Community | Underground Dyke for Ground Water Recharge | 1720006038/WC/22012035243701 — डाइक निर्माण शा.नाला पर रामोतार-मदन के खेत के पास ग्राम बरवई | Approved | 0 | 0 | 2024-10-02
KHATEGAON | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dyke for Community | Underground Dyke for Ground Water Recharge | 1720006038/WC/22012035243703 — डाइक निर्माण शा.नाला पर हरिप्रसाद-रामगोपाल के खेत के पास ग्राम बरवई | Approved | 0 | 0 | 2024-10-02
KHATEGAON | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dyke for Community | Underground Dyke for Ground Water Recharge | 1720006038/WC/22012035243708 — डाइक निर्माण शा.नाला पर अनिल-रामलाल के खेत के पास ग्राम बरवई | Approved | 0 | 0 | 2024-10-02