## Work List
Exported on: 2026-10-01 16:03:34
Filters applied:
Data source: VBGRAMG
District: JHABUA
Block: All
Panchayat: HATYADELI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
RAMA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1721005014/AV/22012034586066 — BOUNDRYWALL CONSTRUCTION MIDILE SCHOOL HATYADELI | Ongoing | 1078442.58 | 18600 | 2021-08-19
RAMA | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1721005014/AV/8615 — SHANTIDHAM PUL KE PAS HATYADELI 2016-17 | Ongoing | 180000 | 0 | 2017-04-01
RAMA | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1721005014/AV/8617 — SHANTIDHAM BALIYA FALIYA NALE PAR WAGNERA HATYADELI 2016-17 | Ongoing | 180000 | 0 | 2017-04-01
RAMA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1721005014/DP/22012034435640 — PAY JAL PATELIA FALIA | Ongoing | 445000 | 0 | 2019-03-07
RAMA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1721005014/DP/22012034521119 — SARWAJANIC PAYJAL KOOP PIDIA KATARA FALIYA RUPAREL HATYADELI | Ongoing | 470874.11 | 0 | 2020-12-21
RAMA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1721005014/DP/22012034524878 — SARWAJANIC PAYJAL KOOP RAMESH KHADIYA FALIYA HATYADELI | Ongoing | 470874.11 | 0 | 2021-05-15
RAMA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1721005014/DP/22012034552741 — SARVJANIK PAYJAL KUP NIRMAN DEVAL FHALIYA RUPAREL | Ongoing | 489496.27 | 0 | 2022-05-06
RAMA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1721005014/DP/22012034552742 — SARVJANIK KUP NIRMAN KOTWAR FHALIYA RUPAREL | Ongoing | 489496.27 | 0 | 2022-05-27
RAMA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1721005014/DP/22012034554541 — SARVJANIK KUP NIRMAN DHUMSINGH MEDA FHALIYA RUPAREL HAYADELI | Ongoing | 489496.27 | 0 | 2022-05-26
RAMA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1721005014/IC/22012034892500 — Sarwajanik kup Nirman Tadvi Mavi Faliya | Approved | 605674.69 | 0 | 2025-06-20
RAMA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1721005014/IC/22012034892675 — Sarwajanik kup Nirman Ramla Bhua Faliya Hatiyadeli | Ongoing | 605674.69 | 6900 | 2026-03-31
RAMA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1721005014/IC/22012034893281 — Sarwajanik kup Nirman Bariya Faliya | New | 0 | 0 | 2025-11-15
RAMA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1721005014/IF/22012034669879 — HITESHI KAPIL DHARA KOOP KARANSINGH SURPAL RUPAREL HATYADELI | Ongoing | 246126.86 | 0 | 2021-04-10
RAMA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1721005014/IF/22012035312564 — Kapil Dhara Kup NIrman Miru Randchod Katara | Ongoing | 312155.12 | 0 | 2025-04-27
RAMA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1721005014/IF/22012035391360 — JGSA 2025 Farm Pond Nirman Chagan Jawala MP-21-005-014-003/106 | New | 0 | 0 | 2025-04-01
RAMA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1721005014/IF/22012035391364 — JGSA 2025 Farm Pond Nirman Chagan Jawala MP-21-005-014-003/106 | New | 0 | 0 | 2025-04-01
RAMA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1721005014/IF/22012035391366 — JGSA 2025 Farm Pond Nirman Chagan Jawala MP-21-005-014-003/106 | New | 0 | 0 | 2025-04-01
RAMA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1721005014/IF/22012035509858 — JGSA 2025 Form Pond Nirman Maniya Lalji MP-21-005-014-003/221 | Ongoing | 147621.16 | 0 | 2025-05-16
RAMA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1721005014/IF/22012035637515 — Kapil Dhara Kup Nirman Dhana Ragu Magliya | Approved | 0 | 0 | 2025-10-02
RAMA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1721005014/IF/IAY/3790345 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104906295 | Ongoing | 27000 | 0 | 2022-05-11
RAMA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1721005014/IF/IAY/5505482 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102663937 | Physically Completed | 23490 | 0 | 2025-07-25 | 2026-08-27
RAMA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1721005014/IF/IAY/5506116 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106613277 | Ongoing | 27000 | 0 | 2025-08-28
RAMA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1721005014/IF/IAY/5507358 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113445204 | Physically Completed | 23490 | 0 | 2025-05-04 | 2026-08-27
RAMA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1721005014/IF/IAY/5507470 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132268382 | Physically Completed | 23490 | 0 | 2025-05-04 | 2026-08-27
RAMA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1721005014/IF/IAY/5507487 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106280021 | Physically Completed | 23490 | 0 | 2025-07-25 | 2026-08-27
RAMA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1721005014/IF/IAY/5508954 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105427621 | Ongoing | 27000 | 0 | 2025-05-04
RAMA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1721005014/IF/IAY/5509417 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106659247 | Ongoing | 27000 | 0 | 2025-05-04
RAMA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1721005014/IF/IAY/5509625 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114100328 | Physically Completed | 23490 | 0 | 2025-05-04 | 2026-08-27
RAMA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1721005014/IF/IAY/5512388 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102225568 | Physically Completed | 27000 | 0 | 2025-08-12 | 2026-09-20
RAMA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1721005014/IF/IAY/5512643 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105431571 | Ongoing | 27000 | 0 | 2025-08-12
RAMA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1721005014/IF/IAY/5512882 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106621416 | Physically Completed | 23490 | 0 | 2025-08-20 | 2026-07-19
RAMA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1721005014/IF/IAY/5512883 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106621503 | Ongoing | 27000 | 0 | 2025-08-12
RAMA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1721005014/IF/IAY/5513285 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102203055 | Ongoing | 27000 | 0 | 2025-08-28
RAMA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1721005014/IF/IAY/5513286 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102203067 | Physically Completed | 23490 | 0 | 2025-08-28 | 2026-08-09
RAMA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1721005014/IF/IAY/5513287 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102203071 | Ongoing | 27000 | 0 | 2025-08-28
RAMA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1721005014/IF/IAY/5668289 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102461684 | Ongoing | 27000 | 0 | 2025-09-23
RAMA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1721005014/IF/IAY/5668308 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113485061 | Physically Completed | 23490 | 0 | 2025-08-12 | 2026-08-27
RAMA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1721005014/IF/IAY/5827704 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103697234 | Ongoing | 27000 | 0 | 2025-12-07
RAMA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1721005014/RC/22012034650316 — Khet sadak Nirman Kalidevi marg se prathmic shala school vaghnera mavi faliya vaghnera g.p. Hatyadel | Ongoing | 2055791.76 | 0 | 2023-08-28
RAMA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1721005014/WC/22012035153678 — CHEAK DAM NIRMAN MOHANIYA WALA NALA WAGHNEHRA HATYADELI | Ongoing | 2134460.81 | 0 | 2024-02-22
RAMA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1721005014/WC/22012035279324 — JGSA 2025 Recharge Structure Sarvjanik Kup Nirman School Bhuriya Fhaliya | New | 0 | 0 | 2025-04-14
RAMA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1721005014/WC/22012035291813 — JGSA 2025 Recharge Structure Sarwajnic payjal koop school bhuriya faliya1721005014/DP/22012034489060 | Approved | 0 | 0 | 2025-04-14
RAMA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1721005/IF/22012034596899 — NEEJI FLODHYAN ROPAN RAKESH HEEMCHAND | Ongoing | 144000 | 0 | 2020-09-10
RAMA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1721005/IF/22012034598946 — NEEJI FLODHYAN ROPAN DULLA KASU | Ongoing | 144000 | 0 | 2020-09-29
RAMA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1721005/IF/22012034598953 — NEEJI FLODHYAN ROPAN BADIYA MUNNA HATYADELI | Ongoing | 144000 | 0 | 2020-09-16
RAMA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1721005/IF/22012035288388 — NEEJI FLODHYAN ROPAN SUNPAL RANJI MEDA RUPAREL | Ongoing | 140000 | 0 | 2025-02-25
RAMA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1721005/IF/22012035288395 — NEEJI FLODHYAN ROPAN RATANSINGH NANIYA PARMAR HATAYADELI | Ongoing | 140000 | 0 | 2025-02-25
RAMA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1721/WC/22012034446584 — NISTAR TALAB MAHUDIWALA NALA WAGNEERA | Ongoing | 2500000 | 0 | 2019-03-08
RAMA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1721/WC/22012035244955 — KHENJDA WALA NANA MINOR TANK FOR FOREST & WILD LIFE ( HATYADELI) | Ongoing | 2499000 | 0 | 2025-02-06
RAMA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1721/WC/22012035244956 — LIMDA WALA NANA MINOR TANK FOR FOREST & WILD LIFE ( HATYADELI) | Ongoing | 2499000 | 0 | 2025-04-23