## Work List
Exported on: 2026-10-24 01:52:43
Filters applied:
Data source: VBGRAMG
District: DHAR
Block: All
Panchayat: Hanumantya Padampura
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SARDARPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Agro Forestry Block Plantation for Community | Plantation | 1722002022/DP/22012034598704 — Vashudha vandan plantation panchayat parisar haumantiya padampura | Physically Completed | 55847.4 | 0 | 2023-08-24 | 2026-08-12
SARDARPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1722002022/IF/22012035108429 — KAPILDHARA KUP NIRMAN BHERULAL KANIRAM | Ongoing | 249970.36 | 0 | 2023-06-09
SARDARPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1722002022/IF/22012035108431 — KAPILDHARA KUP NIRMAN RAMA BHUVAN | Ongoing | 250027.27 | 0 | 2023-07-05
SARDARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1722002022/IF/22012035519082 — Dug Well Recharge Jhammubai Soma | Ongoing | 25899.46 | 0 | 2025-06-06
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1722002022/IF/22012035578490 — KAPILDHARA KUP NIRMAN SAJAN NANDU | Approved | 0 | 0 | 2025-04-14
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1722002022/IF/22012035578492 — KAPILDHARA KUP NIRMAN RAMA NATHA | Approved | 0 | 0 | 2025-04-14
SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/4696053 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113913710 | Completed | 23490 | 0 | 2025-01-11 | 2026-08-12
SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/4699336 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119436160 | Completed | 27000 | 0 | 2025-01-11 | 2026-09-19
SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/4700179 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113939714 | Completed | 27000 | 0 | 2025-02-18 | 2026-09-19
SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/4708648 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124981494 | Physically Completed | 27000 | 6600 | 2025-02-18 | 2026-10-18
SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/4741616 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106652318 | Completed | 23490 | 2400 | 2025-02-18 | 2026-09-19
SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/4785267 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130829497 | Completed | 27000 | 0 | 2025-02-18 | 2026-09-19
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/4889231 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123025432 | Ongoing | 27000 | 3000 | 2025-08-02
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/5357051 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113915329 | Completed | 23490 | 0 | 2025-09-08 | 2026-09-19
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/5357083 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117890446 | Ongoing | 27000 | 4200 | 2025-07-07
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/5360102 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123041794 | Completed | 27000 | 0 | 2025-11-05 | 2026-09-19
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/5360579 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117834723 | Completed | 27000 | 2400 | 2025-06-01 | 2026-09-19
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/5361614 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118057008 | Ongoing | 27000 | 10800 | 2025-07-07
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/5361903 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117822279 | Completed | 23490 | 0 | 2025-09-08 | 2026-08-12
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/5361951 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117821895 | Ongoing | 27000 | 8400 | 2025-06-01
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/5363613 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121398655 | Ongoing | 27000 | 0 | 2025-10-29
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/5364579 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123989540 | Ongoing | 27000 | 0 | 2025-09-13
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/5369449 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106652357 | Ongoing | 27000 | 6600 | 2025-06-01
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/5369696 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114782061 | Completed | 27000 | 4800 | 2025-07-07 | 2026-09-19
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/5370390 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120307930 | Ongoing | 27000 | 10800 | 2025-09-08
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/5370640 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121973530 | Completed | 23490 | 0 | 2025-06-01 | 2026-08-12
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/5371415 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120305715 | Ongoing | 27000 | 2400 | 2025-08-02
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/5372993 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124983298 | Ongoing | 27000 | 0 | 2025-09-29
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/5373428 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123010109 | Ongoing | 27000 | 8400 | 2025-07-23
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/5373962 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123990851 | Ongoing | 27000 | 0 | 2025-11-12
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/5376137 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122811861 | Ongoing | 27000 | 0 | 2025-10-14
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/5377581 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120308972 | Ongoing | 27000 | 0 | 2025-10-29
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/5378098 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114780342 | Ongoing | 27000 | 4800 | 2025-07-07
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/5379508 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122365104 | Completed | 23490 | 0 | 2025-09-13 | 2026-08-12
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/5379863 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113672656 | Ongoing | 27000 | 0 | 2025-09-22
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/5380462 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117924149 | Completed | 27000 | 4800 | 2025-07-07 | 2026-09-19
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/5380542 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121729712 | Ongoing | 27000 | 6600 | 2025-07-07
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/5380934 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123991694 | Completed | 23490 | 2400 | 2025-09-08 | 2026-09-19
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/5381501 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117443052 | Ongoing | 27000 | 8400 | 2025-12-12
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/5382229 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121731593 | Ongoing | 27000 | 0 | 2025-09-08
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/5382596 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106424125 | Ongoing | 27000 | 0 | 2025-11-05
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/5382959 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123993281 | Completed | 27000 | 13200 | 2026-03-17 | 2026-09-19
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/5383053 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113824135 | Completed | 23490 | 3600 | 2025-08-02 | 2026-09-19
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/5497263 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123980686 | Completed | 27000 | 0 | 2025-09-08 | 2026-09-19
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/5498318 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123990352 | Approved | 27000 | 0 | 2025-04-11
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/5499126 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117924301 | Completed | 27000 | 4200 | 2025-07-07 | 2026-09-19
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/5499187 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123024181 | Physically Completed | 27000 | 0 | 2025-09-08 | 2026-10-04
SARDARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/5500504 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123483411 | Ongoing | 27000 | 4800 | 2026-06-22
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/5567937 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123475318 | Completed | 23490 | 3000 | 2025-10-13 | 2026-09-19
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/5568155 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123420006 | Ongoing | 27000 | 0 | 2026-03-17
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/5568714 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123425589 | Approved | 27000 | 0 | 2025-04-23
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/5654140 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106482377 | Ongoing | 27000 | 6600 | 2025-09-08
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/5654490 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123990137 | Ongoing | 27000 | 0 | 2025-10-29
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/5654753 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117442685 | Completed | 23490 | 0 | 2025-09-08 | 2026-08-12
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/5654868 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123991039 | Completed | 23490 | 2400 | 2025-09-08 | 2026-09-19
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/5654869 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123992452 | Physically Completed | 27000 | 6600 | 2025-09-08 | 2026-10-11
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/5656040 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124301931 | Completed | 23490 | 4800 | 2025-09-08 | 2026-09-19
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/5656044 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123469703 | Completed | 27000 | 4800 | 2025-09-08 | 2026-09-19
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/5656187 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123992149 | Ongoing | 27000 | 8700 | 2025-09-08
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/5656188 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123992302 | Completed | 23490 | 0 | 2025-09-08 | 2026-08-12
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/5702501 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121732795 | Ongoing | 27000 | 4200 | 2025-09-08
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/5702506 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113937342 | Ongoing | 27000 | 0 | 2026-03-17
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/5702879 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123910627 | Ongoing | 27000 | 0 | 2025-09-08
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/5702902 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120305854 | Completed | 27000 | 12900 | 2025-09-08 | 2026-09-19
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/5702949 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118056796 | Completed | 27000 | 6600 | 2025-09-08 | 2026-09-19
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/5703397 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117443108 | Ongoing | 27000 | 0 | 2025-10-13
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/5724100 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117442992 | Ongoing | 27000 | 0 | 2025-09-29
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/5724274 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124782535 | Ongoing | 27000 | 0 | 2025-10-13
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/5833744 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123839502 | Ongoing | 27000 | 0 | 2025-11-05
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/5833778 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113924509 | Ongoing | 27000 | 0 | 2025-11-05
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/5833957 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117860848 | Ongoing | 27000 | 12600 | 2025-11-05
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/5834214 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124573210 | Completed | 27000 | 6900 | 2025-11-08 | 2026-09-19
SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/5834788 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118554429 | Approved | 27000 | 0 | 2024-09-20
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/5834999 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106652186 | Ongoing | 27000 | 0 | 2025-11-05
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/5836224 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120372596 | Ongoing | 27000 | 0 | 2025-11-05
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/5836315 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123818613 | Ongoing | 27000 | 0 | 2025-11-05
SARDARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/6118209 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122872243 | Ongoing | 27000 | 0 | 2026-06-22
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/6122783 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119875221 | Approved | 27000 | 0 | 2026-03-09
SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/6129370 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106240563 | Approved | 27000 | 0 | 2025-02-21
SARDARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/6130273 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117821752 | Ongoing | 27000 | 0 | 2026-06-22
SARDARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/6132085 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124780447 | Ongoing | 27000 | 4500 | 2026-06-22
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/6133967 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125325938 | Approved | 27000 | 0 | 2026-03-19
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/6139070 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123981415 | Approved | 27000 | 0 | 2026-03-09
SARDARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/6139074 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123992611 | Ongoing | 27000 | 9000 | 2026-06-22
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/6142903 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117924450 | Approved | 27000 | 0 | 2026-03-09
SARDARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/6155185 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119876311 | Ongoing | 27000 | 9000 | 2026-06-22
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/6157612 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114846242 | Approved | 27000 | 0 | 2026-03-09
SARDARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/6158007 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119875685 | Ongoing | 27000 | 0 | 2026-07-13
SARDARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/6161366 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120307731 | Ongoing | 27000 | 4500 | 2026-06-22
SARDARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/6162102 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124982744 | Ongoing | 27000 | 4500 | 2026-06-22
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/6162247 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123988076 | Approved | 27000 | 0 | 2026-03-09
SARDARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/6172333 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121735610 | Ongoing | 27000 | 6600 | 2026-06-22
SARDARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/6173109 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117924600 | Ongoing | 27000 | 9000 | 2026-06-22
SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002022/IF/IAY/6334705 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123024685 | Approved | 27000 | 0 | 2025-03-10
SARDARPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Construction of Drainage Works in Waterlogged Land for Community | Land Development | 1722002022/LD/22012034948732 — Khel maidan karya middle school padampura | Approved | 478322.83 | 0 | 2024-08-15
SARDARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Construction of Drainage Works in Waterlogged Land for Community | Land Development | 1722002022/LD/22012034948735 — Khel maidan karya primary school hanumantya | Ongoing | 478322.83 | 0 | 2025-05-19
SARDARPUR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1722002022/RC/22012034845461 — CC ROAD GULAB RAWAT KE GHAR SE SOMA PAGGI KE GHAR TAK | Ongoing | 52500 | 0 | 2025-11-04
SARDARPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dyke for Community | Underground Dyke for Ground Water Recharge | 1722002022/WC/22012035041691 — SAMUDAYIK KUP NIRMAN HANUMANTYA | Ongoing | 627605.43 | 0 | 2023-05-01
SARDARPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1722002022/WC/22012035163561 — Parcoletion Tank | New | 0 | 0 | 2024-01-08
SARDARPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722002022/WC/22012035221668 — SANKLAN POND NIRMAN KARYA PADAMPURA | Approved | 445326.03 | 0 | 2024-08-15
SARDARPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722002022/WC/22012035221669 — SANKLAN POND NIRMAN KARYA HANUMANTYA | Approved | 427920.51 | 0 | 2024-08-15
SARDARPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722002022/WC/22012035221670 — SANKLAN POND NIRMAN KARYA MOGJIPADA | Ongoing | 427920.51 | 0 | 2025-01-13
SARDARPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722002022/WC/22012035221671 — SANKLAN POND NIRMAN KARYA TALAVPADA | Approved | 0 | 0 | 2024-08-15
SARDARPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722002022/WC/22012035221672 — SANKLAN POND NIRMAN KARYA WADLIPADA | Approved | 0 | 0 | 2024-08-15
SARDARPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722002022/WC/22012035221673 — SANKLAN POND NIRMAN KARYA NIHALPURA | Approved | 444824.07 | 0 | 2024-08-15
SARDARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722002022/WC/22012035305959 — Dug Well Recharge Samudayik Kup Hanumantya | Approved | 25899.46 | 0 | 2025-04-14
SARDARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722002022/WC/22012035305961 — Dug Well Recharge Samudayik Kup Nihalpura | Approved | 25899.46 | 0 | 2025-04-14
SARDARPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722002/IF/22012034588309 — Naharsingh Shankar Horticulture Plantetion | Ongoing | 408600 | 0 | 2020-12-01