## Work List
Exported on: 2026-10-16 14:22:25
Filters applied:
Data source: VBGRAMG
District: DHAR
Block: All
Panchayat: Dattigaon
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SARDARPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1722002043/DP/22012034521461 — samudayik kup nirman karya narsari ke pass | Ongoing | 567610.07 | 0 | 2021-05-26
SARDARPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1722002043/DP/22012034527456 — poshan vatika nirman karya school campus dattigav | Ongoing | 394459.68 | 0 | 2021-05-20
SARDARPUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1722002043/DP/22012034553174 — samudayik kup nirman karya dayma faliya | Ongoing | 591511.94 | 0 | 2022-05-27
SARDARPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1722002043/DP/22012034591983 — Vasudha Vandan Varsha Ropan karay Chatrawas parisar Dattgov | Ongoing | 55847.4 | 0 | 2023-09-23
SARDARPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722002043/IF/22012034555919 — kapil Darakupnirman Radheshyam mangilal | Ongoing | 242453.87 | 0 | 2020-06-11
SARDARPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722002043/IF/22012034746076 — KAPIL DHARA KUP NIRMAN KARYA SANTABAI SUKHRAM | Ongoing | 247839.67 | 0 | 2021-09-13
SARDARPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722002043/IF/22012034964159 — KAPIL DHARA KUP nirman karya narval ramla | Ongoing | 257014.43 | 0 | 2022-05-27
SARDARPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722002043/IF/22012034964171 — KAPIL DHARA KUP nirman karya munnalal puna | Ongoing | 257014.43 | 0 | 2022-05-27
SARDARPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/22012035030520 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116235084 | Ongoing | 18360 | 0 | 2023-05-01
SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722002043/IF/22012035274944 — KAPIL DHARA KUP NIRMAN KARYA RAMESH JHITRA | Approved | 0 | 0 | 2024-11-20
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722002043/IF/22012035508750 — KAPIL DHARA KUP NIRMAN BACKHAND UKAR DATTIGAON | Approved | 0 | 0 | 2025-04-06
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722002043/IF/22012035508768 — KAPIL DHARA KUP NIRMAN RUGHNATH KASANA DATTIGAON | Ongoing | 322434.5 | 0 | 2025-06-01
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722002043/IF/22012035512288 — KAPIL DHARA KUP NIRMAN BABULAL JHITRA NINAMA DATTIGAON | Approved | 0 | 0 | 2025-04-06
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722002043/IF/22012035512312 — KAPIL DHARA KUP NIRMAN KANA MANSINGH DATTIGAON | Ongoing | 322434.5 | 0 | 2025-07-16
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722002043/IF/22012035512332 — KAPIL DHARA KUP NIRMAN BACKHAND SUKALA DATTIGAON | Approved | 322434.5 | 0 | 2025-04-06
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1722002043/IF/22012035555557 — khet talab nirman kary ratan surpal dattigaov | Ongoing | 450885.64 | 0 | 2025-06-15
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1722002043/IF/22012035555564 — khet talab nirman kary bhuri mohan dattigaov | Ongoing | 450885.64 | 0 | 2025-06-18
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1722002043/IF/22012035555774 — khet talab nirman kary prakash varfa dattigaov | Ongoing | 450885.64 | 0 | 2025-06-15
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1722002043/IF/22012035575133 — Khet talab nirman kary Aydan bhuraji dattigaon | Approved | 0 | 0 | 2025-04-16
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1722002043/IF/22012035646657 — pashu shed nirman kary sharvan dhodwa | Approved | 0 | 0 | 2025-10-02
SARDARPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/195761 — Construction of IAY House -IAY REG. NO. MP-22-002-043-001/23 | Approved | 27000 | 0 | 2015-10-31
SARDARPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/201178 — Construction of IAY House -IAY REG. NO. MP-22-002-043-001/60 | Approved | 27000 | 0 | 2015-10-31
SARDARPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/3732729 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116206757 | Approved | 27000 | 0 | 2022-05-01
SARDARPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/3806483 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117226614 | Approved | 27000 | 0 | 2022-05-02
SARDARPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/4381110 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116205859 | Approved | 27000 | 0 | 2022-10-31
SARDARPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/44981 — Construction of IAY House -IAY REG. NO. MP-22-002-043-003/04 | Approved | 27000 | 0 | 2015-10-31
SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/4544897 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106298083 | Ongoing | 27000 | 0 | 2024-12-02
SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/4548475 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106874136 | Ongoing | 27000 | 0 | 2024-12-02
SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/4550002 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106904072 | Ongoing | 27000 | 0 | 2024-12-02
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/4565341 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116314902 | Physically Completed | 27000 | 0 | 2025-05-28 | 2026-10-11
SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/4567636 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116205769 | Completed | 23490 | 0 | 2024-12-02 | 2026-09-03
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/4569094 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116232414 | Ongoing | 27000 | 0 | 2025-05-28
SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/4572002 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117807950 | Ongoing | 27000 | 0 | 2024-12-02
SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/4572003 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117807967 | Ongoing | 27000 | 0 | 2024-12-02
SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/4572005 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117807990 | Ongoing | 27000 | 0 | 2024-12-02
SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/4573352 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117226183 | Ongoing | 27000 | 0 | 2024-12-02
SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/4573353 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117226550 | Ongoing | 27000 | 0 | 2024-12-02
SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/4573354 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117226616 | Completed | 23490 | 0 | 2024-12-02 | 2026-09-03
SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/4573355 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117226670 | Ongoing | 27000 | 0 | 2024-12-02
SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/4573356 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117226705 | Ongoing | 27000 | 0 | 2024-12-02
SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/4573357 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117226715 | Ongoing | 27000 | 0 | 2024-12-02
SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/4573874 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117573858 | Approved | 27000 | 0 | 2024-09-09
SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/4573881 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117574088 | Ongoing | 27000 | 0 | 2024-12-02
SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/4573885 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117574217 | Ongoing | 27000 | 0 | 2024-12-02
SARDARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/4573886 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117574238 | Ongoing | 27000 | 14100 | 2026-07-08
SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/4576563 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117731558 | Ongoing | 27000 | 0 | 2024-12-02
SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/4576564 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117731565 | Ongoing | 27000 | 0 | 2024-12-02
SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/4576567 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117731719 | Ongoing | 27000 | 0 | 2024-12-02
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/4578188 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118114974 | Physically Completed | 23490 | 0 | 2025-10-08 | 2026-08-23
SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/4578552 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118050427 | Approved | 27000 | 0 | 2024-09-19
SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/4581748 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118195706 | Ongoing | 27000 | 0 | 2024-12-02
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/4739114 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106297642 | Ongoing | 27000 | 0 | 2025-05-28
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/4750282 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117226285 | Ongoing | 27000 | 0 | 2025-05-28
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/4750283 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117226908 | Ongoing | 27000 | 0 | 2025-08-05
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/4863184 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117226336 | Ongoing | 27000 | 0 | 2025-05-28
SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/4863755 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117731600 | Approved | 27000 | 0 | 2024-09-09
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5148882 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105876175 | Ongoing | 27000 | 0 | 2025-08-05
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5152601 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106875458 | Completed | 27000 | 0 | 2025-05-28 | 2026-09-03
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5155058 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117226906 | Ongoing | 27000 | 0 | 2025-08-21
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5156628 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117225887 | Ongoing | 27000 | 0 | 2025-05-28
SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5180932 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117226661 | Approved | 27000 | 0 | 2025-02-17
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5181310 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116197571 | Physically Completed | 27000 | 8400 | 2025-05-28 | 2026-09-27
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5185452 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106304835 | Physically Completed | 23490 | 3300 | 2025-05-28 | 2026-08-23
SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5198573 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117226985 | Approved | 27000 | 0 | 2025-02-18
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5200016 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106304583 | Ongoing | 27000 | 0 | 2025-05-28
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5200464 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117226070 | Ongoing | 27000 | 0 | 2025-08-05
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5201663 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117574139 | Completed | 23490 | 1500 | 2025-10-08 | 2026-09-03
SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5210701 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117225890 | Approved | 27000 | 0 | 2025-02-17
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5220005 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117226395 | Ongoing | 27000 | 0 | 2025-05-28
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5222088 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106203401 | Ongoing | 27000 | 0 | 2025-05-28
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5228133 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106306578 | Ongoing | 27000 | 0 | 2025-05-28
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5265797 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117225687 | Ongoing | 27000 | 16200 | 2025-06-02
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5274063 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116197595 | Ongoing | 27000 | 8400 | 2025-05-28
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5284526 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106304463 | Ongoing | 27000 | 0 | 2025-05-28
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5290514 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106906735 | Ongoing | 27000 | 0 | 2025-05-28
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5290865 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106304660 | Ongoing | 27000 | 0 | 2025-05-28
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5296744 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116317989 | Ongoing | 27000 | 0 | 2025-05-28
SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5306045 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117731534 | Approved | 27000 | 0 | 2024-09-09
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5482958 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106203419 | Ongoing | 27000 | 0 | 2025-05-28
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5483052 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116205830 | Ongoing | 27000 | 0 | 2025-05-28
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5483350 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106298433 | Ongoing | 27000 | 0 | 2025-05-28
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5483385 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106874491 | Ongoing | 27000 | 0 | 2025-08-05
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5483386 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106875215 | Completed | 27000 | 0 | 2025-05-28 | 2026-09-03
SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5483895 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117731546 | Approved | 27000 | 0 | 2025-03-31
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5483996 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106874337 | Approved | 27000 | 0 | 2025-04-03
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5484033 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106904266 | Ongoing | 27000 | 0 | 2025-05-28
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5484095 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106304314 | Completed | 23490 | 0 | 2025-05-28 | 2026-09-03
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5484096 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106304334 | Ongoing | 27000 | 0 | 2025-08-05
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5484498 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121775624 | Ongoing | 27000 | 0 | 2025-08-05
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5484517 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106906066 | Ongoing | 27000 | 0 | 2025-08-05
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5484746 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116197284 | Physically Completed | 27000 | 15000 | 2025-05-28 | 2026-10-11
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5484748 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117573833 | Ongoing | 27000 | 0 | 2025-10-08
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5485216 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116197649 | Physically Completed | 27000 | 5100 | 2026-02-11 | 2026-09-03
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5485217 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116204210 | Ongoing | 27000 | 0 | 2025-05-28
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5485669 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116184669 | Ongoing | 27000 | 0 | 2025-05-28
SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5485740 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117226663 | Approved | 27000 | 0 | 2025-03-31
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5485741 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117226675 | Ongoing | 27000 | 0 | 2025-08-05
SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5485742 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117226721 | Approved | 27000 | 0 | 2025-03-31
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5485744 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117226859 | Ongoing | 27000 | 0 | 2026-01-27
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5485745 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117226912 | Ongoing | 27000 | 0 | 2025-08-05
SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5485746 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117226971 | Approved | 27000 | 0 | 2024-09-10
SARDARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5486289 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106304728 | Ongoing | 27000 | 12300 | 2026-04-04
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5601324 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116197634 | Ongoing | 27000 | 0 | 2026-01-14
SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5602178 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117226187 | Approved | 27000 | 0 | 2024-09-09
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5602351 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106904187 | Ongoing | 27000 | 1500 | 2025-05-28
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5602886 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116197348 | Ongoing | 27000 | 8400 | 2025-05-28
SARDARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5702134 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106904667 | Physically Completed | 23490 | 1500 | 2026-04-04 | 2026-07-24
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5702601 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117226393 | Ongoing | 27000 | 0 | 2025-08-05
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5702602 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117226409 | Completed | 27000 | 0 | 2025-08-05 | 2026-09-03
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5703360 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117954745 | Ongoing | 27000 | 0 | 2025-09-02
SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5805185 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116197693 | Approved | 27000 | 0 | 2025-03-22
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5833831 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106304308 | Approved | 27000 | 0 | 2025-06-12
SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5834006 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106298384 | Physically Completed | 27000 | 0 | 2025-03-31 | 2026-09-27
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5835338 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117226856 | Ongoing | 27000 | 4200 | 2025-12-09
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5835339 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117226904 | Ongoing | 27000 | 8100 | 2026-01-14
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5835471 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116180273 | Ongoing | 27000 | 0 | 2026-01-14
SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5835795 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117226284 | Approved | 27000 | 0 | 2025-02-18
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5835922 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106905621 | Ongoing | 27000 | 0 | 2026-02-11
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5836131 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117574280 | Ongoing | 27000 | 0 | 2025-11-04
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5836144 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116186919 | Completed | 23490 | 0 | 2025-11-04 | 2026-09-03
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5836173 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106875397 | Approved | 27000 | 0 | 2025-04-08
SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5836900 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106304414 | Approved | 27000 | 0 | 2025-03-31
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5836901 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106304600 | Physically Completed | 23490 | 0 | 2025-06-12 | 2026-07-19
SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/5864303 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117573917 | Approved | 27000 | 0 | 2025-02-18
SARDARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/6059767 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117225682 | Ongoing | 27000 | 16500 | 2026-07-28
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/6059768 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117226172 | Approved | 27000 | 0 | 2026-02-25
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/6059769 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117226233 | Approved | 27000 | 0 | 2026-02-25
SARDARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/6061123 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120089134 | Ongoing | 27000 | 16200 | 2026-07-28
SARDARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/6061134 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106875349 | Ongoing | 27000 | 20400 | 2026-07-28
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/6062045 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106036582 | Approved | 27000 | 0 | 2026-02-25
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/6066414 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106876208 | Approved | 27000 | 0 | 2026-02-25
SARDARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/6066423 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117574018 | Ongoing | 27000 | 10200 | 2026-09-05
SARDARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/6068434 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105876725 | Ongoing | 27000 | 10500 | 2026-09-05
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/6068593 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106036538 | Approved | 27000 | 0 | 2026-02-25
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/6068912 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106304393 | Approved | 27000 | 0 | 2026-02-25
SARDARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/6068914 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106304427 | Ongoing | 27000 | 21000 | 2026-09-05
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/6068915 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106304804 | Approved | 27000 | 0 | 2026-02-25
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/6069598 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106875839 | Approved | 27000 | 0 | 2026-02-25
SARDARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/6074078 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116197582 | Ongoing | 27000 | 10500 | 2026-09-05
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/6074079 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116197804 | Approved | 27000 | 0 | 2026-02-25
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/6074082 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116205778 | Approved | 27000 | 0 | 2026-02-25
SARDARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/6074083 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116205811 | Ongoing | 27000 | 21000 | 2026-09-05
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/6074135 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116240441 | Approved | 27000 | 0 | 2026-02-25
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/6075524 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117225393 | Approved | 27000 | 0 | 2026-02-25
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/6075526 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117226191 | Approved | 27000 | 0 | 2026-02-25
SARDARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/6075527 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117226334 | Ongoing | 27000 | 21000 | 2026-09-05
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/6075528 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117226598 | Approved | 27000 | 0 | 2026-02-25
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/6076490 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117731779 | Approved | 27000 | 0 | 2026-02-25
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/6076658 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117808019 | Approved | 27000 | 0 | 2026-02-25
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/6079352 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119618504 | Approved | 27000 | 0 | 2026-02-25
SARDARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/6091860 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129434756 | Ongoing | 27000 | 20100 | 2026-09-15
SARDARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/6094238 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132255923 | Ongoing | 27000 | 10500 | 2026-09-05
SARDARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/6094239 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132256070 | Ongoing | 27000 | 18300 | 2026-09-05
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/6130482 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116314955 | Approved | 27000 | 0 | 2026-02-25
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/6134506 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106036559 | Approved | 27000 | 0 | 2026-02-25
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/6138078 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117225563 | Approved | 27000 | 0 | 2026-02-25
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/6138279 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106875753 | Approved | 27000 | 0 | 2026-03-23
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/6139490 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116205835 | Approved | 27000 | 0 | 2026-02-25
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/6139746 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106304845 | Approved | 27000 | 0 | 2026-02-25
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/6142801 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106906367 | Approved | 27000 | 0 | 2026-03-16
SARDARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/6143552 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106874552 | Ongoing | 27000 | 20700 | 2026-07-28
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/6146938 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116317828 | Approved | 27000 | 0 | 2026-03-23
SARDARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/6160535 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106904993 | Ongoing | 27000 | 16800 | 2026-07-28
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/6160537 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106905051 | Approved | 27000 | 0 | 2026-03-23
SARDARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/6167016 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117225742 | Ongoing | 27000 | 25200 | 2026-07-28
SARDARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/6167018 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117226231 | Ongoing | 27000 | 16200 | 2026-08-30
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/6167378 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116204216 | Approved | 27000 | 0 | 2026-03-21
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/6170248 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116315085 | Approved | 27000 | 0 | 2026-02-25
SARDARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/6170842 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106905537 | Ongoing | 27000 | 21600 | 2026-07-28
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/6172562 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117808004 | Approved | 27000 | 0 | 2026-03-21
SARDARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/6174433 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117226339 | Ongoing | 27000 | 21000 | 2026-09-05
SARDARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/6174434 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117226561 | Ongoing | 27000 | 16800 | 2026-07-28
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/6324187 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118195531 | Approved | 27000 | 0 | 2026-03-25
SARDARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/6343723 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116314454 | Approved | 27000 | 0 | 2026-05-14
SARDARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/6343748 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106904878 | Approved | 27000 | 0 | 2026-05-14
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/6343807 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116197789 | Approved | 27000 | 0 | 2026-03-21
SARDARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/6343847 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106876544 | Approved | 27000 | 0 | 2026-05-14
SARDARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/6343895 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106905997 | Approved | 27000 | 0 | 2026-05-21
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/6344215 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116205833 | Approved | 27000 | 0 | 2026-02-25
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/6398242 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106906524 | Approved | 27000 | 0 | 2026-03-17
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/6398419 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106876406 | Approved | 27000 | 0 | 2026-03-21
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/6398456 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117589002 | Approved | 27000 | 0 | 2026-02-25
SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/6398501 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106904320 | Approved | 27000 | 0 | 2026-02-25
SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/6398555 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119619838 | Approved | 27000 | 0 | 2025-03-31
SARDARPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/82424 — Construction of IAY House -IAY REG. NO. MP-22-002-043-002/68 | Approved | 27000 | 0 | 2015-10-31
SARDARPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1722002043/IF/IAY/82425 — Construction of IAY House -IAY REG. NO. MP-22-002-043-003/03 | Approved | 27000 | 0 | 2015-10-31
SARDARPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Construction of Drainage Works in Waterlogged Land for Community | Land Development | 1722002043/LD/22012034948566 — Samudaiyik kup nirman kary nayakheda par | Approved | 0 | 0 | 2024-10-02
SARDARPUR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1722002043/RC/22012034562335 — C.C road nirman karya sachool ke pass se jalam ke ghar tak | Ongoing | 110000 | 0 | 2022-08-22
SARDARPUR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1722002043/RC/22012034562348 — C.C road nirman karya sitla mata se chamunda mata tak | Ongoing | 187000 | 0 | 2021-04-20
SARDARPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1722002043/RC/22012034637642 — CC Roda Nayakheda HanumanMandir se Galbaba tak | Ongoing | 97000 | 0 | 2023-06-11
SARDARPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1722002043/RC/22012034638056 — CC Road Nirman Bebi Bai ke Ghar se Shaitan jhitara ke Ghar tak Timripada | Ongoing | 80000 | 0 | 2023-06-11
SARDARPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1722002043/WC/22012034611350 — nala treching karya maliya wali khali par dattigav | Ongoing | 654034.56 | 0 | 2021-05-26
SARDARPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1722002043/WC/22012035134067 — Prokolesion Tek Dattigav | Ongoing | 1186002.06 | 0 | 2024-12-24
SARDARPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Gully Plug for Community | Construction of Check Dam/Stop Dam | 1722002043/WC/22012035142999 — PILIYA NIRMAN NIRMAN BHAWARSINGH KE KHET KE PAS | Ongoing | 126000 | 0 | 2023-12-19
SARDARPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1722002043/WC/22012035164225 — percolation tank | New | 0 | 0 | 2024-01-08
SARDARPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722002043/WC/22012035244175 — Nistar talab nirman kary dattigaon | Approved | 0 | 0 | 2024-10-02
SARDARPUR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1722002043/WC/VB/YD/22012035336141 — Construction of Mini Percolation Tank for datigaw | New | 0 | 0 | 2026-09-25
SARDARPUR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Horticulture -Community / Line Plantation of Horticulture Trees for Community | Plantation | 1722002/DP/22012034483507 — नर्सरी स्थापना कार्य एवं पक्के निर्माण कार्य शासकीय उद्यान दत्तीगांव में | Ongoing | 5035000 | 0 | 2020-01-02
SARDARPUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1722002/DP/22012034490948 — block plantation | Ongoing | 633000 | 0 | 2021-03-24
SARDARPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722002/IF/22012034837764 — Narsingh Nana Horti. Plan.GP Dttigaon | Ongoing | 556000 | 0 | 2022-10-13
SARDARPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722002/IF/22012034865095 — Smt.Gyarsibai Gattu Horti.Plant.GP Dattigaon | Ongoing | 542000 | 0 | 2022-09-29
SARDARPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722002/IF/22012034953742 — Rambhaabai Jhitra GP Dattigaon | Ongoing | 216000 | 0 | 2022-03-28
SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722002/IF/22012035258780 — Valu - Dalla GP Dattigaon Horti. Plantation | Approved | 191848 | 0 | 2024-06-12
SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722002/IF/22012035258783 — Prakash - Kodar GP Dattigaon Horti. Plantation | Approved | 191848 | 0 | 2024-06-12
SARDARPUR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1722002/RC/22012034569739 — GRAVEL MAARG NIRMAN KAARY DATTIGAANW SE BHATIYABARDI SIMA TAK DATTIGAANW | Ongoing | 6310000 | 0 | 2021-06-10