## Work List
Exported on: 2026-10-16 13:13:44
Filters applied:
Data source: VBGRAMG
District: DHAR
Block: All
Panchayat: Badlipura
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
TIRLA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1722003024/DP/22012034570862 — Vraksharopan kary main road ki or bardipura gram panchyat badlipura | Ongoing | 409718.19 | 0 | 2024-08-27
TIRLA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1722003024/DP/22012034619656 — पोधा रोपण कार्य शांतिधाम के पास ग्राम पंचायत बादलीपुरा | Approved | 0 | 0 | 2024-06-10
TIRLA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Sericulture- in Fields-Community / Block Plantation of Sericulture Trees in fields for Community | Plantation | 1722003024/DP/22012034628865 — Nirmal neer kup chokidar awar gram sulibardi gram panchayat badlipura | Physically Completed | 588165.42 | 33577.6 | 2025-03-06 | 2026-09-08
TIRLA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in fields for Community | Plantation | 1722003024/DP/22012034628866 — Nirmal neer kup dhansingh ke awar me gram bichhubardi gram panchayat badlipura | Ongoing | 588165.42 | 0 | 2025-09-28
TIRLA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in fields for Community | Plantation | 1722003024/DP/22012034628903 — Nirmal neer kup bajad awar gram panchayat badlipura | Ongoing | 588165.42 | 36000 | 2025-05-30
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722003024/IF/22012035417997 — kapildhara kup fulsingh jaamsingh gram panchayat badlipura | Approved | 286694.96 | 0 | 2025-04-05
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722003024/IF/22012035418378 — Kkapildhara kup Amarsingh Gulsingh gram panchayat badlipura | Approved | 286694.96 | 0 | 2025-04-05
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722003024/IF/22012035418443 — kapildhara kup richa bai Gulsingh Bicchubrdigam panchayat badlipura | Ongoing | 286694.96 | 19500 | 2026-02-16
TIRLA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1722003024/IF/22012035420990 — जल गंगा संवर्धन गुलसिंह अमरसिंह DugWell रिजार्चपीट बिच्‍छुबयडी | Ongoing | 25177.32 | 0 | 2025-05-17
TIRLA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1722003024/IF/22012035421133 — जल गंगा संवर्धन कैलाश बाला DugWell रिजार्चपीट बडलीपुरा | Physically Completed | 25177.32 | 0 | 2025-05-10 | 2026-07-22
TIRLA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1722003024/IF/22012035485803 — JGSA DUGWELL RECHARGE PIT Cokidar awar | Physically Completed | 25899.46 | 0 | 2025-05-10 | 2026-09-08
TIRLA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1722003024/IF/22012035485819 — JGSA DUGWELL RECHARGE PIT Banjara awar | Physically Completed | 25899.46 | 0 | 2025-05-10 | 2026-09-08
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722003024/IF/22012035533078 — kapildhara kup Gulsingh rukhaji gram bhichubardi gram panchayat badalipura | New | 0 | 0 | 2025-05-05
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722003024/IF/22012035582129 — Kapildhara kup Richhabai Gulsingh badlipura | New | 0 | 0 | 2025-04-01
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722003024/IF/22012035582422 — Kapildhara kup Amarsingh Gulsingh | Approved | 0 | 0 | 2025-04-01
TIRLA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003024/IF/IAY/4219128 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100867174 | Completed | 23490 | 0 | 2022-07-30 | 2026-09-29
TIRLA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003024/IF/IAY/4532155 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100683474 | Completed | 23490 | 0 | 2024-10-29 | 2026-07-22
TIRLA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003024/IF/IAY/4532802 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100812379 | Ongoing | 27000 | 0 | 2024-09-25
TIRLA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003024/IF/IAY/4532824 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100815390 | Physically Completed | 23490 | 0 | 2024-10-29 | 2026-08-04
TIRLA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003024/IF/IAY/4533093 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100974092 | Completed | 27000 | 0 | 2024-10-15 | 2026-09-29
TIRLA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003024/IF/IAY/4533285 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100849457 | Completed | 23490 | 0 | 2024-10-15 | 2026-07-22
TIRLA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003024/IF/IAY/4533299 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100851164 | Completed | 23490 | 0 | 2024-10-29 | 2026-07-25
TIRLA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003024/IF/IAY/4533636 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP101138256 | Physically Completed | 23490 | 8100 | 2024-10-29 | 2026-08-24
TIRLA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003024/IF/IAY/4534199 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102129977 | Ongoing | 27000 | 0 | 2024-09-25
TIRLA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003024/IF/IAY/4534232 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102138725 | Completed | 27000 | 0 | 2024-10-15 | 2026-09-29
TIRLA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003024/IF/IAY/4539795 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105266111 | Completed | 23490 | 0 | 2024-12-02 | 2026-07-25
TIRLA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003024/IF/IAY/4647556 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141596331 | Completed | 27000 | 10200 | 2024-10-29 | 2026-09-17
TIRLA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003024/IF/IAY/4652841 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145872181 | Completed | 23490 | 0 | 2024-10-15 | 2026-07-22
TIRLA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003024/IF/IAY/4656638 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147844514 | Completed | 23490 | 8100 | 2024-10-29 | 2026-10-12
TIRLA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003024/IF/IAY/4658716 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148619707 | Physically Completed | 23490 | 0 | 2024-09-25 | 2026-08-04
TIRLA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003024/IF/IAY/4660535 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148235850 | Completed | 23490 | 0 | 2024-10-15 | 2026-07-25
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003024/IF/IAY/4684789 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP101012455 | Completed | 23490 | 0 | 2025-04-19 | 2026-07-22
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003024/IF/IAY/4793654 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146836604 | Completed | 23490 | 0 | 2025-04-11 | 2026-09-17
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003024/IF/IAY/5150541 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105229849 | Physically Completed | 23490 | 0 | 2025-04-11 | 2026-08-04
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003024/IF/IAY/5154151 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102276697 | Completed | 27000 | 10200 | 2025-04-11 | 2026-09-17
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003024/IF/IAY/5169882 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP101011820 | Ongoing | 27000 | 12300 | 2025-04-11
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003024/IF/IAY/5180802 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146786674 | Ongoing | 27000 | 0 | 2025-04-19
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003024/IF/IAY/5182973 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146845067 | Ongoing | 27000 | 2100 | 2025-04-11
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003024/IF/IAY/5197716 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100972109 | Completed | 23490 | 0 | 2025-04-11 | 2026-07-25
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003024/IF/IAY/5212751 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100845359 | Completed | 23490 | 0 | 2025-04-11 | 2026-07-22
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003024/IF/IAY/5214700 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100902651 | Physically Completed | 23490 | 0 | 2025-04-11 | 2026-08-04
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003024/IF/IAY/5217446 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105447900 | Completed | 23490 | 0 | 2025-04-11 | 2026-09-17
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003024/IF/IAY/5221669 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102138172 | Physically Completed | 23490 | 0 | 2025-08-13 | 2026-08-04
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003024/IF/IAY/5227935 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102096678 | Completed | 23490 | 8100 | 2025-08-13 | 2026-09-17
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003024/IF/IAY/5241464 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100848454 | Ongoing | 27000 | 4200 | 2025-04-11
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003024/IF/IAY/5352600 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102277829 | Completed | 27000 | 8100 | 2025-04-11 | 2026-09-17
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003024/IF/IAY/5431088 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105466322 | Completed | 23490 | 0 | 2025-08-20 | 2026-07-22
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003024/IF/IAY/5486980 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146799764 | Ongoing | 27000 | 4200 | 2025-08-13
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003024/IF/IAY/5621255 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102369142 | Completed | 23490 | 0 | 2025-08-13 | 2026-07-25
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003024/IF/IAY/5622043 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145893535 | Physically Completed | 23490 | 0 | 2025-08-13 | 2026-08-04
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003024/IF/IAY/5694576 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146842200 | Completed | 23490 | 0 | 2025-09-17 | 2026-07-25
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003024/IF/IAY/5807143 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104024747 | Completed | 23490 | 0 | 2025-09-17 | 2026-10-10
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003024/IF/IAY/5807361 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100902255 | Physically Completed | 27000 | 0 | 2025-09-17 | 2026-09-13
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003024/IF/IAY/5807368 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP101011695 | Completed | 23490 | 0 | 2025-09-17 | 2026-07-22
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003024/IF/IAY/5808187 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147746070 | Completed | 23490 | 0 | 2025-09-17 | 2026-09-17
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003024/IF/IAY/5808417 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102664160 | Completed | 27000 | 0 | 2025-09-17 | 2026-09-29
TIRLA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003024/IF/IAY/5855587 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115058486 | Ongoing | 27000 | 0 | 2026-05-09
TIRLA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003024/IF/IAY/5855633 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145887843 | Ongoing | 27000 | 0 | 2026-05-09
TIRLA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003024/IF/IAY/5855865 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP101012538 | Physically Completed | 23490 | 0 | 2026-05-09 | 2026-08-04
TIRLA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003024/IF/IAY/5856124 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102353733 | Completed | 27000 | 0 | 2026-05-09 | 2026-09-29
TIRLA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003024/IF/IAY/5856197 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106164008 | Completed | 27000 | 0 | 2026-05-09 | 2026-09-29
TIRLA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003024/IF/IAY/5856316 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146831671 | Completed | 23490 | 0 | 2026-05-09 | 2026-09-29
TIRLA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003024/IF/IAY/5856318 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146833280 | Ongoing | 27000 | 0 | 2026-05-09
TIRLA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1722003024/RS/22012034535962 — SBM SSP/SLP BADLIPURA | Ongoing | 290680.04 | 0 | 2021-10-03
TIRLA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722003024/WC/22012035247772 — तालाब निर्माण कार्य कड़ी वाले नाले पर ग्राम सेमलीपुरा ग्राम पंचायत बादलीपुरा | Ongoing | 1483152.17 | 309872.04 | 2026-08-09
TIRLA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722003024/WC/22012035275080 — तालाब निर्माण कार्य जामुन वाले नाले पर ग्राम सेमलीपुरा ग्राम पंचायत बदलीपुर | Approved | 776656.82 | 0 | 2025-04-13
TIRLA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722003024/WC/22012035275094 — तालाब निर्माण कार्य टेमरू वाले नाले पर ग्राम सेमलीपुरा ग्राम पंचायत बदलीपुर | Approved | 765775.07 | 0 | 2025-04-05
TIRLA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Rejuvenation of Pond for Community | Repair & maint of Pond/ Tank | 1722003024/WH/22012034939606 — Nammami gange sarvjanik payjal koop jirnodhar kary gram panchayat badlipura | Approved | 0 | 0 | 2024-06-02
TIRLA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Rejuvenation of Pond for Community | Repair & maint of Pond/ Tank | 1722003024/WH/22012034939607 — Nammami gange sarvjanik payjal koop jirnodhar kundiya wala jhira | Approved | 0 | 0 | 2024-06-02
TIRLA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Rejuvenation of Pond for Community | Repair & maint of Pond/ Tank | 1722003024/WH/22012034939625 — Nammami gange saskiy koop gram panchayat badlipura | Approved | 0 | 0 | 2024-06-02