## Work List
Exported on: 2026-09-03 02:35:37
Filters applied:
Data source: VBGRAMG
District: DHAR
Block: All
Panchayat: Chhota Umriya
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
TIRLA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1722003032/DP/22012034612347 — Nirmal neer kup girwal mohalle me gram panchayat chotaumariya | Ongoing | 537251.35 | 0 | 2024-03-11
TIRLA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1722003032/DP/22012034612348 — Nirmal neer kup dhaman wala jhira gram panchayat chotaumariya | Ongoing | 537251.35 | 0 | 2025-01-03
TIRLA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722003032/IF/22012035238602 — Kapildhara kup popdiya thawariya gram panchayat Chhota umariya | Ongoing | 278103.77 | 0 | 2025-03-05
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722003032/IF/22012035238604 — Kapildhara kup nabbu Bai raliya gram panchayat Chhota umariya | Ongoing | 278103.77 | 0 | 2025-04-01
TIRLA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722003032/IF/22012035293771 — कपिलधारा कूप पोपडिया भोलिया छोटाउमरिया | Approved | 286694.96 | 0 | 2024-10-02
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722003032/IF/22012035293774 — कपिलधारा कूप रामचंदर गबुरिया छोटाउमरिया | Ongoing | 286694.96 | 1800 | 2025-05-09
TIRLA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722003032/IF/22012035308787 — KAPILDHARA KUP KISHAN TOLARAM CHOUTAUMARIYA | Approved | 286694.96 | 0 | 2025-01-26
TIRLA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722003032/IF/22012035308790 — KAPILDHARA KUP TOLARAM SOBHARAM CHOUTAUMARIYA | Approved | 286694.96 | 0 | 2025-01-26
TIRLA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722003032/IF/22012035308793 — KAPILDHARA KUP VELSINGH MULIYA CHOUTAUMARIYA | Approved | 286694.96 | 0 | 2025-01-26
TIRLA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722003032/IF/22012035308796 — KAPILDHARA KUP METABSINGH FULCHAND CHOUTAUMARIYA | Approved | 286694.96 | 0 | 2025-01-26
TIRLA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1722003032/IF/22012035355590 — जल गंगा संवर्धन के अन्तर्गत रिचार्ज पीट निर्माण कार्य कालीबाई वेलसिंहके कपिलधारा के पास छोटा उमरि | Ongoing | 25177.32 | 0 | 2025-04-24
TIRLA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1722003032/IF/22012035355943 — जल गंगा संवर्धन के अन्तर्गत रिचार्ज पीट निर्माण कार्य खुमान भुलया के कपिलधारा के पास छोटा उमरि | Approved | 25177.32 | 0 | 2025-04-05
TIRLA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1722003032/IF/22012035483955 — JGSA DUGWELL RECHARGE PIT Kisan tolarram | Ongoing | 25899.46 | 0 | 2025-05-12
TIRLA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1722003032/IF/22012035484010 — JGSA DUGWELL RECHARGE PIT Velsingh | New | 0 | 0 | 2025-04-14
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722003032/IF/22012035564458 — कपिलधारा कूप अमरू नागरिया छोटा उमरिया | Approved | 0 | 0 | 2025-04-01
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/5277504 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147773646 | Completed | 23490 | 0 | 2025-05-22 | 2026-07-22
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/5284509 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104925169 | Completed | 23490 | 0 | 2025-05-16 | 2026-07-22
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/5295753 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105849711 | Completed | 23490 | 0 | 2025-04-20 | 2026-07-22
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/5300513 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105849048 | Completed | 23490 | 0 | 2025-04-15 | 2026-07-22
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/5322126 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115941324 | Completed | 23490 | 0 | 2025-09-18 | 2026-07-22
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/5322913 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105477048 | Completed | 23490 | 0 | 2025-04-07 | 2026-07-22
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/5333702 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114021814 | Completed | 23490 | 0 | 2025-04-15 | 2026-07-22
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/5446227 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104928567 | Physically Completed | 23490 | 0 | 2025-09-29 | 2026-08-24
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/5538015 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114728055 | Completed | 23490 | 0 | 2025-05-16 | 2026-07-22
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/5538392 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105588815 | Completed | 23490 | 0 | 2025-07-03 | 2026-09-02
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/5603123 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113941695 | Physically Completed | 23490 | 0 | 2025-05-16 | 2026-07-29
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/5694139 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106599015 | Completed | 23490 | 0 | 2025-08-11 | 2026-07-22
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/5723573 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104921090 | Completed | 23490 | 0 | 2025-09-29 | 2026-07-22
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/5807634 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122000667 | Physically Completed | 27000 | 0 | 2025-09-18 | 2026-09-02
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/5807862 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106066960 | Completed | 23490 | 0 | 2025-12-10 | 2026-07-22
TIRLA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/5885940 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105849009 | Completed | 23490 | 4500 | 2026-04-22 | 2026-09-02
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/5885988 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105577481 | Physically Completed | 23490 | 4500 | 2026-03-13 | 2026-07-19
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/5886052 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105848786 | Physically Completed | 23490 | 9000 | 2026-03-13 | 2026-08-24
TIRLA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/5886056 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114020772 | Ongoing | 27000 | 4500 | 2026-07-19
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/5886063 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114096456 | Completed | 23490 | 0 | 2026-03-13 | 2026-07-22
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/5886066 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115941580 | Ongoing | 27000 | 0 | 2026-03-13
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/5886086 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114075731 | Physically Completed | 23490 | 4500 | 2026-03-13 | 2026-08-04
TIRLA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/5886098 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115277407 | Ongoing | 27000 | 0 | 2026-07-22
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/5886113 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115942220 | Ongoing | 27000 | 4500 | 2026-03-13
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/5886132 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147645821 | Ongoing | 27000 | 0 | 2026-03-13
TIRLA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/5886206 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113940564 | Completed | 23490 | 0 | 2026-04-22 | 2026-07-22
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/5886212 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147563797 | Physically Completed | 23490 | 0 | 2026-03-13 | 2026-08-24
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/5886296 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148178164 | Approved | 27000 | 0 | 2026-02-05
TIRLA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/5886300 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114682406 | Completed | 23490 | 0 | 2026-04-22 | 2026-07-22
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/5886328 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147752727 | Completed | 23490 | 0 | 2026-03-13 | 2026-07-22
TIRLA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/5886374 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147765352 | Ongoing | 27000 | 0 | 2026-07-19
TIRLA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/5886402 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113630721 | Completed | 23490 | 0 | 2026-04-22 | 2026-07-22
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/5886429 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147781581 | Physically Completed | 23490 | 0 | 2026-03-13 | 2026-08-04
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/5886456 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114681573 | Physically Completed | 23490 | 0 | 2026-03-13 | 2026-08-04
TIRLA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/5886507 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148560628 | Ongoing | 27000 | 0 | 2026-04-22
TIRLA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/5886508 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114022522 | Ongoing | 27000 | 0 | 2026-07-19
TIRLA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/5886561 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147149640 | Completed | 23490 | 0 | 2026-04-22 | 2026-07-22
TIRLA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/5886588 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114068650 | Ongoing | 27000 | 0 | 2026-04-22
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/5886603 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113900348 | Physically Completed | 23490 | 0 | 2026-03-13 | 2026-08-04
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/5886676 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113900255 | Physically Completed | 23490 | 2100 | 2026-03-13 | 2026-08-24
TIRLA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/5886724 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149541136 | Completed | 23490 | 0 | 2026-04-22 | 2026-07-22
TIRLA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/5886747 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147709638 | Ongoing | 27000 | 0 | 2026-04-22
TIRLA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/5886748 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105849121 | Ongoing | 27000 | 0 | 2026-04-22
TIRLA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/5886749 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113941395 | Completed | 27000 | 0 | 2026-04-22 | 2026-09-02
TIRLA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/6118054 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113941287 | Ongoing | 27000 | 0 | 2026-06-17
TIRLA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/6118251 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106599054 | Ongoing | 27000 | 0 | 2026-07-22
TIRLA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/6120247 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104932142 | Ongoing | 27000 | 0 | 2026-06-17
TIRLA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/6122644 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114958046 | Ongoing | 27000 | 0 | 2026-06-17
TIRLA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/6123332 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114959508 | Ongoing | 27000 | 0 | 2026-06-17
TIRLA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/6124393 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115127072 | Ongoing | 27000 | 0 | 2026-06-17
TIRLA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/6128149 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115941361 | Ongoing | 27000 | 0 | 2026-08-29
TIRLA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/6128151 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115941411 | Ongoing | 27000 | 0 | 2026-07-19
TIRLA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/6129460 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105997316 | Physically Completed | 23490 | 0 | 2026-06-17 | 2026-08-16
TIRLA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/6129861 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121999995 | Ongoing | 27000 | 0 | 2026-06-17
TIRLA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/6130328 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148153745 | Ongoing | 27000 | 0 | 2026-06-17
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/6134177 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114072031 | Approved | 27000 | 0 | 2026-03-21
TIRLA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/6135881 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113806704 | Ongoing | 27000 | 0 | 2026-07-22
TIRLA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/6137207 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147718705 | Ongoing | 27000 | 0 | 2026-07-19
TIRLA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/6139398 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115947797 | Ongoing | 27000 | 0 | 2026-06-17
TIRLA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/6141651 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148151427 | Physically Completed | 27000 | 0 | 2026-05-05 | 2026-09-02
TIRLA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/6143701 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147175063 | Ongoing | 27000 | 0 | 2026-06-17
TIRLA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/6145285 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149559493 | Completed | 23490 | 0 | 2026-05-05 | 2026-07-22
TIRLA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/6145763 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117401035 | Ongoing | 27000 | 0 | 2026-07-19
TIRLA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/6153014 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147778417 | Ongoing | 27000 | 0 | 2026-08-29
TIRLA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/6153334 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149518651 | Ongoing | 27000 | 0 | 2026-08-29
TIRLA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/6154999 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149567172 | Completed | 23490 | 0 | 2026-05-05 | 2026-07-22
TIRLA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/6155003 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149578041 | Ongoing | 27000 | 0 | 2026-06-17
TIRLA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/6157920 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106019367 | Physically Completed | 23490 | 0 | 2026-07-19 | 2026-08-16
TIRLA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/6159657 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148835296 | Ongoing | 27000 | 0 | 2026-06-17
TIRLA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/6159824 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114683353 | Ongoing | 27000 | 0 | 2026-06-17
TIRLA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/6159825 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114683871 | Ongoing | 27000 | 0 | 2026-07-22
TIRLA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/6164752 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113935765 | Completed | 23490 | 0 | 2026-05-05 | 2026-07-22
TIRLA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/6164756 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105565687 | Ongoing | 27000 | 0 | 2026-07-19
TIRLA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/6164757 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147572279 | Ongoing | 27000 | 0 | 2026-06-17
TIRLA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/6164953 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113940436 | Ongoing | 27000 | 0 | 2026-08-29
TIRLA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/6168721 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105848951 | Ongoing | 27000 | 0 | 2026-06-17
TIRLA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/6168799 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113975059 | Completed | 23490 | 0 | 2026-05-05 | 2026-07-22
TIRLA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/6169616 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145668173 | Ongoing | 27000 | 0 | 2026-06-17
TIRLA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/6173557 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147779965 | Ongoing | 27000 | 0 | 2026-08-29
TIRLA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/6173829 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114022397 | Ongoing | 27000 | 0 | 2026-06-17
TIRLA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722003032/IF/IAY/6175698 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106598717 | Ongoing | 27000 | 0 | 2026-06-17
TIRLA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1722003032/WC/22012035230961 — KUNDALWALA NALA NIRMAN KARYA UMRIYA CHHOTA | Approved | 0 | 0 | 2024-04-01
TIRLA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1722003032/WC/22012035230962 — NISTAR TALAB VIKRAM KE KHET KE PAAS UMRIYA CHHOTA | Approved | 0 | 0 | 2024-04-01
TIRLA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722003032/WC/22012035233907 — तालाब निर्माण कार्य विक्रम के खेत के पास ग्राम पंचायत छोटा उमरिया | Approved | 0 | 0 | 2024-11-01
TIRLA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722003032/WC/22012035233908 — तालाब निर्माण कार्य कुंडल वाले नाले पर ग़म पंचायत छोटा उमरिया | Approved | 0 | 0 | 2024-11-01
TIRLA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722003032/WC/22012035247771 — तालाब निर्माण कार्य कालू मेडा के खेतके पास वाले नाले पर ग्राम पंचायत छोटा उमरिया | Approved | 0 | 0 | 2025-01-01
TIRLA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1722003032/WC/22012035267512 — जल गंगा संवर्धन के अन्तर्गत रिचार्ज पीट निर्माण कार्य बावड़ी झिरी वाले नाले पर ग्राम पंचायत छोउमरि | Approved | 25177.32 | 0 | 2025-04-05
TIRLA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722/WC/22012035316386 — nistar talab nirman kary babul vala nala | Ongoing | 3945000 | 0 | 2026-05-09
TIRLA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722/WC/22012035316390 — nistar talab nirman kary jamun vala nala | Ongoing | 3986000 | 0 | 2026-05-09