## Work List
Exported on: 2026-10-27 06:18:41
Filters applied:
Data source: VBGRAMG
District: DHAR
Block: All
Panchayat: Mafipura
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
TIRLA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound Wall for Government School for Community | Constr of Compound wall | 1722003041/AV/22012034571655 — Boundarywall nirman kary govt Middle school Mafipura | Physically Completed | 656581.35 | 0 | 2021-08-28 | 2026-09-09
TIRLA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1722003041/DP/22012034574800 — nirmal nir cup asharam ke khet ke pass gram panchyat mafipura | Ongoing | 527035.48 | 0 | 2023-05-08
TIRLA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1722003041/DP/22012034616061 — Nirmal neer kup onkar gangaram ke khet ke pass gram mafipura gram panchayat mafipura | Ongoing | 537251.35 | 0 | 2024-03-16
TIRLA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Agro Forestry Block Plantation for Individual | Plantation | 1722003041/IF/22012034648162 — नंदन फलोउघ्यान भगवानसिह पिता रामा | Ongoing | 185000 | 0 | 2021-08-11
TIRLA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1722003041/IF/22012035348778 — (j.g.s.a) के अंतर्गत रिचार्ज पीट शहनाज़ लालका के कुवै के पास ग्राम पंचायत माफीपुरा | New | 0 | 0 | 2025-04-05
TIRLA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1722003041/IF/22012035353131 — जल गंगा संवर्धन के अन्तर्गत रिचार्ज पीट निर्माण कार्य भवरसिंह धन्ना के कपिलधारा के पास माफीपुरा | Approved | 25177.32 | 0 | 2025-04-05
TIRLA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1722003041/IF/22012035353169 — जल गंगा संवर्धन के अन्तर्गत रिचार्ज पीट निर्माण कार्य माडिया सेकड़िया के कपिलधारा के पास mafipura | Approved | 25177.32 | 0 | 2025-04-05
TIRLA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1722003041/IF/22012035353200 — जल गंगा संवर्धन के अन्तर्गत रिचार्ज पीट निर्माण कार्य शहनाज़ लालखा के क पिलधारा के पास माफीपुरा | Approved | 25176.75 | 0 | 2025-04-05
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722003041/IF/22012035361633 — kapildhara kup vikram rajaram gram panchayat mafipura | Approved | 286694.96 | 0 | 2025-04-05
TIRLA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1722003041/IF/22012035488428 — JGSA DUGWELL RECHARGE PIT neermal neer puliya ke pass | Approved | 25899.46 | 0 | 2025-04-01
TIRLA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1722003041/IF/22012035489604 — jgsa duge well reacharge pit nirmal nir bhilala awar | Approved | 25899.46 | 0 | 2025-04-05
TIRLA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1722003041/IF/22012035489625 — jgsa duge well reacharge pit nirmal nir damra awar | Approved | 25899.46 | 0 | 2025-04-05
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1722003041/IF/22012035490819 — JGSA के अन्तर्गत के खेत तालाब कमल केखेत पर पास ग्राम पंचायत माफीपुरा | Ongoing | 354200.84 | 0 | 2025-05-09
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1722003041/IF/22012035490826 — JGSA के अन्तर्गत के खेत तालाब अंबाराम खेत पर ग्राम पंचायत माफीपुरा | Ongoing | 354200.84 | 0 | 2025-05-09
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722003041/IF/22012035531277 — kapildhara kup Arjun bhawsigh gram panchayat mafipura | Approved | 286694.96 | 0 | 2025-04-05
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722003041/IF/22012035549640 — kapildhara kup mulsingh mittu gram panchayat mafipura | Approved | 286694.96 | 0 | 2025-05-15
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1722003041/IF/22012035633511 — khet talab nirman kary sanju Ratan gram panchayat mafipura | Ongoing | 199777.47 | 0 | 2025-12-15
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1722003041/IF/22012035633526 — khet talab nirman kary Rameshwar Kaliya gram panchayat Mafipura | Ongoing | 199777.47 | 0 | 2025-12-29
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1722003041/IF/22012035633536 — khet talab nirman kary Rawsingh Somilya gram panchayat Mafipura | Ongoing | 199777.47 | 0 | 2025-12-29
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1722003041/IF/22012035633545 — khet talab nirman kary indarsingh mukesh gram panchayat Mafipura | Ongoing | 199777.47 | 0 | 2026-01-12
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1722003041/IF/22012035633789 — khet talab rajusingh sarkar gram panchayat mafipura | Ongoing | 199777.47 | 0 | 2026-01-12
TIRLA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1722003041/IF/IAY/196616 — Construction of IAY House -IAY REG. NO. MP-22-003-041-001/30 | Completed | 23490 | 0 | 2026-05-14 | 2026-07-22
TIRLA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003041/IF/IAY/3677646 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105063700 | Approved | 27000 | 0 | 2022-04-29
TIRLA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003041/IF/IAY/4543222 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105048343 | Completed | 23490 | 0 | 2025-02-25 | 2026-07-27
TIRLA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003041/IF/IAY/4550662 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107054862 | Completed | 23490 | 0 | 2024-09-27 | 2026-07-27
TIRLA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003041/IF/IAY/4557462 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114139212 | Completed | 23490 | 0 | 2024-09-27 | 2026-07-27
TIRLA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003041/IF/IAY/4670363 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107081745 | Completed | 23490 | 0 | 2024-09-27 | 2026-07-27
TIRLA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003041/IF/IAY/4690998 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113680037 | Completed | 23490 | 0 | 2024-11-01 | 2026-07-22
TIRLA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003041/IF/IAY/4696211 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114215330 | Completed | 23490 | 0 | 2024-11-19 | 2026-08-04
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003041/IF/IAY/5154808 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123452400 | Completed | 23490 | 0 | 2025-05-07 | 2026-08-04
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003041/IF/IAY/5163468 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116841578 | Completed | 23490 | 0 | 2025-04-10 | 2026-08-04
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003041/IF/IAY/5174716 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115745994 | Completed | 23490 | 0 | 2025-04-10 | 2026-07-22
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003041/IF/IAY/5220088 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113905943 | Ongoing | 27000 | 0 | 2025-04-10
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003041/IF/IAY/5486791 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114153241 | Completed | 23490 | 0 | 2025-06-16 | 2026-07-27
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003041/IF/IAY/5486794 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114140314 | Completed | 23490 | 0 | 2025-04-25 | 2026-07-27
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003041/IF/IAY/5487275 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117734625 | Completed | 23490 | 0 | 2025-05-21 | 2026-08-04
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003041/IF/IAY/5487768 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113906573 | Completed | 23490 | 0 | 2025-09-01 | 2026-08-04
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003041/IF/IAY/5488429 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116808635 | Completed | 23490 | 0 | 2025-09-09 | 2026-07-22
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003041/IF/IAY/5488432 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113872080 | Completed | 23490 | 0 | 2025-05-20 | 2026-07-27
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003041/IF/IAY/5510671 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123449517 | Completed | 23490 | 0 | 2025-05-20 | 2026-07-27
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003041/IF/IAY/5513799 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113925359 | Completed | 23490 | 0 | 2025-05-20 | 2026-07-27
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003041/IF/IAY/5513819 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115169585 | Completed | 23490 | 0 | 2025-06-16 | 2026-07-22
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003041/IF/IAY/5583538 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114215193 | Completed | 23490 | 0 | 2025-06-16 | 2026-08-04
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003041/IF/IAY/5617635 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106187304 | Approved | 27000 | 0 | 2025-05-06
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003041/IF/IAY/5621938 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117734399 | Ongoing | 27000 | 0 | 2025-06-16
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003041/IF/IAY/5693359 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113904777 | Ongoing | 27000 | 0 | 2025-07-30
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003041/IF/IAY/5693621 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115905722 | Completed | 23490 | 0 | 2025-09-01 | 2026-08-04
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003041/IF/IAY/5697496 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115745686 | Completed | 23490 | 0 | 2025-07-30 | 2026-07-22
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003041/IF/IAY/5711616 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115358500 | Completed | 23490 | 0 | 2025-09-09 | 2026-07-22
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003041/IF/IAY/5803947 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113639536 | Approved | 27000 | 0 | 2025-04-12
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003041/IF/IAY/5813162 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117734664 | Ongoing | 27000 | 4500 | 2025-11-20
TIRLA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003041/IF/IAY/5823587 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114701794 | Physically Completed | 23490 | 0 | 2025-02-15 | 2026-08-16
TIRLA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003041/IF/IAY/5874022 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115361298 | Ongoing | 27000 | 4500 | 2026-09-01
TIRLA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003041/IF/IAY/5874059 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123451590 | Completed | 23490 | 4500 | 2026-06-04 | 2026-08-12
TIRLA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003041/IF/IAY/6155013 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115354186 | Ongoing | 27000 | 4500 | 2026-09-01
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003041/IF/IAY/6167434 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117734710 | Approved | 27000 | 0 | 2026-02-26
TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003041/IF/IAY/6346278 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116807833 | Approved | 27000 | 0 | 2025-04-03
TIRLA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1722003041/WC/22012034831444 — CTRA PERCOLATION TANK BARIWALA NALA | Ongoing | 550088.44 | 0 | 2022-05-24
TIRLA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1722003041/WC/22012034831451 — CTRA PERCOLATION TANK MAFIPURA | Ongoing | 507215.56 | 0 | 2022-05-24
TIRLA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1722003041/WC/22012035017168 — नाला ट्रेंच खजुर वाला नाला | Ongoing | 356246.08 | 23099.23 | 2023-05-31
TIRLA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1722003041/WC/22012035017170 — नाला ट्रेंच कुँए के सामने वाला नाला | Ongoing | 356246.08 | 24000 | 2023-03-03
TIRLA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1722003041/WC/22012035110768 — ctra.parcolation tenk rashul khet k pass mafipura | Ongoing | 609642.67 | 0 | 2024-03-06
TIRLA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1722003041/WC/22012035110781 — ctra.parcolation tenk gotam khet k pass mafipura | Ongoing | 491753.74 | 46198.46 | 2024-03-16
TIRLA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry Check Dam for Community | Construction of Check Dam/Stop Dam | 1722003041/WC/22012035146572 — आरएमएस/चेक डे़म निर्माण - नीमवाला नाला, माफीपुरा | Ongoing | 1485081.11 | 0 | 2023-10-09
TIRLA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry Check Dam for Community | Construction of Check Dam/Stop Dam | 1722003041/WC/22012035146575 — आरएमएस/चेक डे़म निर्माण - आमवाला नाला, माफीपुरा | Ongoing | 1492914.09 | 0 | 2023-10-09
TIRLA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1722003041/WC/22012035200229 — Nammami gange talab jirnodhar kary mehndiya talab par gram panchayat mafipura | Approved | 0 | 0 | 2024-06-02
TIRLA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1722003041/WC/22012035266672 — जल गंगा संवर्धन के अन्तर्गत रिचार्ज पीट निर्माण कार्य निर्मल नीर श्मशान घाट के पास माफीपुरा | Approved | 25177.32 | 0 | 2025-04-05
TIRLA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1722003041/WC/22012035266683 — जल गंगा संवर्धन के अन्तर्गत रिचार्ज पीट निर्माण कार्य निर्मल नीर आम के पास माफीपुरा | Approved | 25321.75 | 0 | 2025-04-05
TIRLA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1722003041/WC/22012035266707 — जल गंगा संवर्धन के अन्तर्गत रिचार्ज पीट निर्माण कार्य निर्मल नीर पुलिया के पास बायड़ी आवर माफीपुरा | Approved | 25177.32 | 0 | 2025-04-05
TIRLA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1722003041/WC/22012035266740 — जल गंगा संवर्धन के अन्तर्गत रिचार्ज पीट निर्माण कार्य निर्मल नीर महेश के खेत के पास माफीपुरा | Approved | 25177.32 | 0 | 2025-04-05
TIRLA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1722003041/WC/22012035276362 — JGSA के अन्तर्गत रिचार्ज पीट निर्मल नीर पुलिया के पास मंदिर अवर ग्राम पंचायत माफीपुरा | Approved | 25177.32 | 0 | 2025-04-10
TIRLA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1722003041/WC/22012035286947 — जल गंगा संवर्धन duge well रिचार्ज पीट निर्मल नीर पुलिया की पास। मंदिर आवर | Approved | 25899.46 | 0 | 2025-04-05
TIRLA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1722003041/WC/22012035286949 — जल गंगा संवर्धन duge well रिचार्ज पीट निर्मल नीर श्मशान घाट के पास माफीपुरा | Approved | 25899.46 | 0 | 2025-04-05
TIRLA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1722003041/WC/22012035286951 — जल गंगा संवर्धन duge well रिचार्ज पीट निर्मल नीर आम के पास माफीपुरा | Approved | 25899.46 | 0 | 2025-04-05
TIRLA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1722003041/WC/22012035286954 — जल गंगा संवर्धन duge well रिचार्ज पीट निर्मल नीर पुलिया के पास बेड़ी आवर माफीपुरा | Approved | 25899.46 | 0 | 2025-04-05
TIRLA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1722003041/WC/22012035286957 — जल गंगा संवर्धन duge well रिचार्ज पीट निर्मल नीर महेश के खेत के पास माफीपुरा | Approved | 25899.46 | 0 | 2025-04-05
TIRLA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722003041/WC/22012035308975 — तालाब निर्माण कार्य सूरज के खेत के पास ग्राम पंचायत माफीपुरा | Approved | 802227.74 | 0 | 2025-05-15
TIRLA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722003041/WC/22012035310163 — तालाब निर्माण कार्य कैलाश के भट्ठे के पास ग्राम पंचायत माफीपुरा | Approved | 860112.14 | 0 | 2025-04-05
TIRLA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722003041/WC/22012035325284 — talab nirman Kary samsan ghat ke niche wale nale par gram panchayat mafipura | Ongoing | 999767.06 | 192900 | 2026-05-15
TIRLA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722003041/WC/22012035326815 — तालाब निर्माण कार्य नाले पर ग्राम पंचायत माफीपुरा | Approved | 990951.54 | 0 | 2026-01-18
TIRLA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722003041/WC/22012035326816 — तालाब निर्माण कार्य ग्राम माफीपुरा ग्राम पंचायत माफीपुरा | New | 0 | 0 | 2026-01-15
TIRLA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722003041/WC/22012035326841 — तालाब निर्माण कार्य ग्राम माफीपुरा ग्राम पंचायत माफीपुरा | Ongoing | 990743.52 | 804071.07 | 2026-05-16