## Work List
Exported on: 2026-10-28 13:07:20
Filters applied:
Data source: VBGRAMG
District: DHAR
Block: All
Panchayat: SADALPUR
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
DHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Construction of Goat Shelter for Community / Construction of Goat Shelter for Community | Goat Shelter | 1722004015/AV/22012034624942 — Goat shed At Gau shala Sadalpur | Physically Completed | 94352.21 | 0 | 2022-11-19 | 2026-08-19
DHAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Farm Forestry-Community / Line Plantation of Forestry Trees for Community | Plantation | 1722004015/DP/22012034535047 — Vrakchharopan Shamshan Road Sadalpur | Ongoing | 371989.84 | 0 | 2022-12-21
DHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Farm Forestry-Community / Line Plantation of Forestry Trees for Community | Plantation | 1722004015/DP/22012034535051 — Vrakchharopan Gau shala Sadalpur | Ongoing | 371989.84 | 2100 | 2021-10-01
DHAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004015/IF/22012035037312 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103536613 | Physically Completed | 18360 | 0 | 2023-08-19 | 2026-08-19
DHAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1722004015/IF/IAY/134982 — Construction of IAY House -IAY REG. NO. MP-22-004-015-004/50 | Physically Completed | 23490 | 0 | 2016-02-03 | 2026-08-09
DHAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1722004015/IF/IAY/199897 — Construction of IAY House -IAY REG. NO. MP-22-004-015-004/233 | Approved | 27000 | 0 | 2016-03-22
DHAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1722004015/IF/IAY/199963 — Construction of IAY House -IAY REG. NO. MP-22-004-015-004/173 | Approved | 27000 | 0 | 2016-03-22
DHAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1722004015/IF/IAY/199964 — Construction of IAY House -IAY REG. NO. MP-22-004-015-004/234 | Approved | 27000 | 0 | 2016-03-22
DHAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1722004015/IF/IAY/200123 — Construction of IAY House -IAY REG. NO. MP-22-004-015-004/168 | Approved | 27000 | 0 | 2016-03-22
DHAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004015/IF/IAY/3804882 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105347214 | Ongoing | 27000 | 0 | 2024-01-30
DHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004015/IF/IAY/3831073 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116754139 | Approved | 27000 | 0 | 2022-05-03
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004015/IF/IAY/3877500 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145651342 | Ongoing | 27000 | 0 | 2025-07-28
DHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004015/IF/IAY/3893096 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147801552 | Approved | 27000 | 0 | 2022-05-03
DHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004015/IF/IAY/4543350 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105334938 | Ongoing | 27000 | 0 | 2025-03-02
DHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004015/IF/IAY/4543381 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105341548 | Ongoing | 27000 | 0 | 2025-03-02
DHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004015/IF/IAY/4543417 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105346547 | Completed | 23490 | 0 | 2025-02-05 | 2026-07-19
DHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004015/IF/IAY/4543429 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105348784 | Ongoing | 27000 | 0 | 2025-03-02
DHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004015/IF/IAY/4551815 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113504356 | Ongoing | 27000 | 0 | 2025-02-05
DHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004015/IF/IAY/4556015 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113787619 | Completed | 23490 | 0 | 2025-02-26 | 2026-07-19
DHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004015/IF/IAY/4568878 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116753160 | Ongoing | 27000 | 0 | 2025-02-26
DHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004015/IF/IAY/4651118 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143713703 | Completed | 23490 | 0 | 2025-03-02 | 2026-07-19
DHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004015/IF/IAY/4651833 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144702015 | Ongoing | 27000 | 0 | 2025-02-05
DHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004015/IF/IAY/4652074 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146264491 | Ongoing | 27000 | 0 | 2024-10-04
DHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004015/IF/IAY/4656916 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147319397 | Completed | 23490 | 0 | 2025-02-12 | 2026-07-19
DHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004015/IF/IAY/4659043 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147661754 | Completed | 23490 | 0 | 2025-02-26 | 2026-07-19
DHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004015/IF/IAY/4690835 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113787964 | Approved | 27000 | 0 | 2024-09-19
DHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004015/IF/IAY/4736861 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105346766 | Physically Completed | 23490 | 1800 | 2025-02-05 | 2026-08-03
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004015/IF/IAY/5211034 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113787507 | Ongoing | 27000 | 11400 | 2026-02-09
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004015/IF/IAY/5301541 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105348481 | Physically Completed | 23490 | 3000 | 2025-07-28 | 2026-08-19
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004015/IF/IAY/5388218 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103537806 | Approved | 27000 | 0 | 2025-04-03
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004015/IF/IAY/5420201 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113504469 | Ongoing | 27000 | 0 | 2025-10-30
DHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004015/IF/IAY/5420952 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146570220 | Ongoing | 27000 | 5400 | 2026-08-14
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004015/IF/IAY/5420977 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113526575 | Ongoing | 27000 | 0 | 2025-07-28
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004015/IF/IAY/5422176 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105343611 | Ongoing | 27000 | 16200 | 2025-07-16
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004015/IF/IAY/5422610 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105335764 | Completed | 23490 | 0 | 2025-07-28 | 2026-08-10
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004015/IF/IAY/5422673 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143727970 | Ongoing | 27000 | 0 | 2025-07-28
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004015/IF/IAY/5515474 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144155479 | Completed | 23490 | 0 | 2025-05-31 | 2026-08-19
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004015/IF/IAY/5518813 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105340713 | Approved | 27000 | 0 | 2025-04-19
DHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004015/IF/IAY/5521418 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147814156 | Ongoing | 27000 | 7200 | 2026-08-14
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004015/IF/IAY/5521641 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103540842 | Approved | 27000 | 0 | 2025-04-19
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004015/IF/IAY/5527405 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113527015 | Ongoing | 27000 | 11100 | 2025-07-16
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004015/IF/IAY/5558370 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113563297 | Ongoing | 27000 | 0 | 2025-07-28
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004015/IF/IAY/5559472 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113787461 | Physically Completed | 27000 | 0 | 2025-04-19 | 2026-10-04
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004015/IF/IAY/5579408 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147558870 | Approved | 27000 | 0 | 2025-04-21
DHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004015/IF/IAY/5644093 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116752390 | Ongoing | 27000 | 4200 | 2026-09-30
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004015/IF/IAY/5657529 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143729554 | Approved | 27000 | 0 | 2025-05-22
DHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004015/IF/IAY/5658857 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113525722 | Physically Completed | 27000 | 0 | 2026-10-17 | 2026-10-25
DHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004015/IF/IAY/5693629 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113504451 | Approved | 27000 | 0 | 2024-09-14
DHAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1722004015/IF/IAY/58996 — Construction of IAY House -IAY REG. NO. MP-22-004-015-004/32 | Approved | 27000 | 0 | 2015-12-07
DHAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1722004015/IF/IAY/58998 — Construction of IAY House -IAY REG. NO. MP-22-004-015-004/37 | Approved | 27000 | 0 | 2015-12-07
DHAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1722004015/IF/IAY/59001 — Construction of IAY House -IAY REG. NO. MP-22-004-015-004/40 | Approved | 27000 | 0 | 2015-12-07
DHAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1722004015/IF/IAY/59016 — Construction of IAY House -IAY REG. NO. MP-22-004-015-004/79 | Approved | 27000 | 0 | 2015-12-07
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004015/IF/IAY/6117950 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105342501 | Approved | 27000 | 0 | 2026-02-26
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004015/IF/IAY/6118463 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144171997 | Approved | 27000 | 0 | 2026-02-26
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004015/IF/IAY/6118744 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105348249 | Approved | 27000 | 0 | 2026-02-26
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004015/IF/IAY/6119801 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116753882 | Approved | 27000 | 0 | 2026-02-26
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004015/IF/IAY/6120532 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105336027 | Approved | 27000 | 0 | 2026-02-26
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004015/IF/IAY/6122493 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113787233 | Approved | 27000 | 0 | 2026-02-26
DHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004015/IF/IAY/6414323 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144176133 | Approved | 27000 | 0 | 2025-03-04
DHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004015/IF/IAY/6421294 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105339676 | Approved | 27000 | 0 | 2025-03-02
DHAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1722004015/IF/IAY/67616 — Construction of IAY House -IAY REG. NO. MP-22-004-015-004/53 | Approved | 27000 | 0 | 2015-12-07
DHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Construction of Drainage Works in Waterlogged Land for Community | Land Development | 1722004015/LD/22012034535801 — Charagah Goushala k pas Sadalpur | Ongoing | 792213.45 | 3000 | 2021-04-09
DHAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1722004015/RC/22012034821540 — single coat CC road kushwaha dharam shala se lakshminarayan mandir | New | 0 | 0 | 2024-07-04
DHAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1722004015/RC/22012034821541 — single coat CC road kushwaha dharam shala se lakshminarayan mandir | Approved | 0 | 0 | 2024-07-04
DHAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1722004015/RC/22012034821859 — CC road nirman jal mahal /shamshan ke pas | Approved | 0 | 0 | 2024-06-07
DHAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1722004015/RC/22012034827782 — CC road nirman kushwah dharmshala se lkxminarayan mandir tk sadlpur | Physically Completed | 36000 | 0 | 2024-10-06 | 2026-07-21
DHAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1722004015/RC/22012034827784 — CC road nirman NH se shamshan ghat sadlpur | Physically Completed | 60000 | 300 | 2024-10-09 | 2026-07-21
DHAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1722004015/WC/22012035165866 — Nala trenching karya | New | 0 | 0 | 2024-01-26