## Work List
Exported on: 2026-10-19 00:39:19
Filters applied:
Data source: VBGRAMG
District: DHAR
Block: All
Panchayat: KALSADA KHURD
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004020/IF/IAY/4543252 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105054182 | Ongoing | 27000 | 0 | 2025-04-23
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004020/IF/IAY/4859233 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102147818 | Ongoing | 27000 | 0 | 2025-04-16
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004020/IF/IAY/5196798 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102427365 | Ongoing | 27000 | 12900 | 2025-08-09
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004020/IF/IAY/5202219 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115103972 | Physically Completed | 27000 | 0 | 2025-05-07 | 2026-10-11
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004020/IF/IAY/5216938 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105059600 | Physically Completed | 23490 | 0 | 2025-08-13 | 2026-08-02
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004020/IF/IAY/5218113 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102428010 | Ongoing | 27000 | 16800 | 2025-09-10
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004020/IF/IAY/5227119 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102147032 | Ongoing | 27000 | 1500 | 2025-05-07
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004020/IF/IAY/5555061 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106224095 | Physically Completed | 23490 | 7800 | 2026-01-20 | 2026-08-02
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004020/IF/IAY/5564447 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143739333 | Ongoing | 27000 | 1500 | 2025-08-20
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004020/IF/IAY/5638654 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105056914 | Ongoing | 27000 | 1500 | 2025-08-13
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004020/IF/IAY/5657780 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102427951 | Ongoing | 27000 | 1200 | 2025-09-10
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004020/IF/IAY/5658531 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105058887 | Physically Completed | 23490 | 1827 | 2025-09-22 | 2026-08-11
DHAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1722004020/IF/IAY/82895 — Construction of IAY House -IAY REG. NO. MP-22-004-020-001/016 | Approved | 27000 | 0 | 2015-12-29
DHAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1722004020/IF/IAY/82896 — Construction of IAY House -IAY REG. NO. MP-22-004-020-001/7 | Approved | 27000 | 0 | 2015-12-29
DHAR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1722004020/RC/22012034846753 — CC ROAD PS BHAWAN PRAGAN | Ongoing | 55000 | 40800 | 2025-08-06
DHAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1722004020/WC/22012035165835 — Nala trenching karya | New | 0 | 0 | 2024-01-26