## Work List
Exported on: 2026-10-25 17:48:03
Filters applied:
Data source: MGNREGA
District: DHAR
Block: All
Panchayat: PIPALDA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
DHAR | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1722004032/AV/22012034566323 — BOUNDARY WALL NIRMAN PANCHAYAT PARISAR | Completed | 76000 | 80481 | 2021-08-18 | 2021-10-03
DHAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1722004032/DP/22012034443794 — sarvajnik kup nirman piplda | Closed | 0 | 0 | 2019-01-26
DHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Block Plantation-Horticulture-Community / Along the coast Block Plantation of Horticulture Trees for Community | Plantation | 1722004032/DP/22012034538849 — PLANTATION SHANTI DHAM PIALDA | Closed | 0 | 0 | 2021-09-10
DHAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1722004032/DP/22012034568930 — PLANTATION SHANTIDHAM PIPALDA | Closed | 0 | 0 | 2022-07-25
DHAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1722004032/DP/22012034584422 — VASUDHA VANDAN PLANTATION SHANTIDHAM PIPALDA | Completed | 54564.94 | 24876 | 2023-08-19 | 2026-02-27
DHAR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1722004032/DP/6012 — शांतीवन श्‍मशान पर व़क्षारोपण पिपल्‍दा | Completed | 0 | 16700 | 2010-06-28 | 2011-04-26
DHAR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1722004032/DP/6034 — व़क्षारोपण कार्य पि‍पल्‍दा | Completed | 193000 | 6600 | 2010-08-06 | 2010-08-06
DHAR | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1722004032/IF/1610 — मेंढबंधान देवि‍सि‍ह हरचंद्र | Completed | 0 | 5100 | 2008-07-17 | 2009-01-24
DHAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722004032/IF/22012034339553 — vraksharopan Chogalal Ghisaji | Completed | 335000 | 13254 | 2017-06-02 | 2019-07-24
DHAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722004032/IF/22012034361415 — Vraksharopan Karya Jeevan Patel Pipalda | Completed | 335000 | 1032 | 2017-08-09 | 2019-07-14
DHAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722004032/IF/22012034469155 — varchharopan kary | Closed | 0 | 0 | 2019-01-26
DHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004032/IF/22012035025205 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124821570 | Completed | 18360 | 18156 | 2022-10-09 | 2022-12-20
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722004032/IF/22012035404998 — KHET TALAB NARAYAN DEVCHAND PIPALDA | Ongoing | 147621.16 | 29361 | 2025-05-02
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722004032/IF/22012035465589 — KHET TALAB KANHEIYA LAL GOPAL SINGH | Ongoing | 147621.16 | 29361 | 2025-05-08
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722004032/IF/22012035571748 — PM AAWAS BABU MUNNA MP 10097653 | Approved | 23500 | 0 | 2025-04-15
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722004032/IF/22012035579703 — construction of pmay mahesh kalu pmay id 105119084 | Approved | 0 | 0 | 2025-06-10
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722004032/IF/22012035581297 — PM AAWAS TEJU BAI MP4891348 | Approved | 23500 | 0 | 2025-04-15
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722004032/IF/22012035581298 — PM AAWAS MAHESH KALU MP105119084 | Approved | 23500 | 0 | 2025-04-15
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722004032/IF/22012035581299 — PM AAWAS KALI BAI RAHUL MP105599077 | Completed | 23500 | 22446 | 2025-08-02 | 2026-06-02
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722004032/IF/22012035581300 — PM AAWAS CHITA BAI RATAN MP143673619 | Physically Completed | 23500 | 18792 | 2025-08-02 | 2026-06-25
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722004032/IF/22012035581402 — PM AAWAS BABU MUNNA MP100976537 | Completed | 23500 | 23229 | 2025-07-26 | 2026-05-19
DHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722004032/IF/9993745615 — Indira Avas Sodarabai Bheru | Completed | 14310 | 14068 | 2016-06-06 | 2017-09-01
DHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722004032/IF/9993745616 — Indira Avas Amarsingh Shankarlal | Completed | 14310 | 14195 | 2016-06-06 | 2017-01-10
DHAR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004032/IF/IAY/2399175 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4319650 | Completed | 17100 | 17100 | 2020-06-24 | 2020-10-21
DHAR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004032/IF/IAY/2399221 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4343447 | Completed | 17100 | 17100 | 2020-06-24 | 2020-10-21
DHAR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004032/IF/IAY/2399424 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4347804 | Completed | 17100 | 15770 | 2020-06-24 | 2021-03-31
DHAR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004032/IF/IAY/2405518 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4559078 | Completed | 17100 | 17100 | 2020-06-24 | 2020-10-21
DHAR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004032/IF/IAY/2405832 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4566933 | Completed | 17100 | 15960 | 2020-06-24 | 2021-03-31
DHAR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004032/IF/IAY/2417044 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4341233 | Completed | 17100 | 17100 | 2020-06-24 | 2020-10-21
DHAR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004032/IF/IAY/2520044 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4595792 | Completed | 17100 | 7220 | 2020-06-24 | 2023-10-19
DHAR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004032/IF/IAY/2520925 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4607120 | Completed | 17100 | 17100 | 2020-06-24 | 2020-10-21
DHAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004032/IF/IAY/2800616 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4177057 | Completed | 17100 | 14668 | 2021-07-09 | 2021-11-17
DHAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004032/IF/IAY/2802498 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4319679 | Completed | 17100 | 16212 | 2021-07-09 | 2021-11-17
DHAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004032/IF/IAY/2805001 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4559779 | Completed | 17100 | 16212 | 2021-07-09 | 2021-11-17
DHAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004032/IF/IAY/2807109 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4370554 | Completed | 17100 | 16212 | 2021-07-09 | 2021-11-17
DHAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004032/IF/IAY/2809588 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4336552 | Completed | 17100 | 16212 | 2021-07-09 | 2021-11-17
DHAR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004032/IF/IAY/2819019 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5336106 | Approved | 23490 | 0 | 2020-11-17
DHAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004032/IF/IAY/2822330 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5376564 | Completed | 17100 | 16212 | 2021-07-09 | 2021-11-17
DHAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004032/IF/IAY/2855078 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1745452 | Completed | 17100 | 11580 | 2021-07-09 | 2021-12-03
DHAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004032/IF/IAY/2858796 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4337828 | Completed | 17100 | 15054 | 2021-07-09 | 2021-11-17
DHAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004032/IF/IAY/2859389 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4056873 | Completed | 17100 | 16212 | 2021-07-09 | 2021-11-17
DHAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004032/IF/IAY/2864488 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4347840 | Completed | 17100 | 16212 | 2021-07-09 | 2021-11-17
DHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004032/IF/IAY/374101 — Construction of IAY House -IAY REG. NO. MP1358880 | Completed | 15030 | 15460 | 2017-02-12 | 2018-02-28
DHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004032/IF/IAY/377117 — Construction of IAY House -IAY REG. NO. MP1526329 | Completed | 15030 | 14809 | 2017-02-12 | 2017-10-11
DHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004032/IF/IAY/377188 — Construction of IAY House -IAY REG. NO. MP1530304 | Completed | 15030 | 14809 | 2017-02-12 | 2017-10-11
DHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004032/IF/IAY/377587 — Construction of IAY House -IAY REG. NO. MP1567735 | Completed | 15030 | 14809 | 2017-02-12 | 2017-10-11
DHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004032/IF/IAY/3813108 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105597870 | Completed | 18360 | 17340 | 2022-05-27 | 2022-11-20
DHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004032/IF/IAY/3813110 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105598434 | Completed | 18360 | 18156 | 2022-05-27 | 2022-11-15
DHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004032/IF/IAY/3838669 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125114401 | Completed | 18360 | 16830 | 2022-05-27 | 2023-09-02
DHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004032/IF/IAY/3874099 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146941439 | Completed | 18360 | 18156 | 2022-05-27 | 2022-11-15
DHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004032/IF/IAY/4209241 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105599243 | Completed | 18360 | 18156 | 2022-08-28 | 2022-11-15
DHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004032/IF/IAY/4209242 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105599670 | Completed | 18360 | 18360 | 2022-10-01 | 2022-12-29
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004032/IF/IAY/4541360 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105598905 | Ongoing | 23490 | 20097 | 2025-08-02
DHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004032/IF/IAY/4541361 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105599332 | Completed | 21870 | 21627 | 2024-12-06 | 2026-02-17
DHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004032/IF/IAY/4646940 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142742318 | Completed | 23490 | 21627 | 2024-12-07 | 2026-02-28
DHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004032/IF/IAY/4859250 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105598240 | Completed | 23490 | 20898 | 2025-01-05 | 2026-02-28
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004032/IF/IAY/4891348 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145390629 | Completed | 23490 | 22968 | 2025-04-04 | 2026-02-16
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004032/IF/IAY/5147116 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100971085 | Completed | 23490 | 23229 | 2025-04-23 | 2026-02-16
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004032/IF/IAY/5158882 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143667646 | Ongoing | 23490 | 16965 | 2025-05-15
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004032/IF/IAY/5173830 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105599184 | Completed | 23490 | 23229 | 2025-04-23 | 2026-02-16
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004032/IF/IAY/5177973 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100980366 | Ongoing | 23490 | 12528 | 2025-06-02
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004032/IF/IAY/5203479 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100976582 | Completed | 23490 | 23229 | 2025-06-02 | 2025-11-19
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004032/IF/IAY/5214995 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147286103 | Completed | 23490 | 22968 | 2025-04-23 | 2026-02-16
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004032/IF/IAY/5229607 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123430380 | Physically Completed | 23490 | 11484 | 2025-06-02 | 2026-05-31
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004032/IF/IAY/5232885 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100978365 | Physically Completed | 23490 | 22968 | 2025-06-02 | 2026-04-19
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004032/IF/IAY/5237291 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105598575 | Completed | 23490 | 23490 | 2025-05-24 | 2026-05-28
DHAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004032/IF/IAY/54486 — Construction of IAY House -IAY REG. NO. MP-22-004-032-002/09 | Approved | 23490 | 0 | 2015-10-26
DHAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004032/IF/IAY/54487 — Construction of IAY House -IAY REG. NO. MP-22-004-032-002/28 | Approved | 23490 | 0 | 2015-10-26
DHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004032/IF/IAY/5515033 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105119084 | Approved | 23490 | 0 | 2025-02-21
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004032/IF/IAY/5530490 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105598529 | Physically Completed | 23490 | 22446 | 2025-07-26 | 2026-06-21
DHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004032/IF/IAY/5657885 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105599077 | Approved | 23490 | 0 | 2025-02-21
DHAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004032/IF/IAY/690692 — Construction of IAY House -IAY REG. NO. MP1278655 | Completed | 15030 | 14964 | 2017-05-16 | 2017-10-11
DHAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004032/IF/IAY/707314 — Construction of IAY House -IAY REG. NO. MP1529223 | Completed | 15030 | 14964 | 2017-09-22 | 2018-01-25
DHAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004032/IF/IAY/711249 — Construction of IAY House -IAY REG. NO. MP1576772 | Completed | 15030 | 14964 | 2017-05-16 | 2017-10-11
DHAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004032/IF/IAY/712946 — Construction of IAY House -IAY REG. NO. MP1599974 | Completed | 15030 | 14964 | 2017-05-16 | 2017-10-11
DHAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004032/IF/IAY/712948 — Construction of IAY House -IAY REG. NO. MP1600025 | Completed | 15030 | 14964 | 2017-09-22 | 2018-01-25
DHAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004032/IF/IAY/721708 — Construction of IAY House -IAY REG. NO. MP1745465 | Completed | 15030 | 14964 | 2017-05-16 | 2017-10-11
DHAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004032/IF/IAY/721849 — Construction of IAY House -IAY REG. NO. MP1748589 | Completed | 15030 | 14964 | 2017-05-16 | 2017-10-11
DHAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004032/IF/IAY/722243 — Construction of IAY House -IAY REG. NO. MP1756507 | Completed | 15030 | 14964 | 2017-05-16 | 2017-10-11
DHAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004032/IF/IAY/722244 — Construction of IAY House -IAY REG. NO. MP1756539 | Completed | 15030 | 14964 | 2017-05-16 | 2017-10-11
DHAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004032/IF/IAY/723417 — Construction of IAY House -IAY REG. NO. MP1783738 | Completed | 15030 | 14964 | 2017-05-16 | 2017-10-11
DHAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004032/IF/IAY/724822 — Construction of IAY House -IAY REG. NO. MP1819514 | Completed | 15030 | 14964 | 2017-05-20 | 2017-10-11
DHAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004032/IF/IAY/724915 — Construction of IAY House -IAY REG. NO. MP1821825 | Completed | 15030 | 14964 | 2017-05-16 | 2017-10-11
DHAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004032/IF/IAY/757636 — Construction of IAY House -IAY REG. NO. MP2849854 | Completed | 15030 | 14964 | 2017-05-16 | 2017-10-11
DHAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004032/IF/IAY/764484 — Construction of IAY House -IAY REG. NO. MP3168342 | Completed | 15030 | 14964 | 2017-05-16 | 2017-10-11
DHAR | 2016-2017 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1722004032/LD/22012034294843 — Shmashyan Maidan Samaltalikaran Karya | Completed | 80000 | 840 | 2017-02-09 | 2017-09-07
DHAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Fallow Land for Community / Development of Fallow Land for Community | Land Development | 1722004032/LD/22012034519032 — CPT CUM LEVLING SANTIDHAM PIPALDA | Completed | 105937.42 | 98416 | 2020-09-29 | 2021-04-01
DHAR | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1722004032/LD/23 — ग्रामीण किडांगन खेल मैदान समतलीकरण प्रावि पिपल्‍दा | Completed | 134181 | 79186 | 2011-11-24 | 2012-09-21
DHAR | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1722004032/LD/65 — ग्रामीण कीडांगन खैल्‍ा मैदान समतलीकरण मा वि पिपल्‍ | Completed | 443000 | 438908 | 2011-12-22 | 2014-12-10
DHAR | 2016-2017 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1722004032/PG/9425893427 — Kridangan | Completed | 321000 | 286856.39 | 2017-02-09 | 2019-06-22
DHAR | 2006-2007 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004032/RC/101 — सिमेन्‍ट / क्रंकेट पि‍पल्‍दा | Completed | 0 | 138194 | 2007-01-01 | 2007-03-31
DHAR | 2006-2007 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004032/RC/11 — सीमेंट क्रांक्रीट रोड पिपल्‍दा | Completed | 101500 | 58510 | 2007-03-25 | 2008-08-18
DHAR | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722004032/RC/22012034151805 — मुरम सडक र्नि‍माण पि‍पल्‍दा बग्‍गड मार्ग से कोट भि‍डोता मार्ग भाग II | Completed | 478000 | 163118 | 2011-03-13 | 2012-06-04
DHAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004032/RC/22012034158113 — सीमेंट कांक्रीट आंतरिक मार्ग निर्माण पिपल्‍दा | Deleted | 0 | 0 | 2013-04-14
DHAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004032/RC/22012034158114 — सीमेंट कांक्रीट आंतरिक मार्ग निर्माण पिपल्‍दा | Deleted | 0 | 0 | 2013-04-14
DHAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004032/RC/22012034189952 — सीमेंट कांक्रीट आंतरिक मार्ग निर्माण दिनेश के घर स | Completed | 156000 | 154056 | 2014-02-04 | 2014-08-05
DHAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004032/RC/22012034207187 — सीमेंट कोंक्रेट रोड नरायण पाटीदार माकन करसना के म | Completed | 217000 | 65172 | 2014-02-25 | 2016-12-30
DHAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722004032/RC/22012034207885 — ket road rameshvar raghuvansee ke khet se krashna | Completed | 1499000 | 196798.8 | 2014-02-25 | 2016-12-30
DHAR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004032/RC/22012034226032 — C C Road Mehatab Ke Makan Se Munna Ke Makan Tak | Completed | 148000 | 146920 | 2014-07-28 | 2014-12-10
DHAR | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004032/RC/22012034284421 — C C Road Babu Meena Ke Makan Se P S Tak | Completed | 260000 | 258577 | 2015-10-15 | 2017-09-25
DHAR | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004032/RC/22012034293665 — C C Road Vishnu Sutar Ke Makan Se Main Road Tak | Completed | 50000 | 48738 | 2015-12-29 | 2016-06-22
DHAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722004032/RC/22012034373031 — khet sdak | Closed | 0 | 0 | 2017-10-02
DHAR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004032/RC/22012034473553 — C C Road Main Road Se Salegram Ke Ghar Tak | Completed | 50000 | 34510 | 2019-09-08 | 2020-05-20
DHAR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722004032/RC/22012034553118 — GRAVEL ROAD NIRMAN VIJAY PATIDAR KE KHET SE RADHESHYAM KE KHET TAK | Completed | 1307473.78 | 1284384 | 2021-03-17 | 2022-05-29
DHAR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722004032/RC/22012034553119 — GRAVEL ROAD DHERMENDRA KE KHET SE TEJSINGH KE KHET TAK | Completed | 1486147.37 | 1473667.25 | 2020-12-21 | 2022-09-21
DHAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004032/RC/22012034606477 — C C ROAD MAIN ROAD SE KALU KE MAKAN KI OR | Closed | 0 | 0 | 2022-01-26
DHAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004032/RC/22012034606480 — PULIYA NIRMAN PAPPU MANSUR KE MAKAN KE PASS | Closed | 0 | 0 | 2022-01-26
DHAR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004032/RC/22012034606486 — C C ROAD PANSHAYAT KE GATE SE BABU KE MAKAN KI OR | Completed | 36000 | 17340 | 2022-12-01 | 2024-07-08
DHAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004032/RC/22012034643645 — PIPE PULIYA MALI MOHALLE ME | Completed | 65000 | 59513 | 2023-09-20 | 2024-11-26
DHAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004032/RC/22012034666272 — CC ROAD HANUMAN MANDIR SE TEJAJI KE OTLE TAK | Ongoing | 12000 | 221 | 2023-10-07
DHAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004032/RC/22012034666302 — CC RAOAD RAM MANDIR SE AJAY NPATIDAR KE GHAR TAK | Ongoing | 73000 | 221 | 2023-10-07
DHAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004032/RC/22012034821863 — CC ROAD SUNIL KE GHAR SE HANDPUMP TAK PIPALDA | Approved | 73000 | 0 | 2024-06-20
DHAR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004032/RC/22012034847486 — CC ROAD GOVIND KE GHAR SEUMRANW EVM SAMSAN TAK PIPALDA | Approved | 158000 | 0 | 2025-04-15
DHAR | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722004032/RC/25338 — पाईप पुलि‍या र्नि‍माण बग्‍गड रोड पि‍पल्‍दा | Completed | 238000 | 322050.3 | 2008-04-07 | 2009-01-30
DHAR | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722004032/RC/25358 — आंतरि‍क मार्ग पंचायत भवन से पीडब्‍ल्‍युडी रोड तक पि‍पल्‍दा | Completed | 215200 | 171598 | 2009-02-22 | 2008-10-02
DHAR | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722004032/RC/25507 — ग्रेवल मार्ग पिपल्‍दा के बग्‍गड रोड से भिडोता पिपल्‍दा | Completed | 485000 | 455030 | 2010-03-12 | 2009-08-02
DHAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004032/RC/25741 — सीमेंट कांक्रीट आंतरिक मार्ग निर्माण कैलाश के मकान से सुन्‍दरलाल के मकान तक पिपल्‍दा | Completed | 143000 | 53476 | 2012-11-24 | 2013-01-15
DHAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722004032/RC/25773 — आंतरिक मुरम सडक मुख्‍य मार्ग से प्राथमिल वि. तक पिपल्‍दा | Completed | 153000 | 43728 | 2012-07-25 | 2012-09-21
DHAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004032/RC/25804 — सीमेंट कांक्रीट आंतरिक मार्ग निर्माण उमराव के घर से शंकर के घर तक पिपल्‍दा | Completed | 190000 | 189988 | 2013-02-13 | 2013-03-28
DHAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004032/RC/25821 — सीमेंट कांक्रीट आंतरिक मार्ग श्रीमाता मॉ की गली से बावडी रोड तक पिपल्‍दा | Completed | 48000 | 47662 | 2013-12-30 | 2014-08-05
DHAR | 2007-2008 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722004032/RC/32-05 — पि‍पल्‍दा से बग्‍गड् ग्रेवल मार्ग भाग 2 | Completed | 300000 | 331646 | 2008-01-23 | 2009-03-30
DHAR | 2007-2008 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722004032/RC/5000 — ग्रेवल मार्ग पिपल्‍दा से छडोदा भाग II | Completed | 0 | 51130 | 2007-11-01 | 2008-09-12
DHAR | 2006-2007 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722004032/RC/71 — ग्रेवल रोड् पि‍पल्‍दा से बग्‍गडृ | Completed | 500000 | 254995 | 2006-04-14 | 2007-03-19
DHAR | 2006-2007 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722004032/RC/99 — ग्रेवल रोड पि‍पल्‍दा छाडोदा | Completed | 500000 | 247565 | 2006-12-11 | 2007-03-28
DHAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1722004032/RS/22012034534246 — SBM SCP COMMUNITY COMPOST PIT-PIPALDA | Closed | 47000.06 | 0 | 2021-06-30
DHAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1722004032/RS/22012034536635 — SBM SSP SAMUDAYIK SOAK PIT-10 UNIT PIPALDA | Closed | 59999.77 | 0 | 2021-07-04
DHAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1722004032/RS/22012034537880 — SBM ISP PIPALDA 50 UNIT | Closed | 99999.74 | 0 | 2021-07-06
DHAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Anganwadi Multi Unit Toilets for Comm / Construction of Anganwadi Multi Unit Toilets for Community | Construction of Toilets | 1722004032/RS/22012034640496 — PULIYA NIRMAN PAPPU MANSUR KE MAKAN KE PASS | Closed | 98000 | 0 | 2022-02-02
DHAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Anganwadi Multi Unit Toilets for Comm / Construction of Anganwadi Multi Unit Toilets for Community | Construction of Toilets | 1722004032/RS/22012034640772 — PULIYA NIRMAN PAPPU MANSUR KE MAKAN KE PAS | Closed | 15000 | 0 | 2022-02-03
DHAR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1722004032/RS/22012034640773 — RCC NALI NIRMAN AAGANWADI BHAWAN SE SAMSAN KI OR | Completed | 60000 | 58956 | 2022-05-27 | 2022-12-29
DHAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1722004032/RS/22012034640778 — SWACHHTA EVM JAL NIKASHI BRIDGE KE NICHE PIPALDA | Closed | 14000 | 0 | 2022-02-03
DHAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1722004032/RS/22012034641520 — R C C NALI NIRMAN AAGANWASI BHAVAN SE SAMSAN KI OR | Closed | 0 | 0 | 2022-01-26
DHAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1722004032/RS/22012034641521 — DUSIT JAL NIKASI BRIDGE KE NICHE | Closed | 0 | 0 | 2022-01-26
DHAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1722004032/RS/22012035117943 — NALI NIRMAN SARDAR PATIDAR KE GHAR SE UMRANW KE GHAR TAK | Completed | 68000 | 67993.28 | 2023-10-07 | 2025-04-24
DHAR | 2015-2016 | D--RURAL INFRASTUCTURE / Bharat Nirman Sewa Kendra | New Construction / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1722004032/SK/9993647826 — Bharat Nirman Rajeev Gandhi Sewa Kendra,PIPALDA | Completed | 1285000 | 999021.6 | 2015-08-23 | 2017-10-25
DHAR | 2006-2007 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722004032/WC/200 — खेत तालाब सवजीराम पिपल्‍दा | Completed | 5120 | 0 | 2006-06-04 | 2006-06-10
DHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1722004032/WC/22012034313355 — Jalsangrahan Sanrachana Kanhiya Ke Khet Ke Pas | Completed | 355000 | 227384 | 2017-02-01 | 2019-06-30
DHAR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1722004032/WC/22012034442153 — concret chek dem kanawal wale nale par rapat ke pass | Closed | 553000 | 0 | 2019-01-26
DHAR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1722004032/WC/22012034442263 — Nala Trenching | Closed | 0 | 0 | 2019-01-26
DHAR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1722004032/WC/22012034442267 — Bhu Sankan Pond Suresh Ke Khet Ke Pas | Physically Completed | 170000 | 5630 | 2019-03-11 | 2021-01-10
DHAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1722004032/WC/22012034482494 — Recharge Pit Primary School Piplda | Completed | 5134.63 | 176 | 2019-08-31 | 2021-01-01
DHAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1722004032/WC/22012034482497 — Recharge Pit Middle School Piplda | Completed | 5134.63 | 176 | 2019-08-31 | 2021-01-01
DHAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1722004032/WC/22012034518435 — nala tranching kary pipalda | Closed | 0 | 0 | 2019-10-02
DHAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1722004032/WC/22012034543301 — Nala trenching Abraham parmar ke khet se Narayan patidar ke khet tak | Completed | 467683.82 | 379735.76 | 2020-04-30 | 2020-09-11
DHAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1722004032/WC/22012034604234 — NALA TRENCH DURGESH RAGHUWANSI KE KHET SE TALAB TAK PIPALDA | Physically Completed | 234989.1 | 21850 | 2020-12-24 | 2021-09-09
DHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722004032/WC/22012034633315 — CTRA WORK SANKAN POND RESAM KENDRA PIPALDA | Completed | 350079.43 | 333537 | 2021-05-04 | 2022-09-21
DHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1722004032/WC/22012034636899 — CTRA WORK SAMSAN SE BABU KE KHET TAK PIPALDA | Completed | 331312.5 | 329732 | 2021-05-12 | 2021-11-24
DHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1722004032/WC/22012034641922 — CTRA RWH WORK SAMUDAYIK BHAVAN PIPALDA | Completed | 5500 | 5404 | 2021-05-12 | 2021-12-30
DHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1722004032/WC/22012034664613 — CTRA WORK RWH PRIMARY SCHOOL PIPALDA | Closed | 0 | 0 | 2021-04-01
DHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1722004032/WC/22012034664625 — CTRA WORK RWH PRIMARY SCHOOL PIPALDA | Completed | 5500 | 4825 | 2021-05-12 | 2021-12-30
DHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1722004032/WC/22012034684079 — CTRA RICHARGE PIT-1 SAMSHAN KE PASS NALA | Completed | 13133.77 | 13057 | 2021-05-14 | 2021-09-29
DHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1722004032/WC/22012034684087 — CTRA RICHARGE PIT-2 SAMSHAN KE PASS NALA | Completed | 13133.77 | 10741 | 2021-05-14 | 2021-07-10
DHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1722004032/WC/22012034684091 — CTRA RICHARGE PIT-3 SAMSHAN KE PASS NALA | Completed | 13133.77 | 13057 | 2021-05-14 | 2021-09-29
DHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1722004032/WC/22012034684098 — CTRA RICHARGE PIT-1 AMBARAM KE KHET SE NARAYAN KE KHET NALA | Completed | 13133.77 | 11513 | 2021-05-14 | 2021-09-29
DHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1722004032/WC/22012034684101 — CTRA RICHARGE PIT-2 AMBARAM KE KHET SE NARAYAN KE KHET NALA | Completed | 13133.77 | 11899 | 2021-05-15 | 2021-09-29
DHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1722004032/WC/22012034684106 — CTRA RICHARGE PIT-3 AMBARAM KE KHET SE NARAYAN KE KHET NALA | Completed | 13133.77 | 12478 | 2021-05-15 | 2021-09-29
DHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1722004032/WC/22012034684111 — CTRA RICHARGE PIT-1 TALAB WALA NALA | Closed | 13133.77 | 0 | 2021-04-14
DHAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1722004032/WC/22012034951627 — NSP Nala Trenching Radheshyam k khet se Dhannalal k khet tak Pipalda | Completed | 352825.4 | 227148 | 2022-05-27 | 2022-09-21
DHAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1722004032/WC/22012034951630 — NSP Nala Trenching Radheshyam k khet se Dhannalal k khet tak Pipalda | Closed | 0 | 0 | 2022-04-14
DHAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1722004032/WC/22012034951783 — NSP NALA TRENCH RADHESHYAM KE KHET SE DHANNA LA KE KHET TAK | Closed | 0 | 0 | 2022-04-14
DHAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1722004032/WC/22012034951789 — NSP BHUSANKAN POND TEJSINGH KE KHET KE PASS | Physically Completed | 378175.26 | 314004 | 2022-05-27 | 2026-02-24
DHAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722004032/WC/22012034974749 — SANKAN POND MITHA TALAB KE PAS | Closed | 0 | 0 | 2022-04-14
DHAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1722004032/WC/22012035016942 — NALA TRENCH PADAT SE FULSINGH KE KHET TAK PIPALDA | Completed | 227386.8 | 188637 | 2022-12-08 | 2024-06-13
DHAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1722004032/WC/22012035088469 — BUSANKAN POND RESAM CENTER KE PAS | Completed | 288299.01 | 236691 | 2023-07-28 | 2024-12-04
DHAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1722004032/WC/22012035099978 — NALA TRENCH SOHAN KE KEHET SE CHOUDHARY KE KHET TAK | Physically Completed | 158652.78 | 92478.69 | 2024-06-21 | 2026-04-14
DHAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1722004032/WC/22012035099985 — SANKAN POND PIPALIWALA GOYA | Completed | 215240.52 | 173673 | 2023-10-06 | 2024-06-17
DHAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1722004032/WC/22012035165851 — Nala trenching karya | New | 0 | 0 | 2024-01-26
DHAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1722004032/WC/22012035200308 — NAMAMI GANGE FEEDAR CHANAL TRENCH HANUMAN MANDIR TALAB PIPALDA | Physically Completed | 119182.77 | 57738.88 | 2024-06-14 | 2026-04-19
DHAR | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722004032/WC/4024 — तालाब नि‍र्माण पि‍पल्‍दा | Completed | 216000 | 183638 | 2009-02-15 | 2009-07-28
DHAR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1722004032/WC/4085 — जल संग्रहण सरचना पिपल्‍दा | Completed | 0 | 29800 | 2010-05-25 | 2010-08-11
DHAR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722004032/WC/4115 — जल संग्रहण संरचना, ग्राम पंचायत पिपल्‍दा | Completed | 0 | 32400 | 2010-12-17 | 2010-12-17
DHAR | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722004032/WC/4170 — जल संग्रहण संरचना भाग 1 पिपल्‍दा | Completed | 135000 | 93984 | 2012-06-06 | 2012-09-21
DHAR | 2006-2007 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722004032/WC/75 — खेत तालाब ईश्‍वर -हि‍न्‍दुसि‍हं पि‍पल्‍दा | Completed | 1000 | 0 | 2006-06-04 | 2006-06-10
DHAR | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Sunken Pond / Construction of Community Water Harvesting Ponds | Farm Pond | 1722004032/WC/9993627993 — जल संग्रहण संरचना पिपल्‍दा | Completed | 284000 | 220212 | 2013-06-04 | 2014-07-01
DHAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1722004032/WC/9993667818 — Jal Sangrahan Sanrachana | Deleted | 0 | 0 | 2016-01-26
DHAR | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1722004032/WH/19961248 — Repair Of Nistar Talab | Completed | 837000 | 827415.66 | 2017-06-03 | 2017-12-10
DHAR | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1722004032/WH/19961253 — Ripair Of Nistar Talab | Completed | 554000 | 551479.16 | 2017-06-03 | 2017-12-10
DHAR | 2011-2012 | D--RURAL INFRASTUCTURE / Renovation of traditional water bodies | Strengthening of Embankment / Construction of Embankment for community | Renovation of traditional water bodies | 1722004032/WH/2 — तालाब पाल सुदधरीकरण पिपल्‍दा | Completed | 382951 | 197640 | 2011-06-02 | 2012-09-21