## Work List
Exported on: 2026-09-04 14:36:32
Filters applied:
Data source: MGNREGA + VBGRAMG
District: DHAR
Block: All
Panchayat: BAGDI TURK
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
DHAR | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1722004040/AV/22012034571155 — Construction Of Bench and Desk in Dining हाई स्कूल Bagditurk | Completed | 35101.1 | 34970.6 | 2021-08-19 | 2021-12-15
DHAR | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1722004040/AV/22012034602200 — हाई स्कूल बगड़ी तुर्क मे बाउंड्री वॉल निर्माण | Closed | 0 | 0 | 2021-10-02
DHAR | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1722004040/AV/22012034624611 — आंगनवाड़ी भवन निर्माण बगड़ीतुर्क क्रमांक 01 | Completed | 500000 | 498822.04 | 2022-11-29 | 2024-05-10
DHAR | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1722004040/AV/22012034650616 — नाली निर्माण प्रकाश चम्पालाल के घर से पानी की टंकी तक | Closed | 105000 | 0 | 2023-10-01
DHAR | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1722004040/DP/22012034238755 — Muktidham samsan sade nirman bagdi turk | Completed | 180000 | 180180 | 2017-03-24 | 2019-07-02
DHAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1722004040/DP/22012034443084 — nala trenching | Closed | 0 | 0 | 2019-04-01
DHAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1722004040/DP/22012034484453 — plantation work school parisar evm dharavara kakad bagditurk | Completed | 373990.15 | 354079.75 | 2020-06-03 | 2026-03-08
DHAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Block Plantation - Farm Forestry-Community / Along the coast Block Plantation of Farm Forestry Trees for Community | Plantation | 1722004040/DP/22012034523624 — PLANTATION WORK NEAR TALAB | Closed | 0 | 0 | 2021-01-26
DHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1722004040/DP/22012034527283 — सामुदायिक फलोध्यान गौशाला के पास (UNDER CNG) बगड़ी तुर्क | Completed | 385204.94 | 368718.35 | 2021-05-13 | 2025-07-15
DHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Horticulture -Community / Boundary Line Plantation of Horticulture Trees for Community | Plantation | 1722004040/DP/22012034534317 — मां की बगिया P.S.School Bagditurk | Completed | 11397.42 | 10086 | 2021-08-18 | 2025-01-15
DHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Horticulture -Community / Boundary Line Plantation of Horticulture Trees for Community | Plantation | 1722004040/DP/22012034534739 — SBM ISP Kitchen Garden Unit 10 Bagditurk | Closed | 0 | 0 | 2021-08-15
DHAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Block Plantation of Forestry-Community / Along the coast Block Plantation of Forestry Trees for Community | Plantation | 1722004040/DP/22012034584698 — वसुधा बंधन वृक्षारोपण बगड़ीतुर्क काकड़ 2023-2024 | Completed | 54564.94 | 26962 | 2023-08-15 | 2025-01-15
DHAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Block Plantation of Forestry-Community / Along the coast Block Plantation of Forestry Trees for Community | Plantation | 1722004040/DP/22012034606502 — वृक्षारोपण रमेश प्रजापत के खेत के पास | Closed | 0 | 0 | 2023-08-16
DHAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plntation-Biodrainage-Wastelands for comm / Block Plantation of Biodrainage trees in Wastelands for community | Plantation | 1722004040/DP/22012034625453 — Samudayik Varksaropan dharawara kakad par Bagditurk | Ongoing | 347941.97 | 161397 | 2024-09-26
DHAR | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1722004040/DP/3000 — हरियाली महोत्‍सव बगडीतुर्क II | Completed | 0 | 108523 | 2007-07-13 | 2011-02-01
DHAR | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1722004040/DP/3001 — नंदन फलोद्यान अंबाराम बगडीतुर्क | Completed | 0 | 41795 | 2007-10-24 | 2010-10-05
DHAR | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1722004040/DP/3002 — नंदन फलोद्यान नंदराम बगडीतुक | Completed | 0 | 39514 | 2007-10-24 | 2010-10-05
DHAR | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1722004040/DP/3003 — नंदन फलोद्यान सायरबाई बगडीतुर्क | Completed | 0 | 43376 | 2007-10-24 | 2010-10-05
DHAR | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Forest Protection / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1722004040/DP/6005 — तार फेंसि‍ग व़क्षारोपण बगडीतुर्क | Completed | 0 | 114806 | 2009-06-11 | 2010-07-19
DHAR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1722004040/DP/6017 — शांतीधाम निर्माण शामशान पर बगडीतुर्क | Completed | 0 | 138695 | 2010-07-13 | 2013-11-09
DHAR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1722004040/DP/6023 — शातीवन कब्रस्‍तान पर ग्राम पंचायत बगडीतुर्क | Completed | 0 | 95290.6 | 2010-07-26 | 2013-11-09
DHAR | 2007-2008 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Strengthening of Embankment / Construction of Embankment for community | Strengthening of Embankment | 1722004040/FP/3004 — पुलिया निर्माण बगडीतुर्क | Deleted | 0 | 15450 | 2007-11-28
DHAR | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Flood Control and Protection | Cement lining / Lining of distributary Canal for Community | Works for Flood Control and Protection | 1722004040/FP/3005 — पुलिया निर्माण बगडीतुर्क भाग II | Deleted | 0 | 9850 | 2007-12-05
DHAR | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1722004040/IF/1603 — मेंढबंधान ग्‍यारसीबाई सडि‍या बगडीतुर्क | Completed | 0 | 7318 | 2008-07-18 | 2009-03-29
DHAR | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1722004040/IF/1604 — मेंढबंधान हि‍न्‍दुसि‍ह कि‍शन बगडीतुर्क | Completed | 0 | 8755 | 2008-06-16 | 2009-03-29
DHAR | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1722004040/IF/1605 — मेंढ बधान देवि‍सि‍गं भागि‍रथ | Completed | 0 | 3485 | 2008-07-03 | 2008-07-03
DHAR | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1722004040/IF/1606 — मेढ बंधान भागीरथ गोपाल | Completed | 0 | 2380 | 2008-07-03 | 2009-06-29
DHAR | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1722004040/IF/1607 — मेढ बंधान रमेश धुलजी | Completed | 0 | 3655 | 2008-07-03 | 2008-07-03
DHAR | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1722004040/IF/1608 — मेढ बंधान श्रीमति‍ रेवाबाई फुलचन्‍द | Completed | 0 | 7224 | 2008-06-02 | 2009-06-26
DHAR | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1722004040/IF/1609 — मेढ बंधान प्रकाश हि‍न्‍दुसि‍गं | Completed | 0 | 8196 | 2008-06-20 | 2009-03-29
DHAR | 2009-2010 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722004040/IF/1612 — र्नि‍मल वाटि‍का रमेश अंबाराम बगडीतुर्क | Completed | 2500 | 2500 | 2009-04-13 | 2010-03-30
DHAR | 2009-2010 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722004040/IF/1613 — र्नि‍मल वाटि‍का राजाराम बगदीराम बगडीतुर्क | Completed | 2500 | 2500 | 2009-04-13 | 2010-03-30
DHAR | 2009-2010 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722004040/IF/1614 — र्नि‍मल वाटि‍का मदन शंकर बगडीतुर्क | Completed | 2500 | 2500 | 2009-04-13 | 2010-03-30
DHAR | 2009-2010 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722004040/IF/1615 — र्नि‍मल वाटि‍का बालाराम मंगा बगडीतुर्क | Completed | 2500 | 3183 | 2009-04-13 | 2010-09-04
DHAR | 2009-2010 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722004040/IF/1616 — र्नि‍मल वाटि‍का कन्‍हेयालाल शंकर बगडीतुर्क | Completed | 2500 | 3375 | 2009-04-13 | 2010-09-04
DHAR | 2009-2010 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722004040/IF/1617 — र्नि‍मल वाटि‍का मुन्‍नालाल गब्‍ब्‍ुसि‍हं बगडीतुर्क | Completed | 2500 | 2500 | 2009-04-13 | 2010-09-04
DHAR | 2009-2010 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722004040/IF/1618 — र्नि‍मल वाटि‍का चम्‍पालाल नन्‍दा बगडीतुर्क | Completed | 2500 | 2500 | 2009-04-13 | 2010-09-04
DHAR | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1722004040/IF/1728 — नंदन फलोध्‍यान फकिर मो नुर खा ग्राम पंचायत बगडीतुर | Completed | 157000 | 92464 | 2010-07-26 | 2015-04-12
DHAR | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1722004040/IF/1729 — नंदन फलोध्‍यान यासिनखा अब्‍दुलखा ग्राम पंचायत बगडी | Completed | 157000 | 86528 | 2010-07-26 | 2015-04-12
DHAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722004040/IF/22012034342792 — vraksharopan kary bagditurk | Closed | 335000 | 0 | 2017-04-25
DHAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722004040/IF/22012034353884 — vraksharopan rangilal nathuram bagadirurk | Completed | 335000 | 278963 | 2017-06-03 | 2022-08-15
DHAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722004040/IF/22012034353888 — vraksharopan aatmaram shobharam bagditurk | Closed | 335000 | 0 | 2017-05-25
DHAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722004040/IF/22012034353897 — vraksharopan mukesh bhikalal bagditurk | Completed | 335000 | 283568 | 2017-06-03 | 2022-08-15
DHAR | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1722004040/IF/22012034420853 — kamal bhikalal sochalay nirman bagdi turk | Completed | 12000 | 11866 | 2018-11-01 | 2019-04-20
DHAR | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1722004040/IF/22012034421869 — शौचालय निर्माण राजेश केसु बगड़ी तुर्क | Completed | 12000 | 11866 | 2018-11-01 | 2019-04-30
DHAR | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1722004040/IF/22012034421871 — shauchaalay nirmaan parakaash kanahaiya bagadee turk | Completed | 12000 | 11866 | 2018-11-01 | 2019-04-20
DHAR | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1722004040/IF/22012034421872 — शौचालय निर्माण धापु बाई रुगनाथ बगड़ी तुर्क | Closed | 12000 | 0 | 2018-04-14
DHAR | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1722004040/IF/22012034431627 — शौचालय निर्माण सोरमबाई bagdi turk | Completed | 12000 | 11866 | 2018-11-01 | 2019-04-20
DHAR | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1722004040/IF/22012034431629 — शौचालय निर्माण रंगीला नानुराम bagdi turk | Completed | 12000 | 11880 | 2018-10-25 | 2019-11-01
DHAR | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1722004040/IF/22012034431632 — शौचालय निर्माण राजेंद्र सरदार bagditurk | Completed | 12000 | 11866 | 2018-11-01 | 2019-08-20
DHAR | 2019-2020 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Compost Pit for Individual / Construction of Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1722004040/IF/22012034523849 — varmi pit nirman suresh genda lal bagditurk | Completed | 15073 | 14879 | 2020-02-01 | 2021-12-13
DHAR | 2019-2020 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Berkeley Compost Pit for Individual / Construction of Berkeley Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1722004040/IF/22012034524998 — Varmi pit nirman gabbulal /mangilal | Completed | 15073 | 15055 | 2020-02-01 | 2021-12-13
DHAR | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Berkeley Compost Pit for Individual / Construction of Berkeley Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1722004040/IF/22012034525013 — Varmi pit nirman Dhulji / Shankar | Suspended | 15073 | 0 | 2021-04-01
DHAR | 2019-2020 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Berkeley Compost Pit for Individual / Construction of Berkeley Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1722004040/IF/22012034525016 — Varmi pit nirman Ramesh / Dhulji | Completed | 15073 | 14879 | 2020-02-01 | 2021-12-13
DHAR | 2019-2020 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Berkeley Compost Pit for Individual / Construction of Berkeley Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1722004040/IF/22012034525020 — Varmi pit nirman Gangaram / peeru | Physically Completed | 15073 | 14879 | 2020-02-01 | 2021-02-28
DHAR | 2019-2020 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Berkeley Compost Pit for Individual / Construction of Berkeley Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1722004040/IF/22012034525022 — Varmi pit nirman Rajendra / Mangilal | Completed | 15073 | 14879 | 2020-02-22 | 2021-12-13
DHAR | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Berkeley Compost Pit for Individual / Construction of Berkeley Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1722004040/IF/22012034525023 — Varmi pit nirman Madan / Foolchand | Suspended | 15073 | 0 | 2021-04-01
DHAR | 2019-2020 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Berkeley Compost Pit for Individual / Construction of Berkeley Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1722004040/IF/22012034525024 — Varmi pit nirman Badri / Phoolchand | Closed | 15073 | 0 | 2019-10-02
DHAR | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Berkeley Compost Pit for Individual / Construction of Berkeley Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1722004040/IF/22012034525025 — Varmi pit nirman Muqaddar / Rasulkhan | Suspended | 15073 | 0 | 2021-04-01
DHAR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Goat Shelter for Individuals / Construction of Goat Shelter for Individuals | Goat Shelter | 1722004040/IF/22012034587704 — Goat Shed(Radheshyam/Nanuram) | Closed | 46636.05 | 0 | 2020-04-14
DHAR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Goat Shelter for Individuals / Construction of Goat Shelter for Individuals | Goat Shelter | 1722004040/IF/22012034587705 — Goat Shed(Santoshboi/Nandram)Dedla | Closed | 46636.05 | 0 | 2020-04-14
DHAR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Goat Shelter for Individuals / Construction of Goat Shelter for Individuals | Goat Shelter | 1722004040/IF/22012034587706 — Goat Shed(Rajesh/Keshu)Bagditurk | Closed | 46636.05 | 0 | 2020-04-14
DHAR | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Compost Pit for Individual / Construction of Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1722004040/IF/22012034649309 — Varmi Pit (Tulsiram/ Nandram) | Completed | 16599.35 | 12746 | 2021-04-13 | 2023-10-11
DHAR | 2020-2021 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Compost Pit for Individual / Construction of Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1722004040/IF/22012034649310 — Varmi Pit (Ashok / Balaram) | Closed | 16599.35 | 0 | 2020-12-18
DHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722004040/IF/22012034999430 — NSP Khet Talab Tulsiram Nandram Bagditurk | Closed | 356340.1 | 0 | 2022-04-14
DHAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1722004040/IF/22012035037139 — Individual Lich pit | Ongoing | 40669.44 | 16320.75 | 2023-08-01
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722004040/IF/22012035446311 — Construction of Farm Pond JGSA Tulasiram Nandram Bagditurk | Physically Completed | 450885.64 | 414961 | 2025-05-02 | 2026-04-15
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722004040/IF/22012035499346 — Construction of Aawas of Prakash PMAY ID MP142009331 Bagditurk | Completed | 23500 | 20097 | 2025-05-13 | 2026-06-02
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722004040/IF/22012035584053 — Construction of House Anjum Bi Saied Khan PMAYID MP142227576 | Physically Completed | 23490 | 20880 | 2025-10-05 | 2026-06-21
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722004040/IF/22012035600722 — ek bagiya maa ke naam GAURI SHG RAJU BAI DAYMA | Ongoing | 269386.03 | 123036 | 2025-09-04
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722004040/IF/22012035600727 — ek bagiya maa ke naam GAURI SHG GANGA BAI JAT | Ongoing | 269386.03 | 121755 | 2025-09-02
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722004040/IF/22012035600973 — EK BAGIYA MA KE NAM PLANTATION WORK PAVITRA BAI | Deleted | 0 | 0 | 2025-06-30
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722004040/IF/22012035601243 — EK BAGIYA MA KE NAM PLANTATION WORK TARABAI RAMESH | Ongoing | 269386.03 | 261 | 2025-09-03
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722004040/IF/22012035601249 — EK BAGIYA MA KE NAM PLANTATION WORK MANJU BAI CHAWADA | Ongoing | 269386.03 | 63868 | 2025-09-03
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722004040/IF/22012035601255 — EK BAGIYA MA KE NAM PLANTATION WORK SANGEETA BAI | Ongoing | 269386.03 | 69349 | 2025-09-04
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722004040/IF/22012035601643 — EK BAGIYA MAA KE NAAM PLANTATION PARVATI CHAWADA | Ongoing | 269386.03 | 44845 | 2025-09-11
DHAR | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1722004040/IF/9926723128 — pashu shed hindusingh kishan bagaditurk | Deleted | 0 | 0 | 2014-03-04
DHAR | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1722004040/IF/9993655322 — pashu shed nirman kailash champalal bagaditurk | Deleted | 0 | 0 | 2014-04-01
DHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1722004040/IF/9993681033 — indira awasa yojana bagaditurk1 | Completed | 14310 | 12024 | 2016-06-04 | 2016-07-29
DHAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004040/IF/9993681036 — indira awasa yojana bagditurk2 | Deleted | 14310 | 0 | 2015-10-15
DHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1722004040/IF/9993681038 — indira awasa yojana bagaditurk 3 | Completed | 14310 | 12024 | 2016-06-04 | 2016-07-29
DHAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722004040/IF/9993729082 — cm aawas mukesh ambaram bagdi turk | Closed | 14310 | 0 | 2016-03-15
DHAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722004040/IF/9993730977 — IAY sabu bai hindusingh bagdi turk | Closed | 14310 | 0 | 2015-10-14
DHAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722004040/IF/9993730991 — cm house madan rajaram Bagaditurk | Closed | 14310 | 0 | 2016-01-15
DHAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722004040/IF/9993731000 — IAY Nathi bai seva bagdi turk | Closed | 14310 | 0 | 2015-10-14
DHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1722004040/IF/9993731011 — IAY Anita mohan bagdi turk | Completed | 14310 | 14028 | 2016-06-04 | 2016-11-30
DHAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722004040/IF/9993731014 — cm aawash Thawar pannalal bagdi turk | Closed | 14310 | 0 | 2016-01-15
DHAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004040/IF/IAY/134994 — Construction of IAY House -IAY REG. NO. MP-22-004-040-003/107 | Approved | 27000 | 0 | 2016-02-03
DHAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004040/IF/IAY/134995 — Construction of IAY House -IAY REG. NO. MP-22-004-040-003/164 | Approved | 27000 | 0 | 2016-02-03
DHAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004040/IF/IAY/134996 — Construction of IAY House -IAY REG. NO. MP-22-004-040-003/54 | Approved | 27000 | 0 | 2016-02-03
DHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004040/IF/IAY/3701543 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100813091 | Completed | 18360 | 18156 | 2022-05-26 | 2022-08-16
DHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004040/IF/IAY/3701548 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100813696 | Completed | 18360 | 18360 | 2022-05-26 | 2023-01-02
DHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004040/IF/IAY/3701597 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100817245 | Completed | 18360 | 18360 | 2022-05-27 | 2022-09-01
DHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004040/IF/IAY/370394 — Construction of IAY House -IAY REG. NO. MP1225115 | Completed | 15030 | 14978 | 2017-02-12 | 2017-09-05
DHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004040/IF/IAY/380290 — Construction of IAY House -IAY REG. NO. MP1845455 | Completed | 15030 | 14208 | 2017-03-13 | 2017-06-20
DHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004040/IF/IAY/3871840 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141312979 | Completed | 18360 | 18156 | 2022-05-27 | 2022-08-27
DHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004040/IF/IAY/4037202 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106424907 | Completed | 18360 | 18156 | 2022-05-26 | 2022-08-16
DHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004040/IF/IAY/4057130 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102234598 | Completed | 18360 | 18360 | 2022-05-27 | 2022-10-02
DHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004040/IF/IAY/4253324 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127333156 | Completed | 18360 | 18360 | 2022-08-22 | 2023-01-02
DHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004040/IF/IAY/4255595 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142009323 | Completed | 18360 | 18360 | 2022-08-22 | 2023-01-24
DHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004040/IF/IAY/4255842 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141313046 | Completed | 18360 | 18360 | 2022-08-02 | 2022-11-07
DHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004040/IF/IAY/4533239 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP101000099 | Completed | 21870 | 21870 | 2024-10-24 | 2025-03-03
DHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004040/IF/IAY/4533248 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP101002277 | Completed | 21870 | 21870 | 2024-10-24 | 2024-12-30
DHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004040/IF/IAY/4533251 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP101002379 | Completed | 23490 | 21996 | 2024-11-25 | 2026-02-06
DHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004040/IF/IAY/4549028 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106421794 | Completed | 21870 | 21870 | 2024-10-24 | 2025-03-10
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004040/IF/IAY/4647263 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142009345 | Completed | 23490 | 23490 | 2025-04-15 | 2026-07-16
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004040/IF/IAY/5147514 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142243945 | Completed | 23490 | 23490 | 2025-04-22 | 2026-02-13
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004040/IF/IAY/5149594 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP101002078 | Completed | 23490 | 23490 | 2025-07-12 | 2026-05-19
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004040/IF/IAY/5150863 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100813176 | Completed | 23490 | 23490 | 2025-06-07 | 2026-05-19
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004040/IF/IAY/5152989 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100822345 | Completed | 23490 | 23490 | 2025-04-15 | 2026-02-13
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004040/IF/IAY/5154702 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP101001878 | Completed | 23490 | 16182 | 2025-04-22 | 2026-08-03
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004040/IF/IAY/5157590 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142009304 | Completed | 23490 | 23490 | 2025-05-06 | 2026-02-23
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004040/IF/IAY/5160089 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP101002634 | Completed | 23490 | 18009 | 2025-04-29 | 2026-07-25
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004040/IF/IAY/5161449 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100813279 | Completed | 23490 | 23490 | 2025-04-22 | 2026-03-07
DHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004040/IF/IAY/5163017 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106424721 | Approved | 27000 | 0 | 2025-02-20
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004040/IF/IAY/5165012 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142020958 | Completed | 23490 | 23490 | 2025-04-22 | 2025-09-09
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004040/IF/IAY/5167060 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100817067 | Completed | 23490 | 23490 | 2025-04-22 | 2025-09-09
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004040/IF/IAY/5167295 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100817282 | Completed | 23490 | 23490 | 2025-04-22 | 2026-07-16
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004040/IF/IAY/5172018 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP101001277 | Completed | 23490 | 23490 | 2025-05-06 | 2025-09-09
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004040/IF/IAY/5172188 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102233875 | Completed | 23490 | 23490 | 2026-01-07 | 2026-05-19
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004040/IF/IAY/5179274 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100817000 | Completed | 23490 | 23490 | 2025-04-08 | 2025-09-09
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004040/IF/IAY/5188805 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142020893 | Ongoing | 27000 | 10962 | 2026-01-07
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004040/IF/IAY/5189072 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142020917 | Ongoing | 27000 | 16989 | 2025-05-20
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004040/IF/IAY/5195191 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP101001827 | Completed | 23490 | 23490 | 2025-05-20 | 2025-11-19
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004040/IF/IAY/5197227 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142020839 | Ongoing | 27000 | 14589 | 2026-01-07
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004040/IF/IAY/5216546 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102363846 | Completed | 23490 | 23490 | 2025-05-20 | 2026-05-19
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004040/IF/IAY/5233223 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100817209 | Completed | 23490 | 18009 | 2025-04-08 | 2026-08-04
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004040/IF/IAY/5238079 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106421678 | Ongoing | 27000 | 14616 | 2025-04-29
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004040/IF/IAY/5238472 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100999917 | Completed | 23490 | 23490 | 2025-04-22 | 2026-02-13
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004040/IF/IAY/5238663 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP101002132 | Completed | 23490 | 23490 | 2025-04-08 | 2025-08-05
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004040/IF/IAY/5276522 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106424502 | Completed | 23490 | 16182 | 2025-04-22 | 2026-08-04
DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004040/IF/IAY/5405674 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP101000596 | Completed | 23490 | 23490 | 2025-04-22 | 2026-02-13
DHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004040/IF/IAY/561689 — Construction of IAY House -IAY REG. NO. MP3721480 | Completed | 15030 | 14896 | 2017-02-12 | 2017-09-05
DHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004040/IF/IAY/5643708 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP101001765 | Ongoing | 27000 | 4200 | 2025-05-04
DHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004040/IF/IAY/5881053 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100813313 | Ongoing | 27000 | 7602 | 2026-06-10
DHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004040/IF/IAY/595758 — Construction of IAY House -IAY REG. NO. MP1235052 | Completed | 15030 | 15360 | 2017-02-12 | 2017-11-25
DHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004040/IF/IAY/596677 — Construction of IAY House -IAY REG. NO. MP3052986 | Completed | 15030 | 15195 | 2017-02-12 | 2017-10-04
DHAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1722004040/LD/22012034517072 — Goshala nirman bagditurk | Deleted | 0 | 0 | 2020-04-14
DHAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1722004040/LD/22012034519815 — goushala nirman bagditurk | Ongoing | 3784582.21 | 3435447.28 | 2020-09-28
DHAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1722004040/LD/22012034539782 — CHARAGAH NIRMAN GOSHALA BAGDITURK | Closed | 0 | 0 | 2021-01-26
DHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1722004040/LD/22012034574132 — सामुदायिक फलोद्यान में तार फेंसिंग कार्य बगड़ीतुर्क | Deleted | 0 | 0 | 2021-08-15
DHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Fallow Land for Community / Development of Fallow Land for Community | Land Development | 1722004040/LD/22012034574134 — सामुदायिक फलोध्यान हेतु परती भूमि विकास एवं सुधार | Completed | 110660.94 | 95514 | 2022-01-06 | 2025-04-14
DHAR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1722004040/LD/3 — मेड बंधान बि‍हारीलाल नारायण | Completed | 18500 | 7782 | 2010-06-21 | 2010-07-12
DHAR | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1722004040/LD/32 — ग्रामीण क्रि‍डांगन समतलीकरण मा वि‍ ग्राम बगडीतुर्क | Completed | 50000 | 24120 | 2011-12-26 | 2012-09-16
DHAR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1722004040/LD/4 — मेड बंधान (राजाराम नन्‍दा) बगडीतुर्क | Completed | 18500 | 6894 | 2010-06-21 | 2010-07-12
DHAR | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1722004040/LD/40-01 — मेंढ बंधान अबांराम नंदा | Completed | 0 | 8414 | 2008-06-28 | 2009-06-29
DHAR | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1722004040/LD/40-02 — मेंढबंधान फुलचंद्र लाला | Completed | 0 | 8500 | 2008-06-02 | 2008-07-20
DHAR | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1722004040/LD/40-03 — मेंढ्बंधान नंदराम सडिया | Completed | 0 | 8330 | 2008-06-02 | 2008-06-11
DHAR | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1722004040/LD/52 — ग्रामीण कि‍डांगन खैल मैदान समतलीकरण प्रा वि‍ बगडीत | Completed | 357000 | 349227 | 2012-03-23 | 2016-02-05
DHAR | 2006-2007 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722004040/RC/12-209 — ग्रेवल रोड बगडीतुर्क II | Completed | 0 | 222293 | 2006-12-28 | 2007-09-02
DHAR | 2006-2007 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722004040/RC/12-49 — गेवल रोड बगडीतुर्क | Completed | 185000 | 251300 | 2006-04-11 | 2007-03-28
DHAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004040/RC/22012034159472 — सीमेंट कांक्रीट आंतरिक मांर्ग | Deleted | 0 | 0 | 2013-04-14
DHAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004040/RC/22012034202800 — सी.का.आ.मा.नि. गोरीशंकर के मकान से मेन रोड तक | Completed | 129000 | 128917 | 2014-02-06 | 2014-03-03
DHAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722004040/RC/22012034205823 — ईसाक के खेत से नंदराम के खेत तक | Completed | 1330000 | 549577.2 | 2014-02-20 | 2016-11-18
DHAR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004040/RC/22012034227322 — cement concrete road bihari ke ghar se kamal ke ma | Completed | 129000 | 127930 | 2014-08-23 | 2015-05-15
DHAR | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004040/RC/22012034284068 — cem ent concrete road shitalamata chouck se ramesh kumar ke ghar tak bagaditurk | Completed | 106000 | 105918 | 2015-11-02 | 2016-01-15
DHAR | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004040/RC/22012034301420 — c c road kashiram ke ghar se bondarsing ke ghar tak bagaditurk | Deleted | 0 | 0 | 2016-01-15
DHAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004040/RC/22012034324107 — c c road | Closed | 0 | 0 | 2017-04-01
DHAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722004040/RC/22012034339816 — sudur sadak shravan patel ke ghar se forest talab tak bagaditurk | Completed | 1550000 | 1456152.4 | 2017-06-04 | 2020-05-20
DHAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722004040/RC/22012034371337 — khet sadak | Closed | 0 | 0 | 2017-10-02
DHAR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722004040/RC/22012034512390 — Approach RoadMain road se Nat samaj shamshan tak | Completed | 2035135.2 | 2035130.51 | 2020-02-01 | 2022-10-13
DHAR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722004040/RC/22012034512883 — approch road nirman main road se nat shantidham tak | Closed | 0 | 0 | 2019-10-02
DHAR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004040/RC/22012034533583 — C.C.ROAD NIRMAN HIGH SCHOOL GRAUND SE GAJANAND MHARAJ KE GHAR TAK | Completed | 63000 | 62700 | 2020-08-12 | 2020-09-10
DHAR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722004040/RC/22012034534825 — सुदूर सड़क निर्माण कार्य बागडी तुर्क से उत्तरसी बलराम के घर तक | Deleted | 1381469.23 | 0 | 2020-04-14
DHAR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004040/RC/22012034543165 — Cement concrete road jammurkhedi marg shamshan tak | Completed | 33000 | 32870 | 2020-12-18 | 2021-01-06
DHAR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Bitumen Top Roads for Community / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1722004040/RC/22012034548306 — SUDUR SADAK NIRMAN BAGDITURK SE UTTARSI BALRAM KE GHAR TAK | Ongoing | 1497934.99 | 1248009.87 | 2020-11-26
DHAR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722004040/RC/22012034558856 — approch road nirman nat samaj shantidham se goshala tak bagditurk | Closed | 0 | 0 | 2021-01-26
DHAR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722004040/RC/22012034558857 — approch road nirman nat samaj shantidham se goshala tak bagditurk | Closed | 0 | 0 | 2021-01-26
DHAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004040/RC/22012034608863 — NALI NIRMAN MOHAN KE GHAR SE PANCHHAYAT BHAVAN TAK BAGDITURK | Closed | 0 | 0 | 2021-10-02
DHAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004040/RC/22012034608864 — NALI NIRMAN MOHAN KE GHAR SE PANCHHAYAT BHAVAN TAK BAGDITURK | Completed | 101000 | 100956 | 2022-03-05 | 2022-10-13
DHAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004040/RC/22012034666989 — c c road nirman ramdev ji se main road tak bagditurk | Completed | 29000 | 27404 | 2023-10-08 | 2024-01-03
DHAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004040/RC/22012034823140 — सी सी रोड निर्माण गोरीशकर महाराज के मकान से स्कूल गेट तक | Completed | 20000 | 19926 | 2024-08-01 | 2024-11-26
DHAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004040/RC/22012034831489 — cc road nirman saddam ke ghar se kabristaan tak | Approved | 68000 | 0 | 2024-10-07
DHAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004040/RC/22012034833996 — सीमेन्‍ट कांक्रीट मार्ग निर्माण सद्दाम के घर से कब्रिस्‍तान तक बगडीतुर्क | Completed | 68000 | 66096 | 2025-01-16 | 2025-07-05
DHAR | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722004040/RC/25373 — पूलि‍या नि‍माण भेरूजी नाले के पास भाग 3 | Completed | 0 | 391405 | 2009-06-08 | 2010-05-25
DHAR | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722004040/RC/25374 — ग्रेवल मार्ग बगडीतुर्क से जी ओ टी फाटा तक भाग 4 | Completed | 493000 | 432548 | 2009-06-08 | 2011-04-13
DHAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004040/RC/25753 — सीमेंट कांक्रीट आंतरिक मार्ग निर्माण रमेश के घर से रामचंद्र के घर तक बगडीतुर्क | Completed | 120000 | 119816 | 2012-07-25 | 2013-01-22
DHAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004040/RC/25794 — cc मार्ग निर्माण बंजारा बस्‍ती म | Completed | 48000 | 39988 | 2013-01-28 | 2014-11-12
DHAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004040/RC/25795 — सीमेन्‍ट कांक्रीट आं मार्ग निर्माण पंचायत भवन से र | Completed | 190000 | 189633 | 2012-12-20 | 2013-11-25
DHAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004040/RC/25797 — मार्ग निर्माण रमेश के घर से प | Completed | 120000 | 109999 | 2013-01-07 | 2013-03-30
DHAR | 2006-2007 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722004040/RC/33 — ग्रेवल रोड उतरसी कलमखेडी | Deleted | 300000 | 0 | 2006-12-11
DHAR | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722004040/RC/40-09 — ग्रेवल मार्ग बगडीतुर्क से जीओटी फाटा तक भाग 3 | Completed | 0 | 408234 | 2008-05-26 | 2009-03-31
DHAR | 2006-2007 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722004040/RC/604 — ग्रेवल रोड iii कलमखेडी | Deleted | 500000 | 0 | 2007-01-08
DHAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1722004040/RS/22012034305901 — anupayogi toilets purna karane hetu estimates bagaditurk | Completed | 363000 | 365354 | 2016-11-08 | 2018-12-12
DHAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1722004040/RS/22012034410183 — sochalay nirman kamal bhikalal | Deleted | 12000 | 0 | 2018-04-14
DHAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1722004040/RS/22012034410211 — rajesh kesu sochalay nirman bagdi turk | Deleted | 1200000000 | 0 | 2018-04-14
DHAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1722004040/RS/22012034537529 — SBM CSP Samudaik Soak Pit Unit 10 Bagditurk | Closed | 59999.77 | 0 | 2021-04-01
DHAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1722004040/RS/22012034537532 — SBM CSP Samudaik Soak Pit Unit 10 Bagditurk | Closed | 0 | 0 | 2021-04-01
DHAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1722004040/RS/22012034537534 — SBM CSP Samudaik Soak Pit Unit 05 Bagditurk | Closed | 0 | 0 | 2021-04-01
DHAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1722004040/RS/22012034537539 — SSBM SCP Samudaik Composed Pit Unit 1 Bagditurk | Closed | 29137.16 | 0 | 2021-04-01
DHAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1722004040/RS/22012034644596 — Samudayik Swachata Pariser Bagditurk | Completed | 44000 | 43986 | 2022-02-26 | 2022-06-17
DHAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1722004040/RS/22012034688502 — RCC Nali Nirman Fakir Mohhamad ki dukan se Prakash ke ghar tak | Completed | 19000 | 18785 | 2023-08-18 | 2023-10-26
DHAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1722004040/RS/22012035120733 — नाली निर्माण प्रकाश चम्पालाल के घर से पानी की टंकी तक | Closed | 0 | 0 | 2023-10-01
DHAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1722004040/RS/22012035120734 — नाली निर्माण प्रकाश चम्पालाल के घर से पानी की टंकी तक | Completed | 105000 | 104969 | 2023-12-25 | 2024-02-19
DHAR | 2014-2015 | D--RURAL INFRASTUCTURE / Bharat Nirman Sewa Kendra | New Construction / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1722004040/SK/3150 — Bharat Nirman Rajeev Gandhi Sewa Kendra,BAGDI TURK | Completed | 1285000 | 999960.4 | 2014-06-19 | 2015-12-15
DHAR | 2006-2007 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722004040/WC/12-200 — राजाराम नंदा खेत तालाब बगडीतुर्क | Completed | 0 | 700 | 2006-05-24 | 2007-09-13
DHAR | 2006-2007 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722004040/WC/12-201 — अंबाराम नंदा खेत तालाब बगडीतुर्क | Completed | 0 | 700 | 2006-05-24 | 2007-03-11
DHAR | 2006-2007 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722004040/WC/12-202 — अंबाराम भेरा खेत तालाब बगडीतुर्क | Completed | 0 | 700 | 2006-05-24 | 2007-03-16
DHAR | 2006-2007 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722004040/WC/12-203 — ग्‍यारसीबाई सडिया खेत तालाब बगडीतुर्क | Completed | 9000 | 700 | 2006-05-24 | 2007-03-29
DHAR | 2006-2007 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722004040/WC/12-204 — भागीरथ गोपाल खेत तालाब बगडीतुर्क | Completed | 0 | 700 | 2006-05-29 | 2007-03-21
DHAR | 2006-2007 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722004040/WC/12-205 — निस्‍तार तालाब बगडीतुर्क | Completed | 9000 | 51190 | 2006-12-18 | 2010-05-21
DHAR | 2006-2007 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722004040/WC/12-207 — कुआं निर्माण बाबु रामा बगडीतुर्क | Completed | 1000 | 19897 | 2006-12-28 | 2009-04-20
DHAR | 2006-2007 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722004040/WC/12-208 — कुआं निर्माण बगडीतुर्क चंपालाल नंदा | Completed | 1000 | 30784 | 2006-12-28 | 2009-03-31
DHAR | 2006-2007 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722004040/WC/12-37 — पन्‍नालाल रामा खेत तालाब बगडीतुर्क | Deleted | 0 | 700 | 2006-05-24
DHAR | 2006-2007 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722004040/WC/12-50 — पूनम केशू खेत तालाब बगडीतुर्क | Completed | 0 | 700 | 2006-05-24 | 2007-03-21
DHAR | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Mini Percolation tank / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1722004040/WC/22012034313016 — jal sangrahan sarchana bagadituk | Completed | 533000 | 254179 | 2016-11-04 | 2017-07-30
DHAR | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1722004040/WC/22012034355640 — Bori bandhan shera khal bagaditurk 1 | Completed | 16000 | 11999 | 2017-10-22 | 2017-12-25
DHAR | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1722004040/WC/22012034355644 — Bori bandhan shera khal bagaditurk 2 | Closed | 16000 | 0 | 2017-09-25
DHAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1722004040/WC/22012034380964 — Khet talab Bagdi turk | Completed | 245000 | 218124 | 2017-12-28 | 2019-06-30
DHAR | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Gabions / Construction of Gabion Check Dam for Individuals | Constr of Gabion | 1722004040/WC/22012034380974 — MWC Gabion Bagdi turk | Closed | 107000 | 0 | 2017-08-15
DHAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1722004040/WC/22012034441500 — nala trenching | Closed | 0 | 0 | 2019-04-01
DHAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722004040/WC/22012034550463 — Bhusankan pond Sherakhal Kakad Bagditurk | Completed | 310126.98 | 309452 | 2020-05-20 | 2021-12-15
DHAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1722004040/WC/22012034550464 — Pal Sudrikaran Sherakhal Kakad Bagdi turk | Closed | 768882.33 | 0 | 2020-04-14
DHAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1722004040/WC/22012034604847 — Nala trenching (Nat Samaj Shamshan se Sehra Khal Talab Tak) Bagditurk | Closed | 541885.5 | 0 | 2020-08-15
DHAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & Maint of Earthen Check Dam for Community / Repair and Maintenance of Earthen Check Dam for Community | Repair & Maint of Check Dam/Stop Dam | 1722004040/WC/22012034614691 — RAJAKHAL NALE PAR RMS SAH PULIYA NIRMAN BAGDITURK | Closed | 0 | 0 | 2021-01-26
DHAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1722004040/WC/22012034614692 — RAJAKHAL NALE PAR RMS SAH PULIYA NIRMAN BAGDITURK | Closed | 0 | 0 | 2021-01-26
DHAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1722004040/WC/22012034640848 — CTRA (C.P.T.NIRMAN)DHARAWARA KANKAD BAGDITURK | Completed | 78708.48 | 66502 | 2022-04-11 | 2025-01-15
DHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1722004040/WC/22012034641165 — CTRA ROOF WATER HARVESTING WORK (PANCHAYAT BHAWAN ME) BAGDITURK | Completed | 5500 | 5404 | 2021-04-13 | 2021-06-28
DHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1722004040/WC/22012034641172 — CTRA ROOF WATER HARVESTING WORK (HIGH SCHOOL ME) BAGDITURK | Completed | 5500 | 5404 | 2021-04-13 | 2021-06-28
DHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1722004040/WC/22012034794286 — SBM ISP Individualay Soak Pit Unit 50 Bagditurk | Completed | 99999.74 | 7014 | 2021-10-02 | 2025-01-15
DHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1722004040/WC/22012034794287 — SBM ISP Individualay Soak Pit Unit 50 Bagditurk | Closed | 0 | 0 | 2021-04-01
DHAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722004040/WC/22012034950660 — भू संकलन पोंड वृक्षारोपण के पास बगड़ी तुर्क | Completed | 493121.9 | 351015.2 | 2022-05-19 | 2026-03-08
DHAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722004040/WC/22012034950661 — भू संकलन पोंड वृक्षारोपण के पास बगड़ी तुर्क | Deleted | 0 | 0 | 2022-04-14
DHAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1722004040/WC/22012034950671 — नाला ट्रेंचिंग धरावरा कांकड़ बगड़ी तुर्क | Closed | 0 | 0 | 2022-04-14
DHAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1722004040/WC/22012035165155 — Nala tranching karya | New | 0 | 0 | 2024-01-26
DHAR | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1722004040/WC/22012035198781 — नाला ट्रेंचिंग धरावरा काकड़ पर बगदीतुर्क | Closed | 0 | 0 | 2024-02-20
DHAR | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1722004040/WC/22012035198782 — नाला ट्रेंचिंग धरावरा काकड़ पर बगदीतुर्क | Closed | 0 | 0 | 2024-02-20
DHAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1722004040/WC/22012035199010 — भू संकलन पौंड पुलिया के पास बगड़ीतुर्क | Closed | 390826.08 | 0 | 2024-02-20
DHAR | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722004040/WC/4020 — जल ग्रहरण ढॉचा रमेश कुमार के खेत के पास | Completed | 0 | 74711 | 2009-03-02 | 2009-06-26
DHAR | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722004040/WC/4026 — तालाब गहरीकरण धरावरा शेराखाल कांकड बगडीतुर्क | Completed | 100000 | 97596 | 2009-04-06 | 2009-06-26
DHAR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1722004040/WC/4064 — जल ग्रहरण ढॉचा भाग 2 रमेश के घर के पास बगडीतुर्क | Completed | 0 | 93800 | 2010-04-28 | 2010-05-30
DHAR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1722004040/WC/4071 — जल ग्रहरण ढांचा भाग 3 नर्सरी के पास बगडीतुर्क | Completed | 0 | 63000 | 2010-05-12 | 2010-05-30
DHAR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1722004040/WC/4079 — जल ग्रहरण ढांचा केशरलाल के खेत के पास भाग 4 बगडीतुर्क | Completed | 0 | 129000 | 2010-05-26 | 2010-05-26
DHAR | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1722004040/WC/4142 — जल संग्रहण संरचना भाग 3 बगडीतुर्क | Completed | 263000 | 173909 | 2012-02-18 | 2015-05-14
DHAR | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722004040/WC/802 — कूप निर्माण रेशमबाई बगडीतुर्क | Completed | 20000 | 0 | 2007-05-02 | 2013-01-22
DHAR | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722004040/WC/808 — तालाब गहरीकरण बगडीतुर्क | Completed | 40000 | 16200 | 2007-06-18 | 2007-07-01
DHAR | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1722004040/WC/9993621547 — जल संग्रहण ढांचा मानसि‍हं के खेत के पास बगडीतुर्क | Completed | 146000 | 38880 | 2011-01-17 | 2015-05-15
DHAR | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Sunken Pond / Construction of Community Water Harvesting Ponds | Farm Pond | 1722004040/WC/9993629270 — जल संग्रहण संरचना धरावरा काकड व़क्षारोपण के पास | Deleted | 0 | 0 | 2013-04-14
DHAR | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Sunken Pond / Construction of Community Water Harvesting Ponds | Farm Pond | 1722004040/WC/9993642020 — जल संग्रहण संरचना गफफुरखा के खेत के पास बगडीतुर्क | Completed | 324000 | 322076 | 2014-01-06 | 2015-05-15
DHAR | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1722004040/WC/9993650546 — jal grahan sarchana bagaditurk | Deleted | 0 | 0 | 2014-02-06
DHAR | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1722004040/WC/9993653449 — जल संग्रहण संरचना भाग 8 बगडी तुर्क्‍ | Completed | 280000 | 252840 | 2014-06-19 | 2016-06-11
DHAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722004/IF/22012034445764 — gabbu s/o mangilal horticulture plantetion | Closed | 116000 | 0 | 2018-12-12
DHAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722004/IF/22012034445872 — Nandram S/O Sadiya Horticulture Plantation | Closed | 79700 | 0 | 2018-12-12
DHAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722004/IF/22012034836556 — Dilip horti plantation | Closed | 206310 | 0 | 2021-06-28
DHAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722004/IF/22012034836724 — devisingh Horti Plantation | Closed | 206310 | 0 | 2021-06-28
DHAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722004/IF/22012034836725 — Mukesh Ambaram Horti Plantation | Closed | 206310 | 0 | 2021-06-28
DHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1722004/IF/22012035016363 — Devisingh awla plantation | Physically Completed | 213200 | 127679.32 | 2022-09-20 | 2026-08-12
DHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1722004/IF/22012035016378 — Punibai awala plantation | Physically Completed | 213000 | 161275.32 | 2022-09-18 | 2026-08-12
DHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1722004/IF/22012035016605 — horticulture plantation harisingh gram bagditurk | Ongoing | 213200 | 95428 | 2022-09-19
DHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1722004/IF/22012035016623 — horticulture plantation kamal gram bagditurk | Physically Completed | 213200 | 138480.94 | 2022-09-19 | 2026-08-12
DHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1722004/IF/22012035016667 — horticulture plantation dilip gram bagditurk | Physically Completed | 213200 | 139243.32 | 2022-09-18 | 2026-08-12
DHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1722004/IF/22012035016680 — horticulture plantation ratanlal gram bagditurk | Physically Completed | 213200 | 132684.94 | 2022-09-19 | 2026-08-12
DHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1722004/IF/22012035017658 — horticulture plantation sarjubai gram bagditurk | Physically Completed | 213200 | 126445.32 | 2022-10-03 | 2026-08-12
DHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722004/IF/22012035019073 — horticulture plantation sitaram gram bagditurk | Closed | 0 | 0 | 2022-04-20
DHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1722004/IF/22012035024879 — horticulture plantation sitaram gram bagditurk | Physically Completed | 213200 | 121915.32 | 2022-10-03 | 2026-08-12