## Work List
Exported on: 2026-09-11 13:57:45
Filters applied:
Data source: MGNREGA
District: DHAR
Block: All
Panchayat: Billod
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
NALCHHA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Bharat Nirman Seva Kendra / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1722005019/AV/22012034547165 — गौशाला निर्माण कार्य चंद्रपुरा सर्वे नंबर 191 पर बिल्लोद | Closed | 0 | 0 | 2020-11-24
NALCHHA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Food grain storage / Construction of Food grain Storage Building for Community | Constr of Food Grain storage | 1722005019/AV/22012034550214 — chabutra nirman uparjan kendra chandarpura | Completed | 802553.42 | 702481.45 | 2021-02-26 | 2021-10-24
NALCHHA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Construction of Cattle Shelter for Community / Construction of Cattle Shelter for Community | Cattle Shed | 1722005019/AV/22012034562538 — gou shala nirman karya chandrapura billod | Closed | 3805000 | 0 | 2021-01-04
NALCHHA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1722005019/AV/22012034574588 — RTW Dinig hall middile school Billod | Completed | 44895.93 | 26075.24 | 2021-09-16 | 2021-12-15
NALCHHA | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1722005019/DP/22012034236961 — samshan shed nirman chandrapura | Completed | 180000 | 179592.25 | 2016-12-28 | 2018-07-07
NALCHHA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1722005019/DP/22012034590405 — AKAM वसुधा वंदन अमृत वाटिका कृषि उपार्जन केन्द्र चन्द्रपुरा बिल्लौद | Ongoing | 55847.4 | 22337 | 2023-10-15
NALCHHA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Gov bldng premises Blck Plntation-Forestry-Comunty / Block Plantation of Forestry Trees in Government building premises for Community | Plantation | 1722005019/DP/22012034620912 — वृक्षारोपण कार्य कब्रस्तान परिसर बिलोद | Approved | 0 | 0 | 2024-06-16
NALCHHA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Gov building Block Plantation-Farm Forestry-Comm / Block Plantation of Farm Forestry Trees in Government building premises for Community | Plantation | 1722005019/DP/22012034621427 — वृक्षारोपण कार्य कब्रस्तान परिसर ग्राम पंचायत बिलोद | Ongoing | 382189.37 | 57902.04 | 2024-07-12
NALCHHA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Forest Protection / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1722005019/DP/9926694576 — व्‍यक्तिगत शौचालय क्रमांक 1 | Deleted | 0 | 0 | 2012-12-25
NALCHHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005019/IF/22012034296218 — c.m. aawash ritubai prakash billod | Completed | 14000 | 14028 | 2016-08-07 | 2017-03-09
NALCHHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005019/IF/22012034296235 — c.m. aawash dinesh magilal billod | Completed | 1430000000 | 13861 | 2016-08-07 | 2017-06-05
NALCHHA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005019/IF/22012034296244 — iay munalal jayram billod | Completed | 1430000000 | 14250 | 2020-05-11 | 2021-01-18
NALCHHA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005019/IF/22012034296245 — iay sajan bai ambaram billod | Closed | 14000 | 0 | 2015-12-26
NALCHHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005019/IF/22012034296248 — c.m.aawash jagdish naval billod | Completed | 1430000000 | 11142 | 2016-09-21 | 2018-03-31
NALCHHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005019/IF/22012034296250 — iay umrao babulal billod | Closed | 14000 | 0 | 2016-06-07
NALCHHA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005019/IF/22012034297055 — c.m. aawash nosads/o essak billod | Closed | 14000 | 0 | 2015-11-27
NALCHHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005019/IF/22012034297058 — iay aawash mustak s/o nane kha billod | Completed | 14000 | 18036 | 2016-09-21 | 2017-03-09
NALCHHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005019/IF/22012034297061 — iay aawash aasik s/o daud | Closed | 14000 | 0 | 2016-06-07
NALCHHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005019/IF/22012034297068 — iay jebunbai s/o majit kha billod | Completed | 14000 | 13861 | 2016-09-21 | 2017-03-09
NALCHHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005019/IF/22012034297069 — iay mehbub s/o huseen billod | Completed | 14000 | 10020 | 2016-09-21 | 2018-03-31
NALCHHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005019/IF/22012034297070 — iay muktiyaar s/o nane kha billod | Completed | 14000 | 13861 | 2016-09-21 | 2017-12-28
NALCHHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005019/IF/22012034297071 — iay saida s/o essk billod | Closed | 14000 | 0 | 2016-06-06
NALCHHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005019/IF/22012034297074 — iay usmaan s/o ajij billod | Completed | 14000 | 14615 | 2016-11-03 | 2018-03-30
NALCHHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005019/IF/22012034297080 — iay mukim s/o hakim billod | Closed | 14000 | 0 | 2016-06-07
NALCHHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005019/IF/22012034297090 — iay kaluu s/o abdul billod | Closed | 14000 | 0 | 2016-06-07
NALCHHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005019/IF/22012034297091 — iay said s/o manguu billod | Closed | 14000 | 0 | 2016-06-07
NALCHHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005019/IF/22012034297096 — iay serulal s/o bhuru billod | Completed | 14000 | 167 | 2016-11-03 | 2018-03-31
NALCHHA | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Compost Pit / Construction of Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1722005019/IF/22012034317280 — warmi copost | Closed | 0 | 0 | 2016-08-15
NALCHHA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722005019/IF/22012034368667 — varkchharopan karya panchhyat bhavan ke pass | Completed | 335000 | 4992 | 2017-08-11 | 2020-10-30
NALCHHA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722005019/IF/22012034383890 — Platation Work 2 Heq. Bilod | Closed | 0 | 0 | 2018-04-14
NALCHHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation - Shelter Belt for Individuals / Block Plantation of Shelter Belt Trees for Individuals | Plantation | 1722005019/IF/22012034808803 — nandan phalodyan vraksharopan kary abdul kasam billod | Closed | 144199.83 | 0 | 2021-04-01
NALCHHA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation of Forstry Trees for Individual / Boundary Line Plantation of Forestry Trees for Individuals | Plantation | 1722005019/IF/22012034824652 — vraksharopan nandna falodyan kary samsuddin masum bollid | Physically Completed | 144199.83 | 98576 | 2023-08-21 | 2026-06-28
NALCHHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Raising of Nursery for Individuals / Raising of Nursery for Individuals | Nursery Development | 1722005019/IF/22012035013637 — plantetion work ramesh pita narayan gp billod | Closed | 0 | 0 | 2022-07-15
NALCHHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722005019/IF/22012035032955 — वृक्षायरोपन कार्य रांनारायन के खेत पर | Ongoing | 126831.88 | 97740 | 2022-11-11
NALCHHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722005019/IF/22012035032962 — वृक्षायरोपन कार्य बसंती बाई के खेत पर | Physically Completed | 153560.72 | 104720 | 2022-11-11 | 2026-06-28
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722005019/IF/22012035494583 — jgsa khet talab ramibai pati mulchand ke khet me gp billod | Physically Completed | 73686.42 | 68847 | 2025-05-13 | 2026-05-19
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005019/IF/22012035555082 — Construction of PMAY-G House for Individuals -PMAY -G REG.NO MP113471054 | Deleted | 0 | 0 | 2025-04-01
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005019/IF/22012035555087 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116476813 | Physically Completed | 23490 | 14094 | 2025-06-17 | 2026-06-20
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005019/IF/22012035555117 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116492444 | Physically Completed | 23490 | 20097 | 2025-06-17 | 2026-06-14
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005019/IF/22012035555132 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106241903 | Closed | 23490 | 0 | 2025-06-17
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005019/IF/22012035555151 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113454793 | Physically Completed | 23490 | 20880 | 2025-06-17 | 2026-06-14
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005019/IF/22012035555169 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123015744 | Completed | 23490 | 20880 | 2025-09-10 | 2026-05-23
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005019/IF/22012035572808 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106268722 | Deleted | 0 | 0 | 2025-04-01
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005019/IF/22012035572812 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106268722 | Completed | 23460 | 23229 | 2025-06-21 | 2026-05-23
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005019/IF/22012035572817 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113457669 | Physically Completed | 23490 | 11223 | 2025-07-16 | 2026-06-24
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005019/IF/22012035572822 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117444425 | Completed | 23490 | 23490 | 2025-06-19 | 2026-02-24
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005019/IF/22012035572826 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1174444720 | Completed | 23490 | 23490 | 2025-06-21 | 2026-05-23
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005019/IF/22012035576128 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106271521 | Physically Completed | 23490 | 19836 | 2025-07-23 | 2026-06-14
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005019/IF/22012035576133 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116462144 | Completed | 23490 | 23490 | 2025-07-22 | 2025-10-14
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005019/IF/22012035576139 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126045398 | Physically Completed | 23490 | 19836 | 2025-07-23 | 2026-06-19
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005019/IF/22012035576147 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106256602 | Completed | 23490 | 23490 | 2025-08-14 | 2026-02-03
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005019/IF/22012035582941 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106131339 | Completed | 23490 | 23490 | 2025-08-30 | 2026-06-05
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005019/IF/22012035582942 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119436816 | Completed | 23490 | 23490 | 2025-08-02 | 2025-10-14
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005019/IF/22012035582943 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122837682 | Completed | 23490 | 23490 | 2025-08-30 | 2026-02-24
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005019/IF/22012035582944 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123743329 | Physically Completed | 23490 | 20097 | 2025-08-02 | 2026-06-14
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005019/IF/22012035582945 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126042963 | Completed | 23490 | 23490.04 | 2025-08-02 | 2026-05-23
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005019/IF/22012035582946 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126042318 | Completed | 23490 | 23490 | 2025-08-02 | 2025-10-14
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005019/IF/22012035600196 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO.MP106226658 | Physically Completed | 23490 | 18270 | 2025-08-30 | 2026-06-20
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005019/IF/22012035600328 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO.MP119436360 | Completed | 23490 | 23005.32 | 2025-09-03 | 2026-05-23
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005019/IF/22012035600337 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO.MP117444539 | Completed | 23490 | 23490 | 2025-09-10 | 2026-02-03
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005019/IF/22012035600345 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO.MP116462090 | Physically Completed | 23490 | 16443 | 2025-08-26 | 2026-06-20
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722005019/IF/22012035602675 — Ek bagiya Maa k nam plantation for beneficiary Raisa Bai GP Billod | Ongoing | 235664.27 | 1827 | 2025-09-10
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005019/IF/22012035649131 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113477144 | Physically Completed | 23490 | 3654 | 2026-01-27 | 2026-06-24
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005019/IF/22012035651401 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106241903 | New | 0 | 0 | 2025-10-02
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005019/IF/22012035651412 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113471054 | Physically Completed | 23490 | 9135 | 2026-02-03 | 2026-06-24
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005019/IF/22012035651896 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106244187 | Physically Completed | 23490 | 12789 | 2026-02-03 | 2026-06-26
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005019/IF/22012035651900 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123744122 | Physically Completed | 23490 | 12789 | 2026-02-03 | 2026-06-24
NALCHHA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005019/IF/9993684116 — c.m.hause ritibai prakash | Closed | 14300 | 0 | 2015-10-27
NALCHHA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005019/IF/9993684118 — c m hause radheshyam jayram | Completed | 14300 | 10528.9 | 2015-10-28 | 2018-03-31
NALCHHA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005019/IF/9993684120 — c m hause mohan shankar | Closed | 0 | 0 | 2015-10-12
NALCHHA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005019/IF/9993684122 — c m hause moahan shankar | Completed | 14300 | 13463 | 2015-10-28 | 2017-06-06
NALCHHA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005019/IF/IAY/1142586 — Construction of IAY House -IAY REG. NO. MP-22-005-019-001/120 | Approved | 23490 | 0 | 2016-03-11
NALCHHA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005019/IF/IAY/1151031 — Construction of IAY House -IAY REG. NO. MP2210157 | Approved | 23490 | 0 | 2017-05-25
NALCHHA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005019/IF/IAY/1151756 — Construction of IAY House -IAY REG. NO. MP2330391 | Closed | 17100 | 0 | 2017-05-29
NALCHHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005019/IF/IAY/1153249 — Construction of IAY House -IAY REG. NO. MP2580091 | Completed | 17100 | 17019 | 2022-08-16 | 2024-09-25
NALCHHA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005019/IF/IAY/1155461 — Construction of IAY House -IAY REG. NO. MP2995980 | Completed | 15480 | 14964 | 2019-01-08 | 2019-02-17
NALCHHA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005019/IF/IAY/1318349 — Construction of IAY House -IAY REG. NO. MP2419950 | Completed | 15480 | 14616 | 2018-05-25 | 2018-07-22
NALCHHA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005019/IF/IAY/1318397 — Construction of IAY House -IAY REG. NO. MP2433797 | Completed | 15480 | 14616 | 2018-05-25 | 2018-07-22
NALCHHA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005019/IF/IAY/1553978 — Construction of IAY House -IAY REG. NO. MP2248279 | Completed | 15480 | 15660 | 2018-05-25 | 2018-11-10
NALCHHA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005019/IF/IAY/1789190 — Construction of IAY House -IAY REG. NO. MP3608267 | Deleted | 17100 | 0 | 2018-05-25
NALCHHA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005019/IF/IAY/1803218 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2307719 | Completed | 15660 | 15138 | 2018-07-29 | 2018-11-05
NALCHHA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005019/IF/IAY/200138 — Construction of IAY House -IAY REG. NO. MP-22-005-019-001/105 | Approved | 23490 | 0 | 2016-02-18
NALCHHA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005019/IF/IAY/201215 — Construction of IAY House -IAY REG. NO. MP-22-005-019-001/107 | Approved | 23490 | 0 | 2016-03-11
NALCHHA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005019/IF/IAY/203392 — Construction of IAY House -IAY REG. NO. MP-22-005-019-001/97 | Completed | 15030 | 9460 | 2018-02-02 | 2018-07-08
NALCHHA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005019/IF/IAY/203395 — Construction of IAY House -IAY REG. NO. MP-22-005-019-001/116 | Closed | 23490 | 0 | 2016-03-11
NALCHHA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005019/IF/IAY/203396 — Construction of IAY House -IAY REG. NO. MP-22-005-019-001/125 | Approved | 23490 | 0 | 2016-03-11
NALCHHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005019/IF/IAY/203400 — Construction of IAY House -IAY REG. NO. MP-22-005-019-001/140 | Completed | 15030 | 14484 | 2022-09-07 | 2023-08-25
NALCHHA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005019/IF/IAY/203402 — Construction of IAY House -IAY REG. NO. MP-22-005-019-001/106 | Approved | 23490 | 0 | 2016-03-11
NALCHHA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005019/IF/IAY/2986875 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3964270 | Closed | 17100 | 0 | 2021-03-27
NALCHHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005019/IF/IAY/3686339 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113459849 | Completed | 18360 | 17544 | 2022-06-19 | 2023-03-29
NALCHHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005019/IF/IAY/3691475 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113465278 | Completed | 18360 | 16503 | 2022-07-17 | 2023-12-21
NALCHHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005019/IF/IAY/3962492 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106130918 | Completed | 18360 | 17748 | 2022-08-23 | 2023-02-25
NALCHHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005019/IF/IAY/3965223 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113468793 | Completed | 18360 | 17952 | 2022-06-19 | 2022-10-04
NALCHHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005019/IF/IAY/3966328 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106235312 | Completed | 18360 | 17544 | 2022-06-19 | 2023-01-27
NALCHHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005019/IF/IAY/3976313 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116474925 | Completed | 18360 | 17782 | 2022-09-17 | 2024-05-08
NALCHHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005019/IF/IAY/3978187 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119436667 | Completed | 18360 | 17544 | 2022-06-19 | 2023-02-25
NALCHHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005019/IF/IAY/3982447 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120759719 | Completed | 18360 | 17952 | 2022-07-14 | 2022-11-12
NALCHHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005019/IF/IAY/4277458 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119436140 | Completed | 18360 | 1428 | 2022-08-23 | 2025-01-20
NALCHHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005019/IF/IAY/4543616 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106251725 | Completed | 21870 | 20169 | 2024-10-24 | 2025-02-12
NALCHHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005019/IF/IAY/4544812 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106131603 | Completed | 21870 | 21870 | 2024-10-31 | 2025-02-12
NALCHHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005019/IF/IAY/4574449 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117445069 | Completed | 23490 | 21627 | 2024-12-05 | 2025-05-03
NALCHHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005019/IF/IAY/496207 — Construction of IAY House -IAY REG. NO. MP2209784 | Completed | 15030 | 15470 | 2017-03-01 | 2018-02-23
NALCHHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005019/IF/IAY/496233 — Construction of IAY House -IAY REG. NO. MP2210051 | Completed | 15030 | 16076 | 2017-03-01 | 2018-07-07
NALCHHA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005019/IF/IAY/496241 — Construction of IAY House -IAY REG. NO. MP2210090 | Completed | 15030 | 15204 | 2017-10-11 | 2018-07-26
NALCHHA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005019/IF/IAY/499082 — Construction of IAY House -IAY REG. NO. MP2241156 | Completed | 15030 | 15002 | 2017-10-11 | 2018-08-01
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005019/IF/IAY/5358363 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106131842 | Ongoing | 23490 | 19836 | 2025-04-16
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005019/IF/IAY/5361513 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116462036 | Completed | 23490 | 23490 | 2025-05-21 | 2026-02-03
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005019/IF/IAY/5364259 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106210107 | Completed | 23490 | 23229 | 2025-04-16 | 2026-05-25
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005019/IF/IAY/5367039 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113487091 | Completed | 23490 | 22968 | 2025-04-23 | 2026-05-25
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005019/IF/IAY/5380799 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104995952 | Ongoing | 23490 | 8874 | 2025-09-10
NALCHHA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005019/IF/IAY/55122 — Construction of IAY House -IAY REG. NO. MP-22-005-019-001/17 | Approved | 23490 | 0 | 2015-10-26
NALCHHA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005019/IF/IAY/55123 — Construction of IAY House -IAY REG. NO. MP-22-005-019-001/20 | Approved | 23490 | 0 | 2015-10-26
NALCHHA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005019/IF/IAY/740453 — Construction of IAY House -IAY REG. NO. MP2241176 | Completed | 17100 | 15960 | 2020-08-17 | 2021-03-17
NALCHHA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005019/IF/IAY/742768 — Construction of IAY House -IAY REG. NO. MP2308517 | Completed | 15030 | 14644 | 2018-07-11 | 2019-09-09
NALCHHA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005019/IF/IAY/743860 — Construction of IAY House -IAY REG. NO. MP2341496 | Completed | 15030 | 15002 | 2017-12-22 | 2018-07-20
NALCHHA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005019/IF/IAY/744036 — Construction of IAY House -IAY REG. NO. MP2346002 | Completed | 15030 | 14964 | 2018-02-15 | 2018-09-21
NALCHHA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Upland Bench Terrace Terrace for Comm / Construction of Upland Bench Terrace for Community | Terracing | 1722005019/LD/22012034540323 — construction of food grain storage | Closed | 0 | 0 | 2021-01-26
NALCHHA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1722005019/LD/22012034942176 — शमशान घाट समतलीकरण कार्य ग्राम चंदरपुरा पंचायत बिल्लौद | Approved | 0 | 0 | 2024-06-22
NALCHHA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1722005019/LD/22012034944464 — Shamshaan Ghaat Bhoomi samataleekaran gram chandarpura Gp Billod | Approved | 0 | 0 | 2024-06-16
NALCHHA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1722005019/LD/22012034944465 — Shamshaan Ghaat Bhoomi samataleekaran Kary Gp Billod | Approved | 0 | 0 | 2024-06-16
NALCHHA | 2012-2013 | D--RURAL INFRASTUCTURE / Other Works | Maintenance of rural public assets / Repair and Maintenance of Gram Panchayat/Panchayat Bhavan Building for Community | Repair & Maint of Community infrastructure | 1722005019/OP/9425881488 — पंचायत भवन विस्‍तार कार्य | Deleted | 0 | 0 | 2012-12-25
NALCHHA | 2005-2006 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005019/RC/0000000000 — गलत इंटरी | Deleted | 110000 | 0 | 2006-02-02
NALCHHA | 2005-2006 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005019/RC/1002 — ग्रेवल मार्ग अनवर के घर से बाबु के खेत तक | Deleted | 0 | 0 | 2006-03-01
NALCHHA | 2006-2007 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005019/RC/1003 — ग्रेवल मार्ग अनवर के घर से बाबु के खेत तक | Completed | 191000 | 0 | 2007-01-13 | 2010-03-26
NALCHHA | 2006-2007 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005019/RC/10047 — ग्रेवल मार्ग रहीश के मकान से खारचा नाला तक | Completed | 191000 | 336267 | 2007-01-22 | 2007-09-30
NALCHHA | 2006-2007 | D--RURAL INFRASTUCTURE / Rural Connectivity | Metal Second coat / Construction of WBM Roads for Community | Construction of Road and Culvert | 1722005019/RC/21 — पाईप पुलीया निमार्ण बागला | Deleted | 186000 | 0 | 2006-04-17
NALCHHA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005019/RC/22012034158741 — ग्रेवल मार्ग चन्‍द्रपुरा भाग 1 | Deleted | 0 | 0 | 2012-12-25
NALCHHA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005019/RC/22012034158746 — मिटटी मुरम सडक कार्य क्रमांक 2 | Deleted | 0 | 0 | 2012-12-25
NALCHHA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005019/RC/22012034158747 — मिटटी मुरम सडक कार्य क्रमांक 3 | Deleted | 0 | 0 | 2012-12-25
NALCHHA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722005019/RC/22012034158748 — पंच परमेश्‍वर सीसी रोड क्रमांक 1 | Deleted | 0 | 0 | 2012-12-25
NALCHHA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722005019/RC/22012034158749 — पंच परमेश्‍वर सीसी रोड क्रमांक 6 | Deleted | 0 | 0 | 2012-12-25
NALCHHA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722005019/RC/22012034158753 — क्रास डे्नेज कार्य बिल्‍लौद | Deleted | 0 | 0 | 2012-12-25
NALCHHA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722005019/RC/22012034172153 — पंच परमेश्‍वर सी सी रोड आंतरिक मार्ग श्रीराम मंदीर | Completed | 190000 | 186616 | 2013-06-24 | 2015-12-31
NALCHHA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722005019/RC/22012034182652 — पंच परमेश्‍वर सी सी रोड आंतरिक मार्ग लोहार साद से | Completed | 232000 | 231554 | 2013-09-07 | 2015-12-31
NALCHHA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722005019/RC/22012034190017 — सीमेंट कांक्रेट रोड सांसद निधी दाउद पटेल के घर से | Completed | 125000 | 71806.2 | 2013-10-11 | 2015-12-19
NALCHHA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005019/RC/22012034218113 — muram marg billod talab se ibrahim ke ket tak gram | Completed | 1172000 | 228215.3 | 2014-05-14 | 2017-01-10
NALCHHA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005019/RC/22012034298900 — khet sadak niman jagdish ke khet se sunder lal ke khat tak | Deleted | 0 | 0 | 2016-02-11
NALCHHA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005019/RC/22012034300032 — खेत सडक निर्माण जगदीश के खेत से सुदरलाल के खेत तक बिल्‍लोद | Deleted | 0 | 0 | 2016-01-26
NALCHHA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005019/RC/22012034312542 — khet sadak upyojna grawal marg nirman kailash chodhari ke khet se sarof munsi ke khet tak bilod | Deleted | 1495000 | 0 | 2016-03-31
NALCHHA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005019/RC/22012034312555 — khet sadak marg kelash choudhary ke khet se shareef munshi ke khet tak | Completed | 1495000 | 20708 | 2016-05-08 | 2017-01-10
NALCHHA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005019/RC/22012034321651 — sudur sadak nirman billod se maharajkhedi | Completed | 1444000 | 1442174.17 | 2017-01-27 | 2018-08-01
NALCHHA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005019/RC/22012034322543 — grawal marg | Closed | 0 | 0 | 2016-08-15
NALCHHA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005019/RC/22012034369176 — pipe puliya nirman kunjrod ke nale wala rashta billod | Completed | 570000 | 567784.5 | 2018-05-19 | 2019-01-20
NALCHHA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005019/RC/22012034373655 — Sudur Smpark Sadak | Closed | 0 | 0 | 2018-04-14
NALCHHA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005019/RC/22012034437541 — Sudur gram samprak sadak NIRMAN BILLOD | Closed | 0 | 0 | 2019-04-04
NALCHHA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Gravel Road Roads for Comm / Repair and maintenance of Gravel Road Roads for Community | Repair & maint of Road | 1722005019/RC/22012034511908 — sudur sadak ajmeri sarpacha keghar se pipliya rod thak | Closed | 0 | 0 | 2019-11-23
NALCHHA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Gravel Road Roads for Comm / Repair and maintenance of Gravel Road Roads for Community | Repair & maint of Road | 1722005019/RC/22012034511909 — sudur sadak ajmeri sarpacha keghar se pipliya ro | Closed | 0 | 0 | 2019-12-23
NALCHHA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722005019/RC/22012034512341 — c c roud nirnan shamshan ghat chandar pura | Closed | 0 | 0 | 2019-12-23
NALCHHA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Gravel Road Roads for Comm / Repair and maintenance of Gravel Road Roads for Community | Repair & maint of Road | 1722005019/RC/22012034520440 — sudur shadak ajmari ke ghar se bilod fata | Closed | 0 | 0 | 2019-12-23
NALCHHA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722005019/RC/22012034520567 — CC ROAD NIRMAN SHAMSHAN GHAT CHANDRAPURA BILLOD | Closed | 23000 | 0 | 2018-04-14
NALCHHA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of WBM Roads for Community / Construction of WBM Roads for Community | Construction of Road and Culvert | 1722005019/RC/22012034540213 — sudur sadak prdhanmantri road shiv mandir serayan kakad tak bilod | Physically Completed | 1457547.12 | 1448664.57 | 2020-11-17 | 2026-06-20
NALCHHA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Interlocking block/tiles Roads for Comm / Construction of Inter-locking cement block/tiles Roads for Community | Constr of Cement Concrete Roads | 1722005019/RC/22012034679907 — नाली निर्माण कार्य सफ़ी के घर से तालाब तक | Completed | 45000 | 44919 | 2024-03-05 | 2024-09-13
NALCHHA | 2007-2008 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005019/RC/50079 — Haum Paipe Puliya Nirman Bangla Billod RES | Completed | 0 | 1870233.09 | 2007-06-19 | 2008-12-03
NALCHHA | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005019/RC/50253 — ग्रेवल मार्ग चंद्रपुरा से रायण खदान बि‍ल्‍लोद RES | Completed | 0 | 674511.7 | 2009-11-03 | 2011-11-21
NALCHHA | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005019/RC/50315 — पाईप पुलिया निर्माण कार्य खारचा नाला बिल्‍लोद ग्राम पंचायत बिल्‍लोद | Completed | 0 | 403555 | 2009-06-07 | 2012-09-16
NALCHHA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005019/RC/50467 — ग्रेवल मार्ग बि‍ल्‍लोद से कुंजरोद पहुच बि‍ल्‍लोद | Deleted | 500000 | 144919.8 | 2010-05-20
NALCHHA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005019/RC/50523 — मुरम रोड निर्माण्‍ा निर्माण कार्य चन्‍द्रपुरा से शमशान घाट की ओर ग्राम पंचायत बिल्‍लोद | Completed | 0 | 142780 | 2010-07-02 | 2012-09-10
NALCHHA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722005019/RC/50660 — सीमेन्‍ट कांक्रिट खरंजा निर्माण कार्य मनोहर के घर से पिपल्‍या रोड तक बिल्‍लोद | Completed | 0 | 133068 | 2011-07-19 | 2011-09-25
NALCHHA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005019/RC/50720 — मुरम मार्ग निर्माण अकबर पटेल के घर से नाईबरोदा तक ग्राम पंचायत बिल्‍लोद | Completed | 0 | 397776 | 2011-07-07 | 2012-10-21
NALCHHA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722005019/RC/50844 — Panch parmeshvar si si roed antrik marga aganvadi se agbar patel ke gar tak garam panchayat billod | Completed | 164000 | 120988 | 2012-09-24 | 2013-10-30
NALCHHA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1722005019/RS/22012034531964 — SBM SCP BILLOD | Closed | 0 | 0 | 2021-04-01
NALCHHA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1722005019/RS/22012034569040 — SBM compost pit nirman ravi nadram ke ghar ke pas Billod | Closed | 20615.17 | 0 | 2021-04-01
NALCHHA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Groups / Construction of Compost Pit for Groups | Construction of NADEP/Vermi Compost Pit | 1722005019/RS/22012034569430 — SBM compost pit nirman ramesh narayan ke ghar ke pas Billiod | Closed | 20615.17 | 0 | 2021-04-01
NALCHHA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1722005019/RS/22012034570551 — SBM SP panchayat bhawan ke pas Billod | Closed | 0 | 0 | 2021-04-01
NALCHHA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1722005019/RS/22012034570553 — SBM SP panchayat bhawan ke pas Billod | Closed | 0 | 0 | 2021-04-01
NALCHHA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1722005019/RS/22012034570554 — SBM SP Jasibai ke ghar ke pas Billod | Closed | 0 | 0 | 2021-04-01
NALCHHA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1722005019/RS/22012034570557 — SBM SP Shiv mandir ke pas Billod | Closed | 0 | 0 | 2021-04-01
NALCHHA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1722005019/RS/22012034570559 — SBM SP Chandar pura road par Billod | Closed | 0 | 0 | 2021-04-01
NALCHHA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1722005019/RS/22012034570560 — SBM SP Chandar pura road par Billod | Closed | 0 | 0 | 2021-04-01
NALCHHA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1722005019/RS/22012034570561 — SBM SP Chandar pura road par Billod | Closed | 0 | 0 | 2021-04-01
NALCHHA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1722005019/RS/22012034585234 — SBM ILP Dasharath +Bharat+dasharath+Aamrth+Bhuriya Billod | Closed | 22969.29 | 0 | 2021-04-01
NALCHHA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1722005019/RS/22012034585247 — SBM ILP Mukesh+Mahesh+ Sanjay+ Ashok+Gajanand Billod | Closed | 22969.29 | 0 | 2021-04-01
NALCHHA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1722005019/RS/22012034585264 — SBM ILP Ramlal+Mohan+Subhash+Staram+ramesh Billod | Closed | 22969.29 | 0 | 2021-04-01
NALCHHA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1722005019/RS/22012034585270 — SBM ILP Prakash+Dinesh+Jagdish+Kallu+Ramesh Billod | Closed | 22969.29 | 0 | 2021-04-01
NALCHHA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1722005019/RS/22012034585276 — SBM ILP Ashok+Mukesh+Ramprasad+Lakhan+Govind Billod | Closed | 22969.29 | 0 | 2021-04-01
NALCHHA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1722005019/RS/22012034585283 — SBM ILP aoshab+Jayed+Akaram+Lalu+Katyub Billod | Closed | 22969.29 | 0 | 2021-04-01
NALCHHA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1722005019/RS/22012034585287 — SBM ILP Munalal+Maniram+Shankar+Bhagirath+Suresh Billod | Closed | 22969.29 | 0 | 2021-04-01
NALCHHA | 2006-2007 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722005019/WC/09 — पाईप पुलिया निर्माण बिल्‍लोद | Completed | 186000 | 147170 | 2006-04-21 | 2007-09-30
NALCHHA | 2006-2007 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722005019/WC/196 — खेत तालाब हिरालाल भैरा बागंला, महाराजखेडी | Completed | 0 | 0 | 2006-06-06 | 2009-06-03
NALCHHA | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Dam / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1722005019/WC/22012034317818 — sankan pond nirman | Closed | 0 | 0 | 2016-10-02
NALCHHA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Dam / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1722005019/WC/22012034380374 — sankan pond nirman billod | Closed | 0 | 0 | 2017-10-02
NALCHHA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722005019/WC/22012034430613 — Sunkan pond nirman kharcha wali par billod | Completed | 431000 | 419214 | 2019-01-11 | 2020-01-21
NALCHHA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1722005019/WC/22012034433610 — SANKAN POND NIRMAN BILLOD | Closed | 0 | 0 | 2019-04-04
NALCHHA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand filter for borewell recharge for Community | Well Recharge | 1722005019/WC/22012034481380 — saok pit school parisar me | Closed | 0 | 0 | 2019-04-26
NALCHHA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand filter for borewell recharge for Community | Well Recharge | 1722005019/WC/22012034481381 — saok pit chanderpura mjara | Closed | 0 | 0 | 2019-04-26
NALCHHA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1722005019/WC/22012034519874 — Nala trenching nadi ke pass billod | Completed | 285624.24 | 234080 | 2020-05-11 | 2021-05-05
NALCHHA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1722005019/WC/22012034541259 — shakan pond ram narayan | Closed | 0 | 0 | 2019-12-23
NALCHHA | 2019-2020 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Earthen Spur for Community / Construction of Earthen Spur for Community | Construction of Spur | 1722005019/WC/22012034541260 — bolder chek dem nirman 1 | Closed | 0 | 0 | 2019-12-23
NALCHHA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1722005019/WC/22012034634419 — CTRA- Nala traching nadi wala nala | Closed | 0 | 0 | 2021-01-22
NALCHHA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1722005019/WC/22012034634420 — CTRA- Nala traching kharcha wala | Closed | 0 | 0 | 2021-01-22
NALCHHA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1722005019/WC/22012034634422 — CTRA- Sankan pond nirman | Closed | 0 | 0 | 2021-01-22
NALCHHA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1722005019/WC/22012034634423 — CTRA-Khet talab Radheshyam kesarlal | Closed | 0 | 0 | 2021-01-22
NALCHHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722005019/WC/22012034637118 — CTRA Samudayik pond nirman radhesham ke khet ke pas Billod | Closed | 0 | 0 | 2021-04-01
NALCHHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1722005019/WC/22012034646862 — CTRA Roof top water harvesting middle school Billod | Completed | 24910.3 | 27185 | 2021-05-08 | 2021-10-05
NALCHHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1722005019/WC/22012034646874 — CTRA Roof top water harvesting primary school Billod | Completed | 25614.4 | 22610 | 2021-05-08 | 2021-09-30
NALCHHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1722005019/WC/22012034665507 — CTRA Samudayik pond nirman akram ke khet ke pas Billod | Ongoing | 411157.38 | 26590 | 2022-01-30
NALCHHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1722005019/WC/22012034708528 — CTRA Roof top water harvesting Aaganwadi bhawan Billod | Completed | 26397 | 22770 | 2021-08-11 | 2023-11-29
NALCHHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1722005019/WC/22012034708533 — CTRA Roof top water harvesting primary school Chandanpura Billod | Completed | 31112.32 | 24226 | 2021-09-30 | 2021-11-18
NALCHHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1722005019/WC/22012034708539 — CTRA Roof top water harvesting society chandanpura Billod | Completed | 23558.37 | 17500 | 2021-09-11 | 2021-11-15
NALCHHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1722005019/WC/22012035011110 — खेत तालब श्यामलाल पिता हीरालाल के खेत पर बिलोद | Closed | 0 | 0 | 2022-08-16
NALCHHA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & maint of Fisheries Ponds for Comm / Repair and maintenance of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1722005019/WC/22012035013523 — फार्म पॉण्ड श्यामलाल पिता हरचंद ग्राम पंचायत बिलोद | Closed | 0 | 0 | 2022-08-16
NALCHHA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1722005019/WC/22012035109202 — nala tenching | Closed | 0 | 0 | 2023-08-15
NALCHHA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1722005019/WC/22012035109258 — nala trenching | Closed | 0 | 0 | 2023-08-15
NALCHHA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1722005019/WC/22012035109277 — nala trenching sindhi ghat se dargah tak billod | Completed | 344270.08 | 109648 | 2023-10-01 | 2024-09-23
NALCHHA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1722005019/WC/22012035109279 — nala tenching dargah se billod kakad tak gram billod | Closed | 0 | 0 | 2023-08-15
NALCHHA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1722005019/WC/22012035109280 — nala tenching dargah se billod kakad tak gram billod | Closed | 0 | 0 | 2023-08-15
NALCHHA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1722005019/WC/22012035109393 — nala trenching sindhi ghat se dargah tak billod | Closed | 0 | 0 | 2023-08-15
NALCHHA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1722005019/WC/22012035109401 — nala trenching pir dargah se billod kakad tak | Physically Completed | 386853.9 | 144310.7 | 2023-10-01 | 2026-06-20
NALCHHA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1722005019/WC/22012035142212 — STOP DAM CUM PULLIYA NIRMAN BADI NADI PAR BILOD | Ongoing | 1495283.2 | 1348.04 | 2023-10-08
NALCHHA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1722005019/WC/22012035163789 — Percolation tank | New | 0 | 0 | 2024-04-01
NALCHHA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722005019/WC/22012035243387 — Farm Pond Nirman Narendra Pita Ramlal Ke Khet me | Ongoing | 322287.24 | 235854 | 2025-01-22
NALCHHA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722005019/WC/80491 — स्‍टाप डेम कार्य श्‍मशान घाट नदी के आगे बि‍ल्‍लौद | Completed | 0 | 386400 | 2009-02-28 | 2009-08-31
NALCHHA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1722005019/WC/9993628432 — संकन पोंड निर्माण बिल्‍लौद | Deleted | 0 | 0 | 2012-12-25
NALCHHA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Sunken Pond / Construction of Community Water Harvesting Ponds | Farm Pond | 1722005019/WC/9993666649 — sankun pond nirman narayan ke khet ke paas | Deleted | 491000 | 0 | 2016-02-11
NALCHHA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Sunken Pond / Construction of Community Water Harvesting Ponds | Farm Pond | 1722005019/WC/9993667452 — सकंन पोण्‍ड नारायण के खेत के पास | Deleted | 0 | 0 | 2016-01-26
NALCHHA | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Sunken Pond / Construction of Community Water Harvesting Ponds | Farm Pond | 1722005019/WC/9993674701 — sankanpownd nirmaan billod | Completed | 607000 | 607321.22 | 2016-04-18 | 2017-11-20
NALCHHA | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1722005019/WH/19956565 — TALAB UNNAYAN KARYA CHANDRAPURA | Deleted | 104000 | 0 | 2016-05-24
NALCHHA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1722005019/WH/19961853 — tank renovation | Deleted | 0 | 0 | 2017-05-22
NALCHHA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1722005019/WH/19962160 — tank renovation | Deleted | 0 | 0 | 2017-05-15
NALCHHA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1722005019/WH/19962167 — talab jirnodhar chndrapura billod | Completed | 415000 | 85656 | 2017-05-29 | 2018-07-07
NALCHHA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722005/IF/22012034436137 — horticulture plantation banesingh chagan billod | Completed | 190000 | 89435.5 | 2018-11-03 | 2024-08-23
NALCHHA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722005/IF/22012034436141 — horticulture plantation farzana b billod | Completed | 140600 | 83283.6 | 2018-11-03 | 2024-08-29
NALCHHA | 2020-2021 | D--RURAL INFRASTUCTURE / Coastal Areas | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1722/CA/22012034523903 — gou shala nirman karya chandrapura billod | Closed | 3805000 | 0 | 2021-01-04