## Work List
Exported on: 2026-09-15 06:59:30
Filters applied:
Data source: MGNREGA + VBGRAMG
District: DHAR
Block: All
Panchayat: Kathodiya
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
NALCHHA | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1722005024/AV/22012034401203 — shamshan shed nirman | Completed | 180000 | 171489 | 2019-03-08 | 2021-11-15
NALCHHA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert / cross drainage structues for Community | Culvert | 1722005024/AV/22012034599483 — DINING HALL P.SCHOOL KATHODIYA.RTW | Completed | 46690.94 | 10229 | 2021-09-30 | 2026-04-06
NALCHHA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Construction of Fish Drying Yards for Community / Construction of Fish Drying Yards for Community | Construction of Fish Drying Infrastructure | 1722005024/AV/22012034604405 — DINING HALL M.S. KATHODIYA.RTW | Closed | 0 | 0 | 2021-10-02
NALCHHA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1722005024/DP/22012034494026 — plantation work shamshan ke pass kathodiya | Completed | 385674.48 | 200755 | 2020-09-15 | 2024-07-26
NALCHHA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1722005024/DP/22012034494685 — plantation work in shamshaan ghat kathodiya | Closed | 0 | 0 | 2020-08-21
NALCHHA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1722005024/DP/22012034565379 — Plaantation shamshan ghat groop no. 1 | Closed | 412718.19 | 0 | 2022-04-01
NALCHHA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Shelter Belt Trees (Comm) / Boundary Line Plantation of Shelter Belt Trees for Community | Plantation | 1722005024/DP/22012034589158 — AKAM wasudha vandan amrat watika Shamshan ke pas kathodiya | Closed | 55847.4 | 0 | 2023-04-01
NALCHHA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Block Plantation - Farm Forestry-Community / Along the coast Block Plantation of Farm Forestry Trees for Community | Plantation | 1722005024/DP/22012034628303 — प्लांटेशन शमशान घाट पर भाग 2 | New | 0 | 0 | 2024-08-15
NALCHHA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Block Plantation - Farm Forestry-Community / Along the coast Block Plantation of Farm Forestry Trees for Community | Plantation | 1722005024/DP/22012034628304 — प्लांटेशन शमशान घाट पर भाग 2 | New | 0 | 0 | 2024-08-15
NALCHHA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1722005024/DP/22012034628417 — Plantation work at shamshan ghat Kathdiya part 2 | New | 0 | 0 | 2024-10-02
NALCHHA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1722005024/DP/22012034628418 — Plantation work at shamshan ghat Kathdiya part 2 | Ongoing | 476430.48 | 65575.09 | 2024-10-28
NALCHHA | 2013-2014 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1722005024/DP/9926699994 — शांतीवन कार्य कठोडिया | Completed | 498000 | 274063 | 2014-02-15 | 2018-07-05
NALCHHA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Flood Control and Protection | Cross Bund / Construction of Earthen graded Bund for Community | Works for Flood Control and Protection | 1722005024/FP/10 — शासकीय नाला डायवर्सन कार्य जल संसाधन कार्य कठोडिया | Completed | 480045 | 144160 | 2008-05-04 | 2012-07-11
NALCHHA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Construction of water courses Canal for Community / Construction of water courses for Community | Construction of Canal | 1722005024/IC/22012034885512 — वृक्षारोपण कार्य श्मशान घाट पर भाग 2 | New | 0 | 0 | 2024-08-15
NALCHHA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Construction of water courses Canal for Community / Construction of water courses for Community | Construction of Canal | 1722005024/IC/22012034885970 — खेत तालाब प्रेम नारायण के खेत पर कठोडिया | New | 0 | 0 | 2024-10-02
NALCHHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005024/IF/22012034299091 — C.M.HAUSH BHERUSING-SHIYAMLAL | Completed | 134000 | 13861 | 2016-10-04 | 2018-07-02
NALCHHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005024/IF/22012034299181 — CM.HARUSH Omparkas-badri | Completed | 134000 | 13861 | 2016-10-04 | 2018-01-31
NALCHHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005024/IF/22012034299184 — CM.HAUSH LALCHIND-PANALAL | Completed | 134000 | 16700 | 2016-10-04 | 2017-02-20
NALCHHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005024/IF/22012034299186 — CM.HAUSH RAMESHA-GANPAT | Completed | 134000 | 14028 | 2016-11-01 | 2018-02-23
NALCHHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005024/IF/22012034299187 — CM.HAUSHH MANGILAL -RAMRATAN | Completed | 134000 | 13861 | 2016-10-04 | 2018-02-23
NALCHHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005024/IF/22012034299210 — Cm.haush nirendri -bharatsing | Completed | 134000 | 16199 | 2016-10-04 | 2017-02-20
NALCHHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005024/IF/22012034299211 — Cm.haush nirendri -bharatsing | Closed | 0 | 0 | 2016-08-15
NALCHHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005024/IF/22012034302331 — C.M HOuses-Dinesh Ambaram katodiya | Completed | 15030 | 13861 | 2016-12-20 | 2018-07-02
NALCHHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005024/IF/22012034302721 — C.M .HOUSES DILIP-AMbaram kathodiya | Completed | 134000 | 13527 | 2016-11-08 | 2018-07-02
NALCHHA | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Compost Pit / Construction of Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1722005024/IF/22012034317440 — warmi compost | Closed | 0 | 0 | 2016-08-15
NALCHHA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005024/IF/22012034344537 — CM awash Mahes-badri | Closed | 0 | 0 | 2017-04-14
NALCHHA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005024/IF/22012034344925 — CM AWASH.Nindkisoir-Radhsiyam | Completed | 134000 | 13760 | 2017-10-10 | 2018-01-19
NALCHHA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005024/IF/22012034344934 — CM.Awash MAhes-Badri | Completed | 134000 | 13760 | 2017-10-10 | 2018-01-19
NALCHHA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Forestry Trees-Fields-Individuals / Block Plantation of Forestry Trees in Fields for Individuals | Plantation | 1722005024/IF/22012034364052 — visaropan kary kathodiya bondir bhima | Completed | 335000 | 24866 | 2017-08-08 | 2020-05-20
NALCHHA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Forestry Trees-Fields-Individuals / Block Plantation of Forestry Trees in Fields for Individuals | Plantation | 1722005024/IF/22012034365231 — Varsa Ropan kary Babulal Amirsing | Completed | 335000 | 220988 | 2017-08-08 | 2022-10-17
NALCHHA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722005024/IF/22012034384479 — Platation Work 2 Heq. Kathodiya | Closed | 0 | 0 | 2018-04-14
NALCHHA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005024/IF/22012034391088 — CM Awash kamal bhatu | Closed | 14000 | 0 | 2017-08-02
NALCHHA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005024/IF/22012034391091 — CM Awash lokendra subhash | Closed | 14000 | 0 | 2017-08-02
NALCHHA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005024/IF/22012034391100 — CM.AWASH UNKAR GENDHALAL | Closed | 14000 | 0 | 2017-08-02
NALCHHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005024/IF/22012035030148 — pm aawas Shriram nagga ji kathodiya | Completed | 18600 | 18499 | 2022-11-04 | 2024-07-04
NALCHHA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722005024/IF/22012035182081 — Khet talab nirman premnarayan ke khet par | Closed | 0 | 0 | 2023-10-02
NALCHHA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation - Shelter Belt for Individuals / Block Plantation of Shelter Belt Trees for Individuals | Plantation | 1722005024/IF/22012035261382 — प्लांटेशन शमशान घाट पर भाग 2 | New | 0 | 0 | 2024-08-15
NALCHHA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Mini Percolation Tank for Individuals / Construction of Mini Percolation Tank for Individuals | Construction of Percolation Tank | 1722005024/IF/22012035272846 — khet talab nirman premnarayan khet me kathodiya | New | 0 | 0 | 2024-10-02
NALCHHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1722005024/IF/22012035273725 — khet talab nirman karya premnarayan ke khet par GP kathodiya | Physically Completed | 229752.66 | 224643.36 | 2025-01-10 | 2026-06-17
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1722005024/IF/22012035358198 — khet Talab nirman karya at Santosh ke khet par GP Kathodiya | New | 0 | 0 | 2025-04-01
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1722005024/IF/22012035359985 — khet Talab nirman karya at Santosh ke khet par GP Kathodiya | Ongoing | 299205.55 | 201931.06 | 2025-04-23
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1722005024/IF/22012035360003 — khet Talab nirman karya at Girdhari ke khet par GP Kathodiya | Ongoing | 299205.55 | 261 | 2025-05-17
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005024/IF/22012035598850 — Construction of IAY House -IAY REG. NO. MP120914057 | Physically Completed | 23490 | 8352 | 2025-10-01 | 2026-06-12
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005024/IF/22012035598926 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO.MP120255749 | Completed | 23490 | 22446 | 2025-10-08 | 2026-03-10
NALCHHA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005024/IF/9993684116 — इंदरिा अावास लिलाबाई रामाजी | Deleted | 0 | 0 | 2015-08-15
NALCHHA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005024/IF/9993684131 — इंदरिा अावास कमलाबाई हरिराम | Completed | 14000 | 13979 | 2015-10-27 | 2016-10-06
NALCHHA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005024/IF/9993684138 — इंदरिा अावास क्रष्‍णलाल सिताराम | Completed | 14000 | 14004 | 2015-10-27 | 2016-10-06
NALCHHA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722005024/IF/9993684142 — इंदरिा अावास लिलाबाई रामाजी | Closed | 0 | 0 | 2015-08-15
NALCHHA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005024/IF/9993684145 — इंदिरा आवास लिलाबाई रामाजी | Completed | 14000 | 14020 | 2015-10-27 | 2017-03-09
NALCHHA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722005024/IF/9993690096 — pasu sed lilabai gendalal | Closed | 8676803000 | 0 | 2015-08-15
NALCHHA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722005024/IF/9993690327 — mangilal nindkisoir pirsused nirmann | Closed | 0 | 0 | 2015-08-15
NALCHHA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722005024/IF/9993690335 — mangilal nandkishore pasused nirman | Closed | 0 | 0 | 2015-08-15
NALCHHA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722005024/IF/9993690337 — nathu sing chhitr parsu sed nirman | Closed | 0 | 0 | 2015-08-15
NALCHHA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722005024/IF/9993690553 — pasu sed ramchandra naggaji | Completed | 87000 | 52351.88 | 2015-12-01 | 2016-10-23
NALCHHA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1722005024/IF/9993692290 — pasu sed jagbhadur bhagvatsingh | Completed | 87000 | 51415.93 | 2015-12-01 | 2016-10-23
NALCHHA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722005024/IF/9993692295 — pasu sed liladhar savjiram | Closed | 8676800000 | 0 | 2015-08-15
NALCHHA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1722005024/IF/9993692301 — pasu sed Mangilal nandkisore | Completed | 87000 | 51556.93 | 2015-12-01 | 2016-10-23
NALCHHA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722005024/IF/9993692323 — pasu sed jitendra jasvant | Completed | 8676807000 | 3816 | 2015-12-08 | 2016-10-18
NALCHHA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1722005024/IF/9993692329 — pasu sed nathusingh chitar | Completed | 87000 | 53464.93 | 2015-12-01 | 2016-10-23
NALCHHA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722005024/IF/9993692534 — Mangilal nindkisor parsu sed nirman | Closed | 0 | 0 | 2015-08-15
NALCHHA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722005024/IF/9993692568 — ramchindr nigaji parsu sed nirman | Closed | 0 | 0 | 2015-08-15
NALCHHA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722005024/IF/9993692582 — ramchindr nigaji parsu sed nirman | Closed | 0 | 0 | 2015-08-15
NALCHHA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722005024/IF/9993706288 — lakchminarayan kanayalal | Closed | 0 | 0 | 2015-10-02
NALCHHA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722005024/IF/9993706294 — pasu sed nirman lakchminarayan kanayalal | Closed | 0 | 0 | 2015-10-02
NALCHHA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722005024/IF/9993706299 — pasu sed nirman lakchminarayan kanayalal | Closed | 0 | 0 | 2015-10-02
NALCHHA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722005024/IF/9993706303 — pasu sed nirman lakchminarayan kanhyalal | Completed | 87000 | 55087 | 2016-02-09 | 2016-10-23
NALCHHA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005024/IF/IAY/2483335 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4117039 | Completed | 17100 | 16720 | 2020-06-15 | 2020-10-22
NALCHHA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005024/IF/IAY/2516313 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4551076 | Completed | 17100 | 16530 | 2020-06-15 | 2020-10-22
NALCHHA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005024/IF/IAY/2517149 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4559748 | Completed | 17100 | 16720 | 2020-06-15 | 2020-10-22
NALCHHA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005024/IF/IAY/2520955 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4607348 | Completed | 17100 | 16340 | 2020-06-15 | 2021-06-19
NALCHHA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005024/IF/IAY/2523565 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4647151 | Completed | 17100 | 15748 | 2020-06-15 | 2021-10-15
NALCHHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005024/IF/IAY/3717361 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120913670 | Completed | 18360 | 16932 | 2022-07-05 | 2022-12-22
NALCHHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005024/IF/IAY/3717362 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120913761 | Completed | 18360 | 17952 | 2022-06-13 | 2022-11-13
NALCHHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005024/IF/IAY/3719154 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120915522 | Completed | 18360 | 16932 | 2022-06-13 | 2022-12-22
NALCHHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005024/IF/IAY/3764551 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120418233 | Completed | 18360 | 20112 | 2022-06-13 | 2024-08-16
NALCHHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005024/IF/IAY/4196743 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120913915 | Completed | 18360 | 16308 | 2022-09-09 | 2022-12-22
NALCHHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005024/IF/IAY/4344063 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120255928 | Completed | 18360 | 17748 | 2022-09-29 | 2022-12-10
NALCHHA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005024/IF/IAY/4399731 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120256424 | Closed | 19890 | 0 | 2023-07-08
NALCHHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005024/IF/IAY/4589637 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120916200 | Completed | 23490 | 21816 | 2025-02-12 | 2025-07-16
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005024/IF/IAY/5412860 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120914968 | Physically Completed | 23490 | 14355 | 2025-04-29 | 2026-06-14
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005024/IF/IAY/5414611 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120913553 | Completed | 23490 | 23490 | 2025-04-29 | 2026-03-10
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005024/IF/IAY/5415028 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120252674 | Completed | 23490 | 23229 | 2025-04-29 | 2026-02-04
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005024/IF/IAY/5415335 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120420493 | Completed | 23490 | 23229 | 2025-04-29 | 2026-02-04
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005024/IF/IAY/5415634 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120417724 | Physically Completed | 23490 | 16965 | 2025-04-29 | 2026-08-04
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005024/IF/IAY/5415635 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120417910 | Completed | 23490 | 23490 | 2025-07-08 | 2026-03-10
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005024/IF/IAY/5416063 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120252207 | Physically Completed | 23490 | 11745 | 2025-06-03 | 2026-08-04
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005024/IF/IAY/5416246 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120914265 | Completed | 23490 | 21924 | 2025-04-29 | 2025-08-05
NALCHHA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005024/IF/IAY/645167 — Construction of IAY House -IAY REG. NO. MP1400260 | Completed | 15030 | 15136 | 2017-05-16 | 2017-11-20
NALCHHA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005024/IF/IAY/833652 — Construction of IAY House -IAY REG. NO. MP1247486 | Completed | 15480 | 15308 | 2017-05-30 | 2017-12-28
NALCHHA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005024/IF/IAY/97109 — Construction of IAY House -IAY REG. NO. MP-22-005-024-001/16 | Approved | 27000 | 0 | 2015-10-16
NALCHHA | 2014-2015 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1722005024/LD/22012034253865 — MED BANDHAN KARY JAGDISH HIRALALL GRAM PANCHAYAT KATODIYA | Deleted | 0 | 0 | 2014-09-01
NALCHHA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1722005024/LD/22012034253867 — MED BANDHAN KARY JAGDISH HIRALALL GRAM PANCHAYAT KATODIYA | Completed | 25000 | 24048 | 2016-02-09 | 2016-09-20
NALCHHA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1722005024/LD/22012034254769 — med bandhan kary ramkanyabai sankarlal | Deleted | 0 | 0 | 2016-02-17
NALCHHA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1722005024/LD/22012034254771 — med bandhan kary girdhari tawar | Deleted | 0 | 0 | 2016-02-17
NALCHHA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1722005024/LD/22012034254772 — med bandhan kary panalal jairam | Deleted | 0 | 0 | 2016-02-17
NALCHHA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1722005024/LD/22012034254774 — med bandhan kary rajapalsing bagwansing | Deleted | 0 | 0 | 2016-02-17
NALCHHA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1722005024/LD/22012034254775 — santidam nirman | Deleted | 0 | 0 | 2016-02-17
NALCHHA | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1722005024/LD/22012034273022 — santosh jugnath med bandhan kary | Completed | 2500025000 | 16700 | 2016-05-31 | 2016-10-18
NALCHHA | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Pebble Bunding / Construction of Pebble peripheral/farm/field Bund for Community | Construction of Bund | 1722005024/LD/22012034273023 — sunthoes jugnath med bandhan kary | Deleted | 0 | 0 | 2016-04-14
NALCHHA | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1722005024/LD/22012034273025 — med bandhan kary sures kinhyalal | Completed | 25000 | 20040 | 2016-05-31 | 2016-07-30
NALCHHA | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1722005024/LD/22012034273028 — med bandhan kary juganath kisan | Completed | 25000 | 20040 | 2016-05-31 | 2016-10-18
NALCHHA | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1722005024/LD/22012034273030 — med bandhan kary mahes leladher | Deleted | 0 | 0 | 2016-04-14
NALCHHA | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1722005024/LD/22012034273031 — med bandhan kary mahesh leladhir | Completed | 2500025000 | 19539 | 2016-06-03 | 2016-07-30
NALCHHA | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1722005024/LD/22012034273032 — med bandhan kary mahesh leladhir | Deleted | 25000 | 0 | 2016-04-14
NALCHHA | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1722005024/LD/22012034273034 — med bandhan kary kisor gopal | Completed | 25000 | 20040 | 2016-05-31 | 2016-07-30
NALCHHA | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1722005024/LD/22012034273037 — med bandhan kary kilesh visnudaes | Completed | 25000 | 20040 | 2016-05-31 | 2016-10-18
NALCHHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1722005024/LD/22012034576455 — Shamshan ghat Leveling work Kathodiya | Closed | 0 | 0 | 2021-04-01
NALCHHA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1722005024/LD/22012034585082 — Shamshan Leveling work Kathodiya | Completed | 254619.2 | 134599.66 | 2024-06-20 | 2024-12-04
NALCHHA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1722005024/LD/22012034599832 — Land development | Closed | 0 | 0 | 2023-08-15
NALCHHA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1722005024/LD/22012034602556 — Land development karya at shamshan ghat GP kathodiya | Closed | 584629 | 0 | 2023-08-15
NALCHHA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1722005024/LD/3799383400 — मेढ बंधान दित्‍या गल्‍या कनेरिया | Deleted | 0 | 0 | 2012-12-25
NALCHHA | 2013-2014 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1722005024/LD/3799391223 — खेत तालाब दुर्गाबाई राजेन्‍द्र कठोडिया | Deleted | 15400 | 0 | 2013-04-01
NALCHHA | 2014-2015 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1722005024/LD/9926713946 — मेढ बंधान कार्य रामेश्‍वर गिरधारी ग्राम पंचायत कठो | Completed | 43000 | 47700 | 2014-08-19 | 2015-11-30
NALCHHA | 2017-2018 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1722005024/PG/22012034305219 — khel medan nirman kathodiya | Completed | 193000 | 93740 | 2017-04-24 | 2020-09-17
NALCHHA | 2006-2007 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005024/RC/002 — ग्रेवल मार्ग कठोडिया से खानपुर | Completed | 0 | 652390 | 2006-05-13 | 2008-03-10
NALCHHA | 2006-2007 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005024/RC/0123 — ग्रेवल मार्ग कठोडिया से गुलवा कठोडिया | Completed | 0 | 118446 | 2007-01-03 | 2008-10-20
NALCHHA | 2006-2007 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722005024/RC/12126 — सीमेंट कांक्रिट खरंजा निर्माण कठोडिया RES | Deleted | 1656000 | 29249 | 2007-03-30
NALCHHA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005024/RC/22012034157095 — ग्रेवल मार्ग कठोडिया से शंकरपुरा मार्ग भाग 2 | Deleted | 0 | 0 | 2012-12-25
NALCHHA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005024/RC/22012034157096 — ग्रेवल मार्ग कठोडिया से तलवाडा गुलवा मार्ग पर भाग 2 | Deleted | 0 | 0 | 2012-12-25
NALCHHA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005024/RC/22012034157097 — ग्रेवल मार्ग कठोडिया से बरोदा मार्ग पर | Deleted | 0 | 0 | 2012-12-25
NALCHHA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005024/RC/22012034157098 — सीमेंद कांक्रीट रोड प्रा शा भवन से गाव तक | Deleted | 0 | 0 | 2012-12-25
NALCHHA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005024/RC/22012034157099 — सीमेंद कांक्रीट रोड आंगनवाडी मार्ग तक | Deleted | 0 | 0 | 2012-12-25
NALCHHA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005024/RC/22012034157100 — गंगाबाइ नानुराम खेत तालाबा भीलखेडी | Deleted | 0 | 0 | 2012-12-25
NALCHHA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005024/RC/22012034157101 — रामसिग रूमाल खेत तालाबा भीलखेडी | Deleted | 0 | 0 | 2012-12-25
NALCHHA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Village Drain / Construction of Open / Covered Grey Water/Storm Drain for Community | Construction of Road and Culvert | 1722005024/RC/22012034157106 — नाली निर्माण कार्य सिलोटिया संपुर्ण ग्राम | Deleted | 0 | 0 | 2012-12-25
NALCHHA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Village Drain / Construction of Open / Covered Grey Water/Storm Drain for Community | Construction of Road and Culvert | 1722005024/RC/22012034157109 — नाली निर्माण भीलखेडी | Deleted | 0 | 0 | 2012-12-25
NALCHHA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722005024/RC/22012034180864 — विधायक निधि सीसी रोड रामकिशन के मकान से रामेश्‍वर | Completed | 67000 | 51719.68 | 2013-09-03 | 2014-06-10
NALCHHA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722005024/RC/22012034180866 — विधायक निधि सीसी रोड महिपाल शर्मा के मकान से शंकरल | Completed | 67000 | 53517.6 | 2013-09-03 | 2014-06-10
NALCHHA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722005024/RC/22012034194436 — panch parmeshwar cc roud antrik marg (kathodiya) | Completed | 152000 | 102458 | 2013-12-17 | 2014-04-10
NALCHHA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722005024/RC/22012034218565 — पंच परमेश्‍वर सी सी रोड निर्माण कठोडिया कोठी से गा | Completed | 152000 | 107388 | 2014-05-27 | 2018-03-25
NALCHHA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005024/RC/22012034219541 — ग्रेवल मार्ग निर्माण कार्य कठोडिया तलवाडा मार्ग से | Completed | 105000 | 90021.54 | 2014-05-28 | 2017-01-10
NALCHHA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005024/RC/22012034321621 — sudur gram sampark sadak talab ki pal aaw se kathodiya kakad tak | Deleted | 575000 | 0 | 2016-12-22
NALCHHA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722005024/RC/22012034322400 — 14 vaa vitya cc road nirman rakesh ke ghar se prajapal singh takur ke ghar tak kathodiya | Completed | 182000 | 146288 | 2017-01-31 | 2019-03-14
NALCHHA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005024/RC/22012034369744 — sudur sadak nirman khanpur se bagdi | Closed | 0 | 0 | 2017-10-02
NALCHHA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005024/RC/22012034373708 — Sudur Smpark Sadak | Closed | 0 | 0 | 2018-04-14
NALCHHA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722005024/RC/22012034445519 — CC ROAD NIRMAN LILADHR KE GHAR SE RANJIT KE GHAR TAK KATHODIYA | Completed | 30000 | 28308 | 2019-03-03 | 2025-01-19
NALCHHA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005024/RC/22012034474060 — sudur gram sampark sadak kathodiya kakad se gram kathodiya tak | Completed | 674757.14 | 681953.44 | 2019-09-17 | 2021-11-15
NALCHHA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005024/RC/22012034533370 — grewal marg nirmaan khet sadak upyojna antergat ramesh radheshyam kekhet se dinesh thakur ke khet ta | Completed | 1199998.43 | 1047108.91 | 2020-09-08 | 2021-11-15
NALCHHA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005024/RC/22012034607563 — Khet sadak nirman kathodiya road se gokul chaoudhri ke khet tak Kathodiya | Closed | 0 | 0 | 2021-04-01
NALCHHA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005024/RC/22012034616622 — Sudur sadak nirman puliya se kathodiya kakad tak Kathodiya | Closed | 0 | 0 | 2022-04-01
NALCHHA | 2007-2008 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005024/RC/5000 — ग्रेवल मार्ग निर्माण्‍ा कठोडिया से सुरेशचंद्र कंहैयालाल के खेत तक कठो‍डिया | Completed | 0 | 907859 | 2007-05-21 | 2012-07-01
NALCHHA | 2007-2008 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005024/RC/50047 — गेवल मार्ग घासीराम के खेत से गुलवा तडवाला मार्ग 1 km कठोडिया | Completed | 0 | 721049 | 2007-06-09 | 2012-07-01
NALCHHA | 2007-2008 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005024/RC/50080 — ग्रेवल मार्ग ि‍नर्माण कार्य कठोडि‍या से खानपुरा मार्ग पुराने कार्य से आगे कठोडि‍या | Completed | 200000 | 33040 | 2007-05-29 | 2008-03-31
NALCHHA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005024/RC/50206 — ग्रेवल मार्ग र्नि‍माण कार्य तलवाडा कठोडि‍या मार्ग से गुलवा तलवाडा मार्ग तक कठोडिया | Completed | 0 | 347306 | 2009-02-24 | 2010-01-14
NALCHHA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005024/RC/50319 — पाईप पुलिया निर्माण काठोडिया से तलवाडा फाटा देवकरण के खेत ग्राम पंचायत काठोडिया | Completed | 0 | 290700 | 2010-04-27 | 2012-05-12
NALCHHA | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005024/RC/50320 — पाईप पुलिया निर्माण तलवाडा से काठोडिया मार्ग पर ग्राम पंचायत काठोडिया | Completed | 0 | 0 | 2009-12-08 | 2012-05-12
NALCHHA | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005024/RC/50406 — ग्रेवल मार्ग तलवाडा कठोडि‍या मेन रोड से स्‍कुल भवन | Deleted | 293000 | 0 | 2009-08-29
NALCHHA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005024/RC/50528 — ग्रेवल मार्ग निर्माण कार्य कठौडिया से शंकरपुरा फाटा मार्ग पर ग्राम पंचायत कठौडिया | Deleted | 0 | 94000 | 2010-06-03
NALCHHA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005024/RC/50613 — ग्रेवल मार्ग निर्माण कार्य कठोडिया से बिलोदा मार्ग | Completed | 0 | 599048 | 2011-05-25 | 2013-05-25
NALCHHA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005024/RC/50736 — ग्रेवल मार्ग निर्माण कठोडिया से बिल्‍लोद मार्ग कठो | Completed | 0 | 39528 | 2011-05-05 | 2011-05-22
NALCHHA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005024/RC/50908 — मुरम मार्ग निर्माण कार्य कठोडिया से बिलोदा मार्ग भ | Completed | 0 | 301952 | 2011-11-05 | 2013-05-10
NALCHHA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722005024/RC/50909 — पंच परमेश्‍वर सी सी रोड मेन रोड से पंचायत भवन ग्रा | Completed | 123000 | 121942.5 | 2013-02-12 | 2014-04-10
NALCHHA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1722005024/RS/22012034571201 — SBM SAMUDAYIK COMPOST PIT KATHODIYA | Closed | 19239.91 | 0 | 2021-08-15
NALCHHA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Anganwadi Multi Unit Toilets for Comm / Construction of Anganwadi Multi Unit Toilets for Community | Construction of Toilets | 1722005024/RS/22012035121413 — Samudayik swchta parisar dharmsala ke pass katodiya | Completed | 54000 | 51714 | 2024-01-26 | 2024-09-23
NALCHHA | 2006-2007 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722005024/WC/ — खेत तालाब कठोडीया समन्‍दर राजाराम | Completed | 0 | 0 | 2006-05-25 | 2007-03-25
NALCHHA | 2006-2007 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722005024/WC/2003 — खेत तालाब नाथुसिंह छित्‍तरयिंह कठोडीया | Completed | 0 | 0 | 2006-05-25 | 2007-03-25
NALCHHA | 2006-2007 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722005024/WC/2004 — खेत तालाब राजेन्‍द्रसिंह तेजसिंह कठोडीया | Completed | 0 | 0 | 2006-06-05 | 2007-03-25
NALCHHA | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Sunken Pond / Construction of Community Water Harvesting Ponds | Farm Pond | 1722005024/WC/22012034296803 — sunken pond nirman puliya ke paas nale par kathodiya | Deleted | 464000 | 0 | 2016-06-17
NALCHHA | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Dam / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1722005024/WC/22012034317822 — sankan pond nirman | Closed | 0 | 0 | 2016-10-02
NALCHHA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722005024/WC/22012034321547 — sankan pond nirman puliya ke paas kathodiya | Completed | 464000 | 463038.36 | 2017-06-06 | 2019-03-14
NALCHHA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722005024/WC/22012034432985 — Sunkan pond nirman peli khana par khanpur | Completed | 489000 | 388394.4 | 2019-01-27 | 2021-05-21
NALCHHA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand filter for borewell recharge for Community | Well Recharge | 1722005024/WC/22012034481303 — saok pit nirman manohar bapu ke ghar ke pas | Completed | 5134.63 | 2456 | 2019-09-08 | 2025-01-19
NALCHHA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand filter for borewell recharge for Community | Well Recharge | 1722005024/WC/22012034481304 — saok pit prathmik vidhyalay ke pas | Closed | 0 | 0 | 2019-04-26
NALCHHA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand filter for borewell recharge for Community | Well Recharge | 1722005024/WC/22012034482841 — saok pit nirman prathmik vidhayaly ke pas kathodiya | Completed | 5134.63 | 2456 | 2019-09-08 | 2025-01-19
NALCHHA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand filter for borewell recharge for Community | Well Recharge | 1722005024/WC/22012034482842 — saok pit nirman shamshan ghat pr kathodiya | Closed | 5134.63 | 0 | 2019-04-26
NALCHHA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand filter for borewell recharge for Community | Well Recharge | 1722005024/WC/22012034487394 — soak pit nirman badri ke khet ke pas kathodiya | Closed | 0 | 0 | 2019-04-26
NALCHHA | 2020-2021 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Earthen Spur for Community / Construction of Earthen Spur for Community | Construction of Spur | 1722005024/WC/22012034549520 — Nalha Trenching of Kathodiya | Completed | 500012.68 | 381767 | 2020-05-26 | 2021-11-15
NALCHHA | 2020-2021 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Earthen Spur for Community / Construction of Earthen Spur for Community | Construction of Spur | 1722005024/WC/22012034559231 — Nala treching rahul ke khet se baroda marg tak | Completed | 401828.94 | 338960 | 2020-06-11 | 2021-05-21
NALCHHA | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1722005024/WC/22012034656559 — Nala trenching santosh verma ke khet se vasudev ke khet tak | Completed | 339857.36 | 150918 | 2021-05-13 | 2024-02-08
NALCHHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1722005024/WC/22012034656566 — CTRA rain water harvesting in panchayat bhawan kathodiya | Completed | 24685.92 | 22656 | 2021-05-03 | 2022-07-22
NALCHHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1722005024/WC/22012034664531 — CTRA khet talaab laxman deva | Completed | 337137.04 | 267691 | 2021-05-03 | 2022-10-10
NALCHHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1722005024/WC/22012034701961 — CTRA percolation tank kamal ke khet ke pass khapur | Closed | 0 | 0 | 2021-05-06
NALCHHA | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1722005024/WC/22012034701971 — Nala trenching kary khanpur pulia ke pss | Closed | 401999.1 | 0 | 2021-05-06
NALCHHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1722005024/WC/22012034701975 — CTRA percolatioN tank kamal ke khet ke pass khanpur | Completed | 556709.17 | 172542 | 2021-05-18 | 2024-10-01
NALCHHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1722005024/WC/22012034701976 — CTRA percolatioN tank kamal ke khet ke pass khanpur | Closed | 0 | 0 | 2021-05-06
NALCHHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722005024/WC/22012034838338 — rain watar harvesting in p. school kathodiyakath | Closed | 0 | 0 | 2021-08-15
NALCHHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722005024/WC/22012034838351 — rain water harvesting in samudayik bhavan kathodiya | Closed | 0 | 0 | 2021-08-15
NALCHHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722005024/WC/22012034838362 — rain water harvesting in Aarogya kendra kathodiya | Closed | 0 | 0 | 2021-08-15
NALCHHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1722005024/WC/22012034839938 — SBM SP SHAMSHAN KE PAS KATHODIYA | Closed | 4454.16 | 0 | 2021-10-02
NALCHHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1722005024/WC/22012034839949 — SBM SP HENDPAMP TALAB KE PAS KATHODIYA | Closed | 4418.56 | 0 | 2021-10-02
NALCHHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1722005024/WC/22012034839954 — SBM SP HENDPAMP NATHU SINGH KE GHAR KE PAS KATHODIY KE PAS KATHODIYA | Closed | 4418.56 | 0 | 2021-10-02
NALCHHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Level Bench Terrace Terrace for Comm / Construction of Level Bench Terrace for Community | Terracing | 1722005024/WC/22012034913924 — Nala trenching puliya ke pas Kathodiya | Closed | 0 | 0 | 2021-04-01
NALCHHA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722005024/WC/22012034956638 — NSP sakan pond nirman shamshan ghat ke pas kathodiya | Closed | 0 | 0 | 2022-04-01
NALCHHA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722005024/WC/22012034990505 — Roof water harvesting samudayik bhawan Kathodiya | Closed | 18432.26 | 0 | 2022-04-01
NALCHHA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1722005024/WC/22012035203862 — Nala touching Ramesh ke Ghar se puliya Tak | New | 0 | 0 | 2024-04-14
NALCHHA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1722005024/WC/22012035204017 — Nala Trenching ramesh ke ghar se puliya tak GP kathodiya | Completed | 199825.3 | 170527.37 | 2024-07-02 | 2024-12-24
NALCHHA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation-Biodrainage- Gov blding premises / Block Plantation of Biodrainage Trees in Government building premises for Community | Plantation | 1722005024/WC/22012035221551 — प्लांटेशन शमशान घाट पर भाग 2 | New | 0 | 0 | 2024-08-15
NALCHHA | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722005024/WC/80164 — तालाब गहरीकरण कार्य निमार्ण कठोडिया लागत 0.75 | Completed | 0 | 0 | 2007-06-22 | 2009-04-05
NALCHHA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722005024/WC/9993627301 — कठोडिया खेत तालाबा दुर्गाबाइ राजे्द्रसिग | Deleted | 0 | 0 | 2012-12-25
NALCHHA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722005024/WC/9993627302 — कठोडिया खेत तालाबा बद्रीलाल गप्‍पु जी | Deleted | 0 | 0 | 2012-12-25
NALCHHA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722005024/WC/9993627303 — कठोडिया खेत तालाबा शुरेशच्रद्र कन्हैयालाल | Deleted | 0 | 0 | 2012-12-25
NALCHHA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1722005024/WC/9993627304 — कठोडिया खेत तालाबा कंकुबाइ छितरसिग | Completed | 29854 | 27740 | 2014-01-21 | 2014-04-10
NALCHHA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722005024/WC/9993627305 — शाशकिय तालाब निमार्ण कठोडिया | Deleted | 0 | 0 | 2012-12-25
NALCHHA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722005024/WC/9993627306 — शाशकिय तालाब निमार्ण कठोडिया | Deleted | 0 | 0 | 2012-12-25
NALCHHA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722005024/WC/9993627311 — सुखराम जंगल्‍या खेत तालाबा भीलखेडी | Deleted | 0 | 0 | 2012-12-25
NALCHHA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722005024/WC/9993627312 — गगन रूगनाथ खेत तालाबा भीलखेडी | Deleted | 0 | 0 | 2012-12-25
NALCHHA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1722005024/WC/9993627313 — मोहन रूगनाथकपिल धारा कुप निर्माण भीलखेडी | Deleted | 0 | 0 | 2012-12-25
NALCHHA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1722005024/WC/9993627314 — नानुराम चंपालाल कपिल धारा कुप निर्माण सिलोटिया | Deleted | 0 | 0 | 2012-12-25
NALCHHA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1722005024/WC/9993627315 — किशोर रामसिग कपिल धारा कुप निर्माण कनेरिया | Deleted | 0 | 0 | 2012-12-25
NALCHHA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722005024/WC/9993627316 — जलसंवर्धन गिटटीखदान कनेरिया मे निस्‍तार तालाब | Deleted | 0 | 0 | 2012-12-25
NALCHHA | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Box Trenches / Construction of Water Absorption Trench for Community | Construction of Trench | 1722005024/WC/9993632268 — खेत तालाब बद्रीलाल गप्‍पूजी कठोडिया | Deleted | 15400 | 0 | 2013-04-01
NALCHHA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1722005024/WC/9993632269 — खेत तालाब सुरेशचन्‍द कन्‍हैयालाल कठोडिया | Deleted | 15400 | 0 | 2013-04-01
NALCHHA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1722005024/WC/9993632555 — खेत तालाब राजेन्‍द्रसिंह तेरसिंह ग्राम पंचायत कठोड | Deleted | 15400 | 0 | 2013-06-04
NALCHHA | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1722005024/WH/19956508 — STOP DAM CUM PULIYA UNNAYAN KARYA | Deleted | 120000 | 0 | 2016-05-22
NALCHHA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1722005024/WH/22012034389901 — TALAB JIRNODWAR KATHODIYA | Closed | 0 | 0 | 2019-04-04
NALCHHA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1722005024/WH/22012034389902 — BAVDI JIRNIDWAR KATHODIYA | Closed | 0 | 0 | 2019-04-04