## Work List
Exported on: 2026-09-06 18:13:14
Filters applied:
Data source: MGNREGA + VBGRAMG
District: DHAR
Block: All
Panchayat: Naibaroda
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
NALCHHA | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1722005028/DP/2058 — व़क्षारोपण कार्य कुंजरोद | Deleted | 323000 | 11574 | 2007-08-01
NALCHHA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1722005028/DP/2115 — शांतिवन कार्य कुंजरोद ग्राम पंचायत नाईबरोदा | Completed | 0 | 197799.4 | 2010-08-13 | 2012-05-08
NALCHHA | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1722005028/DP/22012034238562 — shanti dhaam naibaroda | Completed | 180000 | 511 | 2017-03-05 | 2018-07-08
NALCHHA | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1722005028/DP/22012034238564 — SHANTI DHAAM BHERU PIPLAYA | Completed | 180000 | 180868.75 | 2017-03-05 | 2018-07-14
NALCHHA | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1722005028/DP/22012034239285 — shanti dhaam kunjrod | Closed | 0 | 0 | 2017-01-26
NALCHHA | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1722005028/DP/22012034245329 — shamshaan ghat kunjrod | Completed | 180000 | 176183.45 | 2017-06-23 | 2018-08-22
NALCHHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1722005028/DP/22012034528613 — Poshan vatika near school kunjrod | Closed | 0 | 0 | 2021-05-30
NALCHHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1722005028/DP/22012034528614 — Poshan vatika near school kunjrod | Completed | 770494.38 | 270823 | 2021-06-08 | 2026-03-18
NALCHHA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Shelter Belt Trees (Comm) / Boundary Line Plantation of Shelter Belt Trees for Community | Plantation | 1722005028/DP/22012034589166 — AKAM wasudha vandan amrat watika poshan watika ke pas naibaroda | Completed | 55847.4 | 16829 | 2023-08-08 | 2026-05-28
NALCHHA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Land development / Levelling/shaping of Wasteland Land for Community | Land Development | 1722005028/DP/9926694487 — शांतिवन निर्माण कार्य ग्राम पंचायत नाईबरोदा | Deleted | 0 | 0 | 2012-12-25
NALCHHA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Land development / Levelling/shaping of Wasteland Land for Community | Land Development | 1722005028/DP/9993629636 — vyaktigat sochalay ka nirman grop no. 1 naibaroda | Completed | 252000 | 39432 | 2015-09-05 | 2016-06-16
NALCHHA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Land development / Levelling/shaping of Wasteland Land for Community | Land Development | 1722005028/DP/9993629647 — vyaktigat sochalay ka nirman group 02 naibaroda | Completed | 50400 | 47064 | 2015-09-05 | 2016-06-16
NALCHHA | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Land development / Levelling/shaping of Wasteland Land for Community | Land Development | 1722005028/DP/9993629648 — vyaktigat sochalay ka nirman group 03 | Deleted | 0 | 0 | 2016-06-02
NALCHHA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Land development / Levelling/shaping of Wasteland Land for Community | Land Development | 1722005028/DP/9993629657 — vyaktigat sochalay ka nirman group 4 naibaroda | Suspended | 252000 | 6360 | 2015-10-23
NALCHHA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Land development / Levelling/shaping of Wasteland Land for Community | Land Development | 1722005028/DP/9993629658 — vyaktigat sochalay ka nirman group 5 naibaroda | Deleted | 50400 | 0 | 2015-09-04
NALCHHA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Land development / Levelling/shaping of Wasteland Land for Community | Land Development | 1722005028/DP/9993629659 — vyaktigat sochalay ka nirman group 6naibaroda | Deleted | 50400 | 0 | 2015-09-04
NALCHHA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Land development / Levelling/shaping of Wasteland Land for Community | Land Development | 1722005028/DP/9993629660 — vyaktigat sochalay ka nirman07naibaroda | Deleted | 50400 | 0 | 2015-09-04
NALCHHA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Land development / Levelling/shaping of Wasteland Land for Community | Land Development | 1722005028/DP/9993629661 — vyaktigat sochalay ka nirman group 08naibaroda | Deleted | 50400 | 0 | 2015-09-04
NALCHHA | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Land development / Levelling/shaping of Wasteland Land for Community | Land Development | 1722005028/DP/9993629677 — vyaktigat sochalay ka nirman group 09 naibaroda | Deleted | 0 | 0 | 2016-06-02
NALCHHA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Land development / Levelling/shaping of Wasteland Land for Community | Land Development | 1722005028/DP/9993629678 — vyakatigat sochalay ka nirman group 09 naibaroda | Deleted | 50400 | 0 | 2015-09-04
NALCHHA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Land development / Levelling/shaping of Wasteland Land for Community | Land Development | 1722005028/DP/9993629680 — vyakatigat sochalay ka nirman group 03 naibaroda | Completed | 252000 | 15741 | 2015-10-15 | 2016-06-16
NALCHHA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Land development / Levelling/shaping of Wasteland Land for Community | Land Development | 1722005028/DP/9993629681 — vyakatigat sochalay ka nirman group 10 naibaroda | Deleted | 348000 | 0 | 2015-09-04
NALCHHA | 2013-2014 | D--RURAL INFRASTUCTURE / Food Grain | Food Grain / Repair and Maintenance of Food grain Storage Building for Community | Constr of Food Grain storage | 1722005028/FG/9425884099 — गोदाम निर्माण कार्य, kunjrod ग्राम पंचायत नाई बरोद | Completed | 894000 | 372814 | 2014-03-01 | 2019-09-14
NALCHHA | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1722005028/IF/1000003906 — निर्मल भारत शौचालय ग्राम पंचायत नाईबरोदा | Deleted | 0 | 0 | 2012-12-25
NALCHHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005028/IF/22012034295714 — CM HOUSE MUKESH MANGILAAL | Completed | 14000 | 14649 | 2016-08-04 | 2017-06-25
NALCHHA | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Compost Pit / Construction of Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1722005028/IF/22012034317454 — warmicompost | Closed | 0 | 0 | 2016-08-15
NALCHHA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722005028/IF/22012034337143 — KAPIL DHARA KUP HINDU SINGH MAANGILAAL | Completed | 230000 | 66372 | 2017-05-03 | 2026-04-06
NALCHHA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722005028/IF/22012034340960 — व़क्षारोपण कार्य शांतिधाम कुंजरोद नाईबरोदा | Physically Completed | 335000 | 6364 | 2017-07-10 | 2021-01-18
NALCHHA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation - Shelter Belt for Individuals / Block Plantation of Shelter Belt Trees for Individuals | Plantation | 1722005028/IF/22012034364227 — VARKSHA ROPAN BHERU PIPLYA ROAD | Physically Completed | 335000 | 3096 | 2017-07-15 | 2021-01-18
NALCHHA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722005028/IF/22012034364244 — VARKSHA ROPAN KUNJROD UKALA PAR | Physically Completed | 335000 | 6192 | 2017-07-15 | 2021-01-18
NALCHHA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722005028/IF/22012034364248 — VARKSHA ROPAN KUNJROD SE BHERU PIPLYA ROAD PAR | Physically Completed | 335000 | 9976 | 2017-07-15 | 2021-01-18
NALCHHA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722005028/IF/22012034383505 — Plantation Main Raod 2 Side | Closed | 0 | 0 | 2018-04-14
NALCHHA | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722005028/IF/22012034384495 — Platation Work 2 Heq. Naibaroda | Closed | 0 | 0 | 2014-04-14
NALCHHA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722005028/IF/22012034385783 — Plantation Wrok 2 Heq. Naibaroda | Closed | 0 | 0 | 2018-04-14
NALCHHA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1722005028/IF/22012034561004 — kapil dhara kup nirman bheru singh | Closed | 0 | 0 | 2020-04-26
NALCHHA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Sericulture in fields-Individuals / Block Plantation of Sericulture Trees in fields for Individuals | Plantation | 1722005028/IF/22012034587585 — vrakcharopan karya jagdish bulaji | Closed | 0 | 0 | 2020-06-16
NALCHHA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Sericulture in fields-Individuals / Block Plantation of Sericulture Trees in fields for Individuals | Plantation | 1722005028/IF/22012034587586 — vrakcharopan karya hindusingh mangilal | Closed | 0 | 0 | 2020-06-16
NALCHHA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Sericulture in fields-Individuals / Block Plantation of Sericulture Trees in fields for Individuals | Plantation | 1722005028/IF/22012034587587 — vrakcharopan karya chatarsingh champalal | Closed | 0 | 0 | 2020-06-16
NALCHHA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Stone boulder Gully Plugs for Individual / Construction of Stone boulder Gully Plugs for Individuals | Boulder Check/Gully Plug | 1722005028/IF/22012034617847 — Bolder wall kaary Parwati Bai narayan | Ongoing | 76474.65 | 18456 | 2020-12-29
NALCHHA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Stone boulder Gully Plugs for Individual / Construction of Stone boulder Gully Plugs for Individuals | Boulder Check/Gully Plug | 1722005028/IF/22012034617851 — Bolder wall kaary Rahul Karan singh | Completed | 57708.79 | 38256.12 | 2020-12-29 | 2026-05-18
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722005028/IF/22012035166405 — Kapil Dhara kup Gori Bai Jitendra | Ongoing | 248713.8 | 27405 | 2025-04-19
NALCHHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722005028/IF/22012035202235 — Kapil dhara kup Bheru singh Mangilal | Ongoing | 233292.37 | 153060.1 | 2024-04-03
NALCHHA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1722005028/IF/22012035419372 — JGSA Dugg well Recharge pit Nirman Pannalal Bhakta Gram Kunjrod | Completed | 25899.46 | 14877 | 2025-05-13 | 2026-04-23
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722005028/IF/22012035484069 — JGSA DugWell Recharge Pit Gopal Sobhan Gram Bheru pipliya | Completed | 25899.46 | 3915 | 2025-05-13 | 2026-05-02
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722005028/IF/22012035484198 — JGSA DugWell Recharge Pit Sohan Rughnath Gram Kunjrod | Physically Completed | 25899.46 | 12789 | 2025-06-03 | 2026-04-23
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722005028/IF/22012035484247 — JGSA DugWell Recharge Pit Rohit Kumar Gram Kunjrod | Physically Completed | 25899.46 | 12006 | 2025-06-11 | 2026-05-02
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722005028/IF/22012035598380 — Ek bagiya Maa k nam plantation for beneficiary Ganga choudhary GP Naibroda | New | 0 | 0 | 2025-08-15
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722005028/IF/22012035598384 — Ek bagiya Maa k nam plantation for beneficiary Ganga choudhary GP Naibroda | New | 0 | 0 | 2025-08-15
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722005028/IF/22012035598395 — Ek bagiya Maa k nam plantation for beneficiary Ganga choudhary GP Naibroda | New | 0 | 0 | 2025-08-15
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722005028/IF/22012035598398 — Ek bagiya Maa k nam plantation for beneficiary Ganga choudhary GP Naibroda | Ongoing | 235664.27 | 14427 | 2026-02-03
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005028/IF/22012035598903 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117283158 | Approved | 23490 | 0 | 2025-04-14
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005028/IF/22012035598949 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118120455 | Approved | 23490 | 0 | 2025-04-14
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005028/IF/22012035598983 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106126178 | Approved | 23490 | 0 | 2025-04-14
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722005028/IF/22012035602688 — Ek bagiya Maa k nam plantation for beneficiary Rani meda GP Naibroda | Approved | 235664.27 | 0 | 2025-08-15
NALCHHA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005028/IF/9993683881 — cm house babulaal tulsiram | Completed | 14000 | 5247 | 2015-11-05 | 2018-03-25
NALCHHA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005028/IF/9993683888 — cm house sunil ramaji | Completed | 14000 | 5247 | 2015-11-05 | 2018-03-25
NALCHHA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005028/IF/9993683897 — cn house pannalaal phakirchand | Completed | 14000 | 14218 | 2015-11-05 | 2017-03-09
NALCHHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005028/IF/9993731109 — cm house dasharath nandram | Completed | 14300 | 15995 | 2016-08-04 | 2017-09-15
NALCHHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005028/IF/9993734142 — cm house tejsingh dattu | Completed | 14300 | 13527 | 2016-04-17 | 2017-04-26
NALCHHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005028/IF/9993735833 — cm house sunita jayram | Completed | 14300 | 12525 | 2016-04-17 | 2018-03-25
NALCHHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005028/IF/9993736005 — cm house kiran bai dilip | Completed | 14300 | 13527 | 2016-04-17 | 2016-09-19
NALCHHA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005028/IF/9993739674 — CM HOUSE MUKESH MANGILAAL | Closed | 14300 | 0 | 2015-10-02
NALCHHA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005028/IF/IAY/1142587 — Construction of IAY House -IAY REG. NO. MP-22-005-028-004/015 | Completed | 15480 | 10836 | 2018-02-02 | 2019-09-11
NALCHHA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005028/IF/IAY/1142588 — Construction of IAY House -IAY REG. NO. MP-22-005-028-004/020 | Completed | 15480 | 11796 | 2018-02-02 | 2019-09-11
NALCHHA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005028/IF/IAY/1789821 — Construction of IAY House -IAY REG. NO. MP1115439 | Completed | 15660 | 15102 | 2018-08-29 | 2019-11-02
NALCHHA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005028/IF/IAY/1789832 — Construction of IAY House -IAY REG. NO. MP1158208 | Completed | 15660 | 14916 | 2018-10-15 | 2019-01-25
NALCHHA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005028/IF/IAY/2266391 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1090054 | Completed | 17100 | 15624 | 2019-11-04 | 2021-09-14
NALCHHA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005028/IF/IAY/2266506 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1661470 | Completed | 17100 | 13336 | 2019-10-10 | 2021-11-15
NALCHHA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005028/IF/IAY/2568728 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4078479 | Completed | 17100 | 14820 | 2020-07-02 | 2021-09-14
NALCHHA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005028/IF/IAY/2573526 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4504936 | Completed | 17100 | 14820 | 2020-07-02 | 2021-09-14
NALCHHA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005028/IF/IAY/2587167 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4452371 | Completed | 17100 | 17100 | 2020-07-02 | 2021-11-13
NALCHHA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005028/IF/IAY/2783566 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4470465 | Ongoing | 27000 | 9504 | 2021-08-10
NALCHHA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005028/IF/IAY/2784354 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4078563 | Completed | 17100 | 16910 | 2021-08-11 | 2024-02-12
NALCHHA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005028/IF/IAY/2791424 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4967548 | Completed | 17100 | 14668 | 2021-05-01 | 2021-12-10
NALCHHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005028/IF/IAY/321873 — Construction of IAY House -IAY REG. NO. MP1073401 | Completed | 15030 | 15131 | 2017-03-14 | 2018-08-12
NALCHHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005028/IF/IAY/365761 — Construction of IAY House -IAY REG. NO. MP1158225 | Completed | 15030 | 15408 | 2017-02-07 | 2018-08-11
NALCHHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005028/IF/IAY/3686309 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113457915 | Completed | 18360 | 16598 | 2022-08-27 | 2025-01-28
NALCHHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005028/IF/IAY/3705353 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114763278 | Completed | 18360 | 18275 | 2022-07-19 | 2023-09-21
NALCHHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005028/IF/IAY/3742233 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118160001 | Completed | 18360 | 17799 | 2022-07-19 | 2024-04-16
NALCHHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005028/IF/IAY/3754432 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121664694 | Completed | 18360 | 18071 | 2022-08-27 | 2024-04-16
NALCHHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005028/IF/IAY/3756745 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121667698 | Completed | 18360 | 17544 | 2022-06-09 | 2022-12-10
NALCHHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005028/IF/IAY/383870 — Construction of IAY House -IAY REG. NO. MP1165109 | Completed | 15030 | 15292 | 2017-02-23 | 2019-01-20
NALCHHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005028/IF/IAY/395194 — Construction of IAY House -IAY REG. NO. MP1201511 | Completed | 15030 | 14500 | 2017-02-23 | 2018-03-18
NALCHHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005028/IF/IAY/3966707 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106524995 | Completed | 18360 | 17748 | 2022-06-09 | 2022-12-10
NALCHHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005028/IF/IAY/3968513 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114763343 | Completed | 18360 | 18309 | 2022-08-19 | 2024-04-16
NALCHHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005028/IF/IAY/3975180 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118120946 | Completed | 18360 | 17748 | 2022-06-27 | 2022-12-10
NALCHHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005028/IF/IAY/3975182 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118121115 | Completed | 18360 | 18275 | 2022-08-27 | 2023-12-22
NALCHHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005028/IF/IAY/3975247 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118144385 | Completed | 18360 | 17544 | 2022-06-11 | 2022-12-10
NALCHHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005028/IF/IAY/3976674 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117282906 | Completed | 18360 | 11458 | 2022-10-29 | 2025-01-28
NALCHHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005028/IF/IAY/3976694 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117289188 | Completed | 18360 | 18241 | 2022-07-19 | 2024-04-16
NALCHHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005028/IF/IAY/4018553 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131543794 | Completed | 18360 | 14455 | 2022-08-27 | 2025-01-28
NALCHHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005028/IF/IAY/4187986 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106655026 | Ongoing | 27000 | 4999 | 2022-08-26
NALCHHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005028/IF/IAY/4198943 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117253177 | Completed | 18360 | 17544 | 2022-08-03 | 2022-12-10
NALCHHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005028/IF/IAY/4343924 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117253220 | Completed | 18360 | 18275 | 2022-10-26 | 2023-07-06
NALCHHA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005028/IF/IAY/4396068 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113459401 | Ongoing | 27000 | 4795 | 2024-02-16
NALCHHA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005028/IF/IAY/4400353 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117283235 | Completed | 19890 | 18557 | 2024-02-03 | 2025-01-28
NALCHHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005028/IF/IAY/4545437 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106473598 | Approved | 27000 | 0 | 2024-09-15
NALCHHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005028/IF/IAY/4549705 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106742918 | Ongoing | 27000 | 12663 | 2025-03-04
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005028/IF/IAY/4550208 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113458021 | Completed | 23490 | 21924 | 2025-07-12 | 2026-03-10
NALCHHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005028/IF/IAY/457940 — Construction of IAY House -IAY REG. NO. MP1661407 | Completed | 15030 | 14436 | 2017-02-23 | 2018-05-14
NALCHHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005028/IF/IAY/4699698 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106478981 | Completed | 21870 | 21384 | 2024-10-15 | 2026-02-03
NALCHHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005028/IF/IAY/4704459 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121667247 | Physically Completed | 23490 | 17622 | 2025-03-04 | 2026-08-04
NALCHHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005028/IF/IAY/4751237 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117282997 | Physically Completed | 23490 | 21423 | 2025-02-21 | 2026-07-28
NALCHHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005028/IF/IAY/4751238 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117283072 | Physically Completed | 23490 | 15669 | 2025-02-21 | 2026-07-28
NALCHHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005028/IF/IAY/4785586 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131543949 | Ongoing | 27000 | 243 | 2025-03-10
NALCHHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005028/IF/IAY/4803184 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126653076 | Ongoing | 27000 | 1701 | 2025-03-04
NALCHHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005028/IF/IAY/489050 — Construction of IAY House -IAY REG. NO. MP2120584 | Completed | 15030 | 14888 | 2017-02-23 | 2019-11-02
NALCHHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005028/IF/IAY/489199 — Construction of IAY House -IAY REG. NO. MP2122243 | Completed | 15030 | 16272 | 2017-02-07 | 2017-10-10
NALCHHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005028/IF/IAY/5289467 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118151699 | Approved | 27000 | 0 | 2025-02-17
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005028/IF/IAY/5295560 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117282565 | Ongoing | 27000 | 3654 | 2025-07-25
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005028/IF/IAY/5301404 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114753029 | Completed | 23490 | 22968 | 2025-07-12 | 2026-02-03
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005028/IF/IAY/5307481 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118144224 | Completed | 23490 | 21490 | 2025-08-06 | 2026-03-10
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005028/IF/IAY/5314119 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106677824 | Completed | 23490 | 22968 | 2025-10-31 | 2026-03-10
NALCHHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005028/IF/IAY/5348038 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106532924 | Approved | 27000 | 0 | 2025-02-17
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005028/IF/IAY/5359197 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117282877 | Ongoing | 27000 | 1566 | 2025-08-19
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005028/IF/IAY/5364497 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114767073 | Completed | 23490 | 21924 | 2025-07-12 | 2026-03-10
NALCHHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005028/IF/IAY/552847 — Construction of IAY House -IAY REG. NO. MP3444814 | Completed | 15030 | 14672 | 2017-02-23 | 2017-10-10
NALCHHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005028/IF/IAY/61740 — Construction of IAY House -IAY REG. NO. MP-22-005-028-002/10 | Completed | 14310 | 13356 | 2016-04-17 | 2017-08-05
NALCHHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005028/IF/IAY/629971 — Construction of IAY House -IAY REG. NO. MP1037797 | Completed | 15030 | 15076 | 2017-02-23 | 2017-12-25
NALCHHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005028/IF/IAY/629982 — Construction of IAY House -IAY REG. NO. MP1058147 | Completed | 15030 | 17236 | 2017-02-23 | 2018-06-10
NALCHHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005028/IF/IAY/629988 — Construction of IAY House -IAY REG. NO. MP1070536 | Completed | 15030 | 15564 | 2017-02-23 | 2018-06-10
NALCHHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005028/IF/IAY/630039 — Construction of IAY House -IAY REG. NO. MP1661382 | Completed | 15030 | 15569 | 2017-03-20 | 2018-06-29
NALCHHA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005028/IF/IAY/695647 — Construction of IAY House -IAY REG. NO. MP1369224 | Completed | 15030 | 19052 | 2018-02-02 | 2018-06-10
NALCHHA | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1722005028/LD/22012034277375 — VARKASHA ROPAN MIDIL SCHOOL SHAMSHAAN GHAT KUNJROD | Completed | 328000 | 6680 | 2016-07-03 | 2018-08-02
NALCHHA | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1722005028/LD/22012034277391 — VARKSHA ROPAN PRAYAMARI SCHOOL NAIBARODA | Completed | 328000 | 7515 | 2016-07-04 | 2018-08-02
NALCHHA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Fallow Land for Community / Development of Fallow Land for Community | Land Development | 1722005028/LD/22012034534567 — shamshaan shed nirnaam naibaroda kanugo | Completed | 195535.43 | 169916.87 | 2021-02-01 | 2024-01-16
NALCHHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Stone graded Bund for Community / Construction of Stone graded Bund for Community | Construction of Bund | 1722005028/LD/22012034574225 — stone mesonary boundrywall poshan watika kunjarod naibaroda | Closed | 0 | 0 | 2021-04-01
NALCHHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1722005028/LD/22012034574226 — stone mesonary boundrywall poshan watika kunjarod naibaroda | Closed | 0 | 0 | 2021-04-01
NALCHHA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1722005028/LD/3799384066 — मेढ बंधान कार्य ग्राम पंचायत नाईबरोदा | Deleted | 0 | 0 | 2012-12-25
NALCHHA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1722005028/LD/651 — Gramin Krinakan Kunjrod gram panchayat naibaroda | Completed | 0 | 467640 | 2011-12-05 | 2012-07-11
NALCHHA | 2006-2007 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005028/RC/003 — ग्रेवल मार्ग भेरूपीप्‍पलीया से कुजंरोद | Completed | 196000 | 279700 | 2006-04-18 | 2006-08-30
NALCHHA | 2006-2007 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005028/RC/1010 — ग्रेवल मार्ग निमार्ण नाईबरोदा से बिल्‍लोद मार्ग नाईबरोदा | Completed | 0 | 348450 | 2007-01-05 | 2008-03-31
NALCHHA | 2007-2008 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005028/RC/17001 — ग्रेवल मार्ग निर्माण कुंजरोद से भेरूपिपल्‍या नाईबरोदा | Completed | 186000 | 162370 | 2007-04-22 | 2009-09-15
NALCHHA | 2007-2008 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005028/RC/17002 — ग्रेवल मार्ग निर्माण नारायण चौकीदार के घर से उकाला नाईबरोदा | Completed | 200000 | 0 | 2008-01-23 | 2008-09-15
NALCHHA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005028/RC/22012034157913 — ग्रेवल मार्ग निर्माण कार्य नाईबरोदा ग्राम पंचायत नाईबरोदा | Deleted | 0 | 0 | 2012-12-25
NALCHHA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005028/RC/22012034157915 — ग्रेवल मार्ग निर्माण कार्य नाईबरोदा ग्राम पंचायत नाईबरोदा | Deleted | 0 | 0 | 2012-12-25
NALCHHA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722005028/RC/22012034157925 — पंच परमेश्‍वर निर्माण कार्य ग्राम पंचायत नाईबरोदा | Deleted | 0 | 0 | 2012-12-25
NALCHHA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722005028/RC/22012034185735 — CC Road Nirman Kunjroad naibaroda | Completed | 125000 | 2544 | 2013-09-26 | 2018-06-12
NALCHHA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005028/RC/22012034191348 — ग्रेवल मार्ग निर्माण कार्य उकाला से पठार तक ग्राम | Completed | 496000 | 65700 | 2013-11-06 | 2014-04-20
NALCHHA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005028/RC/22012034191349 — ग्रेवल मार्ग निर्माण कार्य गांव से सत्‍यनारायण के | Deleted | 496000 | 0 | 2013-11-06
NALCHHA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722005028/RC/22012034198543 — CC RODE VIDHAYAK NIDHI DARBAR KE GHAR SE MUNNA KE | Completed | 176000 | 111496 | 2014-09-18 | 2018-03-14
NALCHHA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005028/RC/22012034212222 — खेत सडक योजना ग्रेवल मार्ग निर्माण गुलरझिरी रोड से | Completed | 1066000 | 521526.8 | 2014-03-06 | 2017-01-10
NALCHHA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005028/RC/22012034212233 — खेत सडक योजना ग्रेवल मार्ग निर्माण भेरूपिपल्‍या से | Completed | 1066000 | 661916.6 | 2014-03-06 | 2017-01-10
NALCHHA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005028/RC/22012034370314 — khet sadak nirman naibaroda | Closed | 0 | 0 | 2017-10-02
NALCHHA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005028/RC/22012034373737 — Sudur Smpark Sadak | Closed | 0 | 0 | 2018-04-14
NALCHHA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005028/RC/22012034376727 — Sudur Sampark Sadak | Closed | 0 | 0 | 2018-04-14
NALCHHA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005028/RC/22012034376728 — Sudur Sampark Sadak | Closed | 0 | 0 | 2018-04-14
NALCHHA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005028/RC/22012034437503 — GRAWAL MARG NIRMAN NAIBARODA | Closed | 0 | 0 | 2019-04-04
NALCHHA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005028/RC/22012034558506 — grewal marg khetsadak shanker choudhary ke khet se mahesh choudhary ke khet tak naibaroda | Completed | 750085.97 | 724180.48 | 2021-02-16 | 2023-09-08
NALCHHA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722005028/RC/22012034838700 — सीसी रोड मानपुर फोरलेन से मुक्तिधाम तक नाईबरौदा | Ongoing | 26000 | 16443 | 2025-04-01
NALCHHA | 2007-2008 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005028/RC/50028 — Greval Marg Nirman Narayan ke Chokidar Se ukala Tak Naibroda | Completed | 200000 | 286114 | 2007-07-04 | 2008-09-15
NALCHHA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005028/RC/50176 — सिमेन्‍ट कांक्रीट खरंजा निर्माण कार्य नाईबरोदा | Completed | 0 | 0 | 2009-01-02 | 2012-05-04
NALCHHA | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005028/RC/50197 — Paip Puliya Nirman Kunjrod Se Bherupiplya Road Par No. 01 Naibroda | Completed | 0 | 563750 | 2009-04-02 | 2012-05-10
NALCHHA | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005028/RC/50225 — पाईप पुलीया र्नि‍माण हनुमान मंदि‍र के सामने नाईबरोदा ग्राम पंचायत नाईबरोदा | Completed | 0 | 405600 | 2009-04-25 | 2012-05-10
NALCHHA | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005028/RC/50316 — मुरम रोड निर्माण पी एम रोड से नाईबरोदा तक ग्राम पंचायत नाईबरोदा | Completed | 0 | 260000 | 2009-06-16 | 2012-05-08
NALCHHA | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005028/RC/50392 — ग्रेवल मार्ग ‍नि‍र्माण कार्य शंकर चौधरी के खेत से महेश जाट के खेत तक ग्राम पंचायत नाईबरोदा | Completed | 0 | 130000 | 2009-12-08 | 2012-05-10
NALCHHA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005028/RC/50396 — गे्वल मार्ग ि‍नर्माण कुंजरों से भेरूि‍पपल्‍या भाग 2 नाईबरोदा | Completed | 500000 | 220100 | 2010-04-24 | 2012-05-10
NALCHHA | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005028/RC/50397 — ग्रेवल मार्ग शंकर चौधरी से महेश जाट क ेखेत तक नाईबरोदा | Deleted | 500000 | 0 | 2009-08-31
NALCHHA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005028/RC/50442 — पाईप पुलि‍या र्नि‍माण कि‍सनि‍संह के खेत के पास नाईबरोदा | Deleted | 0 | 364299.82 | 2010-04-24
NALCHHA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005028/RC/50609 — ग्रेवल मार्ग निर्माण्‍ा कार्य धुलाजी के खेत से गज्‍जू जाट के खेत तक ग्राम पंचायत नाईबरोदा | Completed | 0 | 386868 | 2011-05-20 | 2012-09-19
NALCHHA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005028/RC/50610 — ग्रेवल मार्ग निर्माण्‍ा कार्य गज्‍जु जाट के खेत से हरि जाट के खेत तक ग्राम पंचायत नाईबरोदा | Completed | 0 | 413382 | 2011-05-20 | 2012-12-16
NALCHHA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005028/RC/50635 — मुरम मार्ग निर्माण कार्य बागला फाटे से रमेश के खेत तक ग्राम पंचायत नाईबरोदा | Completed | 0 | 454252 | 2011-06-10 | 2012-12-16
NALCHHA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005028/RC/50715 — ग्रेवल मार्ग विजय शर्मा के खेत से शेरखा के खेत तक ग्राम पंचायत नाईबरोदा | Completed | 0 | 464506 | 2011-12-25 | 2012-03-20
NALCHHA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005028/RC/50782 — ग्रेवल मार्ग निर्माण मानपुर से बगडी रोड से भेरूपिल्‍या मार्ग ग्राम पंचायत नाईबरोदा (RES) | Completed | 0 | 585855 | 2012-02-18 | 2012-07-11
NALCHHA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722005028/RC/50906 — पंच परमेश्‍वर सीसी रोड विक्रम ठाकुर के घर से मनोज मीणा के घर तक | Completed | 156000 | 125136 | 2013-02-04 | 2013-03-31
NALCHHA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Vermi Compost structure for Community / Construction of Vermi Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1722005028/RS/22012034580553 — SBM Compost pit hot bajaar kunjroad | Closed | 0 | 0 | 2021-08-15
NALCHHA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Vermi Compost structure for Community / Construction of Vermi Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1722005028/RS/22012034580556 — SBM Compost pit hot bajaar kunjroad | Closed | 0 | 0 | 2021-08-15
NALCHHA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Vermi Compost structure for Community / Construction of Vermi Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1722005028/RS/22012034580558 — SBM Compost pit hot bajaar kunjroad | Closed | 0 | 0 | 2021-08-15
NALCHHA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Vermi Compost structure for Community / Construction of Vermi Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1722005028/RS/22012034580559 — SBM Compost pit hot bajaar kunjroad | Closed | 0 | 0 | 2021-08-15
NALCHHA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Vermi Compost structure for Community / Construction of Vermi Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1722005028/RS/22012034580560 — SBM Compost pit hot bajaar kunjroad | Closed | 0 | 0 | 2021-08-15
NALCHHA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1722005028/RS/22012035130286 — सामुदायिक स्वच्छता परिसर कुंजरोद | Completed | 54000 | 51042.36 | 2024-09-30 | 2026-03-18
NALCHHA | 2006-2007 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722005028/WC/ — खेत तालाब कुंजरोद नाईबरोदा राजेन्‍द्र मकुन्‍दसिंह | Completed | 0 | 0 | 2006-05-22 | 2007-03-31
NALCHHA | 2006-2007 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722005028/WC/005 — खेत तालाब कुंजरोद नाईबरोदा दशरथ लालजी | Completed | 0 | 0 | 2006-06-10 | 2007-12-31
NALCHHA | 2006-2007 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722005028/WC/006 — खेत तालाब कुंजरोद नाईबरोदा कालु शंकर | Completed | 0 | 0 | 2006-06-10 | 2006-06-30
NALCHHA | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722005028/WC/105 — कपिल धारा कूप निमार्ण रामूबाई- चेनसिह | Completed | 0 | 0 | 2007-04-03 | 2008-09-15
NALCHHA | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722005028/WC/107 — तालाब गहरीकरण कुंजरोद नाईबरोदा | Completed | 70000 | 0 | 2007-06-21 | 2007-06-30
NALCHHA | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Mini Percolation tank / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1722005028/WC/22012034296696 — sankal pound nirbhay singh ke kheat ke paas rela wala par | Deleted | 0 | 0 | 2016-04-14
NALCHHA | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Mini Percolation tank / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1722005028/WC/22012034296697 — sankal pound nirbhay singh ke kheat ke paas rela wala par | Completed | 464000 | 445152.58 | 2016-06-21 | 2019-10-20
NALCHHA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722005028/WC/22012034326908 — तालाब गहरीकरण नाईबरोदा | Completed | 708000 | 734695.69 | 2017-05-30 | 2021-12-05
NALCHHA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Dam / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1722005028/WC/22012034356528 — BORI BAANDH BHERU PIPLYA NAALE PAR | Completed | 12000 | 5676 | 2017-09-30 | 2018-02-12
NALCHHA | 2017-2018 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Diversion Drain / Construction of Diversion Storm Water Drain for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1722005028/WC/22012034356537 — BORI BAANDH KHENI WAALE NAALE PAR | Completed | 13200 | 6020 | 2017-09-30 | 2018-02-12
NALCHHA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Box Trenches / Construction of Water Absorption Trench for Community | Construction of Trench | 1722005028/WC/22012034380372 — Nistartalab Nirman Shetankhali Nale Per | Closed | 0 | 0 | 2018-04-14
NALCHHA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Box Trenches / Construction of Water Absorption Trench for Community | Construction of Trench | 1722005028/WC/22012034380373 — Nistar Talab Nirman Jangdish Wale Nale Per | Closed | 0 | 0 | 2018-04-14
NALCHHA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & maint of Community Ponds for Comm / Repair and maintenance of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1722005028/WC/22012034440683 — NAALA TRECHING BHERUPIPLIYA | Completed | 397000 | 273912 | 2019-03-04 | 2021-06-19
NALCHHA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722005028/WC/22012034444292 — NISTAR TALAB NIRMAN SHEETALA GHATI NAIBARODA | Completed | 1486000 | 1382717.67 | 2019-03-05 | 2021-05-10
NALCHHA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & maint of Fisheries Ponds for Comm / Repair and maintenance of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1722005028/WC/22012034446797 — sankal pound shaitaan khaali par | Completed | 404000 | 311778 | 2019-03-08 | 2022-07-25
NALCHHA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1722005028/WC/22012034548574 — LBS on Shaitan Khali Kunjrod | Completed | 115923.41 | 77919.76 | 2020-05-12 | 2024-01-16
NALCHHA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1722005028/WC/22012034548753 — LBS on Gendalal ke khet ke pas wala nalha Bherupipliya | Completed | 115923.41 | 87116.74 | 2020-05-12 | 2025-04-09
NALCHHA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1722005028/WC/22012034551054 — Contur trench nirman ukala wali pahadi naibaroda | Completed | 605676.32 | 538740 | 2020-05-22 | 2021-11-15
NALCHHA | 2020-2021 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Stone Spur for Community / Construction of Stone Spur for Community | Construction of Spur | 1722005028/WC/22012034565998 — LBS Nirman Patharwale Nalhe Par Kunjrod | Physically Completed | 206029.68 | 129889.41 | 2020-09-20 | 2021-06-19
NALCHHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1722005028/WC/22012034635401 — CTRA rain water harvesting in panchayat bhawan | Completed | 14186.67 | 14025 | 2021-05-03 | 2022-11-13
NALCHHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1722005028/WC/22012034635403 — gullyplug inukala wali pahaadi kunjrod | Closed | 0 | 0 | 2021-04-01
NALCHHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1722005028/WC/22012034635937 — CTRA gully plug in ukala wali pahaadi kunjrod | Physically Completed | 149340.24 | 147392.53 | 2021-04-07 | 2026-04-22
NALCHHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1722005028/WC/22012034650873 — CTRA lbs on sheetala ghati kunjrod | Completed | 150782.69 | 113355.74 | 2021-04-30 | 2022-11-20
NALCHHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1722005028/WC/22012034676179 — CTRA roof top harvesting in aaganbadi kunjrod | Completed | 28132.42 | 25757 | 2021-05-03 | 2022-11-13
NALCHHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone boulder Gully Plugs for Community | Boulder Check/Gully Plug | 1722005028/WC/22012034713420 — CTRA gullyplug nirmaan pathar wale nale per kunjrod | Completed | 115883.83 | 85153.89 | 2021-05-25 | 2022-11-20
NALCHHA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1722005028/WC/22012034991711 — Countor trench nirman Ukala pahadi kunjrod Naibaroda | Completed | 355278.48 | 312728 | 2022-11-04 | 2025-05-26
NALCHHA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1722005028/WC/22012035022669 — Amarat Sarowar Shetan Khali Nala Naibaroda | Closed | 1476462.23 | 0 | 2022-04-01
NALCHHA | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1722005028/WC/22012035130733 — NALAA TRECHING KAARY KUNJROAD SHAITAAN KHALI | Completed | 217339.49 | 174326.48 | 2023-10-05 | 2026-04-15
NALCHHA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722005028/WC/22012035163778 — Recharge Pond nirman | New | 0 | 0 | 2024-04-01
NALCHHA | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722005028/WC/80034 — कपिल धारा कुप निर्माण जगदीश दोलतराम नाईबरोदा | Deleted | 0 | 0 | 2007-04-01
NALCHHA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722005028/WC/80091 — निस्‍तार तालब सेतान खाली नाले पर कुंजरोद नाईबरोदा | Completed | 499000 | 329910 | 2008-05-09 | 2012-05-08
NALCHHA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722005028/WC/80092 — कपिल धारा कुप निर्माण केसरसिंह भीमराव कुंजरोद नाईबरोदा | Completed | 50000 | 25815 | 2008-06-12 | 2010-05-17
NALCHHA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722005028/WC/80240 — कपिल धारा कुप निर्माण जगदीश दौलतराम नाईबरोा | Completed | 20000 | 17060 | 2008-06-08 | 2009-09-15
NALCHHA | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722005028/WC/80488 — कपील धारा कुप र्नि‍माण पन्‍नालाल भगता ग्राम नाईबारोदा ग्राम पंचायत नाईबारोदा | Completed | 0 | 15290 | 2007-04-02 | 2009-09-05
NALCHHA | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722005028/WC/80489 — कपील धारा कुप र्नि‍माण रूघनाथ मगत्‍या ग्राम नाईबारोदा ग्राम पंचायत नाईबारोदा | Completed | 0 | 19800 | 2007-07-14 | 2012-05-16
NALCHHA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722005028/WC/80490 — कपील धारा कुप र्नि‍माण गोपाल शौभान ग्राम नाईबारोदा ग्राम पंचायत नाईबारोदा | Completed | 0 | 13750 | 2009-05-22 | 2009-09-07
NALCHHA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1722005028/WC/81376 — कपिलधारा कुप निर्माण रोहित तिवारी ग्राम पंचायत नाईबरोदा | Completed | 0 | 189476 | 2012-01-16 | 2012-07-11
NALCHHA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Artificial Recharge of Well Through Sand Filter / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1722005028/WC/81558 — कपिल धारा कुप निर्माण कार्य उंकार शोभान ग्राम पंचा | Completed | 163000 | 163692 | 2012-04-22 | 2016-05-05
NALCHHA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Stop Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722005028/WC/9993627851 — तालाब गहरीकरण नाईबरोदा ग्राम पंचायत नाईबरोदा | Deleted | 0 | 0 | 2012-12-25
NALCHHA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722005028/WC/9993627866 — संकल पोण्‍ड शैतान खाली मैदान पर ग्राम पंचायत नाईबर | Deleted | 408000 | 0 | 2012-12-25
NALCHHA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722005028/WC/9993627873 — संकल पोण्‍ड उकाला पर पंचायत नाईबरोदा | Deleted | 408000 | 0 | 2012-12-25
NALCHHA | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1722005028/WC/9993627874 — कपिल धारा कुप निर्माण मुकेश पुनमचंद | Suspended | 163000 | 83646.36 | 2013-05-08
NALCHHA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1722005028/WC/9993627875 — कपिल धारा कुप निर्माण कार्य ग्राम पंचायत नाईबरोदा | Deleted | 0 | 0 | 2012-12-25
NALCHHA | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1722005028/WC/9993631166 — कपिलधारा कुप पार्वतीबाई नारायणसिंह | Completed | 163000 | 146484 | 2013-05-08 | 2016-01-20
NALCHHA | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Mini Percolation tank / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1722005028/WC/9993638038 — sankal pound | Completed | 408000 | 388895 | 2013-10-05 | 2014-04-30
NALCHHA | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Mini Percolation tank / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1722005028/WC/9993638040 — sankal pound | Completed | 408000 | 397099 | 2013-10-05 | 2014-04-30
NALCHHA | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1722005028/WC/9993649363 — कपिल धारा कुप निर्माण कार्य अरूणाबाई विक्रमसिंह नाईबरोदा | Deleted | 179000 | 0 | 2014-02-28
NALCHHA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Sunken Pond / Construction of Community Water Harvesting Ponds | Farm Pond | 1722005028/WC/9993667454 — sanken pond nirman naibaroda | Deleted | 0 | 0 | 2016-03-31
NALCHHA | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1722005028/WH/19956624 — STOP DAM UNNAYAN KARY KUNJROD | Deleted | 66000 | 0 | 2016-05-24
NALCHHA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722005/IF/22012034426992 — horticulture plantation parwatibai bherupipliya | Physically Completed | 760000 | 79632 | 2018-08-23 | 2021-01-18
NALCHHA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722005/IF/22012034427736 — HORTICULTURE PLANTATION NAIBARODA | Physically Completed | 330600 | 60488 | 2018-08-31 | 2021-01-18
NALCHHA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722005/IF/22012034432173 — horticulture plantation suresh saral kumar | Physically Completed | 551000 | 84356 | 2018-11-19 | 2021-01-18
NALCHHA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722005/WC/22012035240525 — Percolation tank Bherupiplya GP Naibroda | Approved | 0 | 0 | 2024-10-02