## Work List
Exported on: 2026-10-24 09:26:14
Filters applied:
Data source: VBGRAMG
District: DHAR
Block: All
Panchayat: Lunhera
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
NALCHHA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in fields for Community | Plantation | 1722005037/DP/22012034588977 — AKAM वसुधा वंदन अमृत वाटिका निस्तार तालाब शमशान घाट के पास कुंडा लुन्हेरा | Ongoing | 55847.4 | 0 | 2023-08-09
NALCHHA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Forestry Trees-Fields-Individuals / Agro Forestry Block Plantation for Individual | Plantation | 1722005037/IF/22012034617585 — vraksharopan kariya lunhera kundwala maal balwant ganpat | Ongoing | 678010.87 | 189000 | 2020-11-20
NALCHHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722005037/IF/22012035279233 — KAPIL DHARA KUP NIRMAN JAMSINGH BUCHHA | Ongoing | 295895.26 | 0 | 2024-12-31
NALCHHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722005037/IF/22012035279245 — KAPIL DHARA KUP NIRMAN NANURAM NATHU | Ongoing | 295644.61 | 0 | 2025-01-30
NALCHHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722005037/IF/22012035279260 — KAPIL DHARA KUP NIRMAN MAGAN DHULIYA | Ongoing | 294205.58 | 0 | 2024-12-31
NALCHHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722005037/IF/22012035279265 — KAPIL DHARA KUP NIRMAN UMRAV SHANKAR | Ongoing | 293933.71 | 4200 | 2025-02-13
NALCHHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722005037/IF/22012035296925 — Kapil dhar kup nirman kailash chhogalal | Ongoing | 295329.18 | 0 | 2025-02-25
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722005037/IF/22012035602950 — एक बगिया मॉ के नाम ग्रुप श्री गणेश आजीविका समूह लुन्हेरा -श्रीमती रूखमाबाई | Approved | 236004.06 | 0 | 2025-08-15
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722005037/IF/22012035602958 — एक बगिया मॉ के नाम ग्रुप श्री गणेश आजीविका समूह कुन्दा -श्रीमती लीलाबाई | Approved | 235664.27 | 0 | 2025-08-15
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722005037/IF/22012035602970 — एक बगिया मॉ के नाम ग्रुप श्री गणेश आजीविका समूह कुन्दा -श्रीमती अनिताबाई | Approved | 235664.27 | 0 | 2025-08-15
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722005037/IF/22012035602982 — एक बगिया मॉ के नाम ग्रुप मॉ सरस्वती आजीविका समूह कुन्दा -श्रीमती रामकन्याबाई | Approved | 238731.49 | 0 | 2025-08-15
NALCHHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005037/IF/IAY/2336712 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3248218 | Completed | 23490 | 0 | 2024-09-21 | 2026-07-28
NALCHHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005037/IF/IAY/3873269 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145399700 | Approved | 27000 | 0 | 2022-05-01
NALCHHA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1722005037/IF/IAY/39878 — Construction of IAY House -IAY REG. NO. MP-22-005-037-002/33 | Approved | 27000 | 0 | 2015-10-16
NALCHHA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1722005037/IF/IAY/39881 — Construction of IAY House -IAY REG. NO. MP-22-005-037-002/35 | Approved | 27000 | 0 | 2015-10-16
NALCHHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005037/IF/IAY/4194295 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118606550 | Approved | 27000 | 0 | 2022-06-11
NALCHHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005037/IF/IAY/4278129 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119724295 | Ongoing | 27000 | 0 | 2024-11-05
NALCHHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005037/IF/IAY/4611611 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125539830 | Completed | 23490 | 0 | 2024-12-17 | 2026-07-22
NALCHHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005037/IF/IAY/4757872 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119549350 | Completed | 23490 | 0 | 2024-11-20 | 2026-07-28
NALCHHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005037/IF/IAY/4879955 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126455060 | Ongoing | 27000 | 6300 | 2025-01-21
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005037/IF/IAY/5149165 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118831870 | Completed | 23490 | 600 | 2025-05-02 | 2026-09-23
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005037/IF/IAY/5155841 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141463266 | Ongoing | 27000 | 2100 | 2025-04-15
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005037/IF/IAY/5158536 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125825715 | Ongoing | 27000 | 0 | 2025-04-20
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005037/IF/IAY/5161903 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125538977 | Ongoing | 27000 | 0 | 2025-07-18
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005037/IF/IAY/5173049 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115782735 | Completed | 23490 | 1200 | 2025-05-02 | 2026-07-28
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005037/IF/IAY/5175301 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118606088 | Completed | 27000 | 5400 | 2025-04-15 | 2026-10-18
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005037/IF/IAY/5178983 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114214127 | Ongoing | 27000 | 8400 | 2025-04-20
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005037/IF/IAY/5180285 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119549412 | Completed | 23490 | 3600 | 2025-04-15 | 2026-07-28
NALCHHA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005037/IF/IAY/5191500 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119722057 | Ongoing | 27000 | 12000 | 2026-05-15
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005037/IF/IAY/5196202 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114213797 | Completed | 23490 | 0 | 2025-04-20 | 2026-07-28
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005037/IF/IAY/5199128 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118300885 | Completed | 23490 | 0 | 2025-05-02 | 2026-07-22
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005037/IF/IAY/5200059 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118330162 | Physically Completed | 23490 | 0 | 2025-06-19 | 2026-08-11
NALCHHA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005037/IF/IAY/5200468 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119601210 | Completed | 23490 | 15600 | 2026-05-23 | 2026-09-23
NALCHHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005037/IF/IAY/5202925 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119644018 | Approved | 27000 | 0 | 2025-02-17
NALCHHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005037/IF/IAY/5203364 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119600963 | Approved | 27000 | 0 | 2025-02-17
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005037/IF/IAY/5206676 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114213909 | Completed | 23490 | 4200 | 2025-04-20 | 2026-07-28
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005037/IF/IAY/5213578 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116056176 | Ongoing | 27000 | 10500 | 2025-06-05
NALCHHA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005037/IF/IAY/5217275 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126016611 | Ongoing | 27000 | 6600 | 2026-07-28
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005037/IF/IAY/5230561 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113667412 | Completed | 27000 | 25200 | 2025-05-15 | 2026-10-19
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005037/IF/IAY/5232491 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118831834 | Completed | 23490 | 2100 | 2025-05-02 | 2026-07-28
NALCHHA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005037/IF/IAY/5237909 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126015092 | Ongoing | 27000 | 6300 | 2026-07-28
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005037/IF/IAY/5439311 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119631257 | Completed | 23490 | 300 | 2025-07-11 | 2026-07-28
NALCHHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005037/IF/IAY/5826765 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127037490 | Approved | 27000 | 0 | 2025-02-18
NALCHHA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1722005037/IF/IAY/98704 — Construction of IAY House -IAY REG. NO. MP-22-005-037-001/016 | Approved | 27000 | 0 | 2016-01-07
NALCHHA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1722005037/IF/IAY/98726 — Construction of IAY House -IAY REG. NO. MP-22-005-037-001/18 | Approved | 27000 | 0 | 2016-01-07
NALCHHA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone Boulder Gully Plug for Community | Boulder Check/Gully Plug | 1722005037/WC/22012034718144 — CTRA GULLY PLUG KUNDMAL PAR LUNHERA | Ongoing | 146729.79 | 105000 | 2023-08-07
NALCHHA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1722005037/WC/22012035108146 — contur tranch kunda wale nale ke samne wali pahadi | Ongoing | 314617.2 | 215250 | 2023-12-09
NALCHHA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1722005037/WC/22012035108150 — contur tranch kunda wale nale ke pass wali pahadi | Ongoing | 314617.2 | 157500 | 2023-12-28
NALCHHA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1722005037/WC/22012035108154 — contur tranch chokidar ke khet ke samne wali pahadi | Ongoing | 270958.2 | 157500 | 2023-12-25
NALCHHA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722/WC/22012035260584 — nistar talab nirmaan jogi madhi high school ke peeche | Ongoing | 3982000 | 0 | 2025-06-17