## Work List
Exported on: 2026-10-28 13:57:57
Filters applied:
Data source: VBGRAMG
District: DHAR
Block: All
Panchayat: Kothi Sodpur
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
NALCHHA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1722005053/DP/22012034615797 — सामुदायेक कूप निर्माण कार्य तालाब के पास कोठीसोडपुर | Ongoing | 537251.35 | 0 | 2024-03-15
NALCHHA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722005053/IF/22012035220928 — कपिल धारा कूप निर्माण कार्य ताराबाई थावरसिंह कोठीसोड़पुर | Ongoing | 232656.75 | 0 | 2024-03-15
NALCHHA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722005053/IF/22012035220937 — कपिल धारा कूप निर्माण कार्य अनिता मगनसिंहकोठीसोड़पुर | Ongoing | 232656.75 | 0 | 2024-03-15
NALCHHA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722005053/IF/22012035223962 — कपिल धारा कूप निर्माण कार्य अनसिंह डावर उंकरमेहंदीखेड़ी | Ongoing | 232656.75 | 0 | 2024-03-15
NALCHHA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722005053/IF/22012035223967 — कपिल धारा कूप निर्माण कार्य खुमसिंहडावर उंकरमेहंदीखेड़ी | Ongoing | 232656.75 | 0 | 2024-03-15
NALCHHA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722005053/IF/22012035223974 — कपिल धारा कूप निर्माण कार्य भेरू गप्पू मेहंदीखेड़ी | Ongoing | 232656.75 | 0 | 2024-03-15
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722005053/IF/22012035325179 — Kapil dhara kup nirman kary Raysingh sankar | Approved | 0 | 0 | 2025-04-01
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722005053/IF/22012035603065 — एक बगिया मॉ के नाम ग्रुप मॉं शीतला आजीविका महिला बचत समूह कोठीसोडपुर - श्रीमती लक्ष्मी | Ongoing | 261747.23 | 24000 | 2026-02-07
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722005053/IF/22012035603072 — एक बगिया मॉ के नाम ग्रुप गायत्री आजीविका समूह कोठीसोडपुर - श्रीमती मंगलीबाई | Ongoing | 263510.03 | 20400 | 2025-09-14
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722005053/IF/22012035603076 — एक बगिया मॉ के नाम ग्रुप एमआर जागृति आजीविका समूह कोठीसोडपुर - श्रीमती हिराबाई | Approved | 263510.03 | 0 | 2025-08-15
NALCHHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005053/IF/IAY/4572080 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117817482 | Completed | 21870 | 0 | 2024-10-10 | 2026-07-22
NALCHHA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005053/IF/IAY/5385057 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118074309 | Completed | 23490 | 522 | 2026-04-06 | 2026-07-22
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005053/IF/IAY/5389549 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117834314 | Completed | 23490 | 0 | 2025-11-23 | 2026-07-25
NALCHHA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005053/IF/IAY/5389550 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117835123 | Ongoing | 27000 | 10800 | 2026-05-23
NALCHHA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005053/IF/IAY/5395000 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117532362 | Completed | 23490 | 0 | 2026-04-06 | 2026-07-22
NALCHHA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005053/IF/IAY/5395920 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117533251 | Physically Completed | 23490 | 8400 | 2026-05-23 | 2026-07-12
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005053/IF/IAY/5404934 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117690726 | Completed | 23490 | 0 | 2025-06-05 | 2026-07-25
NALCHHA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005053/IF/IAY/5408515 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117861381 | Ongoing | 27000 | 16800 | 2026-09-17
NALCHHA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005053/IF/IAY/5408533 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117645119 | Completed | 23490 | 522 | 2026-04-06 | 2026-07-22
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005053/IF/IAY/5536205 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117542040 | Completed | 23490 | 0 | 2025-06-05 | 2026-07-22
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005053/IF/IAY/5541129 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117841492 | Completed | 23490 | 0 | 2025-05-14 | 2026-07-25
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005053/IF/IAY/5612415 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117898583 | Approved | 27000 | 0 | 2025-05-05
NALCHHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005053/IF/IAY/5657356 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118159810 | Approved | 27000 | 0 | 2025-02-17
NALCHHA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005053/IF/IAY/5659083 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117581137 | Ongoing | 27000 | 16800 | 2026-09-17
NALCHHA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005053/IF/IAY/5904503 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117689828 | Ongoing | 27000 | 16800 | 2026-09-17
NALCHHA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005053/IF/IAY/5906833 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117484057 | Completed | 23490 | 0 | 2026-05-04 | 2026-07-22
NALCHHA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005053/IF/IAY/5908325 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117874451 | Ongoing | 27000 | 16800 | 2026-09-17
NALCHHA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005053/IF/IAY/5909694 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117703749 | Completed | 27000 | 25000 | 2026-07-17 | 2026-10-18
NALCHHA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005053/IF/IAY/5910153 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114840940 | Completed | 23490 | 4800 | 2026-05-04 | 2026-10-18
NALCHHA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005053/IF/IAY/5912975 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117583017 | Completed | 27000 | 10200 | 2026-05-04 | 2026-10-18
NALCHHA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005053/IF/IAY/5913507 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117856101 | Completed | 27000 | 23200 | 2026-07-17 | 2026-10-18
NALCHHA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005053/IF/IAY/5916049 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114835711 | Completed | 27000 | 9600 | 2026-05-04 | 2026-09-23
NALCHHA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005053/IF/IAY/5916509 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114837809 | Physically Completed | 27000 | 8400 | 2026-05-04 | 2026-09-28
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005053/IF/IAY/5916579 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117882102 | Approved | 27000 | 0 | 2026-02-11
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005053/IF/IAY/5917222 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113704062 | Approved | 27000 | 0 | 2026-02-11
NALCHHA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005053/IF/IAY/5919587 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117485630 | Physically Completed | 27000 | 8400 | 2026-05-04 | 2026-09-27
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005053/IF/IAY/5921117 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117836056 | Approved | 27000 | 0 | 2026-02-11
NALCHHA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005053/IF/IAY/5922272 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115996653 | Completed | 23490 | 4800 | 2026-05-04 | 2026-08-10
NALCHHA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005053/IF/IAY/5923746 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117837199 | Physically Completed | 27000 | 6000 | 2026-04-06 | 2026-09-28
NALCHHA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005053/IF/IAY/5924315 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117569666 | Completed | 27000 | 9000 | 2026-05-04 | 2026-10-18
NALCHHA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005053/IF/IAY/5925387 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118061407 | Physically Completed | 27000 | 4200 | 2026-04-06 | 2026-09-28
NALCHHA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005053/IF/IAY/5925761 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117614287 | Physically Completed | 23490 | 10800 | 2026-07-17 | 2026-08-02
NALCHHA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005053/IF/IAY/6243297 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117493412 | Completed | 27000 | 22800 | 2026-07-17 | 2026-10-18
NALCHHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005053/IF/IAY/6372831 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115996258 | Approved | 27000 | 0 | 2025-02-17
NALCHHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005053/IF/IAY/6372875 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117834526 | Approved | 27000 | 0 | 2025-02-17
NALCHHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005053/IF/IAY/6403656 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114834889 | Approved | 27000 | 0 | 2025-02-17
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722005053/IF/IAY/6411825 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114837969 | Approved | 27000 | 0 | 2026-02-11
NALCHHA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1722005053/RC/22012034844670 — सी सी रोड निर्माण माण्‍डव मेन रोड से पुरानी बावडी तक ग्राम मेहन्‍दीखेडी | Approved | 107000 | 0 | 2025-04-15
NALCHHA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1722005053/WC/22012035133129 — Nala Trenching Work Mangilal Gulab Ke Ghar Se Kakadakho Tak Gram Mehandikhedii | Ongoing | 674155.43 | 0 | 2024-03-15
NALCHHA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722005/IF/22012035039879 — rajaram amrude block plantetion 22 | Ongoing | 214000 | 0 | 2023-07-14