## Work List
Exported on: 2026-09-08 08:29:23
Filters applied:
Data source: VBGRAMG
District: DHAR
Block: All
Panchayat: Bhil Barkheda
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
NALCHHA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Farm Forestry-Community / Boundary Line Plantation of Farm Forestry Trees for Community | Plantation | 1722005054/DP/22012034589407 — AKAM Vasuda Vandan Amrit Vatika Purane Talab ke Kinare Gram Bhilbarkheda | Ongoing | 55847.4 | 0 | 2023-08-08
NALCHHA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722005054/IF/22012034363906 — कपिल धारा सह खेत तालाब संजुरीबाई घुरक्या भीलबरखेडा | Ongoing | 230000 | 0 | 2018-02-08
NALCHHA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Goat Shelter for Individuals / Construction of Goat Shelter for Individuals | Goat Shelter | 1722005054/IF/22012034594871 — बकरी पालन चंदर भीमा भीलबरखेड़ा | Ongoing | 46636.05 | 0 | 2023-12-08
NALCHHA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Goat Shelter for Individuals / Construction of Goat Shelter for Individuals | Goat Shelter | 1722005054/IF/22012034861735 — pasu sed nirman ramkali bai bhil bharkhda | Ongoing | 102645.51 | 0 | 2021-11-29
NALCHHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722005054/IF/22012034977466 — Khet Talab Nirman Ballu Shivla Bhilbarkheda | Ongoing | 356340.1 | 0 | 2022-10-27
NALCHHA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005054/IF/22012035058240 — iay/pm aawas Shantibai jhamriya Bhilbarkheda | Physically Completed | 19000 | 0 | 2023-07-30 | 2026-07-30
NALCHHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722005054/IF/22012035240920 — KAPIL DHARA KOOP NIRMAAN GAJJA BISHAN GRAM BHILBARKHEDA | Approved | 0 | 0 | 2024-06-08
NALCHHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722005054/IF/22012035240923 — KAPIL DHARA KOOP NIRMAAN GULAB RUGNATH GRAM BHILBARKHEDA | Approved | 0 | 0 | 2024-06-08
NALCHHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722005054/IF/22012035240992 — KAPIL DHARA KOOP NIRMAAN GAJJA BISHAN GRAM BHILBARKHEDA | Ongoing | 243080.31 | 0 | 2024-07-12
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722005054/IF/22012035371958 — JGSA Khet Talab Nirman Govind Jagan Bhilbarkheda | Approved | 147621.16 | 0 | 2025-04-14
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722005054/IF/22012035372136 — JGSA Khet Talab Nirman Rama Chogiya Bhilbarkheda | Approved | 147621.16 | 0 | 2025-04-14
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722005054/IF/22012035372219 — JGSA Khet Talab Nirman Rugnath Punja Bhilbarkheda | Approved | 147621.16 | 0 | 2025-04-14
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722005054/IF/22012035372325 — JGSA Khet Talab Nirman Mohan Shankar Bhilbarkheda | Approved | 0 | 0 | 2025-04-14
NALCHHA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1722005054/IF/22012035408731 — JGSA DUGG WELL RECHARGE PIT NIRMAN KARYA CHAMPALAL RAMA BHILBARKHEDA | Approved | 0 | 0 | 2025-04-14
NALCHHA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1722005054/IF/22012035408762 — JGSA DUGG WELL RECHARGE PIT NIRMAN KARYA GULAB RUGNATH BHILBARKHEDA | Approved | 0 | 0 | 2025-04-14
NALCHHA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1722005054/IF/22012035408795 — JGSA DUGG WELL RECHARGE PIT NIRMAN KARYA RAJARAM ANARSINGH BHILBARKHEDA | Approved | 0 | 0 | 2025-04-14
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722005054/IF/22012035408847 — JGSA KHET TALAB NIRMAN KARYA CHAMPALAL RAM BHILBARKHEDA | Approved | 0 | 0 | 2025-04-14
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722005054/IF/22012035408877 — JGSA KHET TALAB NIRMAN KARYA RAMA CHOGIYA BHILBARKHEDA | Approved | 0 | 0 | 2025-04-14
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722005054/IF/22012035408898 — JGSA KHET TALAB NIRMAN KARYA GOVIND JAGAN BHILBARKHEDA | Approved | 0 | 0 | 2025-04-14
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722005054/IF/22012035408915 — JGSA KHET TALAB NIRMAN KARYA RUGNATH PUNJA BHILBARKHEDA | Approved | 0 | 0 | 2025-04-14
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722005054/IF/22012035408934 — JGSA KHET TALAB NIRMAN KARYA MOHAN SHANKAR BHILBARKHEDA | Approved | 0 | 0 | 2025-04-14
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722005054/IF/22012035408945 — JGSA KHET TALAB NIRMAN KARYA LAXMAN DHARIYA BHILBARKHEDA | Approved | 0 | 0 | 2025-04-14
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722005054/IF/22012035603033 — एक बगिया मॉ के नाम ग्रुप गंगा आजीविका समूह भीलबरखेडा - श्रीमती धापूबाई | Approved | 266577.25 | 0 | 2025-08-15
NALCHHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005054/IF/IAY/4579497 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118783051 | Approved | 27000 | 0 | 2024-09-10
NALCHHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005054/IF/IAY/4581937 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119564154 | Approved | 27000 | 0 | 2024-09-10
NALCHHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005054/IF/IAY/4582669 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119600757 | Approved | 27000 | 0 | 2024-09-10
NALCHHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005054/IF/IAY/4583806 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119076454 | Completed | 23490 | 0 | 2024-10-09 | 2026-07-30
NALCHHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005054/IF/IAY/4702467 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119658181 | Approved | 27000 | 0 | 2024-09-23
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005054/IF/IAY/4758500 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119583509 | Completed | 23490 | 0 | 2025-04-09 | 2026-07-30
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005054/IF/IAY/5345236 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119662268 | Ongoing | 27000 | 0 | 2025-07-17
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005054/IF/IAY/5348123 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119635483 | Ongoing | 27000 | 2100 | 2025-04-09
NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005054/IF/IAY/5731241 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119543556 | Ongoing | 27000 | 4200 | 2026-02-03
NALCHHA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722005054/RC/22012034844900 — CC ROAD NIRMAN MAIN ROAD SE RAJMAL MANGTYA KE GHAR TAK BHILBARKHEDA | Approved | 46000 | 0 | 2025-04-24
NALCHHA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722005054/RC/22012034850087 — CC Road Nirman Kekadiya Gatliya Ke Ghar Se Lalsingh Chhitar Ke Ghar Tak Bhilbarkheda | Approved | 77000 | 0 | 2025-10-02
NALCHHA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722005054/RC/22012034850088 — CC Road Nirman Main Road Chourahe Se Govind Rumja Ke Ghar Tak Bhilbarkheda | Approved | 60000 | 0 | 2025-04-01
NALCHHA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722005054/RC/22012034850096 — CC Road Nirman Main Road Se Shankar Shobharam Ke Ghar Ki Or Bhilbarkheda | Approved | 86000 | 0 | 2025-04-14
NALCHHA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722005054/RC/22012034850097 — CC Road Nirman Lalsingh Chhitar Ke Ghar Se Fakira Rukhdiya Ke Ghar Tak Bhilbarkheda | Approved | 59000 | 0 | 2025-04-14
NALCHHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1722005054/WC/22012034659788 — CTRA parkolation tenk harniyabayadi | Ongoing | 501943.56 | 0 | 2021-05-21
NALCHHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1722005054/WC/22012034686830 — CTRA Construction of Gebian Bhilbarkehda 1 | Ongoing | 88503.3 | 0 | 2021-05-21
NALCHHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1722005054/WC/22012034686837 — CTRA Construction of Gebian Bhilbarkehda 2 | Ongoing | 88503.3 | 0 | 2021-05-21
NALCHHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1722005054/WC/22012034686849 — CTRA Construction of Gebian Bhilbarkehda 3 | Ongoing | 88503.3 | 0 | 2021-05-21
NALCHHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1722005054/WC/22012034686854 — CTRA Construction of Gebian Bhilbarkehda 4 | Ongoing | 88503.3 | 0 | 2021-05-21
NALCHHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1722005054/WC/22012034688182 — CTRA Construction of Talab Lakhaniya Nalha Bhilbarkheda | Ongoing | 1497552.57 | 0 | 2021-05-21
NALCHHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone boulder Gully Plugs for Community | Boulder Check/Gully Plug | 1722005054/WC/22012034705014 — CTRA Gully Plug Bada Mal Bhilbarkheda 9 | Ongoing | 102311.2 | 0 | 2022-01-30
NALCHHA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722005054/WC/22012035137814 — R.M.S. Nirmaan Work Amichand Ke Khet Ke Paas Gram Bhilbarkheda | Ongoing | 1489482.31 | 0 | 2023-10-07
NALCHHA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722005054/WC/22012035137818 — R.M.S. Nirmaan Work Shamsher Ke Khet Ke Paas Gram Bhilbarkheda | Ongoing | 1488676.47 | 0 | 2023-10-07
NALCHHA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1722005054/WC/22012035163782 — Percolation tank | New | 0 | 0 | 2024-04-01
NALCHHA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1722005054/WC/22012035262242 — Sarvajanik kup nirman kaarya sinchai vighag taalab ke pass Bhilbarkheda | Approved | 0 | 0 | 2025-04-04
NALCHHA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1722005054/WC/22012035262247 — Sarvajanik kup nirman kaarya Lalsingh chitar ke ghar ke pass Bhilbarkheda | Approved | 0 | 0 | 2025-04-04
NALCHHA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1722005054/WC/22012035262270 — Contur trench Nirman Karya Bada mall Bhilbarkheda | Approved | 0 | 0 | 2025-04-04
NALCHHA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1722005054/WH/22012034939593 — NAMAMI GANGE TALAB JIRNODHAR WORK BADA TALAB GRAM BHILBARKHEDA | Approved | 0 | 0 | 2024-04-14
NALCHHA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1722005054/WH/22012034939594 — NAMAMI GANGE BAWADI JIRNODHAR WORK JAAMLA AAWAR BAWADI GRAM BHILBARKHEDA | Approved | 0 | 0 | 2024-04-14