## Work List
Exported on: 2026-09-13 13:24:35
Filters applied:
Data source: VBGRAMG
District: DHAR
Block: All
Panchayat: Dhulsar
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
GANDHWANI | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert for Community | Culvert | 1722006031/AV/22012034667631 — CONSTRUCTION OF PIPE PULIYA NIRMAN KARYA AT BHANDARIYAPURA NALE PAR GHURSAL | Ongoing | 211000 | 0 | 2026-02-01
GANDHWANI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1722006031/DP/22012034444863 — सार्वजनीक कुप रातीतलाई बापु के खेत पास | Ongoing | 235000 | 0 | 2019-03-10
GANDHWANI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1722006031/DP/22012034588676 — Plantation Work Meri Mati Mera Desh Shantidham ke pas Ghurasal | Ongoing | 55847.4 | 0 | 2023-08-21
GANDHWANI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722006031/IF/22012035048143 — कपिलधारा कुप निर्माण गुलसिंह तेरसिंह घुरसल | Ongoing | 230000.24 | 0 | 2023-06-12
GANDHWANI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1722006031/IF/22012035482275 — JGSA 2025 Recharge Structure Kapildhara Kup Munsingh Bhursingh Dhulsar | Ongoing | 25899.46 | 0 | 2025-05-22
GANDHWANI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1722006031/IF/22012035482319 — JGSA 2025 Recharge Structure Kapildhara Kup Nursingh Fulsingh Dhanora | Approved | 0 | 0 | 2025-05-01
GANDHWANI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1722006031/IF/22012035482343 — JGSA 2025 Recharge Structure Kapildhara Kup Kalu Gonda Dhulsar | Approved | 25899.46 | 0 | 2025-05-01
GANDHWANI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006031/IF/IAY/205885 — Construction of IAY House -IAY REG. NO. MP-22-006-031-001/114 | Approved | 27000 | 0 | 2021-02-15
GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006031/IF/IAY/4538361 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103430442 | Approved | 27000 | 0 | 2024-09-13
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006031/IF/IAY/4538610 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102453894 | Ongoing | 27000 | 6300 | 2026-03-25
GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006031/IF/IAY/4861471 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103429746 | Completed | 23490 | 0 | 2025-01-28 | 2026-07-21
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006031/IF/IAY/5149158 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103095689 | Ongoing | 27000 | 6300 | 2025-08-09
GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006031/IF/IAY/5165697 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103095254 | Approved | 27000 | 0 | 2025-02-21
GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006031/IF/IAY/5175878 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103740103 | Physically Completed | 27000 | 0 | 2025-02-21 | 2026-08-30
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006031/IF/IAY/5186996 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102436539 | Ongoing | 27000 | 0 | 2025-08-09
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006031/IF/IAY/5198546 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120380429 | Ongoing | 27000 | 0 | 2025-05-25
GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006031/IF/IAY/5204932 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106302741 | Approved | 27000 | 0 | 2025-02-21
GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006031/IF/IAY/5225840 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102448538 | Approved | 27000 | 0 | 2025-02-21
GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006031/IF/IAY/5243963 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100942279 | Approved | 27000 | 0 | 2025-02-21
GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006031/IF/IAY/5363980 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100946544 | Approved | 27000 | 0 | 2025-03-29
GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006031/IF/IAY/5369550 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102910664 | Approved | 27000 | 0 | 2025-03-29
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006031/IF/IAY/5383186 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100673644 | Ongoing | 27000 | 0 | 2025-07-18
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006031/IF/IAY/5438939 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103095343 | Ongoing | 27000 | 0 | 2026-03-25
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006031/IF/IAY/5497831 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102443957 | Ongoing | 27000 | 0 | 2025-08-09
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006031/IF/IAY/5633977 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100719055 | Completed | 23490 | 0 | 2025-08-09 | 2026-07-21
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006031/IF/IAY/5636552 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105014756 | Ongoing | 27000 | 0 | 2026-03-25
GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006031/IF/IAY/5694226 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102444022 | Approved | 27000 | 0 | 2025-02-21
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006031/IF/IAY/5695934 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102914181 | Ongoing | 27000 | 4200 | 2026-02-01
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006031/IF/IAY/5696749 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103734330 | Ongoing | 27000 | 6300 | 2026-03-25
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006031/IF/IAY/5696841 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104903917 | Ongoing | 27000 | 4200 | 2026-02-01
GANDHWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006031/IF/IAY/6124163 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100968883 | Ongoing | 27000 | 10500 | 2026-05-27
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006031/IF/IAY/6126581 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103733453 | Approved | 27000 | 0 | 2026-02-27
GANDHWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006031/IF/IAY/6126900 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102444218 | Ongoing | 27000 | 6300 | 2026-05-27
GANDHWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006031/IF/IAY/6128962 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103700599 | Ongoing | 27000 | 8400 | 2026-08-04
GANDHWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006031/IF/IAY/6128964 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103701410 | Ongoing | 27000 | 6300 | 2026-05-27
GANDHWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006031/IF/IAY/6128972 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103738051 | Ongoing | 27000 | 6300 | 2026-05-27
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006031/IF/IAY/6129024 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102909822 | Approved | 27000 | 0 | 2026-02-27
GANDHWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006031/IF/IAY/6129034 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102914667 | Ongoing | 27000 | 6300 | 2026-07-28
GANDHWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006031/IF/IAY/6129044 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102928530 | Ongoing | 27000 | 6300 | 2026-07-28
GANDHWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006031/IF/IAY/6129161 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103740878 | Ongoing | 27000 | 8400 | 2026-05-27
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006031/IF/IAY/6130384 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104901955 | Approved | 27000 | 0 | 2026-02-27
GANDHWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006031/IF/IAY/6137224 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102204211 | Ongoing | 27000 | 6300 | 2026-08-04
GANDHWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006031/IF/IAY/6137225 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103701820 | Ongoing | 27000 | 6300 | 2026-05-27
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006031/IF/IAY/6137268 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106245882 | Approved | 27000 | 0 | 2026-02-27
GANDHWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006031/IF/IAY/6141251 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102457611 | Ongoing | 27000 | 8400 | 2026-05-27
GANDHWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006031/IF/IAY/6141988 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103095602 | Ongoing | 27000 | 6300 | 2026-05-27
GANDHWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006031/IF/IAY/6145811 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102301549 | Ongoing | 27000 | 6300 | 2026-05-27
GANDHWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006031/IF/IAY/6153008 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102909903 | Ongoing | 27000 | 4200 | 2026-05-27
GANDHWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006031/IF/IAY/6157473 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102447343 | Ongoing | 27000 | 4200 | 2026-05-27
GANDHWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006031/IF/IAY/6159997 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102223518 | Ongoing | 27000 | 6300 | 2026-05-27
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006031/IF/IAY/6163386 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106268306 | Approved | 27000 | 0 | 2026-03-26
GANDHWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006031/IF/IAY/6164520 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102220597 | Ongoing | 27000 | 4200 | 2026-05-27
GANDHWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006031/IF/IAY/6164700 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102303632 | Ongoing | 27000 | 6300 | 2026-05-27
GANDHWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006031/IF/IAY/6164701 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102219639 | Ongoing | 27000 | 7500 | 2026-05-27
GANDHWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006031/IF/IAY/6164703 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100964871 | Ongoing | 27000 | 8400 | 2026-05-27
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006031/IF/IAY/6164722 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104934028 | Approved | 27000 | 0 | 2026-03-12
GANDHWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006031/IF/IAY/6170176 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100848483 | Ongoing | 27000 | 6300 | 2026-05-27
GANDHWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006031/IF/IAY/6170558 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104904313 | Ongoing | 27000 | 0 | 2026-05-27
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006031/IF/IAY/6170849 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106243152 | Approved | 27000 | 0 | 2026-02-27
GANDHWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006031/IF/IAY/6172831 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103737096 | Ongoing | 27000 | 4200 | 2026-05-27
GANDHWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006031/IF/IAY/6172883 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103734837 | Ongoing | 27000 | 8400 | 2026-05-27
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006031/IF/IAY/6175240 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104928141 | Approved | 27000 | 0 | 2026-02-27
GANDHWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006031/IF/IAY/6175631 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100682848 | Ongoing | 27000 | 6300 | 2026-05-27
GANDHWANI | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722006031/RC/22012034842792 — CONSTRACTION OF C.C. ROAD AT VIDHYUT GIRIT SE HARIJAN BASTI TARAF DHURSAL | Ongoing | 46000 | 0 | 2026-03-07
GANDHWANI | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722006031/RC/22012034843453 — CC ROAD SADAN KE GHAR SE BADRI KE GHAR TAK BHANDAROYAPURA DHURSAL | Approved | 93000 | 0 | 2025-04-14
GANDHWANI | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1722006031/RS/22012034575530 — SBM ISP Shoakpit Gursal Grup 01 | Physically Completed | 44999.82 | 0 | 2023-01-18 | 2026-08-11
GANDHWANI | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1722006031/RS/22012034575538 — SBM ISP Shoakpit Gursal Grup 03 | Physically Completed | 44999.82 | 0 | 2023-02-04 | 2026-08-11
GANDHWANI | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1722006031/RS/22012034575540 — SBM ISP Shoakpit Gursal Grup 04 | Physically Completed | 44999.82 | 0 | 2023-01-21 | 2026-08-11
GANDHWANI | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1722006031/RS/22012034575544 — SBM ISP Shoakpit Gursal Grup 05 | Physically Completed | 44999.82 | 0 | 2023-01-21 | 2026-08-11
GANDHWANI | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1722006031/WC/22012034442391 — निस्‍तार तालाब शेरू के खेत पास जीराबाद | Physically Completed | 1032000 | 0 | 2019-02-28 | 2026-08-11
GANDHWANI | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1722006031/WC/22012034644642 — CTRA Banjar Pahadi Hadwada Baydi Ghursal | Ongoing | 131575.59 | 0 | 2021-04-18
GANDHWANI | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone boulder Gully Plugs for Community | Boulder Check/Gully Plug | 1722006031/WC/22012034652111 — CTRA Gully Plug Nadipar Ratitalai wala Nalla Ghursal | Ongoing | 130037.64 | 0 | 2021-04-16
GANDHWANI | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone boulder Gully Plugs for Community | Boulder Check/Gully Plug | 1722006031/WC/22012034652120 — CTRA Gully Plug Ratitalai Khadan wala Nalla Ghursal | Ongoing | 130037.64 | 0 | 2021-04-18
GANDHWANI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1722006031/WC/22012035166084 — तलाई निर्माण कार्य धुरसल | New | 0 | 0 | 2024-04-12
GANDHWANI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722006031/WC/22012035238040 — NISTAR TALAB BHATA WALE NALE PAR DHURSAL | New | 0 | 0 | 2024-12-25
GANDHWANI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722006031/WC/22012035308521 — SARVJANIK KUP NIRMAN KARYA HARSINGH KE GHAR PASS PATELPURA DHURSAL | Approved | 0 | 0 | 2025-04-14
GANDHWANI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722006031/WC/22012035308524 — SARVJANIK KUP NIRMAN KARYA BHUPENDRA BAPU KE GHAR PASS RATITALAI DHURSAL | Approved | 0 | 0 | 2025-04-14