## Work List
Exported on: 2026-10-28 19:55:39
Filters applied:
Data source: VBGRAMG
District: DHAR
Block: All
Panchayat: Satumari
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
GANDHWANI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1722006045/DP/22012034529636 — सार्वजनीक कुप डोडवापुरा सातउमरी | Ongoing | 445172.64 | 0 | 2022-12-01
GANDHWANI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1722006045/DP/22012034530370 — Sarvajanik koop nirman Amba k pass | Ongoing | 549475.12 | 600 | 2022-04-22
GANDHWANI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722006045/IF/22012034558892 — कपिलधारा कुप गुलाब भुरला सातउमरी | Ongoing | 230002.14 | 0 | 2020-07-25
GANDHWANI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722006045/IF/22012034804966 — कपिलधारा कुप बाटिया जसला सातउमरी | Ongoing | 246218.67 | 0 | 2022-01-31
GANDHWANI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722006045/IF/22012035091037 — कपिलधारा कुप मोहन दगडिया सातउमरी | Ongoing | 232656.75 | 0 | 2023-10-06
GANDHWANI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722006045/IF/22012035093804 — कपिलधारा कुप सोहन दगडिया सातउमरी | Ongoing | 232656.75 | 0 | 2023-10-06
GANDHWANI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722006045/IF/22012035093811 — कपिलधारा कुप बल्‍लु बान्‍दर सातउमरी | Ongoing | 232656.75 | 0 | 2023-10-06
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722006045/IF/22012035595080 — Ek Bagiya Maa Ke Name Suman Bai Ajnare MP22006045002 136 | Ongoing | 282737.53 | 0 | 2025-09-04
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722006045/IF/22012035595125 — Ek Bagiya Maa Ke Name karam bai MP22006045002 156B | Ongoing | 284205.25 | 29400 | 2025-09-04
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722006045/IF/22012035595140 — Ek Bagiya Maa Ke Name Manakabai MP22006045002 85B | Ongoing | 285739.31 | 42000 | 2025-09-04
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722006045/IF/22012035601239 — Ek Bagiya Maa ke Naam Kelabai Ajnare MP 22006045002 135 | Ongoing | 283844.72 | 0 | 2025-09-04
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722006045/IF/22012035604408 — Ek Bagiya Maa Ke Naam Bhangdi Bai MP22006045002 146 | Ongoing | 283844.72 | 48300 | 2025-09-23
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722006045/IF/22012035609934 — Ek Bagiya Maa Ke Naam Radha Bai MP22006045002 83 | Approved | 283844.72 | 0 | 2025-08-15
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006045/IF/IAY/4626321 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127515060 | Completed | 23490 | 0 | 2025-09-08 | 2026-07-24
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006045/IF/IAY/4714152 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127468683 | Physically Completed | 27000 | 0 | 2025-04-03 | 2026-10-17
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006045/IF/IAY/4764173 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121545683 | Completed | 23490 | 0 | 2025-12-16 | 2026-07-24
GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006045/IF/IAY/4882476 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102993758 | Completed | 23490 | 0 | 2025-01-29 | 2026-07-31
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006045/IF/IAY/5636142 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127386628 | Physically Completed | 27000 | 0 | 2025-07-28 | 2026-10-18
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006045/IF/IAY/5695747 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128933542 | Completed | 23490 | 0 | 2025-08-10 | 2026-07-24
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006045/IF/IAY/5696285 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104899345 | Physically Completed | 27000 | 0 | 2025-08-10 | 2026-09-13
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006045/IF/IAY/5843688 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130656635 | Physically Completed | 27000 | 0 | 2025-11-10 | 2026-10-17
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006045/IF/IAY/6125699 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120566712 | Approved | 27000 | 0 | 2026-03-11
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006045/IF/IAY/6126887 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127300063 | Approved | 27000 | 0 | 2026-03-09
GANDHWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006045/IF/IAY/6127442 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126615941 | Completed | 27000 | 27000 | 2026-07-14 | 2026-10-17
GANDHWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006045/IF/IAY/6132129 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127359014 | Completed | 27000 | 27000 | 2026-07-14 | 2026-10-17
GANDHWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006045/IF/IAY/6132397 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127518957 | Completed | 27000 | 27000 | 2026-07-14 | 2026-10-17
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006045/IF/IAY/6132610 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127541686 | Approved | 27000 | 0 | 2026-03-09
GANDHWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006045/IF/IAY/6134374 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127535472 | Completed | 27000 | 27000 | 2026-07-14 | 2026-10-17
GANDHWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006045/IF/IAY/6147846 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127499702 | Completed | 27000 | 27000 | 2026-07-14 | 2026-10-17
GANDHWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006045/IF/IAY/6151712 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127412615 | Completed | 27000 | 27000 | 2026-07-14 | 2026-09-23
GANDHWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006045/IF/IAY/6155521 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127588225 | Ongoing | 27000 | 0 | 2026-10-15
GANDHWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006045/IF/IAY/6156840 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127239279 | Completed | 27000 | 27000 | 2026-07-14 | 2026-10-17
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006045/IF/IAY/6157487 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120790460 | Approved | 27000 | 0 | 2026-03-16
GANDHWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006045/IF/IAY/6161356 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127650655 | Completed | 27000 | 27000 | 2026-07-14 | 2026-09-23
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006045/IF/IAY/6164699 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127501904 | Approved | 27000 | 0 | 2026-03-09
GANDHWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006045/IF/IAY/6175489 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127482637 | Ongoing | 27000 | 8400 | 2026-10-07
GANDHWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006045/IF/IAY/6345926 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127673033 | Ongoing | 27000 | 0 | 2026-10-15
GANDHWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006045/IF/IAY/6393206 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121544719 | Approved | 27000 | 0 | 2026-08-07
GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006045/IF/IAY/6404569 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120563599 | Approved | 27000 | 0 | 2025-02-20
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006045/IF/IAY/6408000 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120572985 | Approved | 27000 | 0 | 2026-03-11
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006045/IF/IAY/6412283 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127500484 | Approved | 27000 | 0 | 2026-03-09
GANDHWANI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1722006045/WC/22012035162574 — Construction of Nistar Talai Nirman Satumri Nala Satumri | New | 0 | 0 | 2024-02-01
GANDHWANI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722006045/WC/22012035251184 — Talai Nirman karya Sindhi Wale Nale Per Satumari | Approved | 382520.16 | 0 | 2024-10-02
GANDHWANI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722006045/WC/22012035316624 — Construction of sarwajanik kup nirman Bhurighati satumri | Approved | 0 | 0 | 2025-04-01