## Work List
Exported on: 2026-09-09 05:55:00
Filters applied:
Data source: MGNREGA + VBGRAMG
District: DHAR
Block: All
Panchayat: GARWAL
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
GANDHWANI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1722006068/DP/22012034573105 — Sarvajnik Kup Niraman Nadipura Garwal | Closed | 0 | 0 | 2022-10-02
GANDHWANI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1722006068/DP/22012034573106 — Sarvajnik Kup Niraman Neem Ka pas Garawal | Closed | 0 | 0 | 2022-10-02
GANDHWANI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1722006068/DP/22012034573107 — Sarvajnik Kup Niraman Nadi Ka pas Garawal | Closed | 0 | 0 | 2022-10-02
GANDHWANI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1722006068/DP/22012034573109 — Sarvajnik Kup Niraman Dhatalaw Garawal | Closed | 0 | 0 | 2022-10-02
GANDHWANI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1722006068/DP/22012034588685 — Plantation Work Meri Mati Mera Desh P.S Nadipura Garwal | Completed | 55847.4 | 45071.38 | 2023-09-07 | 2024-11-06
GANDHWANI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722006068/IF/22012035077532 — कपिलधारा कुप धनसिंह कुवरसिंह धनतलाव गरवाल | Closed | 232213.65 | 0 | 2023-04-12
GANDHWANI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722006068/IF/22012035077534 — कपिलधारा कुप रूगनाथ धनसिंह गरवाल | Completed | 232213.65 | 130534.36 | 2023-06-02 | 2025-04-22
GANDHWANI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722006068/IF/22012035077535 — कपिलधारा कुप अन्‍तरसिंह भंगडा गरवाल | Completed | 232213.65 | 151664.16 | 2023-06-02 | 2025-02-07
GANDHWANI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722006068/IF/22012035077541 — कपिलधारा कुप बल्‍लु थानसिंह गरवाल | Completed | 232213.65 | 125266.16 | 2023-06-18 | 2025-04-22
GANDHWANI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722006068/IF/22012035077543 — कपिलधारा कुप प्रताप खुमसिंह गरवाल | Completed | 232213.65 | 134714.71 | 2023-11-26 | 2025-04-21
GANDHWANI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722006068/IF/22012035123269 — Kapildhara Kup Narsingh Aliya Garwal | Closed | 0 | 0 | 2023-04-14
GANDHWANI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Mini Percolation Tank for Individuals / Construction of Mini Percolation Tank for Individuals | Construction of Percolation Tank | 1722006068/IF/22012035308263 — Construction of Kapildhara Kup Narsingh Aaliya Garwal | Deleted | 0 | 0 | 2025-01-26
GANDHWANI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Mini Percolation Tank for Individuals / Construction of Mini Percolation Tank for Individuals | Construction of Percolation Tank | 1722006068/IF/22012035348394 — Construction of Kapildhara Kup Narsingh Aaliya Garwal | Ongoing | 199775.53 | 154276.74 | 2025-05-31
GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006068/IF/IAY/4705249 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122372131 | Completed | 23490 | 21879 | 2025-01-10 | 2025-04-23
GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006068/IF/IAY/4706999 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123178216 | Completed | 23490 | 21879 | 2025-01-10 | 2025-04-23
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006068/IF/IAY/4707391 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124432780 | Ongoing | 27000 | 12528 | 2025-07-28
GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006068/IF/IAY/4707399 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124435707 | Completed | 23490 | 21879 | 2025-01-10 | 2025-04-23
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006068/IF/IAY/4707400 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124436632 | Completed | 23490 | 23490 | 2025-07-28 | 2026-02-11
GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006068/IF/IAY/4712228 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126175689 | Completed | 23490 | 21879 | 2025-01-10 | 2026-02-11
GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006068/IF/IAY/4713071 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126611251 | Completed | 23490 | 21879 | 2025-01-10 | 2025-04-23
GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006068/IF/IAY/4713180 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126645096 | Completed | 23490 | 21879 | 2025-01-10 | 2025-04-23
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006068/IF/IAY/4713659 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127234061 | Ongoing | 27000 | 10701 | 2025-07-28
GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006068/IF/IAY/4714074 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127420040 | Completed | 23490 | 21879 | 2025-01-10 | 2026-07-24
GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006068/IF/IAY/4716285 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127697745 | Completed | 23490 | 21717 | 2025-01-10 | 2026-02-11
GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006068/IF/IAY/4774975 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125832167 | Completed | 23490 | 21879 | 2025-01-10 | 2025-04-23
GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006068/IF/IAY/4782993 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126162690 | Completed | 23490 | 21879 | 2025-01-10 | 2025-04-23
GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006068/IF/IAY/4785529 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130335680 | Completed | 23490 | 22230 | 2025-01-10 | 2026-02-11
GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006068/IF/IAY/4791823 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126609313 | Completed | 23490 | 21879 | 2025-01-10 | 2025-04-23
GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006068/IF/IAY/4791844 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126612975 | Completed | 23490 | 21879 | 2025-01-10 | 2025-04-23
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006068/IF/IAY/5822098 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123431595 | Completed | 23490 | 23490 | 2025-09-29 | 2026-02-11
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006068/IF/IAY/5822247 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128949436 | Physically Completed | 23490 | 12267 | 2025-09-29 | 2026-01-25
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006068/IF/IAY/5822634 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123168812 | Completed | 23490 | 23490 | 2025-09-29 | 2026-02-11
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006068/IF/IAY/5824324 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123035139 | Completed | 23490 | 23490 | 2025-09-29 | 2026-02-11
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006068/IF/IAY/5824429 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123040021 | Physically Completed | 27000 | 0 | 2025-11-10 | 2026-09-06
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006068/IF/IAY/5824430 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123043148 | Completed | 23490 | 23490 | 2025-09-29 | 2026-02-11
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006068/IF/IAY/5824933 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122373292 | Ongoing | 27000 | 0 | 2025-11-10
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006068/IF/IAY/5825087 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123447428 | Completed | 23490 | 23490 | 2025-09-29 | 2026-02-11
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006068/IF/IAY/5825361 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122388077 | Completed | 23490 | 23490 | 2025-09-29 | 2026-02-11
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006068/IF/IAY/5825593 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127420781 | Physically Completed | 23490 | 5481 | 2026-01-06 | 2026-02-03
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006068/IF/IAY/5825605 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127695669 | Completed | 23490 | 23490 | 2025-11-10 | 2026-02-11
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006068/IF/IAY/5825769 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130335359 | Completed | 23490 | 23490 | 2025-09-29 | 2026-02-11
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006068/IF/IAY/5825907 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127678982 | Completed | 23490 | 23490 | 2025-09-29 | 2026-02-11
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006068/IF/IAY/5825975 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126604035 | Ongoing | 27000 | 0 | 2025-11-10
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006068/IF/IAY/5826105 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122379780 | Completed | 23490 | 23490 | 2025-09-29 | 2026-02-11
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006068/IF/IAY/5826111 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122414591 | Completed | 23490 | 23490 | 2025-11-10 | 2026-08-25
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006068/IF/IAY/5826190 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127462724 | Completed | 23490 | 12006 | 2025-11-10 | 2026-02-11
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006068/IF/IAY/5826483 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122381296 | Completed | 23490 | 23229 | 2025-11-10 | 2026-07-24
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006068/IF/IAY/5826549 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122361997 | Completed | 23490 | 23490 | 2025-09-29 | 2026-02-11
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006068/IF/IAY/5826829 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122414717 | Completed | 23490 | 23490 | 2025-09-29 | 2026-02-11
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006068/IF/IAY/5827035 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126168190 | Completed | 23490 | 23490 | 2025-09-29 | 2026-02-11
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006068/IF/IAY/5827062 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123034536 | Completed | 23490 | 23490 | 2025-09-29 | 2026-02-11
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006068/IF/IAY/5827089 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126161599 | Completed | 23490 | 23490 | 2025-09-29 | 2026-02-11
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006068/IF/IAY/5828180 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123892394 | Completed | 23490 | 23490 | 2025-09-29 | 2026-02-11
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006068/IF/IAY/5843694 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128945318 | Completed | 23490 | 23490 | 2025-11-10 | 2026-08-25
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006068/IF/IAY/5843851 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126614569 | Completed | 23490 | 23490 | 2025-11-10 | 2026-08-25
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006068/IF/IAY/5844054 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122430741 | Completed | 23490 | 23490 | 2025-11-10 | 2026-08-25
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006068/IF/IAY/5845111 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130334931 | Completed | 23490 | 23490 | 2025-11-10 | 2026-08-25
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006068/IF/IAY/5845294 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127216456 | Ongoing | 27000 | 18270 | 2025-11-10
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006068/IF/IAY/5845433 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126645989 | Ongoing | 27000 | 10962 | 2026-03-13
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006068/IF/IAY/5845515 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128997940 | Completed | 23490 | 23490 | 2025-11-10 | 2026-08-25
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006068/IF/IAY/5845715 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128948620 | Completed | 23490 | 23490 | 2025-11-10 | 2026-02-11
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006068/IF/IAY/5845811 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128943371 | Completed | 23490 | 21924 | 2025-11-10 | 2026-02-11
GANDHWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006068/IF/IAY/6129664 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129227309 | Ongoing | 27000 | 10200 | 2026-03-09
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006068/IF/IAY/6131983 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130335035 | Approved | 27000 | 0 | 2026-03-09
GANDHWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006068/IF/IAY/6133011 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127678136 | Ongoing | 27000 | 0 | 2026-03-11
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006068/IF/IAY/6140665 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122414457 | Approved | 27000 | 0 | 2026-03-09
GANDHWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006068/IF/IAY/6140741 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129305863 | Ongoing | 27000 | 8400 | 2026-03-09
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006068/IF/IAY/6149598 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128997313 | Approved | 27000 | 0 | 2026-03-09
GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006068/IF/IAY/6158941 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122380807 | Approved | 27000 | 0 | 2026-03-09
GANDHWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006068/IF/IAY/6160498 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127698948 | Ongoing | 27000 | 8400 | 2026-03-11
GANDHWANI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Fallow Land for Community / Development of Fallow Land for Community | Land Development | 1722006068/LD/22012034943914 — Construction of Plantation Work Panchayat Bhawan Garwal | Physically Completed | 316371.98 | 251026.3 | 2024-10-09 | 2026-05-22
GANDHWANI | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722006068/RC/22012034832139 — Construction of CC Road Nirman Ramesh ke Ghar se Sardar ke Ghar tak Nadipura Garwal | Approved | 56000 | 0 | 2024-10-15
GANDHWANI | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1722006068/RS/22012034688708 — ISP Shok Pit Grup 1 No 50 Nadipura Garwal | Closed | 0 | 0 | 2023-01-26
GANDHWANI | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1722006068/RS/22012034688710 — ISP Shok Pit Grup 2 No 50 Patelpura Garwal | Closed | 0 | 0 | 2023-01-26
GANDHWANI | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1722006068/RS/22012034688711 — ISP Shok Pit Grup 3 No 50 Haranchapda Garwal | Closed | 0 | 0 | 2023-01-26
GANDHWANI | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1722006068/RS/22012034688712 — ISP Shok Pit Grup 4 No 50 Sadkapura Garwal | Closed | 0 | 0 | 2023-01-26
GANDHWANI | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1722006068/RS/22012034688713 — ISP Shok Pit Grup 5 No 50 Patelpura Dhantalaw Garwal | Closed | 0 | 0 | 2023-01-26
GANDHWANI | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1722006068/RS/22012034688714 — ISP Shok Pit Grup 6 No 50 Nigwalpura Dhantalaw Garwal | Closed | 0 | 0 | 2023-01-26
GANDHWANI | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1722006068/RS/22012034688715 — ISP Shok Pit Grup7 No 50 Bhilapura Dhantalaw Garwal | Closed | 0 | 0 | 2023-01-26
GANDHWANI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1722006068/RS/22012034699726 — ISP Shok Pith Nadipura and Patelpura No 100 Garawal | Closed | 0 | 0 | 2023-04-14
GANDHWANI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1722006068/RS/22012034699727 — ISP Shok Pith Haranchapda and Sadakpura No 100 Garawal | Closed | 0 | 0 | 2023-04-14
GANDHWANI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1722006068/RS/22012034699728 — ISP Shok Pith Nigawalpura and Bhilalapura No 100 Garawal | Closed | 0 | 0 | 2023-04-14
GANDHWANI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1722006068/RS/22012034699729 — ISP Shok Pith Dhantalaw and Patelpura No 100 Garawal | Closed | 0 | 0 | 2023-04-14
GANDHWANI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1722006068/WC/22012035029971 — Constr Of Nala Trenching Selkhodri Nala Dhantalaw Garawal | Closed | 0 | 0 | 2022-10-02
GANDHWANI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1722006068/WC/22012035029974 — Constr Of Nala Trenching Shindhi wala Nala Dhantalaw Garawal | Closed | 0 | 0 | 2022-10-02
GANDHWANI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1722006068/WC/22012035029975 — Constr Of Nala Trenching Muhada wala Nala Garawal | Closed | 0 | 0 | 2022-10-02
GANDHWANI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1722006068/WC/22012035029976 — Constr Of Nala Trenching Stapdam wala Nala Garawal | Completed | 520000.24 | 421972 | 2023-06-22 | 2024-08-08
GANDHWANI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1722006068/WC/22012035077241 — निस्‍तार तालाब हरणचापडा नाला गरवाल | Physically Completed | 909513.23 | 844608.06 | 2023-10-09 | 2026-04-24
GANDHWANI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1722006068/WC/22012035077246 — निस्‍तार तालाब बिल्‍ली वाला नाला धनतलाव गरवाल | Closed | 0 | 0 | 2023-04-14
GANDHWANI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1722006068/WC/22012035102816 — GEBIN STRECCHAR Muhwa WALA NALA GARWAL | Closed | 0 | 0 | 2023-08-29
GANDHWANI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1722006068/WC/22012035102817 — GEBIN STRECCHAR NEEM WALA NALA GARWAL | Closed | 0 | 0 | 2023-08-29
GANDHWANI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1722006068/WC/22012035102818 — GEBIN STRECCHAR BABUL WALA NALA GARWAL | Closed | 0 | 0 | 2023-08-29
GANDHWANI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1722006068/WC/22012035102821 — GEBIN STRECCHAR BEHDA WALA NALA DHANTALAV GARWAL | Closed | 0 | 0 | 2023-08-29
GANDHWANI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1722006068/WC/22012035102824 — GEBIN STRECCHAR AAM WALA NALA DHANTALAV GARWAL | Closed | 0 | 0 | 2023-08-29
GANDHWANI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1722006068/WC/22012035120716 — Constuction Of Gabion Structure At Babul Wala Nala Garwal | Completed | 380055.55 | 319090.3 | 2023-10-04 | 2024-11-06
GANDHWANI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1722006068/WC/22012035154685 — Construction of Nala Trechin Work Behda wala Nala Garwal | Completed | 429703.74 | 364024 | 2024-02-13 | 2024-07-04
GANDHWANI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1722006068/WC/22012035154687 — Construction of Nala Trechin Work Babul wala Nala Garwal | Closed | 0 | 0 | 2023-06-15
GANDHWANI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1722006068/WC/22012035154689 — Construction of Gaibion Work Sindhi wala nala Garwal | Closed | 0 | 0 | 2023-06-15
GANDHWANI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1722006068/WC/22012035154691 — Construction of Gaibion Work Gorad wala nala Garwal | Closed | 0 | 0 | 2023-06-15
GANDHWANI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1722006068/WC/22012035165732 — निस्तार तालाब निर्माण कार्य हरनचापड़ा वाला नाला गरवाल | New | 0 | 0 | 2024-10-04
GANDHWANI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1722006068/WC/22012035222380 — CTRA Nala Trenching Bad Wala Nala Garwal | Completed | 399041.55 | 334368 | 2024-10-16 | 2025-05-19
GANDHWANI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1722006068/WC/22012035237321 — Construction of Talai Nirman Beda wale Nale Par Garwal | Completed | 349108.82 | 330505.2 | 2025-05-20 | 2026-04-24
GANDHWANI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722006068/WC/22012035254022 — Construction of Sarwajanik Kup Nirman Nadipura Garwal | Deleted | 0 | 0 | 2025-01-26
GANDHWANI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722006068/WC/22012035265096 — Construction of Sarwajanik Kup Nirman Nadipura Garwal | Ongoing | 450731.39 | 306392.71 | 2025-05-29