## Work List
Exported on: 2026-09-03 06:37:44
Filters applied:
Data source: VBGRAMG
District: DHAR
Block: All
Panchayat: Tarsinga
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BAGH | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1722007004/DP/22012034576131 — निर्मल नीर कूप निर्माण मालपुरा पिपरानी | Ongoing | 519558.1 | 0 | 2023-06-24
BAGH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722007004/IF/22012034821712 — कपिल धारा कूप निर्माण कैला मगत्या पिपरानी | Ongoing | 200000 | 0 | 2021-12-01
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722007004/IF/22012035461625 — JGSA Khet talab Ramesh Limsingh Tarsingha | Physically Completed | 147621.16 | 0 | 2025-05-14 | 2026-07-29
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722007004/IF/22012035461684 — JGSA Khet talab Dolriya Naharsingh Piprani | Physically Completed | 147621.16 | 0 | 2025-05-10 | 2026-07-04
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722007004/IF/22012035461707 — JGSA Khet talab Sahkam Mithu Piprani | Ongoing | 147621.16 | 0 | 2025-05-10
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722007004/IF/22012035464710 — JGSA Khet talab Thakariya Bhisan Pirani | Physically Completed | 147621.16 | 0 | 2025-05-10 | 2026-07-04
BAGH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1722007004/IF/22012035478513 — JGSA Dugwell Recharge Kamalibai samersingh Piprani | Ongoing | 25899.46 | 0 | 2025-05-27
BAGH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1722007004/IF/22012035478529 — JGSA Dugwell Recharge Kamali Juwansingh Piprani | Ongoing | 25899.46 | 0 | 2025-05-27
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722007004/IF/IAY/4698290 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118784980 | Completed | 23490 | 0 | 2025-10-29 | 2026-07-29
BAGH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722007004/IF/IAY/4699213 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119817717 | Ongoing | 27000 | 0 | 2025-01-20
BAGH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722007004/IF/IAY/4704763 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121510009 | Approved | 27000 | 0 | 2024-09-20
BAGH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722007004/IF/IAY/4704764 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121510026 | Approved | 27000 | 0 | 2024-09-20
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722007004/IF/IAY/4705179 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123159611 | Ongoing | 27000 | 0 | 2025-04-12
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722007004/IF/IAY/4705180 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123160118 | Physically Completed | 23490 | 3000 | 2025-04-04 | 2026-08-12
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722007004/IF/IAY/5120051 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118784949 | Physically Completed | 23490 | 0 | 2025-06-28 | 2026-08-12
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722007004/IF/IAY/5132244 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119817643 | Completed | 23490 | 0 | 2025-06-09 | 2026-07-29
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722007004/IF/IAY/5173509 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123157315 | Completed | 23490 | 0 | 2025-10-29 | 2026-07-29
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722007004/IF/IAY/5235527 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130951876 | Ongoing | 27000 | 4800 | 2025-10-29
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722007004/IF/IAY/5239250 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126420539 | Physically Completed | 23490 | 0 | 2025-06-28 | 2026-08-22
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722007004/IF/IAY/5277549 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126375648 | Ongoing | 27000 | 0 | 2025-06-28
BAGH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722007004/IF/IAY/5657701 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121510533 | Completed | 23490 | 0 | 2026-06-01 | 2026-08-03
BAGH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1722007004/WC/22012034635782 — CTRA BHUSANKAN Pond kalam ke passpiparani | Ongoing | 297423.36 | 0 | 2021-09-25
BAGH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722007004/WC/22012035230312 — Nistar Talab Chillar wala nala piprani | Ongoing | 1466828.32 | 0 | 2025-04-22
BAGH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722007004/WC/22012035234794 — Nistar Talab Varli wala nala Tarsingha | Ongoing | 2162049.63 | 18900 | 2025-08-12
BAGH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1722007004/WC/22012035298747 — JGSA Dugwell Recharge Malpura Tarsinga | Ongoing | 25899.46 | 0 | 2025-05-27
BAGH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1722007004/WC/22012035298750 — JGSA Dugwell Recharge Bhilalafaliya Tarsinga | Approved | 25899.46 | 0 | 2025-04-14