## Work List
Exported on: 2026-10-23 04:54:39
Filters applied:
Data source: VBGRAMG
District: DHAR
Block: All
Panchayat: Jamnyapura
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BAGH | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Centre Building for Community | Constr of Aganwadi | 1722007042/AV/22012034623496 — ऑगनवाडी भवन निर्माण कार्य रिसावला | Ongoing | 500000 | 0 | 2022-11-28
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722007042/IF/22012035572143 — Kapildhara kup Madhu Malsingh | New | 0 | 0 | 2025-04-14
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722007042/IF/22012035572148 — Kapildhara kup Thakursingh Bondarsingh | Approved | 0 | 0 | 2025-04-14
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/4552156 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113951022 | Ongoing | 27000 | 0 | 2026-02-18
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/4571430 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117632566 | Ongoing | 27000 | 0 | 2026-02-19
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/4571448 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117634452 | Completed | 23490 | 0 | 2025-11-05 | 2026-07-24
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/4585311 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119548679 | Ongoing | 27000 | 0 | 2026-02-19
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/4587179 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119900382 | Completed | 23490 | 0 | 2025-06-05 | 2026-07-27
BAGH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/4588258 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120900531 | Approved | 27000 | 0 | 2024-09-12
BAGH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/4588340 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120911351 | Approved | 27000 | 0 | 2024-09-16
BAGH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/4590851 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121504748 | Approved | 27000 | 0 | 2024-09-16
BAGH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/4595121 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122521321 | Approved | 27000 | 0 | 2024-09-19
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/4595313 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122339683 | Ongoing | 27000 | 10200 | 2025-11-12
BAGH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/4627310 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128061566 | Approved | 27000 | 0 | 2024-09-16
BAGH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/4627457 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128090589 | Physically Completed | 27000 | 0 | 2024-09-23 | 2026-10-12
BAGH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/4628534 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128103631 | Physically Completed | 27000 | 0 | 2024-09-21 | 2026-10-12
BAGH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/4673198 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118254041 | Approved | 27000 | 0 | 2024-09-18
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/4675351 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120902160 | Completed | 23490 | 0 | 2025-04-01 | 2026-07-27
BAGH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/4675352 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120905075 | Approved | 27000 | 0 | 2024-09-21
BAGH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/4704757 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121504270 | Completed | 23490 | 0 | 2025-02-02 | 2026-07-24
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/4758845 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119301969 | Ongoing | 27000 | 0 | 2026-02-19
BAGH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/4766222 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122773226 | Approved | 27000 | 0 | 2024-09-30
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/4766467 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115424506 | Completed | 23490 | 0 | 2025-05-26 | 2026-07-27
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/5246900 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120897734 | Ongoing | 27000 | 18000 | 2026-02-19
BAGH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/5260548 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117633413 | Ongoing | 27000 | 27000 | 2026-08-11
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/5263064 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118037941 | Ongoing | 27000 | 14400 | 2026-02-06
BAGH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/5269813 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113858068 | Approved | 27000 | 0 | 2025-02-23
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/5272525 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119548815 | Ongoing | 27000 | 4400 | 2025-06-30
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/5279909 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120902053 | Physically Completed | 27000 | 17400 | 2025-11-12 | 2026-10-18
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/5286388 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128057828 | Ongoing | 27000 | 0 | 2025-11-12
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/5290277 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122634861 | Ongoing | 27000 | 8400 | 2025-11-12
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/5300778 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121505950 | Ongoing | 27000 | 16200 | 2025-11-12
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/5304454 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117634845 | Physically Completed | 27000 | 12300 | 2025-11-12 | 2026-10-18
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/5319471 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114863746 | Completed | 23490 | 0 | 2025-06-30 | 2026-07-24
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/5330306 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117633745 | Physically Completed | 27000 | 7800 | 2025-11-06 | 2026-10-18
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/5331844 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122340646 | Ongoing | 27000 | 6300 | 2026-02-06
BAGH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/5343058 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120912221 | Approved | 27000 | 0 | 2025-02-25
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/5384654 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128056794 | Ongoing | 27000 | 0 | 2026-02-18
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/5385133 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119526013 | Ongoing | 27000 | 0 | 2026-02-18
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/5388601 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120278070 | Ongoing | 27000 | 12900 | 2025-11-12
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/5389762 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120944873 | Ongoing | 27000 | 11700 | 2025-11-12
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/5391786 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113950801 | Ongoing | 27000 | 0 | 2026-02-18
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/5391788 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113953997 | Completed | 23490 | 0 | 2025-11-15 | 2026-09-01
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/5402307 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122738247 | Ongoing | 27000 | 4800 | 2026-02-18
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/5407465 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117634375 | Completed | 23490 | 0 | 2025-05-22 | 2026-07-24
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/5409587 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128058917 | Ongoing | 27000 | 26700 | 2026-02-18
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/5482566 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128069373 | Completed | 23490 | 0 | 2025-05-26 | 2026-07-27
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/5484712 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113729994 | Completed | 23490 | 2400 | 2025-05-22 | 2026-07-24
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/5485957 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130361667 | Completed | 27000 | 0 | 2025-05-26 | 2026-09-01
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/5486317 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122295509 | Ongoing | 27000 | 13200 | 2026-02-06
BAGH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/5486403 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113954821 | Approved | 27000 | 0 | 2025-02-28
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/5575855 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115427621 | Ongoing | 27000 | 17400 | 2026-02-18
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/5620790 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120893163 | Physically Completed | 27000 | 6300 | 2025-11-12 | 2026-09-01
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/5698581 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115429234 | Physically Completed | 27000 | 17400 | 2026-02-18 | 2026-10-18
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/5699005 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117621071 | Ongoing | 27000 | 0 | 2026-02-18
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/5706383 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118728027 | Ongoing | 27000 | 12900 | 2026-02-19
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/5714376 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122636658 | Ongoing | 27000 | 26700 | 2026-02-19
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/5724496 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115427200 | Ongoing | 27000 | 0 | 2026-02-18
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/5729414 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119513160 | Ongoing | 27000 | 0 | 2026-02-18
BAGH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/5805362 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120890960 | Physically Completed | 27000 | 9300 | 2026-09-09 | 2026-09-20
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/5805377 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121505425 | Ongoing | 27000 | 0 | 2026-02-19
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/5816026 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125243588 | Completed | 23490 | 0 | 2025-11-16 | 2026-09-01
BAGH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/5816062 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121506105 | Ongoing | 27000 | 12900 | 2026-08-26
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/5816147 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115424802 | Approved | 27000 | 0 | 2025-05-15
BAGH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/5816234 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118727459 | Approved | 27000 | 0 | 2025-02-23
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/5816280 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118279271 | Ongoing | 27000 | 0 | 2025-11-16
BAGH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/5816321 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121730146 | Approved | 27000 | 0 | 2024-09-12
BAGH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/5816325 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121921437 | Approved | 27000 | 0 | 2025-02-27
BAGH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/5816360 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118470811 | Ongoing | 27000 | 4800 | 2026-10-03
BAGH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/5816375 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122635088 | Ongoing | 27000 | 13200 | 2026-09-02
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/5816492 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125069939 | Ongoing | 27000 | 0 | 2026-02-19
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/5816593 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114739071 | Ongoing | 27000 | 13200 | 2025-11-15
BAGH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/5816986 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113954735 | Approved | 27000 | 0 | 2025-03-17
BAGH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/5865575 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115427348 | Ongoing | 27000 | 15900 | 2026-08-26
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/5865595 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119289896 | Approved | 27000 | 0 | 2025-04-11
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/5865782 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114863791 | Ongoing | 27000 | 0 | 2026-02-18
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/5865965 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117275221 | Approved | 27000 | 0 | 2025-04-28
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/5866017 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119513941 | Approved | 27000 | 0 | 2025-04-28
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/5866107 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120542233 | Approved | 27000 | 0 | 2025-04-02
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/5866111 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119513359 | Ongoing | 27000 | 0 | 2026-02-18
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/5866138 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131995229 | Approved | 27000 | 0 | 2025-06-11
BAGH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/5981116 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120834382 | Physically Completed | 27000 | 19200 | 2026-06-18 | 2026-08-30
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/5981758 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121506049 | Physically Completed | 27000 | 0 | 2026-03-01 | 2026-09-20
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/5983283 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117634736 | Approved | 27000 | 0 | 2026-03-01
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/6124436 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120903002 | Approved | 27000 | 0 | 2026-03-07
BAGH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/6132812 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122635749 | Ongoing | 27000 | 12300 | 2026-09-07
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/6133113 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122519796 | Physically Completed | 23490 | 0 | 2026-03-13 | 2026-07-26
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/6139600 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115378649 | Approved | 27000 | 0 | 2026-03-07
BAGH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/6145217 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119548764 | Ongoing | 27000 | 12600 | 2026-09-06
BAGH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/6153370 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118738203 | Ongoing | 27000 | 6600 | 2026-09-26
BAGH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/6154799 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122634790 | Ongoing | 27000 | 19200 | 2026-09-12
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/6154800 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122634837 | Approved | 27000 | 0 | 2026-03-13
BAGH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/6165278 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117275163 | Ongoing | 27000 | 15600 | 2026-09-22
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/6301767 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128087342 | Approved | 27000 | 0 | 2025-06-14
BAGH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/6328213 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115379294 | Approved | 27000 | 0 | 2026-06-24
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/6328667 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117637309 | Approved | 27000 | 0 | 2026-03-26
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/6336551 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128058382 | Approved | 27000 | 0 | 2026-03-25
BAGH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/6336896 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115378745 | Approved | 27000 | 0 | 2026-06-01
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/6337346 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121504990 | Approved | 27000 | 0 | 2026-03-26
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/6364981 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128073826 | Approved | 27000 | 0 | 2026-03-01
BAGH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/6366378 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130361000 | Approved | 27000 | 0 | 2026-06-01
BAGH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/6388823 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121037493 | Approved | 27000 | 0 | 2026-08-18
BAGH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/6402709 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122687413 | Approved | 27000 | 0 | 2026-09-10
BAGH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722007042/IF/IAY/6403193 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128070389 | Approved | 27000 | 0 | 2025-07-08
BAGH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722007042/WC/22012035245335 — Nistar talab Neem wala nala | Approved | 0 | 0 | 2024-10-02
BAGH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722007042/WC/22012035245340 — Nistar talab Palash wala nala | Ongoing | 1470003.47 | 0 | 2025-09-13