## Work List
Exported on: 2026-10-24 12:12:16
Filters applied:
Data source: VBGRAMG
District: DHAR
Block: All
Panchayat: Nisarpur
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
NISARPUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Canal Line Plantation-Horticulture - Community / Canal Line Plantation for Community | Plantation | 1722010024/DP/22012034488463 — व़क्षारोपण कार्य मोजय माता मंदिर परिसर निसरपुर | Ongoing | 390826.48 | 0 | 2020-09-29
NISARPUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation of Forestry-Community / Avenue Plantation for Community | Plantation | 1722010024/DP/22012034495904 — व्रक्षा रोपण श्री राम मन्दीर निसरपुर | Physically Completed | 390826.48 | 0 | 2020-09-21 | 2026-07-23
NISARPUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1722010024/DP/22012034495905 — व्रक्षा रोपण हनुमान मन्दीर | Physically Completed | 390826.48 | 0 | 2020-09-21 | 2026-07-23
NISARPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722010024/IF/22012034785755 — Kapildhara KOOP Shitaram/ BAU Nisarpur | Ongoing | 306971.28 | 0 | 2022-05-26
NISARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1722010024/IF/22012035437718 — Dugwell Richarg Sitaram Bau 1722010024/if22012035437687 | Ongoing | 25899.46 | 0 | 2025-05-13
NISARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722010024/IF/22012035605181 — एक बगिया माँ के नाम समूह | Ongoing | 269386.03 | 0 | 2025-09-12
NISARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722010024/IF/22012035620648 — एक बगीया मां के नाम कैलाश हरेसिंग पटेल | Approved | 269386.03 | 0 | 2025-08-01
NISARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722010024/IF/22012035629444 — Counstruction of Pmayg House For individuals Pmayg Reg No MP146275233 Geeta Rajesh | Physically Completed | 23490 | 0 | 2026-01-01 | 2026-08-10
NISARPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1722010024/IF/IAY/1174240 — Construction of IAY House -IAY REG. NO. MP2663117 | Approved | 27000 | 0 | 2017-06-19
NISARPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1722010024/IF/IAY/1174835 — Construction of IAY House -IAY REG. NO. MP3977726 | Approved | 27000 | 0 | 2017-06-19
NISARPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1722010024/IF/IAY/1181860 — Construction of IAY House -IAY REG. NO. MP1823801 | Approved | 27000 | 0 | 2017-08-19
NISARPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1722010024/IF/IAY/1183053 — Construction of IAY House -IAY REG. NO. MP1725196 | Approved | 27000 | 0 | 2017-09-07
NISARPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1722010024/IF/IAY/1196923 — Construction of IAY House -IAY REG. NO. MP4331164 | Approved | 27000 | 0 | 2017-11-23
NISARPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1722010024/IF/IAY/1196950 — Construction of IAY House -IAY REG. NO. MP5375895 | Approved | 27000 | 0 | 2017-11-23
NISARPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1722010024/IF/IAY/1200839 — Construction of IAY House -IAY REG. NO. MP2357931 | Approved | 27000 | 0 | 2018-01-16
NISARPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1722010024/IF/IAY/1201380 — Construction of IAY House -IAY REG. NO. MP1792796 | Approved | 27000 | 0 | 2018-01-16
NISARPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1722010024/IF/IAY/1204949 — Construction of IAY House -IAY REG. NO. MP5184730 | Approved | 27000 | 0 | 2018-01-30
NISARPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722010024/IF/IAY/2941783 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2623604 | Approved | 27000 | 0 | 2021-03-12
NISARPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722010024/IF/IAY/2944874 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4557275 | Approved | 27000 | 0 | 2021-03-12
NISARPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722010024/IF/IAY/3650010 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1656027 | Approved | 27000 | 0 | 2022-03-28
NISARPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722010024/IF/IAY/4371796 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2466589 | Completed | 23490 | 0 | 2023-01-21 | 2026-08-10
NISARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722010024/IF/IAY/4800760 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150528006 | Completed | 23490 | 0 | 2024-12-16 | 2026-07-23
NISARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722010024/IF/IAY/5811804 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145708838 | Completed | 23490 | 0 | 2025-09-22 | 2026-08-10
NISARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722010024/IF/IAY/5811808 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145780976 | Completed | 23490 | 0 | 2025-09-22 | 2026-07-23
NISARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722010024/IF/IAY/5811896 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145780653 | Completed | 23490 | 0 | 2025-09-22 | 2026-07-23
NISARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722010024/IF/IAY/5811928 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146844147 | Completed | 23490 | 0 | 2025-10-23 | 2026-07-23
NISARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722010024/IF/IAY/5812006 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145709130 | Ongoing | 27000 | 0 | 2026-01-30
NISARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722010024/IF/IAY/5812008 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145709380 | Physically Completed | 23490 | 0 | 2025-02-27 | 2026-07-05
NISARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722010024/IF/IAY/5812009 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145709407 | Approved | 27000 | 0 | 2025-02-27
NISARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722010024/IF/IAY/5812010 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145709474 | Completed | 23490 | 0 | 2025-10-23 | 2026-07-23
NISARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722010024/IF/IAY/5812011 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145709509 | Completed | 23490 | 0 | 2025-10-23 | 2026-07-23
NISARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722010024/IF/IAY/5812035 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148261665 | Approved | 27000 | 0 | 2025-03-20
NISARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722010024/IF/IAY/5812046 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146844221 | Completed | 23490 | 0 | 2025-09-22 | 2026-07-23
NISARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722010024/IF/IAY/5812047 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146844262 | Ongoing | 27000 | 0 | 2025-10-23
NISARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722010024/IF/IAY/5812111 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146274634 | Completed | 23490 | 0 | 2025-10-31 | 2026-08-10
NISARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722010024/IF/IAY/5812112 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146274905 | Completed | 23490 | 0 | 2025-11-01 | 2026-08-10
NISARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722010024/IF/IAY/5812113 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146275025 | Completed | 23490 | 0 | 2025-09-22 | 2026-07-23
NISARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722010024/IF/IAY/5812307 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148262521 | Approved | 27000 | 0 | 2025-02-28
NISARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722010024/IF/IAY/5812356 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148262157 | Completed | 23490 | 0 | 2025-11-03 | 2026-08-10
NISARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722010024/IF/IAY/5812357 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148262836 | Approved | 27000 | 0 | 2025-02-27
NISARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722010024/IF/IAY/5812436 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148260952 | Completed | 23490 | 0 | 2025-10-23 | 2026-07-23
NISARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722010024/IF/IAY/5812437 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148261180 | Approved | 27000 | 0 | 2025-02-28
NISARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722010024/IF/IAY/5812440 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150527749 | Approved | 27000 | 0 | 2025-03-03
NISARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722010024/IF/IAY/5812441 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150527890 | Completed | 23490 | 0 | 2025-09-22 | 2026-07-23
NISARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722010024/IF/IAY/5812442 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150528151 | Approved | 27000 | 0 | 2025-02-27
NISARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722010024/IF/IAY/5812543 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145708657 | Completed | 23490 | 0 | 2025-10-23 | 2026-07-23
NISARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722010024/IF/IAY/5812597 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151285724 | Completed | 23490 | 0 | 2025-10-23 | 2026-07-23
NISARPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex for Community | Community Sanitary Complex | 1722010024/RS/22012035130496 — सामुदायिक स्वछता परिसर टिकम जी मन्दीर परिसर | Approved | 47000 | 0 | 2025-01-25
NISARPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex for Community | Community Sanitary Complex | 1722010024/RS/22012035136977 — सामुदायिक स्वछता परिसर खेडापति हनुमान मंदिरपरिसर निसरपुर | Approved | 56000 | 0 | 2024-08-14
NISARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Coast Line Plntation-Coastal Shelter Belt-Comm / Shelterbelt Plantation for Community | Plantation | 1722010024/WC/22012035319597 — मा नर्मदा परिक्रमा पथ के आश्रय स्थल की सरकारी भूमी पर पोधारोपण कार्य | Ongoing | 864016.76 | 10620 | 2026-01-06
NISARPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722010/IF/22012035018254 — उद्यानिकी निजी खेत धनकुवरबाई निसरपुर | Ongoing | 854720 | 0 | 2022-11-08