## Work List
Exported on: 2026-10-12 20:13:49
Filters applied:
Data source: VBGRAMG
District: DHAR
Block: All
Panchayat: Sirsala
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1722011040/IF/22012035478487 — JGSA KHET TALAB NIRMAN NAVIN HARESINGH GP SIRSALA | Approved | 0 | 0 | 2025-04-14
MANAWAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1722011049/DP/22012034445470 — Saarwjanik Kup Nirmaan Varaksharopan Hetu Naher ke Pass Sirsala (5.35 Lack) | Ongoing | 535000 | 0 | 2019-11-06
MANAWAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in fields for Community | Plantation | 1722011049/DP/22012034563087 — वृक्षारोपण कार्य दिव्येश्वर पहाड़ी पर उत्तर साईड, सिरसाला | Ongoing | 718191.92 | 0 | 2022-11-19
MANAWAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in fields for Community | Plantation | 1722011049/DP/22012034563088 — वृक्षारोपण कार्य दिव्येश्वर पहाड़ी पर पूर्वी साईड, सिरसाला | Ongoing | 718191.92 | 0 | 2022-09-08
MANAWAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in fields for Community | Plantation | 1722011049/DP/22012034564241 — वृक्षारोपन कार्य अमृत सरोवर तालाब के ऊपरी पहाड़ी पर, भोगदाद सिरसाला | Ongoing | 422718.19 | 0 | 2022-09-06
MANAWAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Sericulture- in Fields-Community / Block Plantation of Sericulture Trees in fields for Community | Plantation | 1722011049/DP/22012034599413 — Vasudha vandan Amrit sarovar ke pas Bhogdad Sirsala | Ongoing | 55847.4 | 0 | 2023-08-23
MANAWAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Block Plantation of Forestry Trees in fields for Individual | Other Works | 1722011049/IF/22012034427773 — BP.Plantation (Sanjay Buda) Siv Mandi Pahaadi Parr | Ongoing | 544000 | 0 | 2018-08-22
MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1722011049/IF/22012035399658 — JGSA KHET TALAB NIRMAN DEVDAS GANPAT GP SIRSALA | Ongoing | 147621.16 | 0 | 2025-04-29
MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1722011049/IF/22012035444303 — JGSA KHET TALAB NIRMAN GAMIR GUMAN GP SIRSALA | Approved | 147621.16 | 0 | 2025-04-14
MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722011049/IF/22012035592206 — EK BAGIYA MAA KE NAAM KANCHAN BAI MP-22-011-049-001/63 GP SIRSALA | Approved | 266577.25 | 0 | 2025-08-01
MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722011049/IF/22012035592231 — EK BAGIYA MAA KE NAAM SOMALI MP-22-011-049-001/69 GP SIRSALA | Approved | 266577.25 | 0 | 2025-08-01
MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722011049/IF/22012035592243 — EK BAGIYA MAA KE NAAM JHAVA BAI MP-22-011-049-002/75 GP SIRSALA | Approved | 266577.25 | 0 | 2025-08-01
MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722011049/IF/22012035599611 — EK BAGIYA MAA KE NAME KALA-Santosh Muwel, Kanchan Bai, Manis-MP22011049001/63-GP-SIRSALA | New | 0 | 0 | 2025-08-01
MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722011049/IF/22012035599784 — EK BAGIYA MAA KE NAME KALA-Manga Baghel, Jhava Bai Baghel-MP22011049002/75-GP-SIRSALA | New | 0 | 0 | 2025-08-01
MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722011049/IF/22012035599788 — EK BAGIYA MAA KE NAME KALA-Fulsingh Chouhan, Somalibai Chouh-MP22011049001/69-GP-SIRSALA | New | 0 | 0 | 2025-08-01
MANAWAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011049/IF/IAY/4090155 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128168842 | Ongoing | 27000 | 0 | 2022-11-17
MANAWAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011049/IF/IAY/4674268 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118317493 | Ongoing | 27000 | 3300 | 2024-12-16
MANAWAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011049/IF/IAY/4674272 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118319497 | Ongoing | 27000 | 3600 | 2024-11-23
MANAWAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011049/IF/IAY/4674690 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121625151 | Ongoing | 27000 | 0 | 2025-01-15
MANAWAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011049/IF/IAY/4674898 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120780141 | Ongoing | 27000 | 0 | 2024-11-23
MANAWAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011049/IF/IAY/4679125 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120569410 | Physically Completed | 23490 | 3600 | 2024-11-23 | 2026-08-09
MANAWAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011049/IF/IAY/4741718 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106755662 | Ongoing | 27000 | 3600 | 2024-11-23
MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011049/IF/IAY/5246284 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119391062 | Physically Completed | 27000 | 5100 | 2025-07-26 | 2026-09-20
MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011049/IF/IAY/5256078 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121623737 | Ongoing | 27000 | 4200 | 2025-05-18
MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011049/IF/IAY/5270829 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127467404 | Ongoing | 27000 | 0 | 2025-07-28
MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011049/IF/IAY/5288660 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120780599 | Physically Completed | 23490 | 4200 | 2026-02-06 | 2026-07-19
MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011049/IF/IAY/5299451 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115426586 | Physically Completed | 23490 | 5100 | 2025-09-12 | 2026-08-09
MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011049/IF/IAY/5302919 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120780342 | Completed | 23490 | 3000 | 2025-10-04 | 2026-07-28
MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011049/IF/IAY/5304217 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113948470 | Ongoing | 27000 | 13200 | 2026-02-19
MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011049/IF/IAY/5314624 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106713350 | Ongoing | 27000 | 6900 | 2025-08-28
MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011049/IF/IAY/5318689 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122838340 | Ongoing | 27000 | 11100 | 2025-09-12
MANAWAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011049/IF/IAY/5329324 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118317748 | Ongoing | 27000 | 25200 | 2026-07-21
MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011049/IF/IAY/5332821 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122785281 | Physically Completed | 23490 | 4500 | 2025-08-18 | 2026-07-26
MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011049/IF/IAY/5342554 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118318325 | Physically Completed | 23490 | 2100 | 2025-05-27 | 2026-07-26
MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011049/IF/IAY/5357665 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113721137 | Ongoing | 27000 | 4200 | 2025-04-23
MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011049/IF/IAY/5364276 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106748268 | Physically Completed | 23490 | 4500 | 2025-07-26 | 2026-07-26
MANAWAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011049/IF/IAY/5364574 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106699376 | Ongoing | 27000 | 16800 | 2026-08-20
MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011049/IF/IAY/5365247 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113854852 | Ongoing | 27000 | 4200 | 2025-07-28
MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011049/IF/IAY/5374256 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113742705 | Ongoing | 27000 | 4200 | 2025-04-23
MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011049/IF/IAY/5374570 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115168647 | Ongoing | 27000 | 0 | 2025-07-01
MANAWAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011049/IF/IAY/5374597 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123413515 | Ongoing | 27000 | 26400 | 2026-07-30
MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011049/IF/IAY/5375518 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120780500 | Ongoing | 27000 | 4200 | 2025-08-04
MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011049/IF/IAY/5378628 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113945322 | Ongoing | 27000 | 13200 | 2025-09-12
MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011049/IF/IAY/5379454 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113916528 | Ongoing | 27000 | 2100 | 2025-08-29
MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011049/IF/IAY/5383167 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120779748 | Completed | 23490 | 0 | 2025-07-11 | 2026-07-28
MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011049/IF/IAY/5388697 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125963830 | Physically Completed | 23490 | 4200 | 2025-08-18 | 2026-08-02
MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011049/IF/IAY/5407320 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118317965 | Ongoing | 27000 | 0 | 2025-08-18
MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011049/IF/IAY/5442053 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125800843 | Ongoing | 27000 | 18000 | 2025-09-12
MANAWAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011049/IF/IAY/5443441 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106699496 | Ongoing | 27000 | 0 | 2026-04-28
MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011049/IF/IAY/5445234 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120590923 | Ongoing | 27000 | 0 | 2026-02-11
MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011049/IF/IAY/5609671 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119578193 | Ongoing | 27000 | 0 | 2025-08-18
MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011049/IF/IAY/5610189 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115418345 | Physically Completed | 23490 | 1500 | 2025-10-04 | 2026-07-26
MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011049/IF/IAY/5626953 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120555568 | Physically Completed | 23490 | 12000 | 2026-02-06 | 2026-08-09
MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722011049/IF/IAY/6342445 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118314254 | Approved | 27000 | 0 | 2025-04-10
MANAWAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in fields for Community | Plantation | 1722011049/WC/22012034569412 — Divyeshawar Mandir ki Pahadi Par Platation Work GP Sirsala | Ongoing | 390826.48 | 0 | 2020-08-01
MANAWAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1722011049/WC/22012034641358 — CTRA Contur Trench (Gol byda ke pass, Bhogdar) Sirsala | Ongoing | 250302.72 | 0 | 2021-05-01
MANAWAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Coast Line Plntation-Coastal Shelter Belt-Comm / Shelterbelt Plantation for Community | Plantation | 1722011049/WC/22012035136155 — CNG Poshan Vatika Jan Aarogya Kendra Ke Pass Sirsala | Ongoing | 872145.1 | 15660 | 2023-10-09
MANAWAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1722011049/WC/22012035163863 — Parcolation tank Singaji Pahadi Sirsala | New | 0 | 0 | 2024-01-27
MANAWAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Contour Trench for Community | Construction of Trench | 1722011049/WC/22012035212882 — contour trench nirman Shingaji mandir ke pas | Ongoing | 406157.9 | 0 | 2025-02-20
MANAWAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Rejuvenation of Pond for Community | Repair & maint of Pond/ Tank | 1722011049/WH/22012034931660 — pushkar dharovar stop dam bandu gopal ke khet pass , sirsala | Ongoing | 48000 | 0 | 2022-05-02
MANAWAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry Check Dam for Community | Construction of Check Dam/Stop Dam | 1722/WC/22012035137050 — Slab Culvert Kakad Wala Nala Sirsala | Ongoing | 4690000 | 0 | 2023-10-05
MANAWAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry Check Dam for Community | Construction of Check Dam/Stop Dam | 1722/WC/22012035137071 — RMS Nirman Karya Talab Wala Nala Bhogdar Sirsala | Ongoing | 4626000 | 0 | 2023-10-06