## Work List
Exported on: 2026-09-03 04:20:53
Filters applied:
Data source: VBGRAMG
District: DHAR
Block: All
Panchayat: Udiyapur
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
MANAWAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Road Line Plantation of Forestry Trees for Comm / Road side line plantation of Forestry Trees for Community | Plantation | 1722011061/DP/22012034618194 — PLANTATION SHANTI DHAM KE PASS UDIYAPUR | Ongoing | 299684.32 | 0 | 2024-08-06
MANAWAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722011061/IF/22012034471623 — कपिलधारा (रामसिंह गल्या ) उदियापुर | Physically Completed | 210000 | 0 | 2019-03-08 | 2026-08-02
MANAWAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722011061/IF/22012034472447 — KAPIL DHARA (BILAM SHANKAR) UDIYAPUR | Ongoing | 210000 | 0 | 2019-03-08
MANAWAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722011061/IF/22012034472449 — KAPIL DHARA (KAILASH GULAB) UDIYAPUR | Physically Completed | 210000 | 0 | 2019-03-08 | 2026-07-31
MANAWAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722011061/IF/22012034473626 — Kapil Dhara (Badu -Bhaliya) Udiyapur | Ongoing | 210000 | 0 | 2019-03-10
MANAWAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1722011061/IF/22012035479451 — JGSA dug well nirman at gobind gatliya gp udyapur | Approved | 0 | 0 | 2025-04-02
MANAWAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1722011061/IF/22012035479669 — JGSA dug well nirman at Amir maniya gp udyapur | Approved | 0 | 0 | 2025-04-02
MANAWAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1722011061/IF/22012035479745 — JGSA dug well nirman at laxman maniya gp udyapur | Approved | 0 | 0 | 2025-04-02
MANAWAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1722011061/IF/22012035479802 — JGSA dug well nirman at sitaram fulshing gp udyapur | Approved | 0 | 0 | 2025-04-02
MANAWAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1722011061/IF/22012035481337 — JGSA dug well recharge pit nirman galshing nharshing gp udiyapur | New | 0 | 0 | 2025-04-02
MANAWAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1722011061/IF/22012035481362 — JGSA dug well recharge pit nirman rugnath kisore gp udiyapur | Ongoing | 25899.46 | 0 | 2025-05-24
MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722011061/IF/22012035609500 — ek bagiya maa ke name ramkuwar raju waskel | Ongoing | 266577.25 | 0 | 2025-09-23
MANAWAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011061/IF/IAY/4587155 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119896497 | Ongoing | 27000 | 0 | 2024-10-09
MANAWAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011061/IF/IAY/4589758 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120931246 | Ongoing | 27000 | 0 | 2024-10-02
MANAWAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011061/IF/IAY/4622527 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126545966 | Ongoing | 27000 | 4800 | 2024-10-02
MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011061/IF/IAY/5250385 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119896588 | Physically Completed | 23490 | 0 | 2025-08-12 | 2026-08-11
MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011061/IF/IAY/5253415 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117696914 | Ongoing | 27000 | 4800 | 2025-10-31
MANAWAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011061/IF/IAY/5259535 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117667512 | Ongoing | 27000 | 6300 | 2026-05-16
MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011061/IF/IAY/5273529 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117667704 | Physically Completed | 23490 | 0 | 2025-04-16 | 2026-08-11
MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011061/IF/IAY/5290289 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117667419 | Ongoing | 27000 | 2100 | 2025-08-21
MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011061/IF/IAY/5290528 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106034524 | Completed | 23490 | 2100 | 2025-09-04 | 2026-07-30
MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011061/IF/IAY/5292239 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117667595 | Physically Completed | 23490 | 0 | 2025-04-16 | 2026-08-11
MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011061/IF/IAY/5295696 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127304119 | Ongoing | 27000 | 4200 | 2025-07-30
MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011061/IF/IAY/5295771 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113884136 | Physically Completed | 23490 | 0 | 2025-04-16 | 2026-08-11
MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011061/IF/IAY/5302338 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126526513 | Ongoing | 27000 | 0 | 2025-10-29
MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011061/IF/IAY/5308457 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114155408 | Ongoing | 27000 | 2100 | 2025-08-12
MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011061/IF/IAY/5318507 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113884265 | Ongoing | 27000 | 0 | 2025-09-13
MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011061/IF/IAY/5331204 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125691881 | Ongoing | 27000 | 0 | 2025-07-30
MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011061/IF/IAY/5334816 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126539518 | Ongoing | 27000 | 0 | 2025-10-02
MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011061/IF/IAY/5443958 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117106329 | Completed | 23490 | 0 | 2025-10-26 | 2026-07-27
MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011061/IF/IAY/5444098 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117667478 | Ongoing | 27000 | 0 | 2025-10-31
MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011061/IF/IAY/5444548 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132128084 | Completed | 23490 | 0 | 2025-10-02 | 2026-07-27
MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011061/IF/IAY/5445018 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119896530 | Completed | 23490 | 0 | 2025-06-02 | 2026-07-27
MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011061/IF/IAY/5445857 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117453459 | Approved | 27000 | 0 | 2025-04-10
MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011061/IF/IAY/5446672 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117667049 | Completed | 23490 | 0 | 2026-02-12 | 2026-07-17
MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011061/IF/IAY/5446674 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117667800 | Completed | 23490 | 0 | 2026-02-12 | 2026-07-17
MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011061/IF/IAY/5447507 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130821505 | Ongoing | 27000 | 6900 | 2025-10-31
MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011061/IF/IAY/5492552 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113884446 | Ongoing | 27000 | 6900 | 2025-10-31
MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011061/IF/IAY/5508263 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117667723 | Ongoing | 27000 | 0 | 2025-10-02
MANAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722011061/IF/IAY/5694987 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106485084 | Ongoing | 27000 | 6900 | 2025-10-31
MANAWAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1722011061/RS/22012034403862 — Shochalay nirman (pyarsingh ballu) Udiyapur | Ongoing | 12000 | 0 | 2019-01-29
MANAWAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1722011061/WC/22012035081275 — सार्वजनिक कूप निर्माण कार्य छोटे तालाब के पीछे udyapur | Ongoing | 681778.59 | 0 | 2023-07-01
MANAWAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722011061/WC/22012035163135 — bhusankalan pond bhabarpura udiyapur | New | 0 | 0 | 2024-01-27
MANAWAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722011/IF/22012035028917 — Horticulture plantation bapu banga udiyapur | Ongoing | 149214 | 0 | 2022-12-12
MANAWAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722011/IF/22012035050505 — Horticulture plantation keshar udiyapur | Ongoing | 149214 | 0 | 2023-01-23