## Work List
Exported on: 2026-10-15 22:26:14
Filters applied:
Data source: VBGRAMG
District: DHAR
Block: All
Panchayat: Rangaon
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
UMARBAN | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Const of Level Bench Terrace for Individual / Construction of Level Bench Terrace for Individual | Terracing | 1722012037/IF/22012035127145 — Construction of PMAY-G House for Individuals Rajendra Lachhiram MP115401182 | Ongoing | 18561.48 | 10800 | 2025-09-09
UMARBAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722012037/IF/22012035275395 — MAID BANDHAN NIRMAN TERSINGH ARJUN KALYANPURA RANGAON | New | 0 | 0 | 2024-04-01
UMARBAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722012037/IF/22012035275396 — Construction of PMAY G House for Individuals PMAY G REG. NO. MP115973438 | Approved | 27000 | 0 | 2024-04-01
UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722012037/IF/22012035600465 — EK BAGIYA MAA KE NAME-Rajaram Ranvir, Ramkunwar Ranvir-MP22012037002/1-RANGAON | Ongoing | 266577.25 | 43800 | 2025-09-09
UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722012037/IF/22012035600466 — EK BAGIYA MAA KE NAME-Fulsingh Dawar, Laxmi Bai Dawar, Sonu Dawar, Monu Dawar, Shivraj Dawar-MP22012 | Ongoing | 266577.25 | 0 | 2025-09-09
UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722012037/IF/22012035600469 — EK BAGIYA MAA KE NAME-Savitri Bai Solanki, Rakesh Solanki, Narbdi Solanki, Priyanshi Solanki, Pranja | Ongoing | 266577.25 | 0 | 2025-09-24
UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722012037/IF/22012035600473 — EK BAGIYA MAA KE NAME-Shanta Bai Kanel, Rekha Kanel, Vandana Kanel, Pooja, Kailash Kanel-MP220120370 | Ongoing | 266577.25 | 0 | 2025-09-09
UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722012037/IF/22012035600476 — EK BAGIYA MAA KE NAME-Radha Chouhan, Anita, Sanjay-MP22012037002/57-RANGAON | Ongoing | 266577.25 | 42900 | 2026-02-15
UMARBAN | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/3719519 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115373251 | Physically Completed | 23490 | 0 | 2023-07-18 | 2026-07-22
UMARBAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/4560297 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115350522 | Ongoing | 27000 | 0 | 2025-03-18
UMARBAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/4561208 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115619431 | Ongoing | 27000 | 0 | 2024-10-06
UMARBAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/4743943 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114849559 | Ongoing | 27000 | 2100 | 2024-12-04
UMARBAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/4745383 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115121215 | Ongoing | 27000 | 0 | 2024-12-04
UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/4747096 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114741954 | Ongoing | 27000 | 0 | 2025-11-19
UMARBAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/4747118 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114746359 | Ongoing | 27000 | 4200 | 2024-12-04
UMARBAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/4747256 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114777409 | Ongoing | 27000 | 3600 | 2024-12-04
UMARBAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/4749174 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115945045 | Ongoing | 27000 | 0 | 2024-12-04
UMARBAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/4766544 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115619488 | Ongoing | 27000 | 3600 | 2024-12-04
UMARBAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/4772751 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115879580 | Ongoing | 27000 | 0 | 2024-12-04
UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/4774265 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115879615 | Ongoing | 27000 | 0 | 2025-04-22
UMARBAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/4882832 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115874391 | Ongoing | 27000 | 0 | 2025-01-30
UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/5295974 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113526194 | Physically Completed | 23490 | 0 | 2025-04-22 | 2026-07-14
UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/5296905 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115122847 | Ongoing | 27000 | 6300 | 2025-04-22
UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/5307444 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115728253 | Ongoing | 27000 | 6000 | 2025-05-07
UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/5315401 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115350623 | Completed | 23490 | 0 | 2025-04-22 | 2026-07-21
UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/5318076 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115351472 | Ongoing | 27000 | 0 | 2025-04-22
UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/5324944 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114755909 | Ongoing | 27000 | 0 | 2025-05-07
UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/5335375 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115349301 | Physically Completed | 23490 | 0 | 2025-04-22 | 2026-07-14
UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/5337616 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113495451 | Ongoing | 27000 | 4200 | 2025-05-07
UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/5338810 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107052998 | Ongoing | 27000 | 3927 | 2025-04-22
UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/5344426 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114731651 | Ongoing | 27000 | 2100 | 2025-04-22
UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/5348749 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115159871 | Ongoing | 27000 | 8400 | 2025-04-22
UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/5350669 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115110240 | Physically Completed | 23490 | 0 | 2025-06-01 | 2026-07-14
UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/5352125 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115339952 | Ongoing | 27000 | 6027 | 2025-04-22
UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/5352203 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113514809 | Ongoing | 27000 | 4200 | 2025-04-22
UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/5352393 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115341922 | Ongoing | 27000 | 4200 | 2025-04-22
UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/5353271 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115180070 | Ongoing | 27000 | 6300 | 2025-04-22
UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/5394697 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113536835 | Ongoing | 27000 | 6300 | 2025-10-30
UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/5423240 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114759992 | Ongoing | 27000 | 4200 | 2025-04-22
UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/5423697 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115113232 | Ongoing | 27000 | 2100 | 2025-04-22
UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/5425254 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115336889 | Ongoing | 27000 | 10500 | 2025-04-22
UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/5425255 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115340029 | Ongoing | 27000 | 6300 | 2025-04-22
UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/5425581 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115136483 | Ongoing | 27000 | 8400 | 2025-04-22
UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/5426637 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114219427 | Ongoing | 27000 | 8400 | 2025-04-22
UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/5429552 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114168434 | Ongoing | 27000 | 0 | 2025-04-22
UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/5430606 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114854589 | Completed | 23490 | 0 | 2025-06-01 | 2026-07-21
UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/5432085 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115164207 | Ongoing | 27000 | 6300 | 2025-10-30
UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/5432312 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113458897 | Ongoing | 27000 | 8400 | 2025-05-03
UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/5433596 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115337322 | Ongoing | 27000 | 4200 | 2025-05-03
UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/5433659 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114181281 | Physically Completed | 23490 | 3801 | 2025-05-03 | 2026-08-23
UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/5453886 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115340730 | Ongoing | 27000 | 8400 | 2025-05-03
UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/5453974 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115344548 | Ongoing | 27000 | 2100 | 2025-05-03
UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/5489469 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114781052 | Ongoing | 27000 | 10500 | 2025-05-08
UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/5489822 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114710594 | Ongoing | 27000 | 10500 | 2025-05-08
UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/5490837 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113521901 | Ongoing | 27000 | 6300 | 2025-05-08
UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/5491089 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115339284 | Ongoing | 27000 | 4200 | 2025-11-19
UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/5492022 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106766217 | Ongoing | 27000 | 18900 | 2025-11-19
UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/5492964 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115407094 | Ongoing | 27000 | 0 | 2025-11-19
UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/5553301 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115230205 | Ongoing | 27000 | 0 | 2025-11-19
UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/5553303 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115232839 | Ongoing | 27000 | 6300 | 2025-05-08
UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/5553309 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115235960 | Ongoing | 27000 | 6300 | 2025-05-08
UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/5553310 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115236019 | Physically Completed | 23490 | 2100 | 2025-09-10 | 2026-07-26
UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/5553315 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115242459 | Ongoing | 27000 | 4200 | 2025-05-08
UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/5553955 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115235926 | Ongoing | 27000 | 4200 | 2025-05-08
UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/5556169 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115406817 | Ongoing | 27000 | 4200 | 2025-05-08
UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/5556762 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115339864 | Ongoing | 27000 | 0 | 2025-07-29
UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/5618842 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP111433574 | Ongoing | 27000 | 4200 | 2025-07-28
UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/5693829 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114206666 | Ongoing | 27000 | 4200 | 2025-07-28
UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/5693982 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115126001 | Physically Completed | 23490 | 3780 | 2025-10-30 | 2026-07-22
UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/5694002 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114197687 | Ongoing | 27000 | 4200 | 2025-07-28
UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/5694102 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114208978 | Completed | 23490 | 3780 | 2025-07-28 | 2026-07-28
UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/5694511 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114190799 | Ongoing | 27000 | 4200 | 2025-07-28
UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/5724344 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115236186 | Ongoing | 27000 | 0 | 2025-10-30
UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/5824006 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126457210 | Ongoing | 27000 | 0 | 2025-11-19
UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/6134592 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115124699 | Ongoing | 27000 | 4200 | 2026-07-13
UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/6139496 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115122995 | Ongoing | 27000 | 2100 | 2026-08-19
UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/6139700 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114183634 | Ongoing | 27000 | 8400 | 2026-07-13
UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/6160611 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115194309 | Ongoing | 27000 | 4200 | 2026-07-13
UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/6169462 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114749723 | Ongoing | 27000 | 6300 | 2026-07-13
UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/6171369 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114188629 | Ongoing | 27000 | 8400 | 2026-07-13
UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/6173940 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114744958 | Ongoing | 27000 | 6300 | 2026-07-13
UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/6173941 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114749440 | Ongoing | 27000 | 6300 | 2026-07-13
UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/6340392 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115428222 | Approved | 27000 | 0 | 2025-04-22
UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/6364810 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114172821 | Approved | 27000 | 0 | 2025-06-20
UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/6364831 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114164347 | Approved | 27000 | 0 | 2025-06-20
UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/6365594 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114176795 | Approved | 27000 | 0 | 2026-06-04
UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/6378827 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106773734 | Approved | 27000 | 0 | 2026-07-15
UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/6382837 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114179659 | Approved | 27000 | 0 | 2025-06-18
UMARBAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/6385425 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114788964 | Approved | 27000 | 0 | 2025-06-24
UMARBAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722012037/IF/IAY/6394375 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115401772 | Approved | 27000 | 0 | 2026-08-04
UMARBAN | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Construction of Drainage Works in Waterlogged Land for Community | Land Development | 1722012037/LD/22012034953630 — जल गंगा सवंर्वधन अभियान कुप रिचार्ज रणगॉंव दिनेश-नाना | Approved | 25899.46 | 0 | 2025-04-01
UMARBAN | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Construction of Drainage Works in Waterlogged Land for Community | Land Development | 1722012037/LD/22012034953632 — जल गंगा सवंर्वधन अभियान कुप रिचार्ज रणगॉंव कालीबाई-गोपाल | Approved | 25899.46 | 0 | 2025-04-01
UMARBAN | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1722012037/RC/22012034463723 — रणगॉव सी0सी0 खंरजा निर्माण स्‍कुल से जगदीश के घर तक (मादियापुरा) | Ongoing | 148000 | 0 | 2019-03-10
UMARBAN | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722012037/WC/22012035218409 — SANKAN POUND NIRMAN PARVAT KE KHET KE PASS | New | 0 | 0 | 2024-04-01
UMARBAN | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722012037/WC/22012035254322 — Gram panchayat Rangav kalyanpura me nirmal neer | Approved | 600652.52 | 0 | 2025-03-01