## Work List
Exported on: 2026-10-20 03:42:00
Filters applied:
Data source: VBGRAMG
District: DHAR
Block: All
Panchayat: Kachhwanya
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
DHARAMPURI | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound Wall for Government School for Community | Constr of Compound wall | 1722013004/AV/22012034589068 — GP KACHHWANYA ME HIGH SCHOOL PARISAR ME BOUNDRY WALL NIRMAN DUKANPURA | Ongoing | 554381.7 | 0 | 2024-01-28
DHARAMPURI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722013004/IF/22012035307755 — Gp Kachwanya Me Subhash Fattusingh Ke Khet Me Kapil Dhara Kup Nirman | Approved | 190104.41 | 0 | 2025-01-27
DHARAMPURI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722013004/IF/22012035308588 — Gp Kachwanya Me Gulab Shivla Ke Khet Me Kapil Dhara Kup Nirman Karya | Approved | 0 | 0 | 2025-01-27
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1722013004/IF/22012035571192 — GP KACHWANIYA ME PASHU SHED NIRMAN SEVANTA BAI | Approved | 0 | 0 | 2025-04-14
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1722013004/IF/22012035571197 — GP KACHWANIYA ME PASHU SHED NIRMAN MAMTA BAI | Approved | 0 | 0 | 2025-04-14
DHARAMPURI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/4534469 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102190071 | Approved | 27000 | 0 | 2024-09-13
DHARAMPURI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/4535136 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102357311 | Approved | 27000 | 0 | 2024-09-11
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/4535216 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102374945 | Completed | 23490 | 0 | 2025-04-23 | 2026-08-21
DHARAMPURI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/4535232 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102377014 | Approved | 27000 | 0 | 2024-09-12
DHARAMPURI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/4538688 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102626955 | Approved | 27000 | 0 | 2024-09-12
DHARAMPURI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/4539914 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104940802 | Completed | 23490 | 0 | 2024-12-29 | 2026-08-21
DHARAMPURI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/4687507 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102465996 | Approved | 27000 | 0 | 2024-09-20
DHARAMPURI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/4688412 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105710388 | Approved | 27000 | 0 | 2024-09-21
DHARAMPURI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/4734627 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102212291 | Approved | 27000 | 0 | 2024-10-08
DHARAMPURI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/4884475 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102190054 | Physically Completed | 23490 | 0 | 2024-09-12 | 2026-08-16
DHARAMPURI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5246962 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102367053 | Approved | 27000 | 0 | 2025-02-17
DHARAMPURI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5247546 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102464906 | Approved | 27000 | 0 | 2025-02-17
DHARAMPURI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5248267 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103478441 | Approved | 27000 | 0 | 2025-02-17
DHARAMPURI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5248647 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102928743 | Approved | 27000 | 0 | 2025-02-17
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5258749 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102452119 | Completed | 23490 | 0 | 2025-05-19 | 2026-08-21
DHARAMPURI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5261513 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102360751 | Approved | 27000 | 0 | 2025-02-19
DHARAMPURI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5269270 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103099653 | Approved | 27000 | 0 | 2025-02-17
DHARAMPURI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5271727 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102116682 | Approved | 27000 | 0 | 2025-02-18
DHARAMPURI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5274399 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102427560 | Approved | 27000 | 0 | 2025-02-17
DHARAMPURI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5280650 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102653980 | Approved | 27000 | 0 | 2025-02-17
DHARAMPURI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5281146 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102302711 | Approved | 27000 | 0 | 2025-02-19
DHARAMPURI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5285382 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102444492 | Physically Completed | 23490 | 0 | 2025-02-19 | 2026-07-19
DHARAMPURI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5287549 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102660119 | Approved | 27000 | 0 | 2025-02-23
DHARAMPURI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5288413 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105441645 | Approved | 27000 | 0 | 2025-02-23
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5295007 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102925427 | Completed | 23490 | 0 | 2025-09-10 | 2026-08-15
DHARAMPURI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5302113 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102911477 | Approved | 27000 | 0 | 2025-02-17
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5307073 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102656217 | Completed | 23490 | 0 | 2025-05-19 | 2026-08-21
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5308790 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105445104 | Completed | 23490 | 0 | 2025-04-30 | 2026-08-21
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5310785 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102377629 | Completed | 23490 | 0 | 2025-05-19 | 2026-08-21
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5311779 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103621874 | Completed | 23490 | 0 | 2025-09-03 | 2026-08-21
DHARAMPURI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5325197 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103553794 | Approved | 27000 | 0 | 2025-02-17
DHARAMPURI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5331373 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102442273 | Approved | 27000 | 0 | 2025-02-17
DHARAMPURI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5337529 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104935627 | Approved | 27000 | 0 | 2025-02-19
DHARAMPURI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5338209 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102116737 | Approved | 27000 | 0 | 2025-02-17
DHARAMPURI | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/53621 — Construction of IAY House -IAY REG. NO. MP-22-013-004-002/039 | Approved | 27000 | 0 | 2015-10-16
DHARAMPURI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5384508 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124445478 | Approved | 27000 | 0 | 2025-03-05
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5395824 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102334113 | Ongoing | 27000 | 0 | 2025-08-30
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5479326 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105441417 | Ongoing | 27000 | 0 | 2025-05-26
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5580587 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102127845 | Completed | 23490 | 0 | 2025-05-26 | 2026-08-10
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5600222 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103100062 | Approved | 27000 | 0 | 2025-04-26
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5605185 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105909512 | Ongoing | 27000 | 0 | 2025-05-26
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5605499 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105710429 | Physically Completed | 23490 | 0 | 2025-05-02 | 2026-08-16
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5606234 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102435333 | Completed | 23490 | 0 | 2025-08-30 | 2026-08-21
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5625673 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102654317 | Ongoing | 27000 | 0 | 2025-07-13
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5625999 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102369058 | Approved | 27000 | 0 | 2025-05-09
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5626723 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102466279 | Completed | 23490 | 0 | 2025-09-10 | 2026-08-21
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5650923 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102190087 | Approved | 27000 | 0 | 2025-05-22
DHARAMPURI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5694282 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102265717 | Approved | 27000 | 0 | 2025-02-17
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5697608 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102372898 | Completed | 23490 | 0 | 2025-08-17 | 2026-08-15
DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5903514 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102366986 | Ongoing | 27000 | 6300 | 2026-09-17
DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5903740 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102984599 | Ongoing | 27000 | 10500 | 2026-09-17
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5904021 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102655909 | Approved | 27000 | 0 | 2026-01-08
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5904439 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102375564 | Approved | 27000 | 0 | 2026-01-19
DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5904872 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102366717 | Completed | 23490 | 9600 | 2026-05-06 | 2026-09-20
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5905415 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102915013 | Approved | 27000 | 0 | 2026-01-08
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5905754 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104973282 | Approved | 27000 | 0 | 2026-01-08
DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5906070 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102659438 | Completed | 23490 | 0 | 2026-05-06 | 2026-08-11
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5906910 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102435383 | Approved | 27000 | 0 | 2026-01-08
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5907414 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102241468 | Approved | 27000 | 0 | 2026-01-08
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5907674 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102932808 | Approved | 27000 | 0 | 2026-01-08
DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5907713 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102465783 | Ongoing | 27000 | 6300 | 2026-09-17
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5907738 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102366765 | Approved | 27000 | 0 | 2026-01-08
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5907887 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114952286 | Approved | 27000 | 0 | 2026-01-08
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5908354 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102265693 | Approved | 27000 | 0 | 2026-01-08
DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5908411 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102335804 | Completed | 27000 | 16800 | 2026-05-06 | 2026-10-18
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5908561 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102656884 | Approved | 27000 | 0 | 2026-01-08
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5908598 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102189979 | Approved | 27000 | 0 | 2026-01-08
DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5908950 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102661116 | Completed | 27000 | 12600 | 2026-05-06 | 2026-09-21
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5909123 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102660547 | Physically Completed | 23490 | 0 | 2026-01-08 | 2026-07-19
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5909248 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102439370 | Approved | 27000 | 0 | 2026-01-08
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5909505 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102996626 | Approved | 27000 | 0 | 2026-01-08
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5909633 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102996541 | Approved | 27000 | 0 | 2026-01-08
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5909738 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102653204 | Approved | 27000 | 0 | 2026-01-08
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5910108 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103446163 | Approved | 27000 | 0 | 2026-01-08
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5910213 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102127882 | Physically Completed | 27000 | 0 | 2026-01-08 | 2026-09-06
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5910614 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102466238 | Approved | 27000 | 0 | 2026-01-08
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5910985 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102915068 | Approved | 27000 | 0 | 2026-01-08
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5911587 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102926721 | Approved | 27000 | 0 | 2026-02-12
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5911619 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102241516 | Approved | 27000 | 0 | 2026-01-08
DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5911754 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102932119 | Completed | 23490 | 13200 | 2026-05-06 | 2026-09-20
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5912855 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104940710 | Approved | 27000 | 0 | 2026-01-08
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5912894 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103100097 | Approved | 27000 | 0 | 2026-01-08
DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5913050 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104939870 | Completed | 27000 | 18900 | 2026-05-06 | 2026-10-18
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5913612 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102123311 | Approved | 27000 | 0 | 2026-01-08
DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5913895 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104940502 | Completed | 23490 | 12900 | 2026-05-06 | 2026-09-20
DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5914389 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102197171 | Completed | 23490 | 9300 | 2026-05-06 | 2026-09-21
DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5914394 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102454534 | Ongoing | 27000 | 7200 | 2026-08-12
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5914515 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102650966 | Approved | 27000 | 0 | 2026-01-19
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5914588 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102657598 | Approved | 27000 | 0 | 2026-01-08
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5915193 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102915902 | Approved | 27000 | 0 | 2026-01-08
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5915621 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102466317 | Approved | 27000 | 0 | 2026-01-08
DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5916132 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102950999 | Completed | 27000 | 18900 | 2026-05-06 | 2026-10-16
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5916382 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102466035 | Approved | 27000 | 0 | 2026-01-08
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5916399 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102911943 | Approved | 27000 | 0 | 2026-01-08
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5916449 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103445365 | Approved | 27000 | 0 | 2026-01-08
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5917420 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102915825 | Approved | 27000 | 0 | 2026-01-08
DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5917784 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104940308 | Ongoing | 27000 | 4200 | 2026-10-07
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5917792 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102116697 | Approved | 27000 | 0 | 2026-01-08
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5917829 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104941833 | Approved | 27000 | 0 | 2026-01-08
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5917979 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102666008 | Approved | 27000 | 0 | 2026-01-08
DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5918271 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102334040 | Completed | 27000 | 18900 | 2026-05-19 | 2026-10-18
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5918635 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102358934 | Approved | 27000 | 0 | 2026-01-08
DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5918657 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102665142 | Completed | 27000 | 16800 | 2026-05-06 | 2026-10-18
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5918704 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102248006 | Approved | 27000 | 0 | 2026-01-08
DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5918709 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102355580 | Ongoing | 27000 | 8400 | 2026-08-12
DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5918812 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103446008 | Completed | 27000 | 16800 | 2026-05-06 | 2026-10-18
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5919040 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102659191 | Physically Completed | 23490 | 0 | 2026-01-08 | 2026-08-09
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5919524 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105436335 | Approved | 27000 | 0 | 2026-01-08
DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5920151 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102375048 | Completed | 23490 | 0 | 2026-05-19 | 2026-09-14
DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5920187 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102199777 | Ongoing | 27000 | 6300 | 2026-09-17
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5920584 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102664854 | Approved | 27000 | 0 | 2026-01-08
DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5920908 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102658461 | Completed | 23490 | 9850 | 2026-05-06 | 2026-09-21
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5921078 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102241543 | Approved | 27000 | 0 | 2026-01-12
DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5921861 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102212351 | Completed | 23490 | 0 | 2026-05-06 | 2026-08-10
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5921902 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102440917 | Approved | 27000 | 0 | 2026-01-08
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5922238 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102333351 | Approved | 27000 | 0 | 2026-01-08
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5922654 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104934754 | Approved | 27000 | 0 | 2026-01-08
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5922736 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102912245 | Approved | 27000 | 0 | 2026-01-08
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5922749 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102265565 | Approved | 27000 | 0 | 2026-01-12
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5923004 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102927075 | Approved | 27000 | 0 | 2026-01-08
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5923165 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102465942 | Approved | 27000 | 0 | 2026-01-08
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5923260 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102197156 | Approved | 27000 | 0 | 2026-01-08
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5923939 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105440148 | Approved | 27000 | 0 | 2026-01-08
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5923956 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105445347 | Approved | 27000 | 0 | 2026-01-08
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5924081 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104941277 | Approved | 27000 | 0 | 2026-01-08
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5924187 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102665711 | Approved | 27000 | 0 | 2026-01-12
DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5924265 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102360907 | Ongoing | 27000 | 12600 | 2026-09-17
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5924937 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102191731 | Approved | 27000 | 0 | 2026-01-08
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5925061 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102991612 | Approved | 27000 | 0 | 2026-01-08
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5925101 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102190000 | Approved | 27000 | 0 | 2026-01-08
DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5925527 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102664049 | Ongoing | 27000 | 4200 | 2026-10-07
DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5925753 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104939584 | Completed | 27000 | 18300 | 2026-05-06 | 2026-10-18
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5925795 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102911625 | Approved | 27000 | 0 | 2026-01-12
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5926383 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104937487 | Approved | 27000 | 0 | 2026-01-12
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5926522 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105445207 | Approved | 27000 | 0 | 2026-01-08
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5926654 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102656555 | Approved | 27000 | 0 | 2026-01-08
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5927041 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102375005 | Approved | 27000 | 0 | 2026-01-08
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5927555 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103971534 | Approved | 27000 | 0 | 2026-01-08
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5927783 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103100470 | Approved | 27000 | 0 | 2026-01-08
DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5928309 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102659547 | Ongoing | 27000 | 6300 | 2026-09-17
DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5929439 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102333206 | Ongoing | 27000 | 8400 | 2026-08-12
DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5929658 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102652368 | Ongoing | 27000 | 10500 | 2026-09-17
DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5929889 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102924989 | Ongoing | 27000 | 2100 | 2026-08-12
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5929988 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102440233 | Approved | 27000 | 0 | 2026-01-08
DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5930119 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102449943 | Ongoing | 27000 | 4200 | 2026-10-07
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5931472 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102466299 | Approved | 27000 | 0 | 2026-01-08
DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5936967 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104941109 | Ongoing | 27000 | 0 | 2026-10-15
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/5937797 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105909567 | Approved | 27000 | 0 | 2026-01-08
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/6067245 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102241419 | Approved | 27000 | 0 | 2026-03-06
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/6067246 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102241578 | Approved | 27000 | 0 | 2026-03-06
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/6067395 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102457439 | Approved | 27000 | 0 | 2026-03-06
DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/6067485 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102929265 | Completed | 27000 | 2100 | 2026-09-17 | 2026-09-29
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/6067510 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103031506 | Approved | 27000 | 0 | 2026-03-06
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/6067589 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103478977 | Approved | 27000 | 0 | 2026-03-06
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/6068086 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105404317 | Approved | 27000 | 0 | 2026-03-06
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/6100818 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150967313 | Approved | 27000 | 0 | 2026-03-06
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/6128973 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102996851 | Approved | 27000 | 0 | 2026-03-15
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/6147126 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102127751 | Approved | 27000 | 0 | 2026-03-15
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/6163962 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102216245 | Approved | 27000 | 0 | 2026-03-15
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/6170474 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102664318 | Approved | 27000 | 0 | 2026-03-15
DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/6228397 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102379521 | Approved | 23490 | 0 | 2026-04-07
DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/6228502 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102085691 | Physically Completed | 23490 | 0 | 2026-04-07 | 2026-08-09
DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/6228902 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103100553 | Approved | 23490 | 0 | 2026-04-07
DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/6229330 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102657134 | Approved | 23490 | 0 | 2026-04-07
DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/6229878 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102212274 | Approved | 23490 | 0 | 2026-05-04
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/6243264 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102466262 | Approved | 27000 | 0 | 2025-06-02
DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/6245896 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102265608 | Approved | 27000 | 0 | 2026-05-13
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/6346586 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102433832 | Approved | 27000 | 0 | 2026-01-12
DHARAMPURI | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/97288 — Construction of IAY House -IAY REG. NO. MP-22-013-004-002/036 | Approved | 27000 | 0 | 2015-10-16
DHARAMPURI | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1722013004/IF/IAY/97290 — Construction of IAY House -IAY REG. NO. MP-22-013-004-002/041 | Approved | 27000 | 0 | 2015-10-16
DHARAMPURI | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel / Mitti Murram Road for Community | Construction of Road and Culvert | 1722013004/RC/22012034832541 — ग्राम पंचायत कछवान्याँ मे कछवान्याँ पुलिया से मोहन के घर तरफ सुदूर सड़क निर्माण कार्य | Approved | 0 | 0 | 2024-10-02
DHARAMPURI | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel / Mitti Murram Road for Community | Construction of Road and Culvert | 1722013004/RC/22012034834856 — Ramesh ke khet se mahesh ke khet tak sudur sadak nirman | Approved | 0 | 0 | 2024-11-16
DHARAMPURI | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel / Mitti Murram Road for Community | Construction of Road and Culvert | 1722013004/RC/22012034834857 — Dilip ke khet se ambaram ke khet tak sudur sadak nirman | Approved | 0 | 0 | 2024-11-16
DHARAMPURI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1722013004/WC/22012034939244 — अमृत सरोवर कछवान्या -कुंडिया खोदरा नाले पर टेटिया भेरूसिंह के खेत के पास तालाब निर्माण | Ongoing | 1109035.66 | 0 | 2022-05-09
DHARAMPURI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1722013004/WC/22012034939263 — अमृत सरोवर कछवान्या -भूरी घाटी के पास नाले पर तालाब निर्माण | Ongoing | 963156.38 | 0 | 2022-04-15
DHARAMPURI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & maint of Fisheries Ponds for Comm / Repair & Maintenance of Fishery Pond for Community | Repair & maint of Pond/ Tank | 1722013004/WC/22012035162999 — Gp Me Water Pond Nirman Kary | New | 0 | 0 | 2024-01-28
DHARAMPURI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone Boulder Gully Plug for Community | Boulder Check/Gully Plug | 1722013004/WC/22012035236922 — Bhurighati ke paas Gully Plug Nirman Kary | Approved | 97234.3 | 0 | 2024-11-16
DHARAMPURI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone Boulder Gully Plug for Community | Boulder Check/Gully Plug | 1722013004/WC/22012035236928 — Bhurighati ke paas Gully Plug Nirman Kary Part 2 | Approved | 0 | 0 | 2024-11-16
DHARAMPURI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone Boulder Gully Plug for Community | Boulder Check/Gully Plug | 1722013004/WC/22012035236935 — Bhurighati ke paas Gully Plug Nirman Kary Part 3 | Approved | 0 | 0 | 2024-11-16
DHARAMPURI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone Boulder Gully Plug for Community | Boulder Check/Gully Plug | 1722013004/WC/22012035236941 — Bhurighati ke paas Gully Plug Nirman Kary Part 4 | Approved | 0 | 0 | 2024-11-16
DHARAMPURI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone Boulder Gully Plug for Community | Boulder Check/Gully Plug | 1722013004/WC/22012035236945 — Bhurighati ke paas Gully Plug Nirman Kary Part 5 | Approved | 0 | 0 | 2024-11-16
DHARAMPURI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1722013004/WC/22012035236976 — Gp Kachhwaniya Me Bhuri GHati KE Pass Gali Palig Nirman | Approved | 0 | 0 | 2024-10-02
DHARAMPURI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1722013004/WC/22012035242772 — Himala chhagan ke khet ke paas nale par | Approved | 0 | 0 | 2024-11-16
DHARAMPURI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1722013004/WC/22012035242775 — Motilal ke khet ke paas nale par | Approved | 0 | 0 | 2024-11-16
DHARAMPURI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1722013004/WC/22012035242778 — bhuresingh ke khet ke paas nale par | Approved | 0 | 0 | 2024-11-16
DHARAMPURI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1722013004/WC/22012035242779 — Jhita Ke Khet Ke Paas Nale Par | Approved | 0 | 0 | 2024-11-16
DHARAMPURI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1722013004/WC/22012035242972 — gp kachwaniya me himla ke khet pass nale par boldar check dam nirman | New | 0 | 0 | 2024-08-02
DHARAMPURI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1722013004/WC/22012035253691 — Gp Kachwaniya me Ditya ke khet ke pass nale par boldar check dam nirman | Approved | 0 | 0 | 2025-01-27
DHARAMPURI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1722013004/WC/22012035267919 — JGSA 2025 Recharge Structures Gabian Nirman Bhurighati Wale Nale Par Unit 05 | Approved | 25899.46 | 0 | 2025-04-14
DHARAMPURI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1722013004/WC/22012035270556 — JGSA 2025 Gabian structure 1722013004/WC/22012035270520 Bhurighati nale par unit 05 Gp Kachhwanya | Ongoing | 185248.95 | 0 | 2025-05-15
DHARAMPURI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1722013004/WC/22012035278061 — JGSA 2025 gabian structure1722013004/WC/22012035278043 kundiya wale nale par GP Kachhwanya | Approved | 0 | 0 | 2025-04-14
DHARAMPURI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry Check Dam for Community | Construction of Check Dam/Stop Dam | 1722013004/WC/22012035281667 — JGSA 2025 Gabion structures Nirman Mehandi wale Nale par Gp Kachhwanya | Approved | 0 | 0 | 2025-04-14
DHARAMPURI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry Check Dam for Community | Construction of Check Dam/Stop Dam | 1722013004/WC/22012035281677 — JGSA 2025 Gabion structures Nirman Jhakribayadi wale Nale par Gp Kachhwanya | Approved | 0 | 0 | 2025-04-14
DHARAMPURI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry Check Dam for Community | Construction of Check Dam/Stop Dam | 1722013004/WC/22012035281681 — JGSA 2025 Gabion structures Nirman Bhamda wale Nale par Gp Kachhwanya | Approved | 0 | 0 | 2025-04-14
DHARAMPURI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry Check Dam for Community | Construction of Check Dam/Stop Dam | 1722013004/WC/22012035281686 — JGSA 2025 Gabion structures Nirman Medawale Nale par Gp Kachhwanya | Approved | 0 | 0 | 2025-04-14
DHARAMPURI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry Check Dam for Community | Construction of Check Dam/Stop Dam | 1722013004/WC/22012035281692 — JGSA 2025 Gabion structures Nirman Kunndiyawale Nale par Gp Kachhwanya | Approved | 0 | 0 | 2025-04-14
DHARAMPURI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1722013004/WC/22012035328485 — Gp Kachhwanya Me Manohar Laxman Ke Khet Ke Paas Bolder Check Nirman Karya | New | 0 | 0 | 2026-01-24
DHARAMPURI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1722013004/WC/22012035328524 — GP Kachhwanya me manohar laxman ke khet ke paas bolder check nirman kary | Approved | 0 | 0 | 2026-01-14
DHARAMPURI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1722013004/WC/22012035328525 — GP Kachhwanya me nawal bheriya ke khet ke paas bolder check nirman kary | Approved | 0 | 0 | 2026-01-14
DHARAMPURI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1722013004/WC/22012035328526 — GP Kachhwanya me mahesh tutla ke khet ke paas bolder check nirman kary | Approved | 0 | 0 | 2026-01-14
DHARAMPURI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1722013004/WC/VB/22012035329450 — gp kachwanya me panchayat bhawan ke samne shok pit nirman karya | Approved | 0 | 0 | 2026-04-14
DHARAMPURI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1722013004/WC/VB/22012035329455 — Gp Kachhwanya me sokpit nirman | Ongoing | 26784.01 | 300 | 2026-07-27
DHARAMPURI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1722013004/WC/VB/22012035336887 — VB G RAM G GP KACHHWANYA Me Gabian Nirman Karya Gajja Ke Khet Waale Naale Pass | Approved | 369595.28 | 0 | 2026-04-02
DHARAMPURI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1722013004/WC/VB/22012035336888 — VB G RAM G GP KACHHWANYA Me Gabian nirman Jagdish Ke Khet Waale naale Par | Approved | 393633.73 | 0 | 2026-04-02
DHARAMPURI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1722013004/WC/VB/22012035336889 — VB G RAM G GP KACHHWANYA Me Gabian Nirman Karya Somliya Ke Khet Waale Naale Par | Approved | 469061.23 | 0 | 2026-04-02
DHARAMPURI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1722013004/WC/VB/22012035336890 — VB G RAM G GP KACHHWANYA Me Gabian Nirman Karya Gomda Ke Khet Waale Naale Pass | Approved | 479654.98 | 0 | 2026-04-02
DHARAMPURI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1722013004/WC/VB/22012035336891 — VB G RAM G GP KACHHWANYA Me Gabian Nirman Karya Bhuresingh Babliya Ke Khet Waale Naale Pass | Approved | 485988.22 | 0 | 2026-04-02
DHARAMPURI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dyke for Community | Underground Dyke for Ground Water Recharge | 1722013004/WC/VB/22012035337001 — VB G RAM G GP KACHHWANYA ME LAKSHMAN K KHET PASS WAALE NAALE PAR DYKE NIRMAN | Approved | 0 | 0 | 2026-10-02
DHARAMPURI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dyke for Community | Underground Dyke for Ground Water Recharge | 1722013004/WC/VB/22012035337002 — VB G RAM G GP KACHHWANYA ME KHUMAN KE KHET WAALE NAALE PASS DYKE NIRMAN | Approved | 0 | 0 | 2026-10-02
DHARAMPURI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dyke for Community | Underground Dyke for Ground Water Recharge | 1722013004/WC/VB/22012035337003 — VB G RAM G GP KACHHWANYA Me AMRU KE KHET WAALE NAALE PAR DYKE NIRMAN | Approved | 0 | 0 | 2026-10-02
DHARAMPURI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dyke for Community | Underground Dyke for Ground Water Recharge | 1722013004/WC/VB/22012035337004 — VB G RAM G GP KACHHWANYA Me MEHARBAAN KE KHET WAALE NAALE PAR DYKE NIRMAN | Approved | 0 | 0 | 2026-10-02
DHARAMPURI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dyke for Community | Underground Dyke for Ground Water Recharge | 1722013004/WC/VB/22012035337005 — VB G RAM G GP KACHHWANYA Me BHAMDIYA WAALE NAALE PAR DYKE NIRMAN | Approved | 0 | 0 | 2026-10-02
DHARAMPURI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry Check Dam for Community | Construction of Check Dam/Stop Dam | 1722013004/WC/VB/YD/22012035336823 — Constr of Masonry/CC Anicut for boulder check shamsaan ghat waale nale par | Approved | 262564.27 | 0 | 2026-10-13
DHARAMPURI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1722013004/WC/VB/YD/22012035336881 — Construction of Recharge Pits for 1 | Approved | 129208.93 | 0 | 2026-04-02
DHARAMPURI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Rejuvenation of Pond for Community | Repair & maint of Pond/ Tank | 1722013004/WH/22012034939550 — Namami Gange Abhiyan Gp Kachhwaniya Me Kechment Sudhar Nistar Talab Mohan pura Nale Par | New | 0 | 0 | 2024-05-31
DHARAMPURI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Rejuvenation of Pond for Community | Repair & maint of Pond/ Tank | 1722013004/WH/22012034939552 — Namami Gange Abhiyan Gp Kachhwaniya Me Kechment Sudhar Ginawapura Talab Par | New | 0 | 0 | 2024-05-31
DHARAMPURI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Rejuvenation of Pond for Community | Repair & maint of Pond/ Tank | 1722013004/WH/22012034939553 — Namami Gange Abhiyan Gp Kachhwaniya Me Kechment Sudhar Ginawapura Talab Par | New | 0 | 0 | 2024-05-31
DHARAMPURI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Rejuvenation of Pond for Community | Repair & maint of Pond/ Tank | 1722013004/WH/22012034939554 — Namami Gange Abhiyan Gp Kachhwaniya Me Kechment Sudhar Ginawapura Talab Par | New | 0 | 0 | 2024-05-31
DHARAMPURI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1722013/RC/22012034566561 — CONSTRUCTION OF GRAVEL ROAD HIGH SCHOOL DUKANPURA SE KHUTAMOD KACHHWANYA | Physically Completed | 3622000 | 0 | 2023-09-13 | 2026-09-29