## Work List
Exported on: 2026-09-08 21:51:33
Filters applied:
Data source: VBGRAMG
District: DHAR
Block: All
Panchayat: Gujari
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
DHARAMPURI | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1722013012/AV/22012034663280 — Gp Gujari ke डेहरिया में आगनवाड़ी भवन निर्माण क्रमांक 01 | New | 0 | 0 | 2025-01-01
DHARAMPURI | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1722013012/AV/22012034663281 — Gp Gujari ke डेहरिया में आगनवाड़ी भवन निर्माण क्रमांक 01 | New | 0 | 0 | 2025-01-01
DHARAMPURI | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1722013012/AV/22012034663282 — Gp Gujari ke डेहरिया में आगनवाड़ी भवन निर्माण क्रमांक 01 | New | 0 | 0 | 2024-12-03
DHARAMPURI | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1722013012/AV/22012034663283 — Gp Gujari ke डेहरिया में आगनवाड़ी भवन निर्माण क्रमांक 01 | Approved | 500000 | 0 | 2024-04-01
DHARAMPURI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1722013012/DP/22012034562050 — ग्राम पंचायत गुजरी के मुक्ति धाम में पौधा रोपण | Ongoing | 410218.19 | 0 | 2023-07-15
DHARAMPURI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1722013012/DP/22012034562052 — ग्राम पंचायत गुजरी के डेहरिया डाक बंगला में पौधा रोपण | Ongoing | 410218.19 | 1500 | 2025-05-22
DHARAMPURI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Sericulture- in Fields-Community / Block Plantation of Sericulture Trees in Fields for Community | Plantation | 1722013012/DP/22012034596314 — Gp gujari ke balajee ke pass pantation bhag .1 | Ongoing | 427106.07 | 0 | 2024-08-06
DHARAMPURI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1722013012/DP/22012034596325 — Gp gujari ke balajee ke pass pantation bhag .2 | Ongoing | 427106.07 | 7200 | 2024-08-05
DHARAMPURI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Wasteland Block Plantation-Horticulture-Community / Wasteland Block Plantation of Horticulture Trees for Community | Plantation | 1722013012/DP/22012034625741 — ग्राम पंचायत गुजरी के बालाजी मंदिर के सामने पौधा रोपण | Ongoing | 453563.17 | 11700 | 2025-03-04
DHARAMPURI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Grass Land Development and Silvi-pasture / Development of Silvipasture Grassslands for Community | Grass Land Development | 1722013012/DP/22012034628598 — gp Gujari Dehariya me samsan Ghat nirman | Approved | 0 | 0 | 2024-10-02
DHARAMPURI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1722013012/IF/22012034588741 — GP GUJARI ME CATTLE SHED NIRMAN AMARSINGH / DARIYAV KE GHAR KE PASS DEHRIYA | Ongoing | 63531.21 | 0 | 2020-07-27
DHARAMPURI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Mini Percolation Tank for Individuals / Construction of Mini Percolation Tank for Individuals | Construction of Percolation Tank | 1722013012/IF/22012035477185 — JGSA 2025 Form Pond Nirman Mukesh Mangu Ke khet Hanumantiya Gp Gujari | Physically Completed | 55865.38 | 0 | 2025-05-10 | 2026-08-10
DHARAMPURI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Mini Percolation Tank for Individuals / Construction of Mini Percolation Tank for Individuals | Construction of Percolation Tank | 1722013012/IF/22012035477197 — JGSA 2025 Form Pond Nirman Mahesh Madiya Ke khet Hanumantiya Gp Gujari | Ongoing | 55865.38 | 0 | 2025-05-10
DHARAMPURI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Mini Percolation Tank for Individuals / Construction of Mini Percolation Tank for Individuals | Construction of Percolation Tank | 1722013012/IF/22012035477207 — JGSA 2025 Form Pond Nirman Govind Ke khet Hanumantiya Gp Gujari | Physically Completed | 55865.38 | 0 | 2025-05-15 | 2026-08-10
DHARAMPURI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1722013012/IF/22012035493462 — JGSA 2025 Recharge Structure Kapildhara Kup Ramsingh Bhadariya Gp Gujari | New | 0 | 0 | 2025-04-14
DHARAMPURI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1722013012/IF/22012035493507 — JGSA 2025 Recharge Structure Kapildhara Kup Babu Chogiya Gp Gujari | Physically Completed | 25899.46 | 0 | 2025-05-10 | 2026-08-19
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1722013012/IF/22012035579808 — Gp Gujari me kishore Narayan ke ghar Cattle Shelter Nirman | Approved | 0 | 0 | 2025-04-14
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722013012/IF/22012035600983 — Ek Bagiya maa ke name khusbhuMP22013012001/192-A | Ongoing | 266577.25 | 0 | 2025-09-01
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722013012/IF/22012035600992 — Ek Bagiya maa ke name NIRMLA MP22013012001/39 | Approved | 266577.25 | 0 | 2025-08-18
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722013012/IF/22012035601002 — Ek Bagiya maa ke name SUBHDRA MP22013012001/225 | Ongoing | 266577.25 | 0 | 2025-09-01
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722013012/IF/22012035601007 — Ek Bagiya maa ke name PRATIBHA TIWARI MP22013012001/272 | Ongoing | 266577.25 | 2700 | 2025-09-01
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722013012/IF/22012035601014 — Ek Bagiya maa ke name Anita MP22013012001/76 | Ongoing | 266577.25 | 0 | 2025-09-01
DHARAMPURI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722013012/IF/IAY/4633111 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128246185 | Approved | 27000 | 0 | 2024-09-16
DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722013012/IF/IAY/4685319 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103432606 | Completed | 23490 | 0 | 2026-04-09 | 2026-08-11
DHARAMPURI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722013012/IF/IAY/4691282 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106074398 | Approved | 27000 | 0 | 2024-09-27
DHARAMPURI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722013012/IF/IAY/4723817 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147682489 | Ongoing | 27000 | 0 | 2026-04-09
DHARAMPURI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722013012/IF/IAY/4736146 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104903782 | Ongoing | 27000 | 0 | 2025-01-07
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722013012/IF/IAY/4739941 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106068139 | Ongoing | 27000 | 6300 | 2025-04-02
DHARAMPURI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722013012/IF/IAY/5272371 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106235154 | Physically Completed | 23490 | 0 | 2025-02-21 | 2026-07-19
DHARAMPURI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722013012/IF/IAY/5338570 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126652525 | Approved | 27000 | 0 | 2025-02-20
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722013012/IF/IAY/5349284 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126634247 | Ongoing | 27000 | 4200 | 2025-08-20
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722013012/IF/IAY/5351289 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126237438 | Ongoing | 27000 | 6027 | 2025-08-20
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722013012/IF/IAY/5364100 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106077610 | Ongoing | 27000 | 2100 | 2025-07-30
DHARAMPURI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722013012/IF/IAY/5365667 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106053495 | Approved | 27000 | 0 | 2025-02-28
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722013012/IF/IAY/5367514 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103422492 | Ongoing | 27000 | 0 | 2025-08-20
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722013012/IF/IAY/5368492 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128303384 | Completed | 23490 | 0 | 2025-08-20 | 2026-07-28
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722013012/IF/IAY/5507675 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126544846 | Ongoing | 27000 | 4200 | 2025-08-20
DHARAMPURI | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722013012/RC/22012034834041 — ग्राम पंचायत गुजरी मे गुजरी से हनुमंतीय तक सुदुर सड़क निर्माण कार्य | Approved | 0 | 0 | 2024-04-14
DHARAMPURI | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1722013012/RS/22012034531548 — SBM SSP GP GUJRI ME UNIT 10 | Ongoing | 120022.78 | 0 | 2021-08-23
DHARAMPURI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone boulder Gully Plugs for Community | Boulder Check/Gully Plug | 1722013012/WC/22012034966570 — CTRA GP GUJARI ME GULLY-PLUGS HANUMATIYA PAHADI PAR | Physically Completed | 78281.42 | 0 | 2022-11-19 | 2026-08-15
DHARAMPURI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1722013012/WC/22012035227693 — Gp Gujari ke dehariya me Boldawall Nirman Saman Ghat ke pass | Approved | 0 | 0 | 2024-10-02
DHARAMPURI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1722013012/WC/22012035317624 — Gp Gujari me Contour Trench Nirman Hanumantiya Pahadi pr | Approved | 0 | 0 | 2025-04-14
DHARAMPURI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1722013012/WC/22012035317625 — Gp Gujari me Contour Trench Nirman Hanumantiya badi Pahadi pr | Approved | 0 | 0 | 2025-04-14
DHARAMPURI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1722013012/WH/22012034939713 — Namami Gange Gp Gujari Me Bundsudhar Kary Talab Jeernoddhaar Badakhodra Hanmantya | Approved | 0 | 0 | 2024-04-01
DHARAMPURI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1722013012/WH/22012034939714 — Namami Gange Gp Gujari Me Pitching Sudharkary Talab Jeernoddhaar Badakhodra Hanmantya | Approved | 0 | 0 | 2024-04-01
DHARAMPURI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1722013012/WH/22012034940829 — Namami Gange Gp Gujari Me Feeder Channel Kary Nistartalab Jeernoddhaar Badakhodra Hanmantya | Approved | 0 | 0 | 2024-06-15