## Work List
Exported on: 2026-09-06 10:22:04
Filters applied:
Data source: VBGRAMG
District: DHAR
Block: All
Panchayat: Balwari
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
DHARAMPURI | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1722013013/DP/22012034238955 — GP BALWARI ME SANTIDHAM NIRMAN | Ongoing | 0 | 0 | 2017-09-19
DHARAMPURI | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1722013013/DP/22012034534158 — CTRA - Gp Balwari (Basvi) Me Plantation Hanuman Mandir Parisar part -1 | Ongoing | 394489.84 | 0 | 2021-09-12
DHARAMPURI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Shelter Belt Trees (Comm) / Boundary Line Plantation of Shelter Belt Trees for Community | Plantation | 1722013013/DP/22012034559114 — GP BALWARI ME PLANTATION HIGH SCHOOL CAMPUS | Ongoing | 410218.19 | 0 | 2023-10-07
DHARAMPURI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Shelter Belt Trees (Comm) / Boundary Line Plantation of Shelter Belt Trees for Community | Plantation | 1722013013/DP/22012034609983 — Gp Balwari Me Plantation Khokhriya Moti Baydi ParPart1 | Ongoing | 426720.58 | 0 | 2024-07-08
DHARAMPURI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1722013013/DP/22012034609986 — Gp Balwari Me Plantation Khokhriya Moti Baydi Ke Pass | Ongoing | 426720.58 | 0 | 2023-10-07
DHARAMPURI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Shelter Belt Trees (Comm) / Boundary Line Plantation of Shelter Belt Trees for Community | Plantation | 1722013013/DP/22012034625904 — Gp Balwari Me Plantation Gram Basvi Kaldevi Mata Mandir Parisar Me | Ongoing | 453563.17 | 9000 | 2024-08-13
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722013013/IF/22012035233374 — GP Balwari Me Kapildhara Kup Nirman Pintu Pita Chhibariya Ke Khet Me | Ongoing | 209846.33 | 0 | 2025-04-13
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722013013/IF/22012035484121 — JGSA 2025 Recharge Pit Ambaram ke Khet Me Kup Ke Pass Basvi | Ongoing | 25899.46 | 0 | 2025-05-17
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722013013/IF/22012035598236 — Ek Bagiya Ma ke Name Kasturi Bai Pati Ajeet MP22-013-013-002/17 | Ongoing | 266577.25 | 0 | 2025-09-15
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722013013/IF/22012035600262 — Ek Bagiya Ma Ke Naam Sangeeta /Hiralal MP22013013001/44 | Ongoing | 268031.56 | 0 | 2025-09-11
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722013013/IF/22012035600267 — Ek Bagiya Ma Ke Naam Avanti Bai /Kishore MP22013013001/239 | Ongoing | 266577.25 | 0 | 2025-09-04
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722013013/IF/22012035607997 — Ek Bagiya Ma Ke Naam Ganga Bai /Gabru MP22013013001/41 | Ongoing | 266577.25 | 0 | 2025-09-11
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722013013/IF/22012035608005 — Ek Bagiya Ma Ke Naam Dropati Bai /Jagdish MP22013013001/92 | Ongoing | 266577.25 | 0 | 2025-09-04
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722013013/IF/22012035621637 — Ek Bagiya Ma Ke Naam Tulsi Bai /Sakharam MP22013013001/42 | New | 0 | 0 | 2025-08-15
DHARAMPURI | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722013013/IF/IAY/134329 — Construction of IAY House -IAY REG. NO. MP-22-013-013-001/500 | Approved | 27000 | 0 | 2015-10-16
DHARAMPURI | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722013013/IF/IAY/134330 — Construction of IAY House -IAY REG. NO. MP-22-013-013-002/121 | Approved | 27000 | 0 | 2015-10-16
DHARAMPURI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722013013/IF/IAY/4772843 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125299388 | Ongoing | 27000 | 0 | 2025-02-25
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722013013/IF/IAY/5150080 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125594966 | Ongoing | 27000 | 6300 | 2025-04-25
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722013013/IF/IAY/5172444 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151408601 | Ongoing | 27000 | 2100 | 2025-08-14
DHARAMPURI | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722013013/IF/IAY/53681 — Construction of IAY House -IAY REG. NO. MP-22-013-013-001/0521 | Approved | 27000 | 0 | 2015-10-16
DHARAMPURI | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722013013/IF/IAY/53684 — Construction of IAY House -IAY REG. NO. MP-22-013-013-001/22 | Approved | 27000 | 0 | 2015-10-16
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722013013/IF/IAY/5394252 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125592885 | Ongoing | 27000 | 0 | 2025-07-28
DHARAMPURI | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722013013/IF/IAY/54222 — Construction of IAY House -IAY REG. NO. MP-22-013-013-001/008 | Approved | 27000 | 0 | 2015-10-16
DHARAMPURI | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722013013/IF/IAY/54224 — Construction of IAY House -IAY REG. NO. MP-22-013-013-001/037 | Approved | 27000 | 0 | 2015-10-16
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722013013/IF/IAY/5696904 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125547455 | Physically Completed | 27000 | 4200 | 2025-08-14 | 2026-09-02
DHARAMPURI | 2026-2027 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722013013/RC/22012034854119 — Gp Balwari me Laxman Dhayaram ke ghar se Pm Road Tak | New | 0 | 0 | 2026-06-05
DHARAMPURI | 2026-2027 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722013013/RC/22012034854120 — Gp Balwari Me Laxman Dhayaram Ke Ghar Se Pm Road Tak | Approved | 1605840.38 | 0 | 2026-06-05
DHARAMPURI | 2026-2027 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722013013/RC/22012034854122 — Gp Balwar me Ps School Bhilala Se Singare Pura Tak Sudur sadak Road | Approved | 0 | 0 | 2026-06-05
DHARAMPURI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1722013013/WC/22012035107723 — Gp Balwari Me Galy Plag Khokhriya Talab ke pass | Physically Completed | 295973.98 | 0 | 2023-09-26 | 2026-08-15
DHARAMPURI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1722013013/WC/22012035124764 — Gp Balwari Me Boulder Wall Khokhriya Moti Baydi Ke Pass Part1 | Ongoing | 389236.04 | 2400 | 2023-10-07
DHARAMPURI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1722013013/WC/22012035126532 — Gp Balwari Me Boulder Wall Midile School Part 02 | Ongoing | 292677.03 | 0 | 2023-10-07
DHARAMPURI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1722013013/WC/22012035126536 — Gp Balwari Me Boulder Wall High School Part 02 | Ongoing | 485795.05 | 0 | 2023-10-07
DHARAMPURI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & maint of Fisheries Ponds for Comm / Repair and maintenance of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1722013013/WC/22012035162930 — Water Pond Nirman Kary | New | 0 | 0 | 2024-01-26
DHARAMPURI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1722013013/WH/22012034939712 — NAMAMI GANGE GP BALWARI ME FIDER CHENAL KARYA KHOKHRIYA TALAB | Approved | 0 | 0 | 2024-04-14
DHARAMPURI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722013025/IF/22012035387753 — JGSA2025 Recharge Pit Gp Balwari Me Sitaram ke Kup ke pass | Approved | 0 | 0 | 2025-04-14