## Work List
Exported on: 2026-10-12 17:56:02
Filters applied:
Data source: VBGRAMG
District: KHARGONE
Block: All
Panchayat: BHAGWANPURA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BHIKANGAON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in fields for Community | Plantation | 1724005010/DP/22012034594337 — Vasudha vadan vrakhasaropan bhagwanpura talab kinare | Ongoing | 55847.4 | 0 | 2023-10-04
BHIKANGAON | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724005010/IF/22012035067313 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150677557 | Ongoing | 18360 | 0 | 2023-06-02
BHIKANGAON | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1724005010/IF/22012035118433 — कपिलधारा कूप निर्माण जैमाल रूपला भगवानुपुरा | Ongoing | 282417.57 | 0 | 2023-10-04
BHIKANGAON | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1724005010/IF/22012035127219 — फलोद्यान परियोजना सुनील बाबुलाल भगवानपुरा | Ongoing | 160586.73 | 0 | 2023-08-01
BHIKANGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1724005010/IF/22012035252485 — फलोद्यान परियोजना राधाबाई कमलेश पिपलईखुर्द भगवानपुरा | Ongoing | 173308.58 | 0 | 2025-09-16
BHIKANGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1724005010/IF/22012035540075 — खेततालाब निर्माण JGSA देवीसिंह झामू पिपलईखुर्द भगवानपुरा | Approved | 0 | 0 | 2025-04-14
BHIKANGAON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724005010/IF/IAY/3214336 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4533707 | Ongoing | 27000 | 0 | 2021-11-04
BHIKANGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724005010/IF/IAY/5794326 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117782263 | Ongoing | 27000 | 0 | 2025-09-12
BHIKANGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724005010/IF/IAY/5794499 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117892066 | Physically Completed | 23490 | 0 | 2025-09-12 | 2026-07-20
BHIKANGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724005010/IF/IAY/5795286 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150536599 | Ongoing | 27000 | 0 | 2025-09-12
BHIKANGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724005010/IF/IAY/6120572 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117667589 | Ongoing | 27000 | 19800 | 2026-05-11
BHIKANGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724005010/IF/IAY/6122123 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113938947 | Physically Completed | 27000 | 22200 | 2026-04-20 | 2026-09-24
BHIKANGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724005010/IF/IAY/6125669 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120801418 | Physically Completed | 27000 | 18000 | 2026-04-20 | 2026-09-24
BHIKANGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724005010/IF/IAY/6139562 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149120778 | Physically Completed | 27000 | 10500 | 2026-04-20 | 2026-08-30
BHIKANGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724005010/IF/IAY/6150715 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151406768 | Ongoing | 27000 | 0 | 2026-04-20
BHIKANGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724005010/IF/IAY/6163323 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118265038 | Ongoing | 27000 | 0 | 2026-04-20
BHIKANGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724005010/IF/IAY/6163468 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151401199 | Ongoing | 27000 | 0 | 2026-04-20
BHIKANGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724005010/IF/IAY/6168681 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149123760 | Ongoing | 27000 | 0 | 2026-04-20
BHIKANGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724005010/IF/IAY/6168682 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149123776 | Ongoing | 27000 | 0 | 2026-04-20
BHIKANGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724005010/IF/IAY/6211969 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106165068 | Physically Completed | 27000 | 18000 | 2026-04-20 | 2026-10-09
BHIKANGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724005010/IF/IAY/6247838 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106244856 | Approved | 27000 | 0 | 2026-03-25
BHIKANGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724005010/IF/IAY/6255946 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117894360 | Approved | 27000 | 0 | 2026-03-26
BHIKANGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724005010/IF/IAY/6256508 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118743652 | Approved | 27000 | 0 | 2026-03-26
BHIKANGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724005010/IF/IAY/6257984 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120799782 | Approved | 27000 | 0 | 2026-03-26
BHIKANGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724005010/IF/IAY/6280818 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119583905 | Approved | 27000 | 0 | 2026-03-25
BHIKANGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724005010/IF/IAY/6289884 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118743992 | Approved | 27000 | 0 | 2026-03-05
BHIKANGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724005010/IF/IAY/6302575 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118067061 | Approved | 27000 | 0 | 2026-03-05
BHIKANGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724005010/IF/IAY/6370139 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150279681 | Approved | 27000 | 0 | 2025-03-04
BHIKANGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724005010/IF/IAY/6370161 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149893295 | Approved | 27000 | 0 | 2025-02-27
BHIKANGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724005010/IF/IAY/6372344 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151230177 | Approved | 27000 | 0 | 2026-08-12
BHIKANGAON | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel / Mitti Murram Road for Community | Construction of Road and Culvert | 1724005010/RC/22012034565618 — Khet Sadak Nirman Sardar Jhamu Ke Khale Se Kisan Natthu Ke Khet Tak Pipliyakhurd Bhagwanpura | Ongoing | 1476894.02 | 0 | 2021-03-25
BHIKANGAON | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1724005010/RC/22012034662332 — सीसी रोड निर्माण गोविन्‍द्र के घर से महेश के घर तक पिपलईखुर्द भगवानपुरा | Ongoing | 65000 | 18900 | 2023-10-26
BHIKANGAON | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1724005010/RC/22012034674381 — सीसी रोड निर्माण | New | 0 | 0 | 2024-04-01